## Scheduling Register
Board Name | Operative Name | Appointment Date | Appointment Status | Address | Post Code | Description | Resident Name | Resident Mobile | Resident E-Mail | Zone | Asbestos Report Confirmed | Our Reference | Client Reference | Description of Work
Appointments | Timothy Cotter | 30/06/2026 18:00 | N/A | 2 Woodmead Gardens | BS13 0JY | CARRY OUT WORK | Miss Racheal Millett | 447880884068 | RACHEALMILLETT@HOTMAIL.CO.UK | Area 5 - South West | No | 36/1523 | 109711/1 | Renew Gate to front garden
Appointments | Alan Smith | 30/06/2026 13:00 | Appointment Booked - Staff Allocated | 19 HILLS BARTON | BS13 7JH | CARRY ON WORKS | Ms Daniel Mike | 447914803817 | d_mikke@yahoo.com | Area 5 - South West | No | 36/1439 | 71393/2 | HEATER:RESITE AND RECONNECT - Heater:Isolate supply, disconnect and resite night storage heater, including dismantle and reassemble, move to new site, secure to wall and make all connections, reconnect electricity supply, electrical tests and leave in wor
Appointments | George Sutton-Fricker | 30/06/2026 13:00 | Appointment Booked - Staff Allocated | 35 INNOX GARDENS | BS13 9AG | CARRY ON WORKS | Miss Hayley Bird | 447407536467 | hayleybird@live.co.uk | Area 5 - South West | No | 36/1225 | 74551/1 | Complaints work / BATHROOM: REMOVE AND REPLACE CEILING, REDECORATE ENTIRE ROOM, O/H FAN, REPLACE PANEL WITH PVC, RENEW CISTERN, RENEW VINYL FLOOR, REPLACE SEALANT ON BASIN & BATH
Appointments | Jason Thomas | 30/06/2026 12:00 | Appointment Booked - Staff Allocated | 16 WHITSON HOUSE | BS2 9ED | CARRY ON WORKS | Miss Catherine Wise | 07395708510 | WISECATHERINE29@GMAIL.COM | Area 3 - Central | No | 36/1450 | 101095/1 | BEDR1 , BEDR 2 BATHR EXTERNAL HALLWAY KITCH
Appointments | Shane George Saunders | 30/06/2026 12:00 | Appointment Booked - Staff Allocated | 16 WHITSON HOUSE | BS2 9ED | CARRY ON WORKS | Miss Catherine Wise | 07395708510 | WISECATHERINE29@GMAIL.COM | Area 3 - Central | No | 36/1450 | 101095/1 | BEDR1 , BEDR 2 BATHR EXTERNAL HALLWAY KITCH
Appointments | Glen Norman | 30/06/2026 12:00 | Appointment Booked - Staff Allocated | 19 ELMDALE ROAD | BS3 3JF | CARRY OUT WORK | Mr & Mrs Linda & Victor Lewis | 447795465626 | viclewis1381@hotmail.co.uk | Area 5 - South West | No | 36/1446 | 98050/2 | Jeffway- as per Jeff N-Overhaul PVC windows leave in working order, apply waterproofing seal to spar on rear elevation to a height 1200mm above ground on kitchen wall and rear gable end
Appointments | Jessie Parsons | 30/06/2026 12:00 | Appointment Booked - Staff Allocated | 234 Ilchester Crescent, Bedminster Down | BS13 7HT | CARRY OUT WORK | Ms Susanna Price | 447760332224 | SUSIELICKS@HOTMAIL.COM |  | No | 36/1388 | 85301/2 | Jeff Way - as per John Oyeniyi: Hack off bad rendering and renew to Toilet wall (external) and redecorate.
Appointments | Simon Burrows | 30/06/2026 12:00 | Appointment Booked - Staff Allocated | 44 GREENDITCH AVENUE | BS13 0AT | CARRY OUT WORK | Mr Daniel STELMASZYK | 447544062280 | danielstelmaszyk@ymail.com |  | No | 36/1440 | 71422/2 | Jeff Way - as per John Oyeniyi: Renew handles to 2nos kitchen unit; Renew handle to 1no door; Renew taps to Bath and Sink and renew water cistern.
Appointments | James Stephens | 30/06/2026 09:00 | Appointment Booked - Staff Allocated | 25 Burnell Drive, St Pauls | BS2 9JU | COMPLETE DISREPAIR WORKS - AS PER NOTES | Ms Amina Hussein | 447728540088 | aminahussein77@yahoo.co.uk |  | No | 36/1228 | 53830/2 | Complaint - Please carry out works as listed.
Appointments | Glen Norman | 30/06/2026 09:00 | Appointment Started | 192 BROADLANDS DRIVE | BS11 0PH | COMPLETE DECS - SPEAK WITH MCGREGOR | Miss Louise Lovelace | 447305731956 | louiselovelace117@yahoo.com | Area 1 - North West | No | 36/902 | 30060/1 | Complaints work - works throughout property. Re-raised
Appointments | Darren Whitchurch | 30/06/2026 09:00 | Appointment Started | 5 Brunel Road, Bedminster Down | BS13 7DX | SEND TEXT | Mrs Eman Ibrahim | 447405104540 | fatima.youppa244@gmail.com |  | No | 36/1377 | 96603/2 | JEFF WAY - AS PER ROB D: RENEWAL OF HAND BASIN/ SPLASHBACK / PEDESTAL, FLOORBOARDS AS REQUIRED, BATH PANEL WITH ACRYLIC AND THEN RENEW FLOORING IN FULL TO BATHROOM
Appointments | Darren Wallis | 30/06/2026 08:00 | Appointment Ended - Second Visit Required | 30 Home Mead, Creswicke Road | BS4 1UQ | INTERNAL PAINTING | Mr David Summerhayes | 447845653061 |  |  | No | 36/1048 | 40673/1 | Complaint works- WO- Thomas Lear- please see email and complaint report
Appointments | Timothy Cotter | 30/06/2026 08:00 | Appointment Started | 37 Gay Elms Road, Withywood | BS13 9BB | CARRY OUT WORK | Mr David Whtfield | 447535327867 |  |  | No | 36/1297 | 40520/2 | JEFF WAY - AS PER DAVE PALMER: RENEW SURROUND TO INSPECTION COVER & RENEW BACK INLET GULLY.
Appointments | Kyran Thomas | 30/06/2026 08:00 | N/A | 87 Chalcroft House, Lower Sidney Street | BS3 1ST | CONDENSATION DRIP TREATMENT | Miss Mary Togher | 01179668733 | marytogher916@gmail.com |  | No | 36/1302 | 83580/2 | JEFF WAY - AS PER ROB D: MOULD/ CONDENSATION DRIP TREATMENT & REPAINT WITH HALOPHEN PAINT TO FULL WINDOW WALL & REVEAL & FULL SINK WALL IN KITCHEN
Appointments | Jessie Parsons | 30/06/2026 08:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Sam Benden | 30/06/2026 08:00 | Appointment Booked - Staff Allocated | 15 MURFORD WALK | BS13 9LB | CARRY OUT WORK | Mr Anthony Bloomfield | 447864629526 | ANTBFCBLOOMFIELD@GMAIL.COM | Area 5 - South West | No | 36/1444 | 74219/2 | Jeffway- as per Jeff N-With remove disconnect sink , remove water damage base unit , refix new unit and door. Cut and fix new plinth to suit kitchen. Apply anti condensation paint to ceiling and all walls.
Appointments | Daniel Williams | 30/06/2026 08:00 | Appointment Started | 35 INNOX GARDENS | BS13 9AG | RENEW CEILING - DISREPAIR | Miss Hayley Bird | 447407536467 | hayleybird@live.co.uk | Area 5 - South West | No | 36/1225 | 74551/1 | Complaints work / BATHROOM: REMOVE AND REPLACE CEILING, REDECORATE ENTIRE ROOM, O/H FAN, REPLACE PANEL WITH PVC, RENEW CISTERN, RENEW VINYL FLOOR, REPLACE SEALANT ON BASIN & BATH
Appointments | James Stephens | 30/06/2026 08:00 | Appointment Started | 89 REDFORD CRESCENT | BS13 8SA | CARRY ON WORKS | Ms Samantha Trent | 447399187349 | sammi.trent@hotmail.com | Area 5 - South West | No | 36/1357 | 47044/2 | Jeff Way - as per Jeff N: Works in bathroom, emailed over full description ¦ 72FL432500 x3 SHEET FLOORING:HACK UP VINYL TILES; 72JR305501 x3 FLOORING:SUPPLY AND LAY HARDBOARD; 72FL432507 x3 SHEET FLOORING:LAY NEW VINYL AND SUB-BASE; 72JR388013 x1 BATH PAN
Appointments | Christopher Mcgregor | 30/06/2026 08:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | Glen Norman | 30/06/2026 08:00 | Appointment Started | 18 ST JOHNS LANE | BS3 5AA | CARRY ON WORKS | Mrs Farah Mohammed | 447759674788 |  | Area 4 - South East | No | 36/1262 | 39290/1 | DISREPAIR WORKS
Appointments | Jack Slade | 29/06/2026 14:00 | Appointment Booked - Staff Allocated | 47 Keble Avenue | BS13 8PT | repairs | Miss Chanel Hawkins | 7737217911 | CHANEL19HAWKINS@GMAIL.COM |  | No | 36/1642 | 121556/3 | Jeffway-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 03/08/26. 10 DAY PERIOD ENDS 17/08/26.
Appointments | Simon Burrows | 29/06/2026 14:00 | Appointment Started | 3 Mowcroft Road, Hartcliffe | BS13 0LE | CARRY OUT WORK | Miss Leanne Derrick | 447340995741 | leaderrick1990@gmail.com |  | No | 36/854 | 31982/1 | JW - As per Jeff - Various works required throughout property, See SOR comments for specific location details Hack off damage plaster work to the sides and behind ground floor toilet and reskim to match existing levels. Remove rotten timber skirting at th
Appointments | Simon Burrows | 29/06/2026 13:00 | Appointment Started | 3 Mowcroft Road, Hartcliffe | BS13 0LE | CARRY OUT WORK | Miss Leanne Derrick | 447340995741 | leaderrick1990@gmail.com |  | No | 36/854 | 31982/1 | JW - As per Jeff - Various works required throughout property, See SOR comments for specific location details Hack off damage plaster work to the sides and behind ground floor toilet and reskim to match existing levels. Remove rotten timber skirting at th
Appointments | Sam Benden | 29/06/2026 12:00 | Appointment Booked - Staff Allocated | 49 Southbow House, Duckmoor Road | BS3 2EN | CARRY OUT WORK | Mrs Beryl Mcvey | 447901912822 | mcvey99@googlemail.com |  | No | 36/1463 | 105809/1 | JW- ROB DOIDGE - CRUMBLING SEALANT / SKIM AROUND PIPES TO BED 2 CEILING AND BED 1 WALL. REPAIR AND RESEAL AROUND PIPES. BASIN TO BATHROOM DRAINS SLOWLY, REPAIR AS REQUIRED daughter anna - 07901912822 or louise - 07443480677 - please contact one of them p
Appointments | Simon Burrows | 29/06/2026 12:00 | N/A | 45 BARTON HOUSE | BS5 9SL | paint kitchen ceiling | Miss Kumba Njie | 447403734472 | Kumbis10@outlook.com | Area 3 - Central | No | 36/1120 | 34228/1 | Complaint works- Please see email and report.
Appointments | Daniel Williams | 29/06/2026 09:00 | Appointment Started | 42 Eldon Terrace, Windmill Hill | BS3 4PA | repairs | Miss Lisa Cooper | 447990844185 | lis4cooper@hotmail.co.uk |  | No | 36/1347 | 58180/1 | Renew Bed 2 ceiling tested by CASA , NAD inc ELE / DEC parts R.M
Appointments | Oliver Maurice Shore | 29/06/2026 09:00 | Appointment Started | 42 Eldon Terrace, Windmill Hill | BS3 4PA | repairs | Miss Lisa Cooper | 447990844185 | lis4cooper@hotmail.co.uk |  | No | 36/1347 | 58180/1 | Renew Bed 2 ceiling tested by CASA , NAD inc ELE / DEC parts R.M
Appointments | Jessie Parsons | 29/06/2026 08:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Timothy Cotter | 29/06/2026 08:00 | N/A | 37 Gay Elms Road, Withywood | BS13 9BB | CARRY OUT WORK | Mr David Whtfield | 447535327867 |  |  | No | 36/1297 | 40520/2 | JEFF WAY - AS PER DAVE PALMER: RENEW SURROUND TO INSPECTION COVER & RENEW BACK INLET GULLY.
Appointments | Sam Benden | 29/06/2026 08:00 | Appointment Booked - Staff Allocated | 17 Warden Road | BS3 1BU | CARRY OUT WORK | Miss Nadine Davis | 447597973870 | nadine621@hotmail.co.uk | Area 5 - South West | No | 36/1445 | 74150/2 | Jeffway-as per Jeff N-: Cut out cracks in plaster work at positions thus ground floor kitchen / front room / 1st floor landing / top floor side wall , tenant to verify positions
Appointments | Darren Wallis | 29/06/2026 08:00 | Appointment Started | 5 Englishcombe Road | BS13 0NW | COMPLETE WORKS - DISREPAIR | Mr Kavell Gayle | 07503401703 | kavellgayle@gmail.com | Area 5 - South West | No | 36/984 | 3697/2 | Disrepair works - James Bailey (surveyor) Bedroom - strip back damaged plaster, treat brick, replaster, mist coat, anticondensation paint Kitchen - d+m wash pipes Living room - - strip back damaged plaster, treat brick, replas
Appointments | Christopher Mcgregor | 29/06/2026 08:00 | Appointment Booked - Staff Allocated | 4 Rusham Sherrin Way | BS13 8SH | COMPLETE DISREPAIR WORKS - AS PER NOTES | Ms Maria Spencer | 07494762850 |  | Area 5 - South West | No | 36/1284 | 84934/1 | Complaint works - paint over black staining from old firs place. scrape and repaint bathroom ceiling from old leak
Appointments | George Sutton-Fricker | 29/06/2026 08:00 | Appointment Started | 240 ST JOHNS LANE | BS3 5AU | COMPLETE ELECTRICAL WORKS | Ms Samantha Claridge | 07368305419 | CLARIDGESAMANTHA228@GMAIL.COM |  | No | 36/1172 | 63225/1 | Complaint work- Re render the back of the house., Cupboard/ store room over board and insulate walls and ceiling. bedroom install skirting. bathroom replace extractor. 2 dg units to replace in property.
Appointments | Clayton Burbridge | 29/06/2026 08:00 | Appointment Started | 240 ST JOHNS LANE | BS3 5AU | CUT OUT FASCIAS FOR ELECTRICIAN TO COMPLETE - WILL MEET YOU ON SITE | Ms Samantha Claridge | 07368305419 | CLARIDGESAMANTHA228@GMAIL.COM |  | No | 36/1172 | 63225/1 | Complaint work- Re render the back of the house., Cupboard/ store room over board and insulate walls and ceiling. bedroom install skirting. bathroom replace extractor. 2 dg units to replace in property.
Appointments | Glen Norman | 29/06/2026 08:00 | Appointment Started | 36 Cossington Road | BS4 1DP | CARRY ON WORKS | Mr Nathan Eddolls | 447377764845 |  |  | No | 36/1402 | 102245/1 | Various works to kitchen, bathroom and hallway following complaint
Appointments | Daniel Williams | 29/06/2026 08:00 | Appointment Started | 41 MONTREAL AVENUE | BS7 0NB | COMPLETE REMAINING CRACKS TO KITCHEN | Miss Terri Vining | 447827608271 | terri80@hotmail.co.uk | Area 2 - North East | No | 36/1227 | 76659/1 | Fill all cracks in kitchen
Appointments | Simon Burrows | 29/06/2026 08:00 | Appointment Started | 75 TORRINGTON AVENUE | BS4 1EQ | TIDY UP DECS - SPEAK TO DARREN WHITCHURCH | Ms Rachel Reeves | 447982939319 | rachel84reeves@hotmail.co.uk | Area 4 - South East | No | 36/1054 | 32908/1 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors.
Appointments | Shane George Saunders | 29/06/2026 08:00 | Appointment Booked - Staff Allocated | 4 Rusham Sherrin Way | BS13 8SH | COMPLETE DISREPAIR WORKS - AS PER NOTES | Ms Maria Spencer | 07494762850 |  | Area 5 - South West | No | 36/1284 | 84934/1 | Complaint works - paint over black staining from old firs place. scrape and repaint bathroom ceiling from old leak
Appointments | Clayton Burbridge | 29/06/2026 07:00 | Appointment Ended - Second Visit Required | 24, FIRST FLOOR FLAT WEST MALL | BS8 4BQ | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Deborah Harris | 07561888652 | DEBSHARRIS60@GMAIL.COM | Area 3 - Central | No | 36/1341 | 93183/1 | PD1 - Please carry out works as listed. Access to be arranged through surveyor James Bailey
Appointments | Timothy Cotter | 26/06/2026 19:00 | Appointment Started | 34 Derham Road | BS13 7SB | CARRY ON WORKS | Miss Starr Gillam | 447488454642 | starcollins123@icloud.com | Area 5 - South West | No | 36/1151 | 14985/2 | JEFF WAY - AS PER ROB D: RENEW 2 X MISSING PLINTHS TO MATCH EXISTING TO KITCHEN UNITS. OVERHAUL DOORS / HINGES WHERE DROPPED / HANGING OFF AS REQUIRED
Appointments | Timothy Cotter | 26/06/2026 17:00 | Appointment Booked - Staff Allocated | 17 FOUR ACRES CLOSE | BS13 8QW | CARRY ON WORKS | Miss Rachel Whereatt | 447964187426 | rachelw-18@hotmail.co.uk | Area 5 - South West | No | 36/1403 | 102227/1 | RENEW ALL PLINTHS AS REQUIRED, APPROX 3 LIN M AND RENEW KIT FLOORING APPROX 4M2 WITH BCC VINYL TILES. 1 X WALL TILE RHS OF COOKER TO MATCH / RENEW ALSO, CREAM.
Appointments | Jamie Hunt | 26/06/2026 13:00 | Appointment Started | 2-33 Chard Court, Fortfield Road | BS14 9NL | CARRY ON WORKS |  |  |  |  | No | 36/1339 | 93675/1 | Ceiling patch in communal lounge repair required after leak As above
Appointments | Daniel Williams | 26/06/2026 12:00 | Appointment Started | 15 HOLLIDGE GARDENS | BS3 1AQ | CARRY ON WORKS | Mrs Gloria Benkhelifa | 447780118151 | stevenson488@hotmail.co.uk | Area 5 - South West | No | 36/1198 | 35087/4 | Jeff Way - as per John Oyeniyi: Redecoration works to wall and kitchen in bathroom, mould wash ceiling in kitchen.
Appointments | Kyran Thomas | 26/06/2026 12:00 | Appointment Booked - Staff Allocated | 12 SPENCER HOUSE | BS1 6RL | CARRY ON WORKS | Mr Tomasz Zdebelak | 447717755084 | ZDEBELAKT@GMAIL.COM | Area 3 - Central | No | 36/1582 | 112615/1 | Complaint Work - Please see e-mail and report
Appointments | Darren Wallis | 26/06/2026 12:00 | Appointment Started | 75 TORRINGTON AVENUE | BS4 1EQ | CARRY ON WORKS | Ms Rachel Reeves | 447982939319 | rachel84reeves@hotmail.co.uk | Area 4 - South East | No | 36/1054 | 32908/1 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors.
Appointments | Simon Burrows | 26/06/2026 10:00 | Appointment Started | 43 Harewood Road | BS5 7ST | ACCESS GAINED - FOR SMART FORM PURPOSES | Mrs Diane Evans | 07894060676 | diane.76@hotmail.co.uk |  | No | 36/1029 | 34769/2 | Please carry out disrepairs works as listed out.
Appointments | Jessie Parsons | 26/06/2026 10:00 | Appointment Booked - Staff Allocated | 5 Hartgill Close, Hartcliffe | BS13 0BU | CARRY OUT WORK | Miss Alexandria Yendell | 447895193148 | alexy25@live.co.uk |  | No | 36/1461 | 105842/1 | JW - AS PER JOHN OYNEIYI - Renew Bath panel; skim and redecorate wall behind WC; Renew plasterboard ceiling to staircase and redecorate
Appointments | Jessie Parsons | 26/06/2026 08:00 | Appointment Booked - Staff Allocated | 138 Newland Road, Withywood | BS13 9DX | CARRY OUT WORK | Mrs Shirley Hancock | 447833103079 | Shirleyhancock397@gmail.com |  | No | 36/1374 | 96904/2 | Jeff Way - Crack repair on external render on front elevation and mould wash bedroom walls as per John Oyeniyi.
Appointments | Jamie Hunt | 26/06/2026 08:00 | Appointment Booked - Staff Allocated | 5 Brunel Road, Bedminster Down | BS13 7DX | CARRY OUT WORK | Mrs Eman Ibrahim | 447405104540 | fatima.youppa244@gmail.com |  | No | 36/1377 | 96603/2 | JEFF WAY - AS PER ROB D: RENEWAL OF HAND BASIN/ SPLASHBACK / PEDESTAL, FLOORBOARDS AS REQUIRED, BATH PANEL WITH ACRYLIC AND THEN RENEW FLOORING IN FULL TO BATHROOM
Appointments | Sam Benden | 26/06/2026 08:00 | Appointment Booked - Staff Allocated | 18 GATEHOUSE CLOSE | BS13 9AH | CARRY OUT WORK | Miss Rebecca Walker | 447798755632 | Shelbyw279@gmail.com | Area 5 - South West | No | 36/1418 | 68975/2 | Jeff Way - as per John Oyeniyi: Redecorate Bathroom walls and ceiling; Mould wash bedroom ceiling. ¦ 72PT411107 x3 WALL:RENEW APPLY 3MM SKIM COAT PLASTER - Wall:Renew defective or ; 72PA442001 x2 WALLS AND CEILINGS:APPLY MIST 2 COATS EMULSION - Walls and
Appointments | Oliver Maurice Shore | 26/06/2026 08:00 | Appointment Started | 138 Bedminster Road, Bedminster, Bristol, BS3 5NP | BS3 5NP | CARRY OUT WORK | Miss Sarah Farbrother | 447772879515 |  |  | No | 36/815 | 28437/1 | AS PER NICHOLAS CORY JEFFWAY TO HACK OFF ALL OLD PLASTER ON EXTERNAL WALL PAINT WITH BITUMIN RE RENDER WITH SAND/CEMANT AND WATERPROOFER, SKIM FINISH AND PAINT
Appointments | Kyran Thomas | 26/06/2026 08:00 | Appointment Booked - Staff Allocated | 40 STANTON ROAD | BS10 5SL | CARRY ON WORKS | Ms Kelly Tiley | 447853473253 | kellytiley@yahoo.co.uk |  | No | 36/1634 | 118296/1 | JW to treat mould in WC and front door. Gloss paint front door. Paint bed1 ceiling complete. Hack off and replaster around front door area + decorate. Thermal board WC wall by alley + dec.
Appointments | Simon Burrows | 26/06/2026 08:00 | N/A | 43 Harewood Road | BS5 7ST | Overhaul windows throughout property, oil check trickle vents | Mrs Diane Evans | 07894060676 | diane.76@hotmail.co.uk |  | No | 36/1029 | 34769/2 | Please carry out disrepairs works as listed out.
Appointments | Daniel Williams | 26/06/2026 08:00 | Appointment Started | 138 Bedminster Road, Bedminster, Bristol, BS3 5NP | BS3 5NP | CARRY OUT WORK | Miss Sarah Farbrother | 447772879515 |  |  | No | 36/815 | 28437/1 | AS PER NICHOLAS CORY JEFFWAY TO HACK OFF ALL OLD PLASTER ON EXTERNAL WALL PAINT WITH BITUMIN RE RENDER WITH SAND/CEMANT AND WATERPROOFER, SKIM FINISH AND PAINT
Appointments | Christopher Mcgregor | 26/06/2026 08:00 | Appointment Booked - Staff Allocated | 8 Hersey Gardens, Withywood | BS13 8RR | repairs | Miss Shantelle Mckechnie | 07495879399 |  |  | No | 36/1637 | 115755/2
Appointments | Jamie Hunt | 26/06/2026 07:00 | Appointment Ended - Second Visit Required | 2-33 Chard Court, Fortfield Road | BS14 9NL | CARRY ON WORKS |  |  |  |  | No | 36/1339 | 93675/1 | Ceiling patch in communal lounge repair required after leak As above
Appointments | Clayton Burbridge | 26/06/2026 07:00 | Appointment Ended - Second Visit Required | 95 Coronation Road | BS3 1AX | CARRY OUT WORK | Mrs Salma Hussein | 447308477469 |  |  | No | 36/1437 | 102496/2 | AS PER NICHOLAS CORY JW TO NEW X3 RADS, NEW TRVS, BATHROOM FLR CAP&COVE, VENT COVER IN BACK BEDROOM , X3 NEW INTERNAL DOOR, hack of pla right side of living room chimney, wallpaper reglue front bedroom rightside
Appointments | James Stephens | 26/06/2026 07:00 | Appointment Booked - Staff Allocated | 95 Coronation Road | BS3 1AX | CARRY OUT WORK | Mrs Salma Hussein | 447308477469 |  |  | No | 36/1437 | 102496/2 | AS PER NICHOLAS CORY JW TO NEW X3 RADS, NEW TRVS, BATHROOM FLR CAP&COVE, VENT COVER IN BACK BEDROOM , X3 NEW INTERNAL DOOR, hack of pla right side of living room chimney, wallpaper reglue front bedroom rightside
Appointments | George Sutton-Fricker | 25/06/2026 15:00 | Appointment Booked - Staff Allocated | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Clayton Burbridge | 25/06/2026 14:00 | Appointment Started | 2 Buttercup Walk | BS3 2TZ | CARRY ON WORKS | Miss Natasha McKenna | 447765314576 | tasha-lee2@hotmail.co.uk | Area 5 - South West | No | 36/1060 | 46615/1 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF EXT FAN FROM DOWNSTAIRS W.C, PATCH REPAIR CEILING AFTER AND REPAINT. RENEW DRAUGHT STRIPS TO FRONT DOOR, CURRENT ONES STILL LETTING AIR THROUGH
Appointments | Simon Burrows | 25/06/2026 14:00 | Appointment Started | 2 Buttercup Walk | BS3 2TZ | CARRY ON WORKS | Miss Natasha McKenna | 447765314576 | tasha-lee2@hotmail.co.uk | Area 5 - South West | No | 36/1060 | 46615/1 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF EXT FAN FROM DOWNSTAIRS W.C, PATCH REPAIR CEILING AFTER AND REPAINT. RENEW DRAUGHT STRIPS TO FRONT DOOR, CURRENT ONES STILL LETTING AIR THROUGH
Appointments | James Stephens | 25/06/2026 13:00 | Appointment Booked - Staff Allocated | 18 Malago Road, Bedminster | bs3 4jr | CARRY OUT WORK | Mrs fay murphy | 447947103918 | murphyfurry@gmail.com |  | No | 36/1390 | 74158/2 | Jeff Way - as per John Oyeniyi: Remove laminated floor in kitchen, remove bumps & latex, refix laminated floor. Repair & hairline cracks in bedroom ceiling Overhaul Living room
Appointments | Clayton Burbridge | 25/06/2026 13:00 | Works Completed | 2 Buttercup Walk | BS3 2TZ | CARRY ON WORKS | Miss Natasha McKenna | 447765314576 | tasha-lee2@hotmail.co.uk | Area 5 - South West | No | 36/1060 | 46615/1 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF EXT FAN FROM DOWNSTAIRS W.C, PATCH REPAIR CEILING AFTER AND REPAINT. RENEW DRAUGHT STRIPS TO FRONT DOOR, CURRENT ONES STILL LETTING AIR THROUGH
Appointments | Sam Benden | 25/06/2026 13:00 | Appointment Started | 13 LITTLECROSS HOUSE | BS3 1SQ | CARRY ON WORKS | Mr Stephen Bennett |  |  | Area 5 - South West | No | 36/1200 | 58367/2 | Jeffway-: AS PER ROB D - FOLLOWING LEAK FROM ABOVE FLAT, NOW FIXED. REDECORATE AFFECTED AREAS OF KIT AND BATHROOM WALLS / CEILINGS AS REQUIRED. MATCH IN PAINT COLOURS. APPROX 14M2 TOTAL AREA
Appointments | Daniel Williams | 25/06/2026 13:00 | Appointment Booked - Staff Allocated | 24 Warden Road | BS3 1BU | CARRY ON WORKS | Mr Michael Cox | 07835412388 |  | Area 5 - South West | No | 36/1174 | 69097/1 | Complaint disrepair works : guttering clear water ways. Front elevation inspect and renew gully cover on front. Bathroom reseal joint in the waste pipe
Appointments | Sam Benden | 25/06/2026 12:00 | Appointment Started | 13 LITTLECROSS HOUSE | BS3 1SQ | CARRY ON WORKS | Mr Stephen Bennett |  |  | Area 5 - South West | No | 36/1200 | 58367/2 | Jeffway-: AS PER ROB D - FOLLOWING LEAK FROM ABOVE FLAT, NOW FIXED. REDECORATE AFFECTED AREAS OF KIT AND BATHROOM WALLS / CEILINGS AS REQUIRED. MATCH IN PAINT COLOURS. APPROX 14M2 TOTAL AREA
Appointments | Alan Smith | 25/06/2026 12:00 | Appointment Booked - Staff Allocated | 45 Wrought Drive | BS13 0LL | CARRY ON WORKS | Miss Harriet Alford | 447879777856 | harriet.alford2212@hotmail.co.uk |  | No | 36/1223 | 81266/2 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 1/4/26. 10 DAY PERIOD ENDS 15/4/26
Appointments | Timothy Cotter | 25/06/2026 12:00 | N/A | 67 NEWLAND ROAD | BS13 9DS | CARRY ON WORKS | Miss Vicky Parker | 447553560976 | Parkervicky392@gmail.com | Area 5 - South West | No | 36/1579 | 116515/1 | REPAIR CHIP IN ENAMEL BATH, REPLACE LEAKING PAN CONNECTOR, PREP AND PAINT BATHROOM SKIRTING BEHIND TOILET AND SINK, RENEW ANTI SLIP FLOORING TO BATHROOM.
Appointments | Glen Norman | 25/06/2026 12:00 | Appointment Started | 75 Collinson Road | BS13 9PH | CARRY ON WORKS | Mr Zak Dollin | 447880696290 | Dollinzak4@gmail.com |  | No | 36/1352 | 62738/2 | Jeffway-AS PER DAVE PALMER - EXTRACTOR OVERHAUL TO BATHROOM, RENEW SAFETY FLOORING IN BATHROOM, ROOM REDEC TO DOWNSATAIS BACK ROOM.
Appointments | Darren Wallis | 25/06/2026 12:00 | Appointment Started | 75 TORRINGTON AVENUE | BS4 1EQ | CARRY ON WORKS | Ms Rachel Reeves | 447982939319 | rachel84reeves@hotmail.co.uk | Area 4 - South East | No | 36/1054 | 32908/1 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors.
Appointments | James Stephens | 25/06/2026 11:00 | N/A | 10 Buttercup Walk, Ashton Vale | BS3 2TZ | CARRY OUT WORK | Mr Robert Czaplarski | 447554846229 | DAREKNN09@GMAIL.COM |  | No | 36/1244 | 35188/2 | JEFF WAY - Note tenant to lift bedroom and landing carpets to allow access to loose flooring. Secure loose floor board as shown by tenant. Overhaul sink and basin taps . Replace damage latch on living room door. FAO JEFF NECK BOOKED WITH JEFF NECK 9/3/26
Appointments | Jack Slade | 25/06/2026 10:00 | Appointment Booked - Staff Allocated | 18 Stanley Street North, Bedminster | BS3 3LU | TAKE FAN OFF AND INSTALL VGRILL VENT | Mrs Camilla Qureshi | 447917842484 |  |  | No | 36/1615 | 27368/6 | AS PER NICHOLAS CORY JW TO REMOVE RIVIVI7 FAN IN KITCHEN AND REPLACE WITH HIT AND MISS VENT COVER AND COVER ON OUTSIDE WALL
Appointments | James Stephens | 25/06/2026 10:00 | Appointment Started | 30 Latchmoor House, Banwell Close | BS13 7DS | CARRY ON WORKS | Ms Maria Santos | 447860148645 | marialucia_0209@hotmail.com |  | No | 36/1334 | 47331/2 | Jeffway- as per John O-: Renew double base unit (beneath sink) and paint walls
Appointments | Izaak Ellis | 25/06/2026 10:00 | Works Completed | 92 STILLINGFLEET ROAD | BS13 9RJ | Photo's need of clean | Miss Abigail C Harris | 447377735084 |  | Area 5 - South West | No | 36/185 | 1110103 | D&M -MOULD WASH AS PER NICHOLAS CORY JEFFWAY TO MOULD WASH LIVING ROOM BEHIND SOFA, FRONT BEDROOM CEILING AND CORNER OF WALL, REAR BEDROOM AROUND WINDOW AREA AND REAR CORNER BEHIND BUNK BED
Appointments | Daniel Williams | 25/06/2026 09:00 | Appointment Booked - Staff Allocated | 4 Aldwick Avenue, Hartcliffe | BS13 0NZ | RENEW TAPS ON WHB | Ms Leanne Gainard | 447956594789 | leanne.gainard@icloud.com |  | No | 36/1298 | 50243/3 | Jeffway- as per John O-Renew tap to Kitchen sink
Appointments | Daniel Williams | 25/06/2026 09:00 | Appointment Ended - Second Visit Required | 4 Aldwick Avenue, Hartcliffe | BS13 0NZ | COMPLETE WORKS AS PER NOTES | Ms Leanne Gainard | 447956594789 | leanne.gainard@icloud.com |  | No | 36/1287 | 50243/2 | JEFF WAY - Crack repair to Rear Elevation wall and Mould wash bedroom 1 FAO JOHN OYENIYI
Appointments | Jamie Hunt | 25/06/2026 09:00 | N/A | 120 Stillingfleet Road | BS13 9RJ | CARRY ON WORKS | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Sam Benden | 25/06/2026 09:00 | Appointment Booked - Staff Allocated | 430 Bishport Avenue | BS13 0HU | CARRY ON WORKS | Miss Odette O'Connor | 447342180306 |  | Area 5 - South West | No | 36/1129 | 60035/1 | Jeffway - As per Rob D - INSTALL WINDOW MOUNTED FANS TO KITCHEN AND BATHROOM , CORNISH TYPE PROPERTY. ALSO RENEW SILICON AROUND BATH IN FULL
Appointments | James Stephens | 25/06/2026 09:00 | Appointment Started | 30 Latchmoor House, Banwell Close | BS13 7DS | CARRY ON WORKS | Ms Maria Santos | 447860148645 | marialucia_0209@hotmail.com |  | No | 36/1334 | 47331/2 | Jeffway- as per John O-: Renew double base unit (beneath sink) and paint walls
Appointments | Izaak Ellis | 25/06/2026 09:00 | Appointment Booked - Staff Allocated | 5 KEBLE AVENUE | BS13 8PP | repairs | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Clayton Burbridge | 25/06/2026 09:00 | Appointment Started | 52 Redwood House, | BS13 0RW | CARRY ON WORKS | Ms Kirsty Jerome | 447825327626 | kirstyjerome24@gmail.com |  | No | 36/1300 | 41343/2 | Jeff Way - as per John Oyeniyi: Renew 1no double Kitchen unit and renew 1no handle to kitchen unit
Appointments | Simon Burrows | 25/06/2026 09:00 | Appointment Started | 52 Redwood House, | BS13 0RW | CARRY ON WORKS | Ms Kirsty Jerome | 447825327626 | kirstyjerome24@gmail.com |  | No | 36/1300 | 41343/2 | Jeff Way - as per John Oyeniyi: Renew 1no double Kitchen unit and renew 1no handle to kitchen unit
Appointments | Luke Coleman | 25/06/2026 08:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Alan Smith | 25/06/2026 08:00 | Appointment Booked - Staff Allocated | 30 Home Mead, Creswicke Road | BS4 1UQ | overhaul fan | Mr David Summerhayes | 447845653061 |  |  | No | 36/1048 | 40673/1 | Complaint works- WO- Thomas Lear- please see email and complaint report
Appointments | Sam Benden | 25/06/2026 08:00 | Works Completed | 55 SHERRIN WAY | BS13 8RX | CARRY OUT WORK | Miss Jessica Bartlett | 447535653711 | jess.bartlett@hotmail.co.uk | Area 5 - South West | No | 36/1183 | 63719/2 | Jeffway- as per John O-Renew elbow joint to shower drain pipe on the Rear Elevation, overhaul windows, Renew lead flashing to entrance canopy & other works. Renew water cistern, pvc trims to window cill, tile up splashback above bath, and renew bath pa
Appointments | Timothy Cotter | 25/06/2026 08:00 | Appointment Booked - Staff Allocated | 89 REDFORD CRESCENT | BS13 8SA | CARRY OUT WORK | Ms Samantha Trent | 447399187349 | sammi.trent@hotmail.com | Area 5 - South West | No | 36/1357 | 47044/2 | Jeff Way - as per Jeff N: Works in bathroom, emailed over full description ¦ 72FL432500 x3 SHEET FLOORING:HACK UP VINYL TILES; 72JR305501 x3 FLOORING:SUPPLY AND LAY HARDBOARD; 72FL432507 x3 SHEET FLOORING:LAY NEW VINYL AND SUB-BASE; 72JR388013 x1 BATH PAN
Appointments | Kyran Thomas | 25/06/2026 08:00 | N/A | 4 Aldwick Avenue, Hartcliffe | BS13 0NZ | COMPLETE WORKS AS PER NOTES | Ms Leanne Gainard | 447956594789 | leanne.gainard@icloud.com |  | No | 36/1287 | 50243/2 | JEFF WAY - Crack repair to Rear Elevation wall and Mould wash bedroom 1 FAO JOHN OYENIYI
Appointments | Jamie Hunt | 25/06/2026 08:00 | Appointment Started | 120 Stillingfleet Road | BS13 9RJ | CARRY ON WORKS | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Glen Norman | 25/06/2026 08:00 | Appointment Booked - Staff Allocated | 6 LAMBERT PLACE | BS4 1XH | CARRY ON WORKS | Miss Freya Mccardle | 447301026749 | freyamccardle90@icloud.com | Area 4 - South East | No | 36/1196 | 69916/1 | AS PER GERRY RYAN - PLM to remove cistern and hand basin, pla to skim damage walls and renew tiles to the basin and tap end of bath - dec to paint bahtroom and paint not emulsion ele to over haul bathroom
Appointments | James Stephens | 25/06/2026 08:00 | Appointment Started | 30 Latchmoor House, Banwell Close | BS13 7DS | CARRY ON WORKS | Ms Maria Santos | 447860148645 | marialucia_0209@hotmail.com |  | No | 36/1334 | 47331/2 | Jeffway- as per John O-: Renew double base unit (beneath sink) and paint walls
Appointments | Clayton Burbridge | 25/06/2026 08:00 | Appointment Started | 5 KEBLE AVENUE | BS13 8PP | Adjust Chubb lock to back door, fit new vent cover in Bed 3 | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Simon Burrows | 25/06/2026 08:00 | Appointment Started | 5 KEBLE AVENUE | BS13 8PP | Adjust Chubb lock to back door, fit new vent cover in Bed 3 | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Darren Wallis | 25/06/2026 08:00 | Appointment Started | 3 Teal Close | BS11 0FF | CARRY ON WORKS | Miss Stephanie White | 447777134761 | Stephany-francies@hotmail.co.uk |  | No | 36/1094 | 54414/1 | Complaint works- Please see email and report.
Appointments | Sam Benden | 24/06/2026 16:00 | Appointment Booked - Staff Allocated | 26 MOWCROFT ROAD | BS13 0LS | CARRY ON WORKS | Miss Lyric Hiscox-Barrett | 07766981913 | LYRICBARRETT00@ICLOUD.COM | Area 5 - South West | No | 36/1115 | 59127/1 | carry out GRP roof to 26, 24 Mowcroft as discussed with Steve and Mike, closest codes to get started, Mike agreed to discus techeal spec for Steve and meet on site to ensure works are done to standard .Matt Ford
Appointments | Jamie Hunt | 24/06/2026 13:00 | Appointment Started | 75 Collinson Road | BS13 9PH | CARRY ON WORKS | Mr Zak Dollin | 447880696290 | Dollinzak4@gmail.com |  | No | 36/1352 | 62738/2 | Jeffway-AS PER DAVE PALMER - EXTRACTOR OVERHAUL TO BATHROOM, RENEW SAFETY FLOORING IN BATHROOM, ROOM REDEC TO DOWNSATAIS BACK ROOM.
Appointments | Jason Thomas | 24/06/2026 12:00 | Appointment Booked - Staff Allocated | 106a Cotham Brow | BS6 6AP | repairs | Ms Corrise Crahart | 447305710455 | corrise97@gmail.com |  | No | 36/1452 | 102216/1 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled lottie.smart@bristol.gov.uk
Appointments | Kyran Thomas | 24/06/2026 12:00 | Appointment Booked - Staff Allocated | 106a Cotham Brow | BS6 6AP | repairs | Ms Corrise Crahart | 447305710455 | corrise97@gmail.com |  | No | 36/1452 | 102216/1 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled lottie.smart@bristol.gov.uk
Appointments | Clayton Burbridge | 24/06/2026 12:00 | Appointment Booked - Staff Allocated | 52 Redwood House, | BS13 0RW | CARRY OUT WORK | Ms Kirsty Jerome | 447825327626 | kirstyjerome24@gmail.com |  | No | 36/1300 | 41343/2 | Jeff Way - as per John Oyeniyi: Renew 1no double Kitchen unit and renew 1no handle to kitchen unit
Appointments | Sam Benden | 24/06/2026 12:00 | N/A | 61 Rowan House | BS13 0RT | CARRY OUT WORK | Mr Jordan Allaway | 447496239765 | Jordanallaway12386@gmail.com | Area 5 - South West | No | 36/1426 | 90073/2 | Jeffway- as per John O-Renew silicone to Vinyl sheet flooring, bath and door frame in bathroom; Fix PVC skirting to bath panel ¦ 72FL433001 x20 SEALANT; 72JR318201 x1 DOOR; 72PL631501 x1 SEALANT:RENEW; 72FL432703 x3 SKIRTING:RENEW - NO ASBESTOS REPORT WIT
Appointments | Jamie Hunt | 24/06/2026 12:00 | Appointment Started | 75 Collinson Road | BS13 9PH | CARRY OUT WORK | Mr Zak Dollin | 447880696290 | Dollinzak4@gmail.com |  | No | 36/1352 | 62738/2 | Jeffway-AS PER DAVE PALMER - EXTRACTOR OVERHAUL TO BATHROOM, RENEW SAFETY FLOORING IN BATHROOM, ROOM REDEC TO DOWNSATAIS BACK ROOM.
Appointments | Timothy Cotter | 24/06/2026 12:00 | Appointment Booked - Staff Allocated | 223 Coronation Road, Southville | BS3 1RL | CARRY ON WORKS | Miss Samantha Kelly | 447707133710 | sambokelly39@gmail.com |  | No | 36/1550 | 112815/1 | JW - AS PER JEFF NECK - Please arrange roof inspection now scaffold move to front elevation to check front chimney and flashings. As per Darren
Appointments | Alan Smith | 24/06/2026 11:00 | Appointment Booked - Staff Allocated | 1 HOME GROUND | BS9 4UB | PLEASE SEE EMAIL RELATING TO REWIRING SHOWER | Miss Mona Aboutorabi | 07400200990 | IMONART@ICLOUD.COM | Area 1 - North West | No | 36/1638 | 119980/1 | JEFFWAY- replace the shower supply from the board to the shower switch. please respond to responseelectrical@bristol.gov.uk
Appointments | Sam Benden | 24/06/2026 09:00 | Appointment Booked - Staff Allocated | 14 Holbrook Crescent, Hartcliffe, Bristol BS13 0EU | BS13 0EU | CARRY ON WORKS | Mr George Fisher | 447916558909 |  |  | No | 36/1124 | 60323/1 | vJeffway-AS PER ROB DOIDGE - TREATMENT / PAINTING TO SMALL AREAS OF MOULD BY FRONT DOOR, TO BATHROOM WALLS BY W.C AND LIVING ROOM UNDER WINDOW.
Appointments | Sam Benden | 24/06/2026 09:00 | N/A | 91 NEWLAND ROAD | BS13 9DS | CARRY OUT WORK | Mr Steven Kenny | 447872014971 |  |  | No | 36/1126 | 61109/1 | JEFF WAY - Bathroom Repairs and redecorations FAO JOHN OYENIYI
Appointments | Glen Norman | 24/06/2026 09:00 | Appointment Started | 75 TORRINGTON AVENUE | BS4 1EQ | CARRY ON WORKS | Ms Rachel Reeves | 447982939319 | rachel84reeves@hotmail.co.uk | Area 4 - South East | No | 36/1054 | 32908/1 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors.
Appointments | Izaak Ellis | 24/06/2026 09:00 | Appointment Started | 43 Harewood Road | BS5 7ST | repairs | Mrs Diane Evans | 07894060676 | diane.76@hotmail.co.uk |  | No | 36/1029 | 34769/2 | Please carry out disrepairs works as listed out.
Appointments | Luke Coleman | 24/06/2026 08:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Darren Wallis | 24/06/2026 08:00 | Appointment Booked - Staff Allocated | 3 Teal Close | BS11 0FF | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Stephanie White | 447777134761 | Stephany-francies@hotmail.co.uk |  | No | 36/1094 | 54414/1 | Complaint works- Please see email and report.
Appointments | Alan Smith | 24/06/2026 08:00 | N/A | 39 MANCROFT AVENUE | BS11 0HX | INSTALL EXTRACTOR FANS - DISREPAIR | Mrs & Mrs LABIAN AND LOUISE WILLIAMS | 447380427485 | l.williams76@hotmail.co.uk | Area 1 - North West | No | 36/901 | 29993/2 | DN786139-response repairs overflow - Complaint disrepair works - as G Squared survey.
Appointments | Glen Norman | 24/06/2026 08:00 | N/A | 39 MANCROFT AVENUE | BS11 0HX | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mrs & Mrs LABIAN AND LOUISE WILLIAMS | 447380427485 | l.williams76@hotmail.co.uk | Area 1 - North West | No | 36/901 | 29993/2 | DN786139-response repairs overflow - Complaint disrepair works - as G Squared survey.
Appointments | Luke Coleman | 24/06/2026 08:00 | Appointment Started | 60 WROUGHTON DRIVE | BS13 0LN | CARRY OUT WORK | Mr Scott Henson | 07307632183 |  | Area 5 - South West | No | 36/1016 | 44148/1 | Jeffway -As per John O - Scrape back plaster work in Lounge Ceiling, skim and paint; Latex floor in lounge and Landing. Paint woodwork in Bathroom, Overhaul fan to kitchen
Appointments | Sam Benden | 24/06/2026 08:00 | N/A | 91 NEWLAND ROAD | BS13 9DS | CARRY OUT WORK | Mr Steven Kenny | 447872014971 |  |  | No | 36/1126 | 61109/1 | JEFF WAY - Bathroom Repairs and redecorations FAO JOHN OYENIYI
Appointments | Jamie Hunt | 24/06/2026 08:00 | Appointment Booked - Staff Allocated | 1 HIGHRIDGE CRESCENT | BS13 8HN | CARRY ON WORKS | Mr & Mrs Irene and Graham Payne | 447867680786 | graham48.payne@btopenworld.com/Irene.payne@btopenworld.com |  | No | 36/1061 | 8502/2 | JEFF WAY - FAO JEFF NECK RENDER EXT WALL TO BOTTOM OF STAIRS & WORKS TO REAR SHOWER CUBICLE AS PER EMAIL
Appointments | Simon Burrows | 24/06/2026 08:00 | Appointment Started | fakestreet | BS13 9JP | testing |  |  |  |  | No | 36/1396 | 64293/4 | JEFF WAY - MAIN WORKS. VOID WORKS. KEYSAFE: 9163. SWES AREA
Appointments | Jason Thomas | 24/06/2026 08:00 | Appointment Booked - Staff Allocated | 162 Luckwell Road | BS3 3HG | REPAIRS | Miss Shauna Lippiatt | 07824621996 | SHAUNALOUISE92XX@HOTMAIL.COM |  | No | 36/1584 | 114211/1 | Complaint Work - Please see e-mail and report
Appointments | Kyran Thomas | 24/06/2026 08:00 | Appointment Booked - Staff Allocated | 162 Luckwell Road | BS3 3HG | REPAIRS | Miss Shauna Lippiatt | 07824621996 | SHAUNALOUISE92XX@HOTMAIL.COM |  | No | 36/1584 | 114211/1 | Complaint Work - Please see e-mail and report
Appointments | Daniel Williams | 24/06/2026 08:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY ON WORKS | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Jason Thomas | 23/06/2026 16:00 | Appointment Booked - Staff Allocated | 223 Coronation Road, Southville | BS3 1RL | chimney works, parapets | Miss Samantha Kelly | 447707133710 | sambokelly39@gmail.com |  | No | 36/1550 | 112815/1 | JW - AS PER JEFF NECK - Please arrange roof inspection now scaffold move to front elevation to check front chimney and flashings. As per Darren
Appointments | Timothy Cotter | 23/06/2026 14:00 | Appointment Started | 75 Murford Avenue, Hartcliffe, Bristol BS13 9JY | BS13 9JY | CARRY OUT WORK | Miss Tammy L Blammon | 447402807630 | tammyblammon5@googlemail.com |  | No | 36/690 | 1219891 | JEFF WAY - Make repairs to plaster walls in bathroom and apply sealer to staining on walls .Paint ceiling and walls in anti condensation paint. Fix new plastic skirting around perimeter of walls.
Appointments | Glen Norman | 23/06/2026 13:00 | N/A | 192 BROADLANDS DRIVE | BS11 0PH | COMPLETE DECS | Miss Louise Lovelace | 447305731956 | louiselovelace117@yahoo.com | Area 1 - North West | No | 36/902 | 30060/1 | Complaints work - works throughout property. Re-raised
Appointments | Darren Wallis | 23/06/2026 13:00 | Appointment Started | 37 COTSWOLD ROAD | BS3 4NX | PAINT NEW PLASTER - DISREPAIR | Miss Natasha A Parsons | 447586700058 |  | Area 4 - South East | No | 36/1362 | 97885/1 | PD1 - Please carry out works as listed. Any questions, the surveyor is James Bailey
Appointments | Alan Smith | 23/06/2026 13:00 | Appointment Booked - Staff Allocated | 430 Bishport Avenue | BS13 0HU | 2xddgu bathroom/kitchen | Miss Odette O'Connor | 447342180306 |  | Area 5 - South West | No | 36/1129 | 60035/1 | Jeffway - As per Rob D - INSTALL WINDOW MOUNTED FANS TO KITCHEN AND BATHROOM , CORNISH TYPE PROPERTY. ALSO RENEW SILICON AROUND BATH IN FULL
Appointments | Jack Slade | 23/06/2026 13:00 | Appointment Booked - Staff Allocated | 45 Spartley Drive, Highridge | BS13 8DQ | CARRY ON WORKS | Miss Diane Campbell | 447845800154 | diane33campbell@gmail.com |  | No | 36/1246 | 64289/2 | Jeffway- as per Joe C-Scrape back loose paint prep surface and decorate - overhaul extractor and grill
Appointments | Timothy Cotter | 23/06/2026 13:00 | N/A | 75 Murford Avenue, Hartcliffe, Bristol BS13 9JY | BS13 9JY | CARRY OUT WORK | Miss Tammy L Blammon | 447402807630 | tammyblammon5@googlemail.com |  | No | 36/690 | 1219891 | JEFF WAY - Make repairs to plaster walls in bathroom and apply sealer to staining on walls .Paint ceiling and walls in anti condensation paint. Fix new plastic skirting around perimeter of walls.
Appointments | Christopher Mcgregor | 23/06/2026 12:00 | Appointment Booked - Staff Allocated | 2 DURWESTON WALK | BS14 8BE | COMPLETE AIRBRICK/ETERNAL GRILL - FAN HAS BEEN COMPLETED | Mr Ian Spencer | 447849079944 | SPENIAN1971@GMAIL.COM | Area 4 - South East | No | 36/1346 | 93957/1 | Complaints: New one to Kitchen -BL to provide aperture; new front door
Appointments | Sam Benden | 23/06/2026 12:00 | N/A | 42 DURWESTON WALK | BS14 8BE | CARRY OUT WORK | Miss April Skye | 447753428344 | APRIL_SKYE@OUTLOOK.COM | Area 4 - South East | No | 36/1025 | 44155/1 | JW- As per Sean P : there is a hole in the T&G/ chipboard flooring. Please cut out and renew to patch in with existing to living room floor.
Appointments | Sahib Singh | 23/06/2026 12:00 | Appointment Booked - Staff Allocated | 396 BISHPORT AVENUE | BS13 0HE | CARRY OUT WORK | Miss Courtney Williams | 447899711445 | courtscjw@hotmail.co.uk | Area 5 - South West | No | 36/1412 | 54190/2 | Jeffway- as per Dave Palmer-BATHROOM WORKS TO INCLUDE HACK OFF TILES, FITTING OF ACRYLIC LINING BOARD TO BATH SURROUND. STAIN BLOCK AND ANTI CONDENSATION PAINT. ¦ 72WF431003 x1 WALL; 72JR350017 x5 LINING; 72PA435121 x6 STAIN; 72PA442001 x9 WALLS; +5 more
Appointments | Christopher Mcgregor | 23/06/2026 11:00 | Appointment Booked - Staff Allocated | 90 EASTWOOD CRESCENT | BS4 4ST | FIT DRAUGHT EXCLUDERS | Mr Kelvin Duncan | 07836726936 | kelvinduncan42@gmail.com | Area 4 - South East | No | 36/1294 | 87412/1 | Complaint works- works to address mould within the hallway.
Appointments | Glen Norman | 23/06/2026 10:00 | Appointment Booked - Staff Allocated | 53 Coleshill Drive, Hartcliffe, Bristol | BS13 9QT | REPAIRS | Miss Danielle Randall | 07548664155 | danielle2020xo@outlook.com |  | No | 36/1496 | 106836/1 | JW - ROB D - REPAIR / RESEALING TO FRONT DOOR FRAME RHS AND TOP AND WINDOWFRAME LHS OF DOOR WHERE SEALANT FALLEN OUT SILL AND TOP. RUB DOWN AND REGLOSS WINDOW , FRAME AND DOOR
Appointments | Sam Benden | 23/06/2026 10:00 | Appointment Booked - Staff Allocated | 39 Creswicke Road, Knowle | BS4 1UE | CARRY OUT WORK | Mrs Helen Jones | 447741330382 | peanutjonesfamily@yahoo.co.uk |  | No | 36/1330 | 58616/2 | JEFF WAY - AS PER ROB DOIDGE - RENEW BOTTOM STAIR WINDER / TREAD IN FULL, FALLING DOWN TOWARDS WALL AT BACK CORNER Booked in with Rob D 23/04/2026 08:00-12pm via text
Appointments | Jamie Hunt | 23/06/2026 09:00 | Appointment Started | 36 Cossington Road | BS4 1DP | CARRY ON WORKS | Mr Nathan Eddolls | 447377764845 |  |  | No | 36/1402 | 102245/1 | Various works to kitchen, bathroom and hallway following complaint
Appointments | James Stephens | 23/06/2026 09:00 | Appointment Started | 36 Cossington Road | BS4 1DP | CARRY ON WORKS | Mr Nathan Eddolls | 447377764845 |  |  | No | 36/1402 | 102245/1 | Various works to kitchen, bathroom and hallway following complaint
Appointments | Sam Benden | 23/06/2026 09:00 | Appointment Booked - Staff Allocated | 77 Murford Avenue, Hartcliffe | BS13 9JY | CARRY ON WORKS | Miss Leanne Perlini | 447913627653 |  |  | No | 36/1430 | 100551/1 | DA - Make good external render around any pipe, brackets, other projections and the like, fill holes, make good render. Old kitchen waste hole ¦ 72PT423009 x1 DWELLING REPAIR:MAKE GOOD AROUND PIPE ETC - Dwelling:Make good an - NO ASBESTOS REPORT WITH ORDE
Appointments | Jessie Parsons | 23/06/2026 09:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY ON WORKS | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Jason Thomas | 23/06/2026 09:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY ON WORKS | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Glen Norman | 23/06/2026 08:00 | N/A | 3 FOUR ACRES CLOSE | BS13 8QW | DISREPAIR WORKS AS PER NOTES | Miss Carrie Winstone | 447946857641 | winstonecarrie@mail.com | Area 5 - South West | No | 36/1056 | 45287/1 | Complaint disrepair work - repair finish above front door and paint. Repoint crack in brickwork on front elevation. patch repair plaster by Bed1 and Kitchen and paint to finish. Check radiators and bleed if necessary.
Appointments | Darren Wallis | 23/06/2026 08:00 | N/A | 16 MURFORD WALK | BS13 9LB | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mr Lee Collins | 447863221791 |  | Area 5 - South West | No | 36/992 | 37119/1 | complaint works- Thomas Lear- please see report and email.
Appointments | Christopher Mcgregor | 23/06/2026 08:00 | Appointment Booked - Staff Allocated | 201 FOUR ACRES | BS13 8QQ | COMPLETE OTHER SIDE OF LOFT INSULATION | Mrs Debra Hooper | 447496632495 | debhooper60@hotmail.co.uk |  | No | 36/877 | 1191303 | Damp and Mould as per BB tidy existing loft insulation and overlay with 250mm of mineral insulation ensuring placement up to the eaves.
Appointments | Oliver Maurice Shore | 23/06/2026 08:00 | Appointment Booked - Staff Allocated | 201 FOUR ACRES | BS13 8QQ | COMPLETE OTHER SIDE OF LOFT INSULATION | Mrs Debra Hooper | 447496632495 | debhooper60@hotmail.co.uk |  | No | 36/877 | 1191303 | Damp and Mould as per BB tidy existing loft insulation and overlay with 250mm of mineral insulation ensuring placement up to the eaves.
Appointments | Daniel Williams | 23/06/2026 08:00 | Appointment Started | 96 Capgrave Crescent | BS4 4TP | REDO PLASTER IN BEDROOM THATS CRACKING | Miss Somer Matthews | 447706627504 | SOMERMATTHEWS1234@ICLOUD.COM | Area 4 - South East | No | 36/960 | 34475/1 | complaint works- Bedroom 2 works- Daughters bedroom
Appointments | Sam Benden | 23/06/2026 08:00 | Appointment Booked - Staff Allocated | 77 Murford Avenue, Hartcliffe | BS13 9JY | CARRY OUT WORK | Miss Leanne Perlini | 447913627653 |  |  | No | 36/1431 | 100563/1 | DA - Skirting:Renew any size softwood plain, moulded or chamfered skirting plugged to brickwork, including all ends and angles and prepare for redecoration, and remove waste and debris. ¦ 72JR381001 x1 SKIRTING:RENEW - NO ASBESTOS REPORT WITH ORDER
Appointments | Jamie Hunt | 23/06/2026 08:00 | Appointment Started | 36 Cossington Road | BS4 1DP | CARRY ON WORKS | Mr Nathan Eddolls | 447377764845 |  |  | No | 36/1402 | 102245/1 | Various works to kitchen, bathroom and hallway following complaint
Appointments | Sahib Singh | 23/06/2026 08:00 | Appointment Booked - Staff Allocated | 14 Holbrook Crescent, Hartcliffe, Bristol BS13 0EU | BS13 0EU | CARRY ON WORKS | Mr George Fisher | 447916558909 |  |  | No | 36/1124 | 60323/1 | vJeffway-AS PER ROB DOIDGE - TREATMENT / PAINTING TO SMALL AREAS OF MOULD BY FRONT DOOR, TO BATHROOM WALLS BY W.C AND LIVING ROOM UNDER WINDOW.
Appointments | Izaak Ellis | 23/06/2026 08:00 | Works Completed | 110 EXMOUTH ROAD | BS4 1BE | attend to carry out customer care visit | Mrs Barbara Livesey | 447341372047 |  | Area 4 - South East | No | 36/833 | 1234784 | Complaint Disrepair work: Jeffway to prep and gloss paint both the rear and front doors. (second sor code is on previous order to be re-attended)
Appointments | James Stephens | 23/06/2026 08:00 | Appointment Started | 36 Cossington Road | BS4 1DP | CARRY ON WORKS | Mr Nathan Eddolls | 447377764845 |  |  | No | 36/1402 | 102245/1 | Various works to kitchen, bathroom and hallway following complaint
Appointments | Clayton Burbridge | 23/06/2026 08:00 | Appointment Started | 45 BARTON HOUSE | BS5 9SL | DISREPAIR- COMPLETE WORKS ASK SHAN FOR JOB SHEET | Miss Kumba Njie | 447403734472 | Kumbis10@outlook.com | Area 3 - Central | No | 36/1120 | 34228/1 | Complaint works- Please see email and report.
Appointments | Jessie Parsons | 23/06/2026 08:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY ON WORKS | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Jason Thomas | 23/06/2026 08:00 | Appointment Started | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY ON WORKS | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Jack Slade | 23/06/2026 08:00 | Appointment Booked - Staff Allocated | 4 Broadstone Walk, Hartcliffe | BS13 0AN | CARRY ON WORKS | Mr Edward Smith | 447359931114 | smith1957eddie@gmail.com |  | No | 36/1562 | 114250/1 | JW - AS PER JOHN OYENIYI - Renew Kitchen Flooring, Renew Extractor Fan to Bathroom, Mould wash Bathroom ceiling, Bedroom 1, and Living Room, Gutter repairs
Appointments | Luke Coleman | 23/06/2026 07:00 | Appointment Started | 223 Coronation Road, Southville | BS3 1RL | Repoint chimney stack, re render parapet walls LHS, renew flaunching, renew chimney pots | Miss Samantha Kelly | 447707133710 | sambokelly39@gmail.com |  | No | 36/1550 | 112815/1 | JW - AS PER JEFF NECK - Please arrange roof inspection now scaffold move to front elevation to check front chimney and flashings. As per Darren
Appointments | Glen Norman | 22/06/2026 13:00 | Appointment Started | 30 Downton Road | BS4 1PZ | DISREPAIR - DECS. PLEASE ASK SHAN TO SEND WORKS TO YOU AS TO BIG FOR NOTES | Mrs Elizabeth Holbrook | 7494645368 | lizhol2005@hotmail.co.uk | Area 4 - South East | No | 36/1211 | 71356/1 | Complaint works- Please see email and Report
Appointments | Alan Smith | 22/06/2026 12:00 | Appointment Booked - Staff Allocated | 16 Millground Road, Withywood, Bristol BS13 8NF | BS13 8NF | COMPLETE EICR | Ms Amber Trott | 07570099005 |  |  | No | 36/1635 | 119766/3 | Jeffway-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 01/07/26. 10 DAY PERIOD ENDS 15/07/26
Appointments | Clayton Burbridge | 22/06/2026 12:00 | Appointment Booked - Staff Allocated | 3 LANGTON HOUSE | BS2 0DR | COMPLETE DISREPAIR WORKS | Miss Jade Richards | 447865720719 | missrichards996@gmail.com |  | No | 36/1296 | 47071/4 | Please carry out disrepair works as listed
Appointments | James Stephens | 22/06/2026 12:00 | Appointment Started | 120 Stillingfleet Road | BS13 9RJ | CARRY ON WORKS | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | George Sutton-Fricker | 22/06/2026 09:00 | Appointment Started | 72 Dunkerry Road | BS3 4LA | INSTALL FAN TO BATHROOM | Ms Tamsin Carruthers-Cole | 07470179069 | tamcarruthers93@icloud.com | Area 4 - South East | No | 36/1213 | 71961/1 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled
Appointments | James Stephens | 22/06/2026 08:00 | Appointment Booked - Staff Allocated | 18 Maynard Close | BS13 0AR | CARRY OUT WORK | Mr Stephen Reed | 07385640542 |  |  | No | 36/1319 | 81339/2 | Jeff Way - As per Rob Doidge: Renewal of w.c in full, renewal of basin & bath taps & renew non slip floor covering to bathroom. Please liaise with h/o Lisa Taylor regarding appts / access.
Appointments | Luke Coleman | 22/06/2026 08:00 | Appointment Started | 223 Coronation Road, Southville | BS3 1RL | Repoint chimney stack, re render parapet walls LHS, renew flaunching, renew chimney pots | Miss Samantha Kelly | 447707133710 | sambokelly39@gmail.com |  | No | 36/1550 | 112815/1 | JW - AS PER JEFF NECK - Please arrange roof inspection now scaffold move to front elevation to check front chimney and flashings. As per Darren
Appointments | Christopher Mcgregor | 22/06/2026 08:00 | Appointment Booked - Staff Allocated | 187 Four Acres, Withywood | BS13 8QQ | CARRY OUT WORK | Mrs Anita Chetoui | 447851684171 | angelsdemons200@hotmail.fr |  | No | 36/1327 | 63837/2 | Jeffway- John O-2m2 paving repair to the entrance paving slab John Oyeniyi booked to attend 22/04/26 10am-2pm - text sent External
Appointments | Glen Norman | 22/06/2026 08:00 | N/A | 120 Stillingfleet Road | BS13 9RJ | CARRY OUT WORK | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Darren Wallis | 22/06/2026 08:00 | Appointment Booked - Staff Allocated | 60 Stillingfleet Road | BS13 9RH | COMPLETE DISREPAIR WORKS AS PER NOTES | Miss Gemma Goodman | 447534177512 | gemma-goodman@hotmail.com | Area 5 - South West | No | 36/1234 | 63929/1 | Repairs to ceiling cracks and external wall insulation - some additional minor works
Appointments | Luke Coleman | 22/06/2026 08:00 | Appointment Ended - No Access | 16 MURFORD WALK | BS13 9LB | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mr Lee Collins | 447863221791 |  | Area 5 - South West | No | 36/992 | 37119/1 | complaint works- Thomas Lear- please see report and email.
Appointments | Sam Benden | 22/06/2026 08:00 | Appointment Booked - Staff Allocated | 30 Latchmoor House, Banwell Close | BS13 7DS | CARRY OUT WORK | Ms Maria Santos | 447860148645 | marialucia_0209@hotmail.com |  | No | 36/1334 | 47331/2 | Jeffway- as per John O-: Renew double base unit (beneath sink) and paint walls
Appointments | Jessie Parsons | 22/06/2026 08:00 | Appointment Booked - Staff Allocated | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | George Sutton-Fricker | 22/06/2026 08:00 | Appointment Booked - Staff Allocated | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Clayton Burbridge | 22/06/2026 08:00 | Appointment Started | 72 Dunkerry Road | BS3 4LA | COMPLETE DISREPAIR WORKS - AS PER NOTES | Ms Tamsin Carruthers-Cole | 07470179069 | tamcarruthers93@icloud.com | Area 4 - South East | No | 36/1213 | 71961/1 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled
Appointments | Christopher Mcgregor | 22/06/2026 08:00 | Appointment Ended - No Access | 29 LONG CROSS | BS11 0HG | DISREPAIR - ROOM DECS | Miss Kiesha Jarvis | 447983650359 | Kieshajarvis92@hotmail.com | Area 1 - North West | No | 36/1031 | 38624/1 | DISREPAIR WORKS / AS PER G SQUARED SITE SURVEY
Appointments | James Stephens | 22/06/2026 07:00 | Appointment Ended - No Access | 43 Hareclive Road | BS13 9JL | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Terri Barrett | 07384853647 | missterribarrett1@gmail.com | Area 5 - South West | No | 36/1281 | 78797/1 | Repairs throughout property
Appointments | Izaak Ellis | 22/06/2026 07:00 | Works Completed | 15 WHITTOCK SQUARE | BS14 8DA | pre inspection for handover | Mrs Suzanne Brunsdon | 447768750715 | sbrunsdon1959@yahoo.com | Area 4 - South East | No | 36/1066 | 34956/2 | Please carry out additional disrepair works as listed.
Appointments | Christopher Mcgregor | 22/06/2026 07:00 | Appointment Ended - No Access | 11 Briscoes Avenue, Hartcliffe | BS13 0LB | CARRY OUT WORK | Miss Kirsty Dibble | 447446850161 | kirstydibble11@msn.com |  | No | 36/1328 | 92694/1 | Jeffway-as per John O-Renew 2 panels of fence at Rear Elevation
Appointments | Sam Benden | 22/06/2026 07:00 | Appointment Ended - No Access | 1 Chelvey Close | BS13 0DW | CARRY OUT WORK | Ms Jade Inker | 447447161490 | jadeinker@icloud.com | Area 5 - South West | No | 36/1409 | 102260/1 | 1 X DIAGONAL CRACK TO FRONT BEDROOM TO FILL AND PATCH PAINT. WILL MONITOR FOR FURTHER MOVEMENT GOING FORWARD
Appointments | Sam Benden | 19/06/2026 13:00 | N/A | 72 Birch Road, Southville, Bristol BS3 1PF |  | ATTEMPT TO COMPLETE WORKS | Miss Marion Stanley | 447473505500 | marion.stanley100@gmail.com |  | No | 36/1181 | 65004/2 | Jeffway-as per John O-Repair to Plasterboard ceiling in Kitchen, Refix Handrails to wall, Overhaul 3nos door, Renew loft hatch
Appointments | Jessie Parsons | 19/06/2026 13:00 | Appointment Started | 61 Sherrin Way | BS13 8RX | CARRY ON WORKS | Miss Caroline Smyth | 447340352334 |  |  | No | 36/1261 | 24570/1 | Scrape loose paint work in ground floor bathroom ceiling. Remove existing wall heater and apply plaster skim to side wall and window head. Apply anti condensation paint to completed ceiling and reskimmed wall.
Appointments | Christopher Mcgregor | 19/06/2026 12:00 | Appointment Ended - Follow On Work Required | 30 Downton Road | BS4 1PZ | ASSIST GLEN WITH ENSURING ALL DECS ARE COMPLETED | Mrs Elizabeth Holbrook | 7494645368 | lizhol2005@hotmail.co.uk | Area 4 - South East | No | 36/1211 | 71356/1 | Complaint works- Please see email and Report
Appointments | Daniel Williams | 19/06/2026 12:00 | Appointment Booked - Staff Allocated | 326 Bishport Avenue, Hartcliffe | BS13 0HE | DISREPAIR PLASTERING WORKS | Mrs Kim Rickwood | 07900518571 |  |  | No | 36/1277 | 82059/1 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled
Appointments | Sam Benden | 19/06/2026 12:00 | N/A | 72 Birch Road, Southville, Bristol BS3 1PF |  | ATTEMPT TO COMPLETE WORKS | Miss Marion Stanley | 447473505500 | marion.stanley100@gmail.com |  | No | 36/1181 | 65004/2 | Jeffway-as per John O-Repair to Plasterboard ceiling in Kitchen, Refix Handrails to wall, Overhaul 3nos door, Renew loft hatch
Appointments | Jessie Parsons | 19/06/2026 12:00 | Appointment Started | 61 Sherrin Way | BS13 8RX | CARRY ON WORKS | Miss Caroline Smyth | 447340352334 |  |  | No | 36/1261 | 24570/1 | Scrape loose paint work in ground floor bathroom ceiling. Remove existing wall heater and apply plaster skim to side wall and window head. Apply anti condensation paint to completed ceiling and reskimmed wall.
Appointments | Jessie Parsons | 19/06/2026 10:00 | Appointment Booked - Staff Allocated | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | Jamie Hunt | 19/06/2026 10:00 | Appointment Booked - Staff Allocated | 21 Pavey Road, Hartcliffe | BS13 0JX | CARRY OUT WORK | Ms Angela Pearce | 447703409060 | angepearce@hotmail.com |  | No | 36/1368 | 95466/1 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M
Appointments | James Stephens | 19/06/2026 09:00 | Appointment Booked - Staff Allocated | 120 Stillingfleet Road | BS13 9RJ | CARRY OUT WORK | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Daniel Williams | 19/06/2026 08:00 | N/A | 3 FOUR ACRES CLOSE | BS13 8QW | DISREPAIR WORKS AS PER NOTES | Miss Carrie Winstone | 447946857641 | winstonecarrie@mail.com | Area 5 - South West | No | 36/1056 | 45287/1 | Complaint disrepair work - repair finish above front door and paint. Repoint crack in brickwork on front elevation. patch repair plaster by Bed1 and Kitchen and paint to finish. Check radiators and bleed if necessary.
Appointments | Darren Wallis | 19/06/2026 08:00 | Appointment Ended - No Access | 3 FOUR ACRES CLOSE | BS13 8QW | DISREPAIR NOTES - SEE NOTES | Miss Carrie Winstone | 447946857641 | winstonecarrie@mail.com | Area 5 - South West | No | 36/1056 | 45287/1 | Complaint disrepair work - repair finish above front door and paint. Repoint crack in brickwork on front elevation. patch repair plaster by Bed1 and Kitchen and paint to finish. Check radiators and bleed if necessary.
Appointments | Jamie Hunt | 19/06/2026 08:00 | N/A | 36 Englishcombe Road, Hartcliffe | BS13 0NP | CARRY OUT WORK | Miss Johanna Waite | 447754037109 | johannawaite0@gmail.com |  | No | 36/1326 | 64468/2 | Jeffway-as per Ian O-Paint Living room ceiling and Kitchen walls John Oyeniyi booked to attend 22/04/26 between 12-5.30pm - text sent Property
Appointments | Sam Benden | 19/06/2026 08:00 | N/A | 75 Collinson Road | BS13 9PH | CARRY OUT WORK | Mr Zak Dollin | 447880696290 | Dollinzak4@gmail.com |  | No | 36/1352 | 62738/2 | Jeffway-AS PER DAVE PALMER - EXTRACTOR OVERHAUL TO BATHROOM, RENEW SAFETY FLOORING IN BATHROOM, ROOM REDEC TO DOWNSATAIS BACK ROOM.
Appointments | Jessie Parsons | 19/06/2026 08:00 | Appointment Booked - Staff Allocated | 1 HIGHRIDGE CRESCENT | BS13 8HN | repairs | Mr & Mrs Irene and Graham Payne | 447867680786 | graham48.payne@btopenworld.com/Irene.payne@btopenworld.com |  | No | 36/1061 | 8502/2 | JEFF WAY - FAO JEFF NECK RENDER EXT WALL TO BOTTOM OF STAIRS & WORKS TO REAR SHOWER CUBICLE AS PER EMAIL
Appointments | Glen Norman | 19/06/2026 08:00 | Appointment Ended - Follow On Work Required | 30 Downton Road | BS4 1PZ | DISREPAIR - DECS. PLEASE ASK SHAN TO SEND WORKS TO YOU AS TO BIG FOR NOTES | Mrs Elizabeth Holbrook | 7494645368 | lizhol2005@hotmail.co.uk | Area 4 - South East | No | 36/1211 | 71356/1 | Complaint works- Please see email and Report
Appointments | Christopher Mcgregor | 19/06/2026 08:00 | Appointment Started | 41 Charfield Road | BS10 5QS | REMOVAL OF IVY FOR CAVITY WALL INSULATION | Miss Shalliza Lee | 07985456244 | Shallizalee2017@outlook.com | Area 1 - North West | No | 36/1511 | 107205/1 | Complaint works- Please see email and report ( works to rectify leak damage thought address)
Appointments | Darren Wallis | 18/06/2026 15:00 | Appointment Started | 20 Stillingfleet Road | BS13 9QN | repairs | Miss Katie Nelson | 447860232180 |  | Area 5 - South West | No | 36/219 | 1177729 | Hack off loose plaster ceiling and re-skim
Appointments | Shane George Saunders | 18/06/2026 15:00 | Appointment Started | 61 WALKER CLOSE | BS5 0XB | clean treat paint | Mr Ousman Jeng | 447429459303 | ousujeng61@yahoo.co.uk | Area 3 - Central | No | 36/1041 | 41375/1 | DISREPAIR - JEFF WAY TO CARRY OUT WORKS RAISED BY CHARLOTTE SMART 07920616045
Appointments | Darren Whitchurch | 18/06/2026 15:00 | Appointment Booked - Staff Allocated | 1 HIGHRIDGE CRESCENT | BS13 8HN | SITE VISIT | Mr & Mrs Irene and Graham Payne | 447867680786 | graham48.payne@btopenworld.com/Irene.payne@btopenworld.com |  | No | 36/1061 | 8502/2 | JEFF WAY - FAO JEFF NECK RENDER EXT WALL TO BOTTOM OF STAIRS & WORKS TO REAR SHOWER CUBICLE AS PER EMAIL
Appointments | Jessie Parsons | 18/06/2026 14:00 | Appointment Started | 1 Gorham Close | BS11 0TP | CARRY ON WORKS | Miss Jessica Kroneck-Morgan | 447938490254 | Jessicamorgan7279@gmail.com |  | No | 36/1304 | 90676/1 | As per darryls (07733831884) - Repoint where mortar missing and crumbling - refer to pics
Appointments | Alan Smith | 18/06/2026 13:00 | Appointment Started | 17 MILLPOOL COURT | BS10 6AX | LIGHT:RENEW FLEX LAMPHOLDER ROSE | Mr Steven Bendall | 447498020555 | stevebendall19@gmail.com | Area 1 - North West | No | 36/1229 | 76933/1 | PD1 - Please carry out works as listed.
Appointments | Jessie Parsons | 18/06/2026 13:00 | Appointment Started | 1 Gorham Close | BS11 0TP | CARRY ON WORKS | Miss Jessica Kroneck-Morgan | 447938490254 | Jessicamorgan7279@gmail.com |  | No | 36/1304 | 90676/1 | As per darryls (07733831884) - Repoint where mortar missing and crumbling - refer to pics
Appointments | Alan Smith | 18/06/2026 12:00 | Appointment Booked - Staff Allocated | 28 Martock Road, Bedminster | BS3 5QL | eicr test | Miss Naomi Edwards | 447926857924 | naomi_edwards96@hotmail.com |  | No | 36/1548 | 103681/3 | JEFF WAY A? PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 10/06/26. 10 DAY PERIOD ENDS 24/06/26.
Appointments | Darren Wallis | 18/06/2026 12:00 | Appointment Started | 20 Stillingfleet Road | BS13 9QN | repairs | Miss Katie Nelson | 447860232180 |  | Area 5 - South West | No | 36/219 | 1177729 | Hack off loose plaster ceiling and re-skim
Appointments | Sahib Singh | 18/06/2026 12:00 | N/A | 430 Bishport Avenue | BS13 0HU | 2xddgu bathroom/kitchen | Miss Odette O'Connor | 447342180306 |  | Area 5 - South West | No | 36/1129 | 60035/1 | Jeffway - As per Rob D - INSTALL WINDOW MOUNTED FANS TO KITCHEN AND BATHROOM , CORNISH TYPE PROPERTY. ALSO RENEW SILICON AROUND BATH IN FULL
Appointments | Shane George Saunders | 18/06/2026 11:00 | Appointment Booked - Staff Allocated | 34 BAYNTON HOUSE | BS5 0DH | PLEASE ATTEND WITH SAB - 2 HANDED JOB | Mr Mark Laudat | 07365575045 | MARKLENZ50@HOTMAIL.CO.UK | Area 3 - Central | No | 36/1591 | 117381/1 | ELE- Water dripping from the light fixture in the kitchen - make safe
Appointments | Daniel Williams | 18/06/2026 09:00 | Appointment Booked - Staff Allocated | 24 Warden Road | BS3 1BU | START INTERNAL WORKS | Mr Michael Cox | 07835412388 |  | Area 5 - South West | No | 36/1174 | 69097/1 | Complaint disrepair works : guttering clear water ways. Front elevation inspect and renew gully cover on front. Bathroom reseal joint in the waste pipe
Appointments | Sahib Singh | 18/06/2026 09:00 | Appointment Booked - Staff Allocated | 8 Campian Walk, Inns Court | BS4 1XE | CARRY OUT WORK | Miss Rachel Hayward | 447512532626 | HAYWARD935@GMAIL.COM |  | No | 36/1456 | 105847/1 | AS PER GERRY RYAN = EMMA HIND = Remove wall and put back rooms after hidden grow room behind Airing cupboard and also inspected loft for damage
Appointments | Darren Wallis | 18/06/2026 08:00 | Appointment Booked - Staff Allocated | 91 TRYM SIDE | BS9 2HG | DISREPAIR WORKS - COMPLETE WORKS | Mr & Mrs Donna and Shane Phelps | 447948963077 | cooper_dona@hotmail.com |  | No | 36/1044 | 39385/1 | Complaint disrepair works / as per G Squared site survey.
Appointments | Daniel Williams | 18/06/2026 08:00 | Appointment Started | 39 MANCROFT AVENUE | BS11 0HX | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mrs & Mrs LABIAN AND LOUISE WILLIAMS | 447380427485 | l.williams76@hotmail.co.uk | Area 1 - North West | No | 36/901 | 29993/2 | DN786139-response repairs overflow - Complaint disrepair works - as G Squared survey.
Appointments | Sam Benden | 18/06/2026 08:00 | Appointment Started | 6 LAMBERT PLACE | BS4 1XH | TILLE/GROUT/DECORATE BATHROOM | Miss Freya Mccardle | 447301026749 | freyamccardle90@icloud.com | Area 4 - South East | No | 36/1196 | 69916/1 | AS PER GERRY RYAN - PLM to remove cistern and hand basin, pla to skim damage walls and renew tiles to the basin and tap end of bath - dec to paint bahtroom and paint not emulsion ele to over haul bathroom
Appointments | Jamie Hunt | 18/06/2026 08:00 | Appointment Started | 160 Crosscombe Drive, Hartcliffe, Bristol | BS13 0BS | repairs | Mrs Helen Radford | 447454475403 |  |  | No | 36/810 | 27014/1 | JEFF WAY - AS PER ROB DOIDGE - RENEWAL OF KITCHEN PLASTERBOARD CEILING DAMAGED AFTER VARIOUS LEAKS. NA.D TO ARTEX COATING. 2 X COATS OF PAINT TO NEW CEILING AND MIST COAT . APPROX 7M2
Appointments | Jessie Parsons | 18/06/2026 08:00 | Appointment Started | 51 Church Lane | BS3 4NE | REMOVAL OF SHRUB / WEED SELF SET IN CHIMNEY STACK | Miss Janice Maule | 7495760228 | maulejanice@gmail.com |  | No | 36/1127 | 61262/1 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF SHRUB / WEED SELF SET IN CHIMNEY STACK & M/G ANY HOLES FROM REMOVING TO STOP WATER INGRESS. REPAIR TO DAMAGED CORNER OF BLACK ACO DRAINAGE BY BK GATE
Appointments | Glen Norman | 18/06/2026 08:00 | Appointment Started | 30 Downton Road | BS4 1PZ | DISREPAIR - DECS. PLEASE ASK SHAN TO SEND WORKS TO YOU AS TO BIG FOR NOTES | Mrs Elizabeth Holbrook | 7494645368 | lizhol2005@hotmail.co.uk | Area 4 - South East | No | 36/1211 | 71356/1 | Complaint works- Please see email and Report
Appointments | Sahib Singh | 18/06/2026 08:00 | Appointment Booked - Staff Allocated | 34 BAYNTON HOUSE | BS5 0DH | EMERGENCY JOB - MAKE SAFE OF KITCHEN LIGHT | Mr Mark Laudat | 07365575045 | MARKLENZ50@HOTMAIL.CO.UK | Area 3 - Central | No | 36/1591 | 117381/1 | ELE- Water dripping from the light fixture in the kitchen - make safe
Appointments | James Stephens | 18/06/2026 08:00 | Appointment Booked - Staff Allocated | 41 Torrington Avenue, Knowle | BS4 1EQ | Complete Work | Mr Mohammed Alfashtaki | 447428044488 | RUBENHOOD476@GMAIL.COM |  | No | 36/1384 | 98660/1 | Daniel Allen - Please renew bath and fittings
Appointments | Clayton Burbridge | 17/06/2026 15:00 | Appointment Started | 5 KEBLE AVENUE | BS13 8PP | COMPLETE WORKS - ASK SHAN TO SEND SHEET | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Izaak Ellis | 17/06/2026 13:00 | Appointment Started | 215 FOUR ACRES | BS13 8QQ | site visit | Miss Charlie Cowan | 447392902528 | CHARLIEPETAL1992@GMAIL.COM | Area 5 - South West | No | 36/1153 | 64479/1 | JEFF WAY - AS PER IAN O: CLEAR ANY BUILDING WASTE IN LOFT , STAIN BLOCK ,STOP COCK , DRAINAGE REAR , DRAINAGE FRONT .WEATHER
Appointments | Jessie Parsons | 17/06/2026 12:00 | Appointment Booked - Staff Allocated | 25 Henbury Court, Station Road, Henbury | BS10 7QL | repairs | Miss Emma Phillips | 447710259094 | emmaphillips2010@hotmail.co.uk |  | No | 36/1323 | 92275/1 | As per Darryl's request - Works to bathroom and hallway - Many thanks
Appointments | Darren Wallis | 17/06/2026 12:00 | Appointment Started | 20 Hills Barton | BS13 7JH | stain block wall rhs of cooker // paint wall rhs of cooker4smts;; kitchen,, Prep and Paint ceiling upto 20 sq mts kitchen | Mr Craig Gillespie | 447767365800 | gillespiec521@gmail.com | Area 5 - South West | No | 36/1192 | 61846/2 | Jeff Way - As per John Oyeniyi: Redecorate Kitchen ceiling; Part of wall and Living Room Ceiling
Appointments | Shane George Saunders | 17/06/2026 09:00 | N/A | 28A KNOWLE ROAD | BS4 2EE | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Chloe Roberts | 447508760753 | CWEAREN123@GMAIL.COM | Area 4 - South East | No | 36/1380 | 98472/1 | Complaint Work - Please see e-mail and report
Appointments | Jamie Hunt | 17/06/2026 08:00 | Appointment Started | 4 MOW BARTON | BS13 8DW | WORKS TO BE CONFIRMED - PLEASE SPEAK WITH OFFICE. | Miss Rachel Best | 07450906821 | bestrachel38@gmail.com | Area 5 - South West | No | 36/1432 | 100812/1 | JW - As per Jeff Neck - Bellcast repairs, remove existing PVC moulding across window head/opening, new silicone seal - Copy of WO information emailed to JW 14.05.2026 ¦ 72PT423007 x5 RENDER REPAIRS:RENEW BELLCAST FEATURE - Render Repairs:Renew bell; 72JR3
Appointments | Daniel Williams | 17/06/2026 08:00 | Appointment Booked - Staff Allocated | 43 Hareclive Road | BS13 9JL | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Terri Barrett | 07384853647 | missterribarrett1@gmail.com | Area 5 - South West | No | 36/1281 | 78797/1 | Repairs throughout property
Appointments | Oliver Maurice Shore | 17/06/2026 08:00 | Appointment Booked - Staff Allocated | 43 Hareclive Road | BS13 9JL | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Terri Barrett | 07384853647 | missterribarrett1@gmail.com | Area 5 - South West | No | 36/1281 | 78797/1 | Repairs throughout property
Appointments | Jessie Parsons | 17/06/2026 08:00 | Appointment Booked - Staff Allocated | 42 Eldon Terrace, Windmill Hill | BS3 4PA | repairs | Miss Lisa Cooper | 447990844185 | lis4cooper@hotmail.co.uk |  | No | 36/1347 | 58180/1 | Renew Bed 2 ceiling tested by CASA , NAD inc ELE / DEC parts R.M
Appointments | Alan Smith | 17/06/2026 08:00 | Appointment Booked - Staff Allocated | 139 NEWLAND ROAD | BS13 9DT | FIT NEW EXTRACTOR FAN IN KITCHEN AND BATHROOM | Mr Warwick Curran | 447388195569 |  | Area 5 - South West | No | 36/626 | 1064042 | Window overhaul, throughout. Damp and mould wash - throughout. Extractors - supply and fit new extractor in bathroom and kitchen. Replace blownDGU - living room. Fill hole and skim - kitchen (behind boiler) 2 x smoke alarks - hallway and living room
Appointments | Christopher Mcgregor | 17/06/2026 08:00 | Appointment Booked - Staff Allocated | 24 DORCHESTER ROAD | BS7 0LA | COMPLETE WORKS - DISREPAIR | Mrs Natasha Wolfe | 07523285628 | nswolfe1986@gmail.com | Area 2 - North East | No | 36/1451 | 100636/1 | Complaint works- please see email and report- Bedroom 1 Stain-block affected section of ceiling Repaint ceiling (small section) Bedroom 2 Decorate ceiling Hack off damaged sections of wall and make good Sink sections of wall as required Room si
Appointments | Clayton Burbridge | 17/06/2026 08:00 | Appointment Started | 120 Stillingfleet Road | BS13 9RJ | CARRY ON WORKS | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Darren Wallis | 17/06/2026 07:00 | Appointment Ended - No Access | 45 Spartley Drive, Highridge | BS13 8DQ | mould clean treat paint | Miss Diane Campbell | 447845800154 | diane33campbell@gmail.com |  | No | 36/1246 | 64289/2 | Jeffway- as per Joe C-Scrape back loose paint prep surface and decorate - overhaul extractor and grill
Appointments | James Stephens | 16/06/2026 14:00 | Appointment Booked - Staff Allocated | 96 CUTLER ROAD | BS13 8DY | COMPLETE DISREPAIR WORKS - WE ARE UNABLE TO ATTEND UNTIL 1PM | Miss Nicola Brewer | 447391976230 | britneybrewer10@icloud.com | Area 5 - South West | No | 36/1132 | 58481/1 | Tenants daughters number is - 07501593854 - Brittany - Jeffway to clean and service windows, renew sealant in bathroom, S&F door frame, refix surface mounted box.
Appointments | Jack Slade | 16/06/2026 14:00 | N/A | 96 CUTLER ROAD | BS13 8DY | COMPLETE DISREPAIR WORKS | Miss Nicola Brewer | 447391976230 | britneybrewer10@icloud.com | Area 5 - South West | No | 36/1132 | 58481/1 | Tenants daughters number is - 07501593854 - Brittany - Jeffway to clean and service windows, renew sealant in bathroom, S&F door frame, refix surface mounted box.
Appointments | Sam Benden | 16/06/2026 14:00 | Appointment Started | 15 HOLLIDGE GARDENS | BS3 1AQ | CARRY OUT WORK | Mrs Gloria Benkhelifa | 447780118151 | stevenson488@hotmail.co.uk | Area 5 - South West | No | 36/1198 | 35087/4 | Jeff Way - as per John Oyeniyi: Redecoration works to wall and kitchen in bathroom, mould wash ceiling in kitchen.
Appointments | Alan Smith | 16/06/2026 14:00 | Appointment Started | 24 DORCHESTER ROAD | BS7 0LA | OVERHAUL FANS AND REPLACE AS NEEDED | Mrs Natasha Wolfe | 07523285628 | nswolfe1986@gmail.com | Area 2 - North East | No | 36/1451 | 100636/1 | Complaint works- please see email and report- Bedroom 1 Stain-block affected section of ceiling Repaint ceiling (small section) Bedroom 2 Decorate ceiling Hack off damaged sections of wall and make good Sink sections of wall as required Room si
Appointments | Darren Whitchurch | 16/06/2026 14:00 | Appointment Started | 120 Stillingfleet Road | BS13 9RJ | SITE VISIT | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | James Stephens | 16/06/2026 13:00 | Appointment Started | 37 MAYNARD ROAD | BS13 0AX | CARRY OUT WORK | Miss Joanna Coles | 447824427329 | jocoles@blueyonder.co.uk | Area 5 - South West | No | 36/1155 | 64574/1 | JEFF WAY-AS PER ROB D: WHERE ABSENT , FIT NEW NEWEL POST, HANDRAIL AND BALUSTERS TO STAIRCASE RHS. CURRENTLY HHSRS HAZARD WITH YOUNG CHILDREN IN PROPERTY.
Appointments | Sam Benden | 16/06/2026 12:00 | Appointment Started | 15 HOLLIDGE GARDENS | BS3 1AQ | CARRY ON WORKS | Mrs Gloria Benkhelifa | 447780118151 | stevenson488@hotmail.co.uk | Area 5 - South West | No | 36/1198 | 35087/4 | Jeff Way - as per John Oyeniyi: Redecoration works to wall and kitchen in bathroom, mould wash ceiling in kitchen.
Appointments | James Stephens | 16/06/2026 12:00 | Appointment Started | 37 MAYNARD ROAD | BS13 0AX | CARRY OUT WORK | Miss Joanna Coles | 447824427329 | jocoles@blueyonder.co.uk | Area 5 - South West | No | 36/1155 | 64574/1 | JEFF WAY-AS PER ROB D: WHERE ABSENT , FIT NEW NEWEL POST, HANDRAIL AND BALUSTERS TO STAIRCASE RHS. CURRENTLY HHSRS HAZARD WITH YOUNG CHILDREN IN PROPERTY.
Appointments | Jack Slade | 16/06/2026 12:00 | Appointment Booked - Staff Allocated | 4 Crosscombe Drive | BS13 0DW | replace kitchen fan | Miss Jade Inker | 447447161490 | jadeinker@icloud.com |  | No | 36/1498 | 102266/1 | JW - AS PER ROB D- RENEW POORLY CUT TILES TO LHS AND RHS OF NEW BOILER. REGROUT/SILICON THE WORKTOP/TILE JOINT BEHIND SINK. RENEW 2 X SHELVES TO SINK UNIT , RENEW PLINTH AND RAISE DOOR HINGE TO SAME UNIT, RENEW EXTRACTOR FAN ALSO
Appointments | Sam Benden | 16/06/2026 10:00 | Appointment Booked - Staff Allocated | 4 Crosscombe Drive | BS13 0DW | CARRY OUT WORK | Miss Jade Inker | 447447161490 | jadeinker@icloud.com |  | No | 36/1498 | 102266/1 | JW - AS PER ROB D- RENEW POORLY CUT TILES TO LHS AND RHS OF NEW BOILER. REGROUT/SILICON THE WORKTOP/TILE JOINT BEHIND SINK. RENEW 2 X SHELVES TO SINK UNIT , RENEW PLINTH AND RAISE DOOR HINGE TO SAME UNIT, RENEW EXTRACTOR FAN ALSO
Appointments | Darren Whitchurch | 16/06/2026 10:00 | Appointment Booked - Staff Allocated | 62 Willinton Road | BS4 1HU | site inspection | Mrs Dawn Bodley | 447359235852 | DAWNBODLEY8@GMAIL.COM ,mark2010bodley@hotmail.co.uk | Area 4 - South East | No | 36/130 | 1176914 | Ventilator and wall hack replaster and insulation
Appointments | Izaak Ellis | 16/06/2026 10:00 | Appointment Booked - Staff Allocated | 51 CLAVERHAM ROAD | BS16 2HT | PLEASE LOOK AT BATHROOM WORKS AS PER JOB SHEET | Mrs Ekhlas Ahmed | 447852136389 | ekhlas.ahmed62@gmail.com | Area 2 - North East | No | 36/1039 | 39230/1 | Complaint disrepair works / as per G Squared site survey
Appointments | Jack Slade | 16/06/2026 09:00 | N/A | 9 BERRYCROFT | BS3 1XG | replace kitchen | Mr Wilton Martin | 447826505269 |  | Area 5 - South West | No | 36/1342 | 93362/1 | Complaint works throughout property; Renew kitchen and bathroom extract fans; resecure hot tap on kitchen sink; replace window handle (with key) in bathroom as per Tom Taylor
Appointments | Jamie Hunt | 16/06/2026 09:00 | Appointment Booked - Staff Allocated | 37 COTSWOLD ROAD | BS3 4NX | COMPLETE DISREPAIR WORKS AS PER NOTES | Miss Natasha A Parsons | 447586700058 |  | Area 4 - South East | No | 36/1362 | 97885/1 | PD1 - Please carry out works as listed. Any questions, the surveyor is James Bailey
Appointments | Darren Wallis | 16/06/2026 08:00 | Appointment Started | 29 LONG CROSS | BS11 0HG | RAKE AND RESEAL 3 X WINDOWS - RENEW KITCHEN PLINTH | Miss Kiesha Jarvis | 447983650359 | Kieshajarvis92@hotmail.com | Area 1 - North West | No | 36/1031 | 38624/1 | DISREPAIR WORKS / AS PER G SQUARED SITE SURVEY
Appointments | Jessie Parsons | 16/06/2026 08:00 | Appointment Booked - Staff Allocated | 42 Eldon Terrace, Windmill Hill | BS3 4PA | repairs | Miss Lisa Cooper | 447990844185 | lis4cooper@hotmail.co.uk |  | No | 36/982 | 40478/1 | Living room ceiling partially collapsed, now made safe, requires mortar removing/boarding and skimming, ELE and DEC parts included R.M
Appointments | Jamie Hunt | 16/06/2026 08:00 | Works Completed | 16 Martock Crescent, Bedminster | BS3 5QJ | repairs | Ms Chloe Hester-Drew | 447884556875 |  |  | No | 36/971 | 39947/1 | Jeffway- as per Joe Cotrell- Various works at property including flooring. Please see email for full works description
Appointments | Kyran Thomas | 16/06/2026 08:00 | N/A | 87 Chalcroft House, Lower Sidney Street | BS3 1ST | CONDENSATION DRIP TREATMENT | Miss Mary Togher | 01179668733 | marytogher916@gmail.com |  | No | 36/1302 | 83580/2 | JEFF WAY - AS PER ROB D: MOULD/ CONDENSATION DRIP TREATMENT & REPAINT WITH HALOPHEN PAINT TO FULL WINDOW WALL & REVEAL & FULL SINK WALL IN KITCHEN
Appointments | Clayton Burbridge | 16/06/2026 08:00 | Appointment Started | 5 KEBLE AVENUE | BS13 8PP | COMPLETE WORKS - ASK SHAN TO SEND SHEET | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Christopher Mcgregor | 16/06/2026 08:00 | Appointment Booked - Staff Allocated | 24 DORCHESTER ROAD | BS7 0LA | COMPLETE WORKS - DISREPAIR | Mrs Natasha Wolfe | 07523285628 | nswolfe1986@gmail.com | Area 2 - North East | No | 36/1451 | 100636/1 | Complaint works- please see email and report- Bedroom 1 Stain-block affected section of ceiling Repaint ceiling (small section) Bedroom 2 Decorate ceiling Hack off damaged sections of wall and make good Sink sections of wall as required Room si
Appointments | Darren Wallis | 16/06/2026 08:00 | Appointment Ended - No Access | 154 Mancroft Avenue | BS11 0JA | PAINTING AND OVERHAUL WINDOWS | Miss Hannah Harley | 07948415734 |  | Area 1 - North West | No | 36/635 | 1163169 | Complaint works as per tom taylor - bed 1 overhaul window. Bed 2 - overhaul window, stain block area of staining to the front corner of the wall in W.C, remove flaking paint and redec affected area
Appointments | Sam Benden | 16/06/2026 08:00 | N/A | 34 HIGHBURY ROAD | BS3 5NT | CARRY ON WORKS | Mr & Mrs Spencer | 447487238953 | barbarabev5@gmail.com | Area 5 - South West | No | 36/882 | 33711/1 | JW - Rob Doidge - Renew base unit to kitchen, Renew drawer to kitchen unit, Flooring - Discuss with Rob for locations
Appointments | Daniel Williams | 16/06/2026 08:00 | Appointment Booked - Staff Allocated | 24 Warden Road | BS3 1BU | MEET DARREN ON SITE TO LOOK AT ROOF WORKS | Mr Michael Cox | 07835412388 |  | Area 5 - South West | No | 36/1174 | 69097/1 | Complaint disrepair works : guttering clear water ways. Front elevation inspect and renew gully cover on front. Bathroom reseal joint in the waste pipe
Appointments | Jamie Hunt | 15/06/2026 18:00 | Appointment Started | 11 Hersey Gardens, Withywood | BS13 8RR | ASK SHAN TO SEND U JOB SHEET | Mr Wayne Gardiner | 447984212331 | wgardinercharles@hotmail.com |  | No | 36/864 | 32892/1 | Jeffway - As per John Oyeniyi - REDECORATION WORK IN THE KITCHEN AND BATHROOM
Appointments | Jamie Hunt | 15/06/2026 18:00 | N/A | 32 Sampsons Road, Hartcliffe | BS13 0EN | DISREPAIR - PLEASE COMPLETE INCOMPLETE WORKS AS PER NOTES | Mr Dylan Micheal Phipps | 447774702931 |  |  | No | 36/1212 | 71807/1 | Complaint works- living room,kitchen and bathroom. scrape off peeling paint on walls seal and repaint. replace glass units in livingroom. treat pipes in bathroom, replace broken down pipe
Appointments | Alan Smith | 15/06/2026 16:00 | Appointment Started | 108 Capgrave Crescent | BS4 4TP | RECONNECT FAN TO BATHROOM | Miss Ella Watts | 447741656356 | Ellawatts@gmail.com | Area 4 - South East | No | 36/1068 | 38801/2 | Complaint disrepair works / as per CG
Appointments | Glen Norman | 15/06/2026 12:00 | Appointment Booked - Staff Allocated | 37 COTSWOLD ROAD | BS3 4NX | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Natasha A Parsons | 447586700058 |  | Area 4 - South East | No | 36/1362 | 97885/1 | PD1 - Please carry out works as listed. Any questions, the surveyor is James Bailey
Appointments | Darren Wallis | 15/06/2026 12:00 | Appointment Started | 7 HARECLIVE ROAD | BS13 9JL | source and replace missing window handles, | Miss Michaela Minall | 447846915006 | MAKEEMINALL1990@GMAIL.COM | Area 5 - South West | No | 36/1077 | 16747/2 | Jeff Way - Redecorate Bathroom Ceiling, and overhaul windows as per John Oyeniyi.
Appointments | Izaak Ellis | 15/06/2026 12:00 | Works Completed | 53 Maidenhead Road, Hartcliffe | BS13 0PR | attend to carry out customer care visit | Mrs Deborah Walsh | 447519205725 | walshdeborah59@gmail.com |  | No | 36/1148 | 10162/4 | Fill cracks in Hallway and Kitchen, and patch plaster to Liv Rm wall including expamet, to stabilise - temporary repairs while waiting for decant.
Appointments | Izaak Ellis | 15/06/2026 11:00 | Works Completed | 43 Harewood Road | BS5 7ST | pre inspection for handover | Mrs Diane Evans | 07894060676 | diane.76@hotmail.co.uk |  | No | 36/1029 | 34769/2 | Please carry out disrepairs works as listed out.
Appointments | Daniel Williams | 15/06/2026 09:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | COMPLETE PLASTERING WORKS -D | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | Clayton Burbridge | 15/06/2026 09:00 | Appointment Booked - Staff Allocated | 17 THOMSON ROAD | BS5 0JR | COMPLETE PAINTING WORKS | Miss Nicola Carmichael | 447415434570 | nicola.ccarmichael@yahoo.com |  | No | 36/1078 | 45318/3 | Disrepair - Roofing and front elevation works as per Darren.
Appointments | Ryan Greenslade | 15/06/2026 08:00 | Appointment Booked - Staff Allocated | 120 Stillingfleet Road | BS13 9RJ | CARRY OUT WORK | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Daniel Williams | 15/06/2026 08:00 | Appointment Ended - No Access | 60 Stillingfleet Road | BS13 9RH | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Gemma Goodman | 447534177512 | gemma-goodman@hotmail.com | Area 5 - South West | No | 36/1234 | 63929/1 | Repairs to ceiling cracks and external wall insulation - some additional minor works
Appointments | Darren Whitchurch | 15/06/2026 08:00 | Appointment Booked - Staff Allocated | 120 Stillingfleet Road | BS13 9RJ | site visit | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Jessie Parsons | 15/06/2026 08:00 | Appointment Booked - Staff Allocated | 120 Stillingfleet Road | BS13 9RJ | CARRY ON WORKS | Ms Kirsty Morgan | 447513271146 | brojoeandad@gmail.com |  | No | 36/1305 | 53053/2 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber
Appointments | Glen Norman | 15/06/2026 08:00 | Appointment Started | 11 Borver Grove | BS13 9LX | CARRY ON WORKS | Miss Danielle Pine | 7518663029 | danniipine@gmail.com |  | No | 36/1285 | 86409/1 | JEFF WAY - AS PER ROB DOIDGE - FOLLOWING PROPERTY FIRE - SMOKE CLEAN WHERE REQUIRED TO PROPERTY FOLLOWING FIRE. REPAIR / RENEWAL AS REQUIRED TO STAIRCASE, DOWNSTAIRS DOORFRAMES AND METER CUPBOARD UNDER STAIRS
Appointments | Jack Slade | 12/06/2026 13:00 | Appointment Booked - Staff Allocated | 15 WHITSON HOUSE | BS2 9ED | 2 x overhauls | Mr Abdulai Sow | 447961024412 | sowabdulai85@yahoo.co.uk | Area 3 - Central | No | 36/1383 | 98769/1 | Complaint works- Clear guttering around walkway. inspect loft and do what's necessary. over haul all fans. refit kitche unit doors. Replace bath panel
Appointments | Timothy Cotter | 12/06/2026 13:00 | N/A | Greenway Bush Lane Site, Greenway Bush Lane | BS3 1SG | CARRY OUT WORK |  |  |  |  | No | 36/1371 | 87948/2 | Jeff Way - as per John Oyeniyi: Patch repair to tarmac on accessible ramp. John Oyeniyi booked to attend 30/04/26.
Appointments | Glen Norman | 12/06/2026 12:00 | Appointment Booked - Staff Allocated | 19 Pavey Close | BS13 0JZ | Paint papered wall | Mr Brock Corner | 447946852690 |  | Area 5 - South West | No | 36/165 | 1069440 | AS PER NICHOLAS CORY JEFFWAY TO USE SEMPATAP PRODUCT ON WALL IN LIVING ROOM AGAINST NEXT DOOR STAIR CASE( BRICK WALL PAPER)
Appointments | Jessie Parsons | 12/06/2026 12:00 | Appointment Booked - Staff Allocated | 61 Sherrin Way | BS13 8RX | CARRY OUT WORK | Miss Caroline Smyth | 447340352334 |  |  | No | 36/1261 | 24570/1 | Scrape loose paint work in ground floor bathroom ceiling. Remove existing wall heater and apply plaster skim to side wall and window head. Apply anti condensation paint to completed ceiling and reskimmed wall.
Appointments | Darren Whitchurch | 12/06/2026 12:00 | Works Completed | 384 BishportAvenue | BS13 0HE | CARRY ON WORKS | Miss Natasha Pearce | 07502076490 | Pearce133@hotmail.com |  | No | 36/1009 | 12541/2 | JEFF WAY - AS PER ROB DOIDGE - WINDOW OVERHAUL TO PROPERTY , VARIOUS INCLUDING LIVING ROOM , BALCONY AND BEDROOMS ARE DRAUGHTY, LIKELY HINGE ISSUES
Appointments | Alan Smith | 12/06/2026 10:00 | N/A | 75 Collinson Road | BS13 9PH | overhaul bathroom fan | Mr Zak Dollin | 447880696290 | Dollinzak4@gmail.com |  | No | 36/1352 | 62738/2 | Jeffway-AS PER DAVE PALMER - EXTRACTOR OVERHAUL TO BATHROOM, RENEW SAFETY FLOORING IN BATHROOM, ROOM REDEC TO DOWNSATAIS BACK ROOM.
Appointments | Clayton Burbridge | 12/06/2026 10:00 | Appointment Booked - Staff Allocated | 2 Chestnut House | BS13 0RP | CARRY OUT WORK | Ms Sharon Stevens | 07983478777 | sharonstevens1970@hotmail.com |  | No | 36/1442 | 72741/2 | JEFF WAY-AS PER ROB D:RENEWAL OF BATH PANEL WITH ACRYLIC, WHILE PANEL OFF FILL RODENT HOLES UNDER BATH & PHOTOGRAPH. ALSO FILL HOLES AROUND BATHROOM PIPEWORK NEXT TO WC & SMALL HOLES TO BEDROOM CORNER & COMMUNAL LOBBY
Appointments | Darren Whitchurch | 12/06/2026 10:00 | Appointment Booked - Staff Allocated | 223 Coronation Road, Southville | BS3 1RL | site inspection | Miss Samantha Kelly | 447707133710 | sambokelly39@gmail.com |  | No | 36/1550 | 112815/1 | JW - AS PER JEFF NECK - Please arrange roof inspection now scaffold move to front elevation to check front chimney and flashings. As per Darren
Appointments | George Sutton-Fricker | 12/06/2026 09:00 | Appointment Started | 61 Sherrin Way | BS13 8RX | CARRY ON WORKS | Miss Caroline Smyth | 447340352334 |  |  | No | 36/1261 | 24570/1 | Scrape loose paint work in ground floor bathroom ceiling. Remove existing wall heater and apply plaster skim to side wall and window head. Apply anti condensation paint to completed ceiling and reskimmed wall.
Appointments | Jamie Hunt | 12/06/2026 09:00 | Appointment Booked - Staff Allocated | 15 WHITSON HOUSE | BS2 9ED | COMPLETE DISREPAIR WORKS AS PER JOB SHEET | Mr Abdulai Sow | 447961024412 | sowabdulai85@yahoo.co.uk | Area 3 - Central | No | 36/1383 | 98769/1 | Complaint works- Clear guttering around walkway. inspect loft and do what's necessary. over haul all fans. refit kitche unit doors. Replace bath panel
Appointments | Sam Benden | 12/06/2026 08:00 | N/A | 72 Birch Road, Southville, Bristol BS3 1PF |  | patch plaster ceiling, matching artex finish | Miss Marion Stanley | 447473505500 | marion.stanley100@gmail.com |  | No | 36/1181 | 65004/2 | Jeffway-as per John O-Repair to Plasterboard ceiling in Kitchen, Refix Handrails to wall, Overhaul 3nos door, Renew loft hatch
Appointments | Sahib Singh | 12/06/2026 08:00 | Appointment Booked - Staff Allocated | 20 COWLING ROAD | BS14 8DX | 1new kitchen dgu | Miss Victoria Burleton | 447736030606 | vixnriley@gmail.com | Area 4 - South East | No | 36/1082 | 53058/1 | As per sean p : Install fan through window in kitchen.
Appointments | Clayton Burbridge | 12/06/2026 08:00 | Appointment Booked - Staff Allocated | 10 Rowan House, Bishport Avenue | BS13 0RS | CARRY OUT WORK | Miss Jenny Hurst | 07916409252 | JENNYHURST38@GMAIL.COM |  | No | 36/1271 | 84362/1 | Jeff Way - FAO John O - Renew trickle air vent to Window in bedroom 1 and overhaul vent in bathroom
Appointments | Darren Wallis | 12/06/2026 08:00 | Appointment Booked - Staff Allocated | 18 ST JOHNS LANE | BS3 5AA | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mrs Farah Mohammed | 447759674788 |  | Area 4 - South East | No | 36/1262 | 39290/1 | DISREPAIR WORKS
Appointments | Timothy Cotter | 12/06/2026 08:00 | N/A | 9 Wymbush Crescent | BS13 0BB | COMPLETE CONCRETING WORKS | Miss Tara Miles | 07796964367 | seyes2014@outlook.com |  | No | 36/1053 | 44988/1 | jw - AS PER ROB DOIDGE - REPAIRS TO EXTERNAL PATHWAY / GARDEN AROUND DRAIN WHERE CRACKED, APPROX 3M2
Appointments | Daniel Williams | 12/06/2026 08:00 | Appointment Booked - Staff Allocated | 84 FREMANTLE HOUSE | BS2 8LH | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mr Ahmed Adam | 447729669360 | muhamadineahmed@gmail.com | Area 3 - Central | No | 36/1168 | 3719/2 | Disrepair Works - James Bailey (surveyor) Plumber/ Gas engineer to carry out checks for leaks in flat and to water heater. Living room/ boiler cupboard/ cupboard - remove damaged plaster, replaster, apply 2 mist coats and 2 coats of emulsion. Doors - supp
Appointments | James Stephens | 12/06/2026 08:00 | Appointment Started | 88 Four Acres | BS13 8RD | latex WC | Mrs Wendy Jones | 07885974191 | snobleandcocandles@outlook.com |  | No | 36/1199 | 75911/1 | Jeffway - As Per Rob D - Various works to downstairs WC (see email sent with full job description 17.03.2026) - DOWNSTAIRS WC, HACK OFF LOOSE PLASTER TO WC WALL AND WINDOW WALL AS REQUIRED AND REPLASTER, HAVE ALLOWED FOR 2M2 BUT UNKNOWN TOTAL AMOUNT. HAVE
Appointments | Jason Thomas | 12/06/2026 08:00 | Appointment Booked - Staff Allocated | 77 Murford Avenue, Hartcliffe | BS13 9JY | MOULD CLEAN | Miss Leanne Perlini | 447913627653 |  |  | No | 36/1386 | 98689/1 | Daniel Allen - apply treatment to window surrounds in front bedrooms 1 and 2
Appointments | Jessie Parsons | 12/06/2026 08:00 | Appointment Started | 24 DORCHESTER ROAD | BS7 0LA | DISREPAIR - COMPLETE PLASTERING TO L/ROOM | Mrs Natasha Wolfe | 07523285628 | nswolfe1986@gmail.com | Area 2 - North East | No | 36/1451 | 100636/1 | Complaint works- please see email and report- Bedroom 1 Stain-block affected section of ceiling Repaint ceiling (small section) Bedroom 2 Decorate ceiling Hack off damaged sections of wall and make good Sink sections of wall as required Room si
Appointments | Glen Norman | 12/06/2026 08:00 | N/A | 46 MURFORD AVENUE | BS13 9JY | DISREPAIR - PAINT BOTTOM OF STAIRS | Miss Carmel Jay | 07572106138 | Carmeljay15@gmail.com | Area 5 - South West | No | 36/1087 | 46466/1 | Complaint works- please see email and report- Thomas Lear
Appointments | Christopher Mcgregor | 12/06/2026 08:00 | Appointment Started | 11 Borver Grove | BS13 9LX | CARRY ON WORKS | Miss Danielle Pine | 7518663029 | danniipine@gmail.com |  | No | 36/1285 | 86409/1 | JEFF WAY - AS PER ROB DOIDGE - FOLLOWING PROPERTY FIRE - SMOKE CLEAN WHERE REQUIRED TO PROPERTY FOLLOWING FIRE. REPAIR / RENEWAL AS REQUIRED TO STAIRCASE, DOWNSTAIRS DOORFRAMES AND METER CUPBOARD UNDER STAIRS
Appointments | Sam Benden | 12/06/2026 07:00 | Appointment Ended - Second Visit Required | 72 Birch Road, Southville, Bristol BS3 1PF |  | patch plaster ceiling, matching artex finish | Miss Marion Stanley | 447473505500 | marion.stanley100@gmail.com |  | No | 36/1181 | 65004/2 | Jeffway-as per John O-Repair to Plasterboard ceiling in Kitchen, Refix Handrails to wall, Overhaul 3nos door, Renew loft hatch
Appointments | Sam Benden | 11/06/2026 16:00 | Appointment Started | 11 Borver Grove | BS13 9LX | CARRY ON WORKS | Miss Danielle Pine | 7518663029 | danniipine@gmail.com |  | No | 36/1285 | 86409/1 | JEFF WAY - AS PER ROB DOIDGE - FOLLOWING PROPERTY FIRE - SMOKE CLEAN WHERE REQUIRED TO PROPERTY FOLLOWING FIRE. REPAIR / RENEWAL AS REQUIRED TO STAIRCASE, DOWNSTAIRS DOORFRAMES AND METER CUPBOARD UNDER STAIRS
Appointments | Jack Slade | 11/06/2026 16:00 | Works Completed | 15 WHITTOCK SQUARE | BS14 8DA | re complaint | Mrs Suzanne Brunsdon | 447768750715 | sbrunsdon1959@yahoo.com | Area 4 - South East | No | 36/1066 | 34956/2 | Please carry out additional disrepair works as listed.
Appointments | Jamie Hunt | 11/06/2026 16:00 | Appointment Started | 160 Crosscombe Drive, Hartcliffe, Bristol | BS13 0BS | repairs | Mrs Helen Radford | 447454475403 |  |  | No | 36/810 | 27014/1 | JEFF WAY - AS PER ROB DOIDGE - RENEWAL OF KITCHEN PLASTERBOARD CEILING DAMAGED AFTER VARIOUS LEAKS. NA.D TO ARTEX COATING. 2 X COATS OF PAINT TO NEW CEILING AND MIST COAT . APPROX 7M2
Appointments | Jack Slade | 11/06/2026 12:00 | N/A | 9 BERRYCROFT | BS3 1XG | REPLACE TWO FANS | Mr Wilton Martin | 447826505269 |  | Area 5 - South West | No | 36/1342 | 93362/1 | Complaint works throughout property; Renew kitchen and bathroom extract fans; resecure hot tap on kitchen sink; replace window handle (with key) in bathroom as per Tom Taylor
Appointments | James Stephens | 11/06/2026 12:00 | Appointment Booked - Staff Allocated | 9 BERRYCROFT | BS3 1XG | DISREPAIR - RESECURE HOT TAP ON KITCHENS INK AND REPLACE WINDOW HANDLE WITH KEY TO BATHROOM | Mr Wilton Martin | 447826505269 |  | Area 5 - South West | No | 36/1342 | 93362/1 | Complaint works throughout property; Renew kitchen and bathroom extract fans; resecure hot tap on kitchen sink; replace window handle (with key) in bathroom as per Tom Taylor
Appointments | Jessie Parsons | 11/06/2026 12:00 | Appointment Started | 20 Stillingfleet Road | BS13 9QN | repairs | Miss Katie Nelson | 447860232180 |  | Area 5 - South West | No | 36/219 | 1177729 | Hack off loose plaster ceiling and re-skim
Appointments | Christopher Mcgregor | 11/06/2026 11:00 | Appointment Started | 146 WOOTTON ROAD | BS4 4AT | COMPLETE REMAINING WORKS | Mr Nathan Taylor | 447300869515 |  | Area 4 - South East | No | 36/194 | 001123136 | DISREPAIR - Various jobs around property
Appointments | Darren Whitchurch | 11/06/2026 11:00 | Works Completed | 1 Gorham Close | BS11 0TP | SITE INSPECTION FOR BATHROOM WORKS | Miss Jessica Kroneck-Morgan | 447938490254 | Jessicamorgan7279@gmail.com |  | No | 36/1304 | 90676/1 | As per darryls (07733831884) - Repoint where mortar missing and crumbling - refer to pics
Appointments | Jack Slade | 11/06/2026 10:00 | N/A | 640 Long Cross | BS11 0TT | DISREPAIR WORKS - COMPELTE ELECTRICAL WORKS | Miss Tereza Candida Das Neves Carneiro | 447598794303 | terezacarneiro23@gmail.com | Area 1 - North West | No | 36/843 | 28604/1 | Bathroom Mould by window. fit extrct fan, rnw bath panel. LIV ROOM - ceiling, hack off, replaster & decorate. BED1 - Mould on ceiling in the corner, APPLY MLD WASH, EXTERNAL - Exposed wires loose on wall & back of door. cut down aerial/ele
Appointments | James Stephens | 11/06/2026 09:00 | Appointment Booked - Staff Allocated | 1 Failand Crescent (KS1985) | BS9 2HH | DISREPAIR WORKS - ASK FOR KEYSAFE | Miss Miss Leah Rouabhi & Mr Daniel Scott | 07702401969 | dannytscot@yahoo.co.uk |  | No | 36/1532 | 108445/1 | PD1 - Carryout overhaul whilst conducting other works
Appointments | Izaak Ellis | 11/06/2026 09:00 | Appointment Started | 36 FULFORD ROAD | BS13 9PB | POST INSPECTION OF WORKS | Miss Clare Hands | 447493455288 |  | Area 5 - South West | No | 36/1083 | 53314/1 | Jeff Way - Renew silicone to bath, patch plaster repair and redecoration as per John Oyeniyi.
Appointments | James Stephens | 11/06/2026 09:00 | N/A | 31 Maynard Close | BS13 0AS | CARRY OUT WORK | Mr Thomas Parslow | 447491231553 | thomas.parslow@hotmail.co.uk | Area 5 - South West | No | 36/927 | 36534/1 | JW - AS PER JOHN O: PLEASE FIX WALL TILES ON WALL ABOVE BATH AND REPAIR SPOT ON BATH
Appointments | Glen Norman | 11/06/2026 09:00 | Appointment Started | 13 LITTLECROSS HOUSE | BS3 1SQ | CARRY ON WORKS | Mr Stephen Bennett |  |  | Area 5 - South West | No | 36/1200 | 58367/2 | Jeffway-: AS PER ROB D - FOLLOWING LEAK FROM ABOVE FLAT, NOW FIXED. REDECORATE AFFECTED AREAS OF KIT AND BATHROOM WALLS / CEILINGS AS REQUIRED. MATCH IN PAINT COLOURS. APPROX 14M2 TOTAL AREA
Appointments | Timothy Cotter | 11/06/2026 08:00 | Appointment Booked - Staff Allocated | 557 Hareclive Road, Hartcliffe | BS13 0LU | CARRY OUT WORK | Miss Nina Sharp | 447873801044 | NEEN54338@GMAIL.COM |  | No | 36/1248 | 79995/1 | Jeffway-Rob D-AS PER ROB DOIDGE - RENEWAL OF SMALL SKIRTING TO KIT CUPBOARD. MAKING GOOD TO BOTTOM OF WALLS AND HOLE IN LATEX FLOORING FIRST
Appointments | Darren Wallis | 11/06/2026 08:00 | Appointment Booked - Staff Allocated | 18 ST JOHNS LANE | BS3 5AA | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mrs Farah Mohammed | 447759674788 |  | Area 4 - South East | No | 36/1262 | 39290/1 | DISREPAIR WORKS
Appointments | Sam Benden | 11/06/2026 08:00 | Appointment Started | 57 Whittock Road | BS14 8DQ | COMPLETE DISREPAIR WORKS - COLLECT PAPERWORK | Mr David Beal | 447753816018 |  |  | No | 36/831 | 1230835 | complaints works- Kitchen New extractor fan. Remove and renew silicone to window and door. Pvc mould wash to window and door. Mould wash and anti mould paint to window and door reveals. Window overhaul. Living Room Renew plasterboard to head of ba
Appointments | Jamie Hunt | 11/06/2026 08:00 | N/A | 57 Whittock Road | BS14 8DQ | COMPLETE DISREPAIR WORKS | Mr David Beal | 447753816018 |  |  | No | 36/831 | 1230835 | complaints works- Kitchen New extractor fan. Remove and renew silicone to window and door. Pvc mould wash to window and door. Mould wash and anti mould paint to window and door reveals. Window overhaul. Living Room Renew plasterboard to head of ba
Appointments | Jamie Hunt | 11/06/2026 08:00 | N/A | 638 Long Cross |  | DISREPAIR - COMPLETE WORKS FROM YESTERDAY | Mr Michael Hawker | 07510860155 | michael.hawker@ymail.com |  | No | 36/899 | 29196/1 | Complaint- Charlotte Smart As per Scott Schedule, charlotte.smart2@bristol.gov.uk
Appointments | Jack Slade | 11/06/2026 08:00 | Appointment Started | 6 LAMBERT PLACE | BS4 1XH | overhaul fan bathroom | Miss Freya Mccardle | 447301026749 | freyamccardle90@icloud.com | Area 4 - South East | No | 36/1196 | 69916/1 | AS PER GERRY RYAN - PLM to remove cistern and hand basin, pla to skim damage walls and renew tiles to the basin and tap end of bath - dec to paint bahtroom and paint not emulsion ele to over haul bathroom
Appointments | Christopher Mcgregor | 11/06/2026 08:00 | Appointment Started | 28 Hersey Gardens, Withywood, Bristol BS13 8RR | BS13 8RR | try and move roof vent tile up a few courses as its tight to the eaves from the inside, once done connect ducting from bathroom fan to tile , paint ceiling in bathroom | Miss Nicola M Godwin | 447759909414 |  |  | No | 36/733 | 1231839 | Recommended works as per Site visit from Gavin authorised by KPD/AW - Fan works, Roof vent tile, Scaffolding & Dec works
Appointments | James Stephens | 11/06/2026 08:00 | Appointment Started | 31 Maynard Close | BS13 0AS | CARRY OUT WORK | Mr Thomas Parslow | 447491231553 | thomas.parslow@hotmail.co.uk | Area 5 - South West | No | 36/927 | 36534/1 | JW - AS PER JOHN O: PLEASE FIX WALL TILES ON WALL ABOVE BATH AND REPAIR SPOT ON BATH
Appointments | Daniel Williams | 11/06/2026 08:00 | Appointment Booked - Staff Allocated | 5 KEBLE AVENUE | BS13 8PP | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Oliver Maurice Shore | 11/06/2026 08:00 | Appointment Booked - Staff Allocated | 5 KEBLE AVENUE | BS13 8PP | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Glen Norman | 11/06/2026 08:00 | N/A | 13 LITTLECROSS HOUSE | BS3 1SQ | CARRY ON WORKS | Mr Stephen Bennett |  |  | Area 5 - South West | No | 36/1200 | 58367/2 | Jeffway-: AS PER ROB D - FOLLOWING LEAK FROM ABOVE FLAT, NOW FIXED. REDECORATE AFFECTED AREAS OF KIT AND BATHROOM WALLS / CEILINGS AS REQUIRED. MATCH IN PAINT COLOURS. APPROX 14M2 TOTAL AREA
Appointments | Izaak Ellis | 11/06/2026 08:00 | Appointment Started | 46 MURFORD AVENUE | BS13 9JY | POST INSPECTION OF WORKS | Miss Carmel Jay | 07572106138 | Carmeljay15@gmail.com | Area 5 - South West | No | 36/1087 | 46466/1 | Complaint works- please see email and report- Thomas Lear
Appointments | Darren Wallis | 11/06/2026 07:00 | Appointment Booked - Staff Allocated | 36 Cossington Road | BS4 1DP | CARRY ON WORKS | Mr Nathan Eddolls | 447377764845 |  |  | No | 36/1402 | 102245/1 | Various works to kitchen, bathroom and hallway following complaint
Appointments | Sam Benden | 10/06/2026 16:00 | Appointment Booked - Staff Allocated | 41 Charfield Road | BS10 5QS | CARRY ON WORKS | Miss Shalliza Lee | 07985456244 | Shallizalee2017@outlook.com | Area 1 - North West | No | 36/1511 | 107205/1 | Complaint works- Please see email and report ( works to rectify leak damage thought address)
Appointments | Sahib Singh | 10/06/2026 15:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | OVERHAUL FANS X2 AND SOCKET IN BEDROOM 1 | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | James Stephens | 10/06/2026 15:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | RE FIT RAD TO WALL | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | Sam Benden | 10/06/2026 15:00 | Appointment Started | 1-62 Millmead House, | BS13 0JL | retile behind basin in communal room |  |  |  |  | No | 36/1293 | 89315/1 | Jeffway-AS PER DAVE PALMER - RENEW TILES TO VARIOUS AREAS IN THE FOYER AND LAUNDRY ROOM, RENEW TILES IN TOILET, REMOVE SINK, REMOVE CLEAN AND REFIX TILES TO WALL WHERE SINK IS FIXED.AS PER SURVEY PHOTOS
Appointments | James Stephens | 10/06/2026 14:00 | Works Completed | 23 Hersey Gardens, Withywood | BS13 8RR | CARRY ON WORKS | Miss Chantelle Munford | 447999171822 |  |  | No | 36/1203 | 70046/2 | Jeffway- as per John O-Overhaul windows; Paint Bathroom ceiling
Appointments | James Stephens | 10/06/2026 13:00 | Appointment Started | 357 Bishport Avenue | BS13 0BN | DISREPARI - CARRY OUT WORKS AS PER SHEET. COLLECT PAPERWORK | Miss Carly Moore | 447415442529 | carlyjmoore@hotmail.co.uk | Area 5 - South West | No | 36/1052 | 44995/1 | JW-AS PER ROB DOIDGE - RENEWAL OF BATH, APPROX 1SQM TILES TO SHOWER WALL AND TAPS TO BASIN . FIT EXTRACTOR FAN WHERE PASSIVE VENT IS AND OVERHAUL W.C FOR LEAKS
Appointments | Jason Thomas | 10/06/2026 12:00 | N/A | 139 NEWLAND ROAD | BS13 9DT | mould clean throughout | Mr Warwick Curran | 447388195569 |  | Area 5 - South West | No | 36/626 | 1064042 | Window overhaul, throughout. Damp and mould wash - throughout. Extractors - supply and fit new extractor in bathroom and kitchen. Replace blownDGU - living room. Fill hole and skim - kitchen (behind boiler) 2 x smoke alarks - hallway and living room
Appointments | Izaak Ellis | 10/06/2026 12:00 | Appointment Started | 4 MOOR GROVE | BS11 0LR | POST INSPECTION OF WORKS | Miss Natasha Howie | 447900515261 | nathowie@yahoo.co.uk | Area 1 - North West | No | 36/1147 | TBC | DISREPAIR WORKS
Appointments | Jessie Parsons | 10/06/2026 12:00 | Appointment Started | 160 ST JOHNS LANE | BS3 5AJ | LOFT INSULATION, MOVE CABINET. CHECK PAINTING TOO. | Miss Bernice Pearce | 447305159966 |  | Area 4 - South East | No | 36/655 | 1215799 | remove existing loft insulation and replace to 450mm, stain block and paint landing ceiling
Appointments | Kyran Thomas | 10/06/2026 12:00 | Appointment Started | 16 WHITING ROAD | BS13 9EX | mould wash | Miss JULIE YEARSLEY | 447984946188 |  |  | No | 36/658 | 1207534 | Complaint works following letter of claim- silicone sealant to be replace on the external of the front door frame. hack off 1 square meter to head of front door and decorate. Stick back wallpaper to hallway. Overhaul both windows Cut out
Appointments | Christopher Mcgregor | 10/06/2026 11:00 | Appointment Started | 29 LONG CROSS | BS11 0HG | DISREPAIR WORKS AS PER NOTES | Miss Kiesha Jarvis | 447983650359 | Kieshajarvis92@hotmail.com | Area 1 - North West | No | 36/1031 | 38624/1 | DISREPAIR WORKS / AS PER G SQUARED SITE SURVEY
Appointments | Jessie Parsons | 10/06/2026 10:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | CARRY ON WORKS | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | Alan Smith | 10/06/2026 10:00 | N/A | 25 Burnell Drive, St Pauls | BS2 9JU | INSTALL FAN TO BATHROOM | Ms Amina Hussein | 447728540088 | aminahussein77@yahoo.co.uk |  | No | 36/1228 | 53830/2 | Complaint - Please carry out works as listed.
Appointments | Shane George Saunders | 10/06/2026 10:00 | Appointment Booked - Staff Allocated | 192 BROADLANDS DRIVE | BS11 0PH | mould clean | Miss Louise Lovelace | 447305731956 | louiselovelace117@yahoo.com | Area 1 - North West | No | 36/902 | 30060/1 | Complaints work - works throughout property. Re-raised
Appointments | Izaak Ellis | 10/06/2026 10:00 | Works Completed | 41 MONTREAL AVENUE | BS7 0NB | POST INSPECTION OF WORKS | Miss Terri Vining | 447827608271 | terri80@hotmail.co.uk | Area 2 - North East | No | 36/1227 | 76659/1 | Fill all cracks in kitchen
Appointments | Clayton Burbridge | 10/06/2026 09:00 | Appointment Started | 89, FLAT 10 ASHLEY ROAD | BS6 5NR | COMPLETE KITCHEN WORKS | Ms Harriet Kitchen | 447557980673 | ladyhcrazydiamond@gmail.com |  | No | 36/986 | 34878/1 | Please carry out additional disrepair works as listed out
Appointments | Darren Wallis | 10/06/2026 09:00 | Appointment Started | 89, FLAT 10 ASHLEY ROAD | BS6 5NR | COMPLETE KITCHEN WORKS | Ms Harriet Kitchen | 447557980673 | ladyhcrazydiamond@gmail.com |  | No | 36/986 | 34878/1 | Please carry out additional disrepair works as listed out
Appointments | Glen Norman | 10/06/2026 08:00 | Appointment Started | 19 Pavey Close | BS13 0JZ | strip paper, apply insulated paper to wall in living room | Mr Brock Corner | 447946852690 |  | Area 5 - South West | No | 36/165 | 1069440 | AS PER NICHOLAS CORY JEFFWAY TO USE SEMPATAP PRODUCT ON WALL IN LIVING ROOM AGAINST NEXT DOOR STAIR CASE( BRICK WALL PAPER)
Appointments | Timothy Cotter | 10/06/2026 08:00 | Appointment Booked - Staff Allocated | 22 Newland Walk, Withywood, Bristol BS13 9DZ | BS13 9DZ | CARRY OUT WORK | Mrs Kim E Jones | 447831486119 |  |  | No | 36/741 | 1232815 | Repair crack running through central position of 1st floor front bedroom ceiling, rub back to suit existing levels and apply emulsion paint to compete ceiling. Cut concrete foot path at the bottom of concrete garden steps and fix new plastic ACO drain in
Appointments | Christopher Mcgregor | 10/06/2026 08:00 | Appointment Started | 11 DYERS CLOSE | BS13 0LW | CARRY OUT WORK | Miss Kylie V Brooks | 447494972396 |  | Area 5 - South West | No | 36/593 | 1209879 | JEFF WAY - Apply mould treatment to bathroom ceiling . Fix new fan in external sloping wall with external tiled roof vent. Make repair to plastered window head in bathroom . Overhaul all windows. FAO JEFF NECK
Appointments | Jessie Parsons | 10/06/2026 08:00 | Appointment Booked - Staff Allocated | 64 Vincent Close | BS11 0UA | COMPLETE DISREPAIR WORKS | Miss Aimee Phillips | 447598440155 | aimee.jaynephillips@icloud.com | Area 1 - North West | No | 36/1169 | 4654/2 | Disrepair Works - James Bailey (surveyor) Roof - carry out roof inspection (flat roof will need to arrange access) Livingroom- scrape back chimney, scrape back chimney, treat brick, replaster, mist coat and stain block Kitchen - Damp and mould wash around
Appointments | Jamie Hunt | 10/06/2026 08:00 | Appointment Booked - Staff Allocated | 638 Long Cross |  | CARPENTRY WORKS | Mr Michael Hawker | 07510860155 | michael.hawker@ymail.com |  | No | 36/899 | 29196/1 | Complaint- Charlotte Smart As per Scott Schedule, charlotte.smart2@bristol.gov.uk
Appointments | Shane George Saunders | 10/06/2026 08:00 | N/A | 52 St Peters House | BS8 1DZ | mould/clean/treat | Mr Paul Stevens | 447769760106 |  | Area 3 - Central | No | 36/1360 | 95672/1 | COMPLAINT WORKS
Appointments | Kyran Thomas | 10/06/2026 08:00 | N/A | 33 FOUR ACRES CLOSE | BS13 8QW | damp/mould clean | Miss Sana Ahmed | 447796323150 | sana54@hotmail.com | Area 5 - South West | No | 36/627 | 1072724 | DISREPAIR - Living room - once TT has removed her tv from the wall, strip plaster back install dehum to dry, then replaster and apply mist coat. Damp and mould wash as necessary around the living room. Bathroom - damp and mould wash as necessary around th
Appointments | Daniel Williams | 10/06/2026 08:00 | Appointment Booked - Staff Allocated | 5 KEBLE AVENUE | BS13 8PP | PLASTERING WORKS AS PER DISREPAIR | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Oliver Maurice Shore | 10/06/2026 08:00 | Appointment Booked - Staff Allocated | 5 KEBLE AVENUE | BS13 8PP | PLASTERING WORKS AS PER DISREPAIR | Miss Hannah Quirk | 447481452299 | hannahquirk20@gmail.com | Area 5 - South West | No | 36/1238 | 79765/1 | PD1 - Please carry out works as listed
Appointments | Sam Benden | 09/06/2026 15:00 | Appointment Started | 2-33 Chard Court, Fortfield Road | BS14 9NL | CARRY ON WORKS |  |  |  |  | No | 36/1339 | 93675/1 | Ceiling patch in communal lounge repair required after leak As above
Appointments | Kyran Thomas | 09/06/2026 14:00 | N/A | 148 NEWQUAY ROAD | BS4 1EF | mould /clean/treat | Miss Bethany Hemmings | 447780442537 | bethanygrace87@icloud.com | Area 4 - South East | No | 36/1448 | 100263/1 | Direpair Claims works required
Appointments | Glen Norman | 09/06/2026 12:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | CARRY ON WORKS | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | Jason Thomas | 09/06/2026 12:00 | Appointment Started | 14 Holbrook Crescent, Hartcliffe, Bristol BS13 0EU | BS13 0EU | TREATMENT / PAINTING TO SMALL AREAS OF MOULD BY FRONT DOOR, TO BATHROOM WALLS BY W.C AND LIVING ROOM UNDER WINDOW. | Mr George Fisher | 447916558909 |  |  | No | 36/1124 | 60323/1 | vJeffway-AS PER ROB DOIDGE - TREATMENT / PAINTING TO SMALL AREAS OF MOULD BY FRONT DOOR, TO BATHROOM WALLS BY W.C AND LIVING ROOM UNDER WINDOW.
Appointments | Shane George Saunders | 09/06/2026 11:00 | N/A | 74 Willinton Road | BS4 1HU | mould wash to windows | Mr & Mrs Christina and Server Varga | 447404032310 | severvarga525@yahoo.com | Area 4 - South East | No | 36/1254 | 81613/1 | complaint works- please see email and report- Jeremy Price
Appointments | Daniel Williams | 09/06/2026 11:00 | Appointment Started | 55 Elmtree Drive | BS13 8NA | CARRY ON WORKS | Miss Nikki Cole | 447874225579 | cole2020cole@hotmail.com |  | No | 36/1307 | 61595/2 | Jeff Way - as per Jeff Neck: Apply plaster skim to all damage walls in 1st floor front bedroom.
Appointments | Christopher Mcgregor | 09/06/2026 10:00 | Appointment Booked - Staff Allocated | 192 BROADLANDS DRIVE | BS11 0PH | COMPLETE WORKS - PLEASE SPEAK TO CLAYTON | Miss Louise Lovelace | 447305731956 | louiselovelace117@yahoo.com | Area 1 - North West | No | 36/902 | 30060/1 | Complaints work - works throughout property. Re-raised
Appointments | Sam Benden | 09/06/2026 10:00 | N/A | 51 Hareclive Road | BS13 9JP | repairs | Miss Kaceyleigh Bailey | 447354335115 | KACYLEIGH20@YAHOO.COM |  | No | 36/1348 | 80828/1 | Attend Property - Remove sink unit to gain access for possible pest proof internal of the property.
Appointments | Sahib Singh | 09/06/2026 09:00 | Appointment Booked - Staff Allocated | 142 Long Cross, Lawrence Weston | BS11 0NS | eicr test | Miss Nicole Holmes | 447555075643 | nicoleh201013@hotmail.com |  | No | 36/1272 | 83660/3 | DN786139 RESPONSIVE REPAIRS OVERFLOW - JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 16/4/26 - 10 DAY PERIOD ENDS 30/4/26
Appointments | Jack Slade | 09/06/2026 09:00 | Appointment Started | 100 Carolina House | BS2 8LP | OVERHAUL FANS AND REPLACE AS NEEDED | Mr Abdelkader Mokhtari | 447488344064 |  |  | No | 36/993 | 27925/2 | Contact Andrew Griffiths
Appointments | Daniel Williams | 09/06/2026 09:00 | N/A | 40 HONEY GARSTON ROAD | BS13 9LT | CARRY ON WORKS | Mr Andrew Williams | 447414039781 | harrisonbell117@gmail.com | Area 5 - South West | No | 36/1014 | 43366/1 | Jeffway - As per John O: Repair Kitchen worktop, overhaul and resilicone window
Appointments | Daniel Williams | 09/06/2026 08:00 | N/A | 24 Faber Grove | BS13 0LD | DISREPAIR SEE WJOB SHEET | Miss Reanne Davis | 447435678630 | reanne2345@live.co.uk | Area 5 - South West | No | 36/1283 | 83392/1 | Repairs throughout property -
Appointments | Jessie Parsons | 09/06/2026 08:00 | Appointment Booked - Staff Allocated | 55 Elmtree Drive | BS13 8NA | CARRY OUT WORK | Miss Nikki Cole | 447874225579 | cole2020cole@hotmail.com |  | No | 36/1307 | 61595/2 | Jeff Way - as per Jeff Neck: Apply plaster skim to all damage walls in 1st floor front bedroom.
Appointments | Jamie Hunt | 09/06/2026 08:00 | N/A | 45 BARTON HOUSE | BS5 9SL | DISREPAIR WORKS - COMPLETE WORKS | Miss Kumba Njie | 447403734472 | Kumbis10@outlook.com | Area 3 - Central | No | 36/1120 | 34228/1 | Complaint works- Please see email and report.
Appointments | Christopher Mcgregor | 09/06/2026 08:00 | Appointment Booked - Staff Allocated | 21 Lansdowne Court | BS5 0RX | DISREPAIR - REPAIR CHIP TO BATH | Mrs Roselyn Gardens | 07340047328 | ROSEMCGOWAN975@GMAIL.COM |  | No | 36/1364 | 97924/1 | Touch up chip in bath. (tnt wants to keep the bath)
Appointments | Jason Thomas | 09/06/2026 08:00 | N/A | 87 Chalcroft House, Lower Sidney Street | BS3 1ST | CONDENSATION DRIP TREATMENT | Miss Mary Togher | 01179668733 | marytogher916@gmail.com |  | No | 36/1302 | 83580/2 | JEFF WAY - AS PER ROB D: MOULD/ CONDENSATION DRIP TREATMENT & REPAINT WITH HALOPHEN PAINT TO FULL WINDOW WALL & REVEAL & FULL SINK WALL IN KITCHEN
Appointments | Kyran Thomas | 09/06/2026 08:00 | N/A | 57 Whittock Road | BS14 8DQ | clean/tr3eat/paint/silicone | Mr David Beal | 447753816018 |  |  | No | 36/831 | 1230835 | complaints works- Kitchen New extractor fan. Remove and renew silicone to window and door. Pvc mould wash to window and door. Mould wash and anti mould paint to window and door reveals. Window overhaul. Living Room Renew plasterboard to head of ba
Appointments | Shane George Saunders | 09/06/2026 08:00 | N/A | 30 Home Mead, Creswicke Road | BS4 1UQ | mould wash/clean/treat | Mr David Summerhayes | 447845653061 |  |  | No | 36/1048 | 40673/1 | Complaint works- WO- Thomas Lear- please see email and complaint report
Appointments | Clayton Burbridge | 09/06/2026 08:00 | Appointment Started | 89, FLAT 10 ASHLEY ROAD | BS6 5NR | COMPLETE KITCHEN WORKS | Ms Harriet Kitchen | 447557980673 | ladyhcrazydiamond@gmail.com |  | No | 36/986 | 34878/1 | Please carry out additional disrepair works as listed out
Appointments | Darren Wallis | 09/06/2026 08:00 | Appointment Started | 89, FLAT 10 ASHLEY ROAD | BS6 5NR | COMPLETE KITCHEN WORKS | Ms Harriet Kitchen | 447557980673 | ladyhcrazydiamond@gmail.com |  | No | 36/986 | 34878/1 | Please carry out additional disrepair works as listed out
Appointments | Glen Norman | 09/06/2026 08:00 | Appointment Booked - Staff Allocated | 56 Sherrin Way, Withywood, | BS13 8RS | CARRY OUT WORK | Mrs Angela Gilmartin | 447837628663 | agilmartin@email.com |  | No | 36/1393 | 70105/2 | Jeff Way - Crack repair to Bedroom wall and ceiling, and redecoration as per John Oyeniyi.
Appointments | Jack Slade | 09/06/2026 08:00 | Works Completed | 17 MACEYS ROAD | BS13 0NQ | assess install of fan in kitchen | Miss Hayley Ward | 447847799942 | Ward10@hotmail.co.uk |  | No | 36/1161 | 65774/1 | AS PER ROB DOIDGE - FIT EXT FAN TO KIT WALL IN PLACE OF VENT. REMOVE WINDOW FAN AND REGLAZE WINDOW. FIT WINDOW FAN TO BATHROOM WINDOW. RUB DOWN AND REPAINT BATH RADIATIOR WITH GLOSS. RENEW STAIR TREAD TO 3RD STEP IN STAIRCASE. REPAIR DAMAGED FLOORBOARDS U
Appointments | James Stephens | 09/06/2026 08:00 | Appointment Started | 89, FLAT 10 ASHLEY ROAD | BS6 5NR | COMPLETE KITCHEN WORKS | Ms Harriet Kitchen | 447557980673 | ladyhcrazydiamond@gmail.com |  | No | 36/986 | 34878/1 | Please carry out additional disrepair works as listed out
Appointments | Jason Thomas | 08/06/2026 15:00 | Appointment Booked - Staff Allocated | 24 ARMADA HOUSE | BS2 8JX | MOULD CLEAN | Mr Ahmed Abdelaal | 447550607200 | shata110@yahoo.com | Area 3 - Central | No | 36/1453 | 103696/1 | Complaint Work - Please see e-mail and report
Appointments | Clayton Burbridge | 08/06/2026 13:00 | Appointment Booked - Staff Allocated | 8 Felton Grove, Bedminster Down | bs13 7ef | CARRY OUT WORK | Mrs Felicity Mcquiness | 447757162878 | fizmcguinness@virginmedia.com |  | No | 36/1303 | 76772/2 | Jeffway- as per Jeff N-Cut damage wallpaper to head and sides of 1st floor rear bedroom window to expose loose plasterwork. hack off and apply skim finish to match existing levels. Apply emulsion paint to new plasterwork only. Overhaul all PVC windows le
Appointments | Kyran Thomas | 08/06/2026 12:00 | Works Completed | 106a Cotham Brow | BS6 6AP | mould clean /treat/paint | Ms Corrise Crahart | 447305710455 | corrise97@gmail.com |  | No | 36/897 | 29125/1 | Disrepair- Charlotte Smart As per Scott Schedule,, quantities not accurate please advise when work is starting to meet on site to finalise quantities charlotte.smart2@bristol.gov.uk
Appointments | Izaak Ellis | 08/06/2026 12:00 | Appointment Booked - Staff Allocated | 54 ILMINSTER AVENUE | BS4 1LY | POST INSPECTION OF WORKS | Miss Angela Nash | 447407849891 | anash6703@gmail.com | Area 4 - South East | No | 36/1145 | 63374/1 | PD1 - Please carry out works as listed.
Appointments | Shane George Saunders | 08/06/2026 11:00 | N/A | 61 WALKER CLOSE | BS5 0XB | clean treat paint | Mr Ousman Jeng | 447429459303 | ousujeng61@yahoo.co.uk | Area 3 - Central | No | 36/1041 | 41375/1 | DISREPAIR - JEFF WAY TO CARRY OUT WORKS RAISED BY CHARLOTTE SMART 07920616045
Appointments | Glen Norman | 08/06/2026 11:00 | Appointment Booked - Staff Allocated | Millmead House, 1 Silcox Road | BS13 0JL | DISREPAIR - PAINT NEW PLASTER | Miss Sarah Rowe | 447849997283 | important40@outlook.com | Area 5 - South West | No | 36/1113 | 58870/1 | Complaint works- New works following leak WO- THOMAS LEAR
Appointments | Darren Wallis | 08/06/2026 09:00 | Appointment Started | 28B BRUNEL ROAD | BS13 7DZ | COMPLETE DISREPAIR WORKS - ASK SHAN TO ISSUE JOB SHEET | Mr Mohsen Oun | 447880000398 |  | Area 5 - South West | No | 36/1040 | 43926/1 | Complaint works- As per Andy inspection raised by James. Works include decorative finishes flooring and tiling.
Appointments | Daniel Williams | 08/06/2026 09:00 | Appointment Booked - Staff Allocated | 6 LAMBERT PLACE | BS4 1XH | PLASTER WALL TO BATHROOM, HACK OF SQMT OF TILES | Miss Freya Mccardle | 447301026749 | freyamccardle90@icloud.com | Area 4 - South East | No | 36/1196 | 69916/1 | AS PER GERRY RYAN - PLM to remove cistern and hand basin, pla to skim damage walls and renew tiles to the basin and tap end of bath - dec to paint bahtroom and paint not emulsion ele to over haul bathroom
Appointments | Kyran Thomas | 08/06/2026 08:00 | N/A | 45 Spartley Drive, Highridge | BS13 8DQ | mould clean treat paint | Miss Diane Campbell | 447845800154 | diane33campbell@gmail.com |  | No | 36/1246 | 64289/2 | Jeffway- as per Joe C-Scrape back loose paint prep surface and decorate - overhaul extractor and grill
Appointments | Clayton Burbridge | 08/06/2026 08:00 | Appointment Booked - Staff Allocated | 8 Crosscombe Drive | BS13 0DW | RENEW KITCHEN PLINTH AND OVERHAUL KITCHEN UNIT | Miss Tina Rice | 447899011357 |  | Area 5 - South West | No | 36/1226 | 75900/1 | Kitchen works- replace missing plinth, install extractor in current vent hole and refit loose dummy draw front.
Appointments | Daniel Williams | 08/06/2026 08:00 | Appointment Booked - Staff Allocated | 24 Faber Grove | BS13 0LD | DISREPAIR SEE WJOB SHEET | Miss Reanne Davis | 447435678630 | reanne2345@live.co.uk | Area 5 - South West | No | 36/1283 | 83392/1 | Repairs throughout property -
Appointments | Glen Norman | 08/06/2026 08:00 | Appointment Booked - Staff Allocated | 53 RISDALE ROAD | BS3 2RA | CARRY OUT WORK | Mr John Windridge | 447727998367 | JOHN_WINDRIDGE@LIVE.COM | Area 5 - South West | No | 36/1164 | 65788/1 | JEFFWAY - Renew defective Plasterboard wall in lobby and rooms and make good. FAO John Oyeniyi
Appointments | Jamie Hunt | 08/06/2026 08:00 | Appointment Booked - Staff Allocated | 18 ST JOHNS LANE | BS3 5AA | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mrs Farah Mohammed | 447759674788 |  | Area 4 - South East | No | 36/1262 | 39290/1 | DISREPAIR WORKS
Appointments | Darren Wallis | 08/06/2026 08:00 | Appointment Started | 6 LAMBERT PLACE | BS4 1XH | REMOVE WHB, W/C SUITE AND SET ASIDE FOR PLASTERING | Miss Freya Mccardle | 447301026749 | freyamccardle90@icloud.com | Area 4 - South East | No | 36/1196 | 69916/1 | AS PER GERRY RYAN - PLM to remove cistern and hand basin, pla to skim damage walls and renew tiles to the basin and tap end of bath - dec to paint bahtroom and paint not emulsion ele to over haul bathroom
Appointments | Izaak Ellis | 08/06/2026 08:00 | Works Completed | 10 CROSSCOMBE DRIVE | BS13 0DW | post inspection | Mr GARY HUMPHRIES | 447425918860 |  | Area 5 - South West | No | 36/790 | 1221432 - 11554/1 | complaint works- (Area name) Description of works needed. Livingroom Hack off a replaster around door frame. Small section of paint to scrape back and redecorate. One double socket to replace. Overhaul of window unit. Renew silicone to window unit.
Appointments | Sam Benden | 08/06/2026 08:00 | Appointment Booked - Staff Allocated | 2-33 Chard Court, Fortfield Road | BS14 9NL | CARRY ON WORKS |  |  |  |  | No | 36/1339 | 93675/1 | Ceiling patch in communal lounge repair required after leak As above
Appointments | James Stephens | 05/06/2026 16:00 | Appointment Booked - Staff Allocated | 215 FOUR ACRES | BS13 8QQ | repairs | Miss Charlie Cowan | 447392902528 | CHARLIEPETAL1992@GMAIL.COM | Area 5 - South West | No | 36/1153 | 64479/1 | JEFF WAY - AS PER IAN O: CLEAR ANY BUILDING WASTE IN LOFT , STAIN BLOCK ,STOP COCK , DRAINAGE REAR , DRAINAGE FRONT .WEATHER
Appointments | Izaak Ellis | 05/06/2026 15:00 | Works Completed | 2 GOULSTON WALK | BS13 7SH | site inspection | Mrs Linda J Norris | 447931249774 |  | Area 5 - South West | No | 36/584 | 1208582 | JEFF WAY - KITCHEN FLOORING , RE/SECURE REAR BACK DOOR FRAME , WEATHER PROOF REAR DOOR ( JOB IS AWAITING STRUCTURAL SURVEY) AS PER IAN OGBORNE.
Appointments | Glen Norman | 05/06/2026 13:00 | Appointment Started | 13 LITTLECROSS HOUSE | BS3 1SQ | CARRY OUT WORK | Mr Stephen Bennett |  |  | Area 5 - South West | No | 36/1200 | 58367/2 | Jeffway-: AS PER ROB D - FOLLOWING LEAK FROM ABOVE FLAT, NOW FIXED. REDECORATE AFFECTED AREAS OF KIT AND BATHROOM WALLS / CEILINGS AS REQUIRED. MATCH IN PAINT COLOURS. APPROX 14M2 TOTAL AREA
Appointments | Kyran Thomas | 05/06/2026 13:00 | Appointment Booked - Staff Allocated | 138 Newland Road, Withywood | BS13 9DX | mould clean /treat/paint | Mrs Shirley Hancock | 447833103079 | Shirleyhancock397@gmail.com |  | No | 36/1374 | 96904/2 | Jeff Way - Crack repair on external render on front elevation and mould wash bedroom walls as per John Oyeniyi.
Appointments | Glen Norman | 05/06/2026 12:00 | Appointment Started | 13 LITTLECROSS HOUSE | BS3 1SQ | CARRY OUT WORK | Mr Stephen Bennett |  |  | Area 5 - South West | No | 36/1200 | 58367/2 | Jeffway-: AS PER ROB D - FOLLOWING LEAK FROM ABOVE FLAT, NOW FIXED. REDECORATE AFFECTED AREAS OF KIT AND BATHROOM WALLS / CEILINGS AS REQUIRED. MATCH IN PAINT COLOURS. APPROX 14M2 TOTAL AREA
Appointments | Sam Benden | 05/06/2026 12:00 | N/A | 33 FOUR ACRES CLOSE | BS13 8QW | COMPLETE PLASTERING WORKS TO L/ROOM | Miss Sana Ahmed | 447796323150 | sana54@hotmail.com | Area 5 - South West | No | 36/627 | 1072724 | DISREPAIR - Living room - once TT has removed her tv from the wall, strip plaster back install dehum to dry, then replaster and apply mist coat. Damp and mould wash as necessary around the living room. Bathroom - damp and mould wash as necessary around th
Appointments | Kyran Thomas | 05/06/2026 12:00 | Appointment Booked - Staff Allocated | 23 Humberstan Walk | BS11 0EU | MOULD CLEAN | Mr Jasmin Gluhic | 447383983248 | ukgluhic@hotmail.co.uk | Area 1 - North West | No | 36/894 | 4719/2 | Disrepair Work. 1. Electric Shower - Overhaul 2. Install new extract fan to bathroom 3. Install new extract fan to kitchen 4. Overhaul all windows and doors to property 5. Treat mould and decorate bedroom 2 6. Decorate bedroom 1 7. Replace defective light
Appointments | Jamie Hunt | 05/06/2026 12:00 | Appointment Started | 75 TORRINGTON AVENUE | BS4 1EQ | CARRY ON WORKS | Ms Rachel Reeves | 447982939319 | rachel84reeves@hotmail.co.uk | Area 4 - South East | No | 36/1054 | 32908/1 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors.
Appointments | James Stephens | 05/06/2026 11:00 | Appointment Booked - Staff Allocated | 215 FOUR ACRES | BS13 8QQ | repairs | Miss Charlie Cowan | 447392902528 | CHARLIEPETAL1992@GMAIL.COM | Area 5 - South West | No | 36/1153 | 64479/1 | JEFF WAY - AS PER IAN O: CLEAR ANY BUILDING WASTE IN LOFT , STAIN BLOCK ,STOP COCK , DRAINAGE REAR , DRAINAGE FRONT .WEATHER
Appointments | George Sutton-Fricker | 05/06/2026 10:00 | Appointment Started | 357 Bishport Avenue | BS13 0BN | fit shower to wall | Miss Carly Moore | 447415442529 | carlyjmoore@hotmail.co.uk | Area 5 - South West | No | 36/1052 | 44995/1 | JW-AS PER ROB DOIDGE - RENEWAL OF BATH, APPROX 1SQM TILES TO SHOWER WALL AND TAPS TO BASIN . FIT EXTRACTOR FAN WHERE PASSIVE VENT IS AND OVERHAUL W.C FOR LEAKS
Appointments | Darren Whitchurch | 05/06/2026 10:00 | Appointment Booked - Staff Allocated | 8 Campian Walk, Inns Court | BS4 1XE | INSPECT LOFT | Miss Rachel Hayward | 447512532626 | HAYWARD935@GMAIL.COM |  | No | 36/1456 | 105847/1 | AS PER GERRY RYAN = EMMA HIND = Remove wall and put back rooms after hidden grow room behind Airing cupboard and also inspected loft for damage
Appointments | Jamie Hunt | 05/06/2026 09:00 | Appointment Started | 38 MILLMEAD HOUSE | BS13 0JN | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Zoe Munsey | 07449462689 | pynezoe1986@yahoo.co.uk | Area 5 - South West | No | 36/1209 | 71309/1 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled
Appointments | George Sutton-Fricker | 05/06/2026 08:00 | Appointment Booked - Staff Allocated | 139 Ilchester Crescent | BS13 7HP | CARRY OUT WORK | Ms Annemarie Excell | 07435217105 | annmarie.excell@yahoo.co.uk |  | No | 36/1484 | 5599/1 | Jeffway-As per Ian Ogborne-KITCHEN REPAIRS , BATHROOM FLOORING AND PANEL , OUT BUILDING ROOF AND REPAIRS
Appointments | Clayton Burbridge | 05/06/2026 08:00 | Appointment Booked - Staff Allocated | 42 Grinfield Avenue | BS13 0JU | COMPLETE DISREPAIR WORKS | Mr Allen Taylor | 07716954519 | amtaylor1979@outlook.com | Area 5 - South West | No | 36/1230 | 77090/1 | Disrepair - repairs throughout property - DN786139 - Responsive Repairs Overflow
Appointments | Daniel Williams | 05/06/2026 08:00 | N/A | 64 Vincent Close | BS11 0UA | DISREPAIR NOTES - AS PER NOTES | Miss Aimee Phillips | 447598440155 | aimee.jaynephillips@icloud.com | Area 1 - North West | No | 36/1169 | 4654/2 | Disrepair Works - James Bailey (surveyor) Roof - carry out roof inspection (flat roof will need to arrange access) Livingroom- scrape back chimney, scrape back chimney, treat brick, replaster, mist coat and stain block Kitchen - Damp and mould wash around
Appointments | Oliver Maurice Shore | 05/06/2026 08:00 | Appointment Booked - Staff Allocated | 64 Vincent Close | BS11 0UA | DISREPAIR NOTES - AS PER NOTES | Miss Aimee Phillips | 447598440155 | aimee.jaynephillips@icloud.com | Area 1 - North West | No | 36/1169 | 4654/2 | Disrepair Works - James Bailey (surveyor) Roof - carry out roof inspection (flat roof will need to arrange access) Livingroom- scrape back chimney, scrape back chimney, treat brick, replaster, mist coat and stain block Kitchen - Damp and mould wash around
Appointments | Sam Benden | 05/06/2026 08:00 | N/A | 18 ST JOHNS LANE | BS3 5AA | COMPLETE DISREPAIR WORKS - AS PER NOTES | Mrs Farah Mohammed | 447759674788 |  | Area 4 - South East | No | 36/1262 | 39290/1 | DISREPAIR WORKS
Appointments | Jessie Parsons | 05/06/2026 08:00 | Appointment Booked - Staff Allocated | 34 Four Acres Close, Withywood | BS13 8QN | repairs | Miss Brianna o connor | 07376121440 | BRIANNAMARY13@OUTLOOK.COM |  | No | 36/1391 | 59378/4 | Jeff Way - As per Tom Walker: Over board and plaster skim Kitchen ceiling
Appointments | Darren Wallis | 05/06/2026 08:00 | Appointment Started | 357 Bishport Avenue | BS13 0BN | fit shower onto wall | Miss Carly Moore | 447415442529 | carlyjmoore@hotmail.co.uk | Area 5 - South West | No | 36/1052 | 44995/1 | JW-AS PER ROB DOIDGE - RENEWAL OF BATH, APPROX 1SQM TILES TO SHOWER WALL AND TAPS TO BASIN . FIT EXTRACTOR FAN WHERE PASSIVE VENT IS AND OVERHAUL W.C FOR LEAKS
Appointments | Kyran Thomas | 05/06/2026 08:00 | N/A | 138 Newland Road, Withywood | BS13 9DX | mould clean /treat/paint | Mrs Shirley Hancock | 447833103079 | Shirleyhancock397@gmail.com |  | No | 36/1374 | 96904/2 | Jeff Way - Crack repair on external render on front elevation and mould wash bedroom walls as per John Oyeniyi.
Appointments | Jack Slade | 04/06/2026 17:00 | Appointment Started | 29 Broadbury Road | BS4 1JR | 1 new bathroom | Mr Mark Brinkham | 447490757764 | brinkmanmark9@gmail.com | Area 4 - South East | No | 36/1131 | 62114/1 | Repairs throughout property - DN786139 - Responsive Repairs Overflow
Appointments | James Stephens | 04/06/2026 14:00 | Appointment Booked - Staff Allocated | 4 Aldwick Avenue, Hartcliffe | BS13 0NZ | CARRY OUT WORK | Ms Leanne Gainard | 447956594789 | leanne.gainard@icloud.com |  | No | 36/1298 | 50243/3 | Jeffway- as per John O-Renew tap to Kitchen sink
Appointments | Daniel Williams | 04/06/2026 14:00 | Appointment Started | 90 EASTWOOD CRESCENT | BS4 4ST | RING SHAN AND ASK FOR ORDER TO BE SENT TO YOU | Mr Kelvin Duncan | 07836726936 | kelvinduncan42@gmail.com | Area 4 - South East | No | 36/1294 | 87412/1 | Complaint works- works to address mould within the hallway.
Appointments | Alan Smith | 04/06/2026 13:00 | Appointment Started | 36 Cossington Road | BS4 1DP | OVERHAUL FANS | Mr Nathan Eddolls | 447377764845 |  |  | No | 36/1378 | 76796/1 | Complaint Job - Rodents within property - Work with Orbis to remove waste below bathroom flooring - Various works see other comments - Brick up Old vent hole - Replace Base unit and wall unit - Remove Toilet pan and Floorboards for orbis access to clear
Appointments | Glen Norman | 04/06/2026 12:00 | Appointment Booked - Staff Allocated | 14 LANGFORD ROAD | BS13 7AP | CARRY OUT WORK | Mrs Diane Simmonds | 447582993190 | diane_simmonds@hotmail.co.uk | Area 5 - South West | No | 36/1136 | 6896/2 | jeff way - Hack off defective wall and ceiling rendering and renew Plaster, skim, and redecorate fao John Oyeniyi
Appointments | Alan Smith | 04/06/2026 12:00 | N/A | 17 MILLPOOL COURT | BS10 6AX | REPLACE PENDANT LIGHT IN LIVING ROOM | Mr Steven Bendall | 447498020555 | stevebendall19@gmail.com | Area 1 - North West | No | 36/1229 | 76933/1 | PD1 - Please carry out works as listed.
Appointments | Sahib Singh | 04/06/2026 12:00 | Works Completed | 29 Broadbury Road | BS4 1JR | 1 new kitchen | Mr Mark Brinkham | 447490757764 | brinkmanmark9@gmail.com | Area 4 - South East | No | 36/1131 | 62114/1 | Repairs throughout property - DN786139 - Responsive Repairs Overflow
Appointments | Izaak Ellis | 04/06/2026 12:00 | N/A | 2 GOULSTON WALK | BS13 7SH | site visit | Mrs Linda J Norris | 447931249774 |  | Area 5 - South West | No | 36/584 | 1208582 | JEFF WAY - KITCHEN FLOORING , RE/SECURE REAR BACK DOOR FRAME , WEATHER PROOF REAR DOOR ( JOB IS AWAITING STRUCTURAL SURVEY) AS PER IAN OGBORNE.
Appointments | Clayton Burbridge | 04/06/2026 11:00 | Appointment Booked - Staff Allocated | 18 ST JOHNS LANE | BS3 5AA | COMPLETE DISREPAIR WORKS AS PER NOTES | Mrs Farah Mohammed | 447759674788 |  | Area 4 - South East | No | 36/1262 | 39290/1 | DISREPAIR WORKS
Appointments | Darren Wallis | 04/06/2026 10:00 | Appointment Booked - Staff Allocated | 174 BROADLANDS DRIVE | BS11 0PH | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Rebecca Dick | 07794623916 | beckysaintjd@gmail.com | Area 1 - North West | No | 36/1030 | 38606/1 | Complaint disrepair works / as per G Squared site survey
Appointments | Izaak Ellis | 04/06/2026 09:00 | Appointment Started | 90 Willinton Road | BS4 1HY | post inspection | Mrs & Mrs Ibra & Thiane Diop Ep Diop | 447440223699 | ibradiop058@gmail.com |  | No | 36/1286 | 84946/1 | COMPLAINT WORKS - FOR CHARLOTTE SMART Lottie.Smart@bristol.gov.uk
Appointments | James Stephens | 04/06/2026 09:00 | Appointment Booked - Staff Allocated | 41 Torrington Avenue, Knowle | BS4 1EQ | CARRY OUT WORK | Mr Mohammed Alfashtaki | 447428044488 | RUBENHOOD476@GMAIL.COM |  | No | 36/1384 | 98660/1 | Daniel Allen - Please renew bath and fittings
Appointments | James Stephens | 04/06/2026 09:00 | N/A | 91 NEWLAND ROAD | BS13 9DS | CARRY OUT WORK | Mr Steven Kenny | 447872014971 |  |  | No | 36/1126 | 61109/1 | JEFF WAY - Bathroom Repairs and redecorations FAO JOHN OYENIYI
Appointments | Timothy Cotter | 04/06/2026 08:00 | N/A | 34 Derham Road | BS13 7SB | CARRY OUT WORK | Miss Starr Gillam | 447488454642 | starcollins123@icloud.com | Area 5 - South West | No | 36/1151 | 14985/2 | JEFF WAY - AS PER ROB D: RENEW 2 X MISSING PLINTHS TO MATCH EXISTING TO KITCHEN UNITS. OVERHAUL DOORS / HINGES WHERE DROPPED / HANGING OFF AS REQUIRED
Appointments | Ryan Greenslade | 04/06/2026 08:00 | Appointment Started | 59 Avonleigh Road, Bedminster | BS3 3JA | CARRY OUT WORK | Miss Samantha Thompson | 07535078089 | noemail@outlook.com |  | No | 36/1088 | 53627/1 | Jeffway- as per Jeff Neck-: Break out sloping concrete area to the rear of the property draining towards rear kitchen wall and clear and various other works sent over via email
Appointments | James Stephens | 04/06/2026 08:00 | N/A | 91 NEWLAND ROAD | BS13 9DS | CARRY OUT WORK | Mr Steven Kenny | 447872014971 |  |  | No | 36/1126 | 61109/1 | JEFF WAY - Bathroom Repairs and redecorations FAO JOHN OYENIYI
Appointments | Darren Wallis | 04/06/2026 08:00 | Appointment Started | 18 WAINBROOK DRIVE | BS5 7EG | RENEW AND OVERHAUL FLUSH PIPE TO CISTERN | Miss Amanda Mccalla | 447786325927 | mccalla23amanda@gmail.com | Area 2 - North East | No | 36/1065 | 40015/2 | Please carry out disrepairs work as listed
Appointments | David Cottrell | 04/06/2026 08:00 | Appointment Booked - Staff Allocated | 34 HIGHBURY ROAD | BS3 5NT | repairs | Mr & Mrs Spencer | 447487238953 | barbarabev5@gmail.com | Area 5 - South West | No | 36/882 | 33711/1 | JW - Rob Doidge - Renew base unit to kitchen, Renew drawer to kitchen unit, Flooring - Discuss with Rob for locations
Appointments | Jamie Hunt | 04/06/2026 08:00 | Appointment Started | 72 CHELSEA ROAD | BS5 6AT | COMPLETE DISREPAIR WORKS | Mrs & Mrs Tanya & Victor Thame | 447833218227 | tt007p0385@blueyonder.co.uk | Area 3 - Central | No | 36/1140 | 61312/1 | Complaint Works - bathroom remove wall paper treat and paint with anti condensation paint. reseal bath. remove ceiling tiles and paint. repair front door. through out remove paper that's loose and treat mould.
Appointments | Alan Smith | 04/06/2026 08:00 | Appointment Booked - Staff Allocated | 4 Edington Grove, Henbury, | BS10 7EF | eicr test | Mr Max Gillet | 447471778924 | mbristol1991@gmail.com |  | No | 36/1376 | 97921/3 | JJEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 21/05/26. 10 DAY PERIOD ENDS 05/06/26.
Appointments | Sam Benden | 04/06/2026 08:00 | Appointment Started | 16 WHITSON HOUSE | BS2 9ED | COMPLETE WORKS - DISREPAIR | Miss Catherine Wise | 07395708510 | WISECATHERINE29@GMAIL.COM | Area 3 - Central | No | 36/1450 | 101095/1 | BEDR1 , BEDR 2 BATHR EXTERNAL HALLWAY KITCH
Appointments | Jessie Parsons | 04/06/2026 08:00 | Appointment Started | 22 Totshill Drive, Hartcliffe, Bristol BS13 0QU | BS13 0QU | COMPLETE PLASTERING WORKS TO L/ROOM | Miss Shannon T Dolin | 447535920600 | shannondolin1991@icloud.com |  | No | 36/730 | 1231446 | race leak to cupboard under stairs from kitchen , replace stop tap and check fittings. Due to the internal leakage hack off damage plaster work to internal cupboard walls and living room wall on the adjacent side. Again on the external living corner wall
Appointments | Glen Norman | 04/06/2026 08:00 | N/A | 20 Hills Barton | BS13 7JH | stain block wall rhs of cooker // paint wall rhs of cooker4smts;; kitchen,, Prep and Paint ceiling upto 20 sq mts kitchen | Mr Craig Gillespie | 447767365800 | gillespiec521@gmail.com | Area 5 - South West | No | 36/1192 | 61846/2 | Jeff Way - As per John Oyeniyi: Redecorate Kitchen ceiling; Part of wall and Living Room Ceiling
Appointments | Clayton Burbridge | 03/06/2026 16:00 | Appointment Started | 61 WALKER CLOSE | BS5 0XB | DISREPAIR WORKS - COMPLETE BATHROOM WORKS | Mr Ousman Jeng | 447429459303 | ousujeng61@yahoo.co.uk | Area 3 - Central | No | 36/1041 | 41375/1 | DISREPAIR - JEFF WAY TO CARRY OUT WORKS RAISED BY CHARLOTTE SMART 07920616045
Appointments | James Stephens | 03/06/2026 16:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | REMOVE RADIATOR ON L/ROOM WALL FOR TIMBERWISE | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | Alan Smith | 03/06/2026 14:00 | Appointment Started | 93 GORSE HILL | BS16 4PL | DROP SOCKETS FOR PLASTERING - EXTERNAL WALL AND CHIMNEY BREAST WALL IN LIVING ROOM | Mr Nadir El Achhab | 447494888775 | l.umm3@hotmail.com | Area 2 - North East | No | 36/1038 | 38923/1 | Complaint disrepair works / as per CG
Appointments | Darren Wallis | 03/06/2026 14:00 | Appointment Booked - Staff Allocated | 93 COLESHILL DRIVE | BS13 9QW | ATTEMPT PHOTOS OF LOFT INSULATION PLEASE | Mrs Tracy Royston | 07539630355 |  | Area 5 - South West | No | 36/389 | 1194951 | DAMP & MOULD Insulation as per BB tidy existing loft insulation ensuring there are no voids and overlay with 200mm of mineral wool insulation ensuring placement right up to the eaves
Appointments | James Stephens | 03/06/2026 13:00 | Appointment Booked - Staff Allocated | 41 Coleshill Drive, Hartcliffe | BS13 9QT | repairs | Mrs Barbara Denman | 01179870106 | MD75@HOTMAIL.CO.UK |  | No | 36/1243 | 79292/1 | JEFF WAY - Overhaul front and rear timber doors leave in working order. Fix new external vents grill fix over existing to prevent water ingress FAO JEFF NECK
Appointments | Glen Norman | 03/06/2026 13:00 | Appointment Started | 60 WROUGHTON DRIVE | BS13 0LN | CARRY OUT WORK | Mr Scott Henson | 07307632183 |  | Area 5 - South West | No | 36/1016 | 44148/1 | Jeffway -As per John O - Scrape back plaster work in Lounge Ceiling, skim and paint; Latex floor in lounge and Landing. Paint woodwork in Bathroom, Overhaul fan to kitchen
Appointments | Darren Wallis | 03/06/2026 13:00 | Appointment Started | 108 Capgrave Crescent | BS4 4TP | COMPLETE PAINT WORKS TO BATHROOM | Miss Ella Watts | 447741656356 | Ellawatts@gmail.com | Area 4 - South East | No | 36/1068 | 38801/2 | Complaint disrepair works / as per CG
Appointments | James Stephens | 03/06/2026 12:00 | Appointment Booked - Staff Allocated | 213 GATEHOUSE AVENUE | BS13 9AQ | Check and overhaul all PVC windows. Check and overhaul all PVC windows,// Cut and fix new PVC cill to Check and overhaul all PVC windows. ut and fix plasterboard across existing window cills in front and rear bedrooms and clad in new PVC cill to form a insulation bridge front and rear bedrooms | Miss Lacey Reader | 447951056330 | laceyloreader@icloud.com | Area 5 - South West | No | 36/1184 | 29066/2 | Jeffway- as per Jeff N- Apply mould wash to side of PVC windows in front and rear bedrooms. Overhaul all PVC windows. Cut and fix plasterboard across existing window cills and clad over in in PVC cill to form insulation bridge Fix new fan in external bat
Appointments | James Stephens | 03/06/2026 12:00 | N/A | 10 Buttercup Walk, Ashton Vale | BS3 2TZ | CARRY OUT WORK | Mr Robert Czaplarski | 447554846229 | DAREKNN09@GMAIL.COM |  | No | 36/1244 | 35188/2 | JEFF WAY - Note tenant to lift bedroom and landing carpets to allow access to loose flooring. Secure loose floor board as shown by tenant. Overhaul sink and basin taps . Replace damage latch on living room door. FAO JEFF NECK BOOKED WITH JEFF NECK 9/3/26
Appointments | Glen Norman | 03/06/2026 12:00 | Appointment Started | 60 WROUGHTON DRIVE | BS13 0LN | CARRY OUT WORK | Mr Scott Henson | 07307632183 |  | Area 5 - South West | No | 36/1016 | 44148/1 | Jeffway -As per John O - Scrape back plaster work in Lounge Ceiling, skim and paint; Latex floor in lounge and Landing. Paint woodwork in Bathroom, Overhaul fan to kitchen
Appointments | Daniel Williams | 03/06/2026 12:00 | Appointment Booked - Staff Allocated | 57 Whittock Road | BS14 8DQ | COMPLETE DISREPAIR WORKS | Mr David Beal | 447753816018 |  |  | No | 36/831 | 1230835 | complaints works- Kitchen New extractor fan. Remove and renew silicone to window and door. Pvc mould wash to window and door. Mould wash and anti mould paint to window and door reveals. Window overhaul. Living Room Renew plasterboard to head of ba
Appointments | Ryan Greenslade | 03/06/2026 11:00 | Appointment Started | 138 Bedminster Road, Bedminster, Bristol, BS3 5NP | BS3 5NP | CARRY OUT WORK | Miss Sarah Farbrother | 447772879515 |  |  | No | 36/815 | 28437/1 | AS PER NICHOLAS CORY JEFFWAY TO HACK OFF ALL OLD PLASTER ON EXTERNAL WALL PAINT WITH BITUMIN RE RENDER WITH SAND/CEMANT AND WATERPROOFER, SKIM FINISH AND PAINT
Appointments | Glen Norman | 03/06/2026 09:00 | Appointment Started | 39 SPENCER HOUSE | BS1 6RL | PAINT NEW PLASTER TO KITCHEN AND BATHROOM - SILICONE BEDROOM WINDOWS. | Mrs Dianah Namusoke | 07491096611 | diananamusoke1@gmail.com | Area 3 - Central | No | 36/996 | 37917/1 | complaint works- see report and email- WO- Thomas Lear
Appointments | Darren Wallis | 03/06/2026 08:00 | Appointment Booked - Staff Allocated | 17 Berchel House | BS3 1XE | CARRY OUT WORK | Mr Keith Chamberlain |  |  |  | No | 36/1312 | 71497/2 | Jeffway- John O-Renew Toilet bowl and cistern; and overhaul kitchen sink
Appointments | Clayton Burbridge | 03/06/2026 08:00 | N/A | 167 DUTTON ROAD | BS14 8BZ | COMPLETE WORKS - SPEAK WITH SHAN FOR EMAIL | Mr MaX MORGAN | 07759981724 |  | Area 4 - South East | No | 36/631 | 1146242 | DISREPAIR/MOULD WORKS
Appointments | Daniel Williams | 03/06/2026 08:00 | N/A | 42 Grinfield Avenue | BS13 0JU | PLASTERING DISREPAIR WORKS | Mr Allen Taylor | 07716954519 | amtaylor1979@outlook.com | Area 5 - South West | No | 36/1230 | 77090/1 | Disrepair - repairs throughout property - DN786139 - Responsive Repairs Overflow
Appointments | Timothy Cotter | 03/06/2026 08:00 | Appointment Booked - Staff Allocated | 1 Dyers Close, Hartcliffe | BS13 0LW | CARRY OUT WORK | Miss Seyai Hess Sambou | 447477933355 | sambouhess@yahoo.com |  | No | 36/1245 | 79714/1 | JEFF WAY - Fix new round plastic gully grill to drain on rear elevation . Apply stain block to water damage kitchen ceiling and repaint area. FAO JEFF NECK
Appointments | Jessie Parsons | 03/06/2026 08:00 | Appointment Booked - Staff Allocated | 53 RISDALE ROAD | BS3 2RA | CARRY OUT WORK | Mr John Windridge | 447727998367 | JOHN_WINDRIDGE@LIVE.COM | Area 5 - South West | No | 36/1164 | 65788/1 | JEFFWAY - Renew defective Plasterboard wall in lobby and rooms and make good. FAO John Oyeniyi
Appointments | Jamie Hunt | 03/06/2026 08:00 | Appointment Started | 75 TORRINGTON AVENUE | BS4 1EQ | DISREPAIR - PLEASE COME SEE SHAN FOR PAPER WORK OF WORKS | Ms Rachel Reeves | 447982939319 | rachel84reeves@hotmail.co.uk | Area 4 - South East | No | 36/1054 | 32908/1 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors.
Appointments | Sam Benden | 03/06/2026 08:00 | Appointment Started | 16 WHITSON HOUSE | BS2 9ED | COMPLETE DISREPAIR WORKS - AS PER NOTES | Miss Catherine Wise | 07395708510 | WISECATHERINE29@GMAIL.COM | Area 3 - Central | No | 36/1450 | 101095/1 | BEDR1 , BEDR 2 BATHR EXTERNAL HALLWAY KITCH
Appointments | Jack Slade | 02/06/2026 16:00 | Appointment Started | 46 MURFORD AVENUE | BS13 9JY | replace bathroom overhaulo kitchen | Miss Carmel Jay | 07572106138 | Carmeljay15@gmail.com | Area 5 - South West | No | 36/1087 | 46466/1 | Complaint works- please see email and report- Thomas Lear
Appointments | Ryan Greenslade | 02/06/2026 15:00 | Appointment Booked - Staff Allocated | 53 RISDALE ROAD | BS3 2RA | CARRY OUT WORK | Mr John Windridge | 447727998367 | JOHN_WINDRIDGE@LIVE.COM | Area 5 - South West | No | 36/1164 | 65788/1 | JEFFWAY - Renew defective Plasterboard wall in lobby and rooms and make good. FAO John Oyeniyi
Appointments | Sahib Singh | 02/06/2026 14:00 | Appointment Started | 72 CHELSEA ROAD | BS5 6AT | replace bathroom | Mrs & Mrs Tanya & Victor Thame | 447833218227 | tt007p0385@blueyonder.co.uk | Area 3 - Central | No | 36/1140 | 61312/1 | Complaint Works - bathroom remove wall paper treat and paint with anti condensation paint. reseal bath. remove ceiling tiles and paint. repair front door. through out remove paper that's loose and treat mould.
Appointments | Alan Smith | 02/06/2026 13:00 | Appointment Started | 21 CLAPTON WALK | BS9 2HR | CHECK FAN AS APPARENTLY RUNNING CONTINOUSLY. | Mr David Roberts | 447818171301 | der96868@gmail.com | Area 1 - North West | No | 36/1037 | 38867/1 | Complaints work/G Squared report (WO raised by A Williams)
Appointments | Timothy Cotter | 02/06/2026 13:00 | Appointment Started | 21 HOME MEAD | BS4 1UQ | COMPLETE DISREPAIR WORKS | Mr Giuseppe Solari | 447466753134 |  | Area 4 - South East | No | 36/1133 | 58805/2 | COMPLAINT WORKS: KITCHEN: FAN REPAIR/RENEW. BATHROOM: FAN REPAIR RENEW, PLASTER HOLES AND ROUND PIPE. BED1: PATCH REPAIR WALLPAPER AND FIX PERKO TYPE TO CONCEALLED DOOR
Appointments | Jack Slade | 02/06/2026 12:00 | N/A | 28B BRUNEL ROAD | BS13 7DZ | replace kitchen fan | Mr Mohsen Oun | 447880000398 |  | Area 5 - South West | No | 36/1040 | 43926/1 | Complaint works- As per Andy inspection raised by James. Works include decorative finishes flooring and tiling.
Appointments | Sam Benden | 02/06/2026 12:00 | Appointment Completed | 198 Four Acres | BS13 8QH | Make good plaster to reveal frame, check and overhaul windows throughout (lubricate check handles are workiing, seal where missing) | Miss Ellie Crahart | 447471581450 | elliec2020@icloud.com | Area 5 - South West | No | 36/1114 | 58831/1 | JWAY - Strip rear bedroom wallpaper, cut out damaged plasterwork. Dub out w sand/cement to suit existing levels. Reskim complete wall. Make good to reveal timber door frame. Fix new floor double power back box. Overhaul PVC windows - J Neck
Appointments | Christopher Mcgregor | 02/06/2026 11:00 | Appointment Booked - Staff Allocated | 40 OAK HOUSE | BS13 0RZ | COMPETE WORKS | Miss Jessica Britton | 447403129746 |  | Area 5 - South West | No | 36/883 | 33695/1 | JW - Rob D - renew bath panel, renew sealant around bath in full,Renew skirting on wc wall & bath panel,Renew bathroom non slip flooring&renew boxing behind w.c, L-Room - renew self levelling screed to floor in full, 16m2
Appointments | Clayton Burbridge | 02/06/2026 11:00 | Appointment Started | 100 Carolina House | BS2 8LP | ASSIST DARREN WITH WORKS | Mr Abdelkader Mokhtari | 447488344064 |  |  | No | 36/993 | 27925/2 | Contact Andrew Griffiths
Appointments | Timothy Cotter | 02/06/2026 09:00 | N/A | 75 Murford Avenue, Hartcliffe, Bristol BS13 9JY | BS13 9JY | CARRY OUT WORK | Miss Tammy L Blammon | 447402807630 | tammyblammon5@googlemail.com |  | No | 36/690 | 1219891 | JEFF WAY - Make repairs to plaster walls in bathroom and apply sealer to staining on walls .Paint ceiling and walls in anti condensation paint. Fix new plastic skirting around perimeter of walls.
Appointments | Darren Wallis | 02/06/2026 08:00 | Appointment Started | 100 Carolina House | BS2 8LP | DISREPAIR - AS PER NOTES | Mr Abdelkader Mokhtari | 447488344064 |  |  | No | 36/993 | 27925/2 | Contact Andrew Griffiths
Appointments | Timothy Cotter | 02/06/2026 08:00 | N/A | 75 Murford Avenue, Hartcliffe, Bristol BS13 9JY | BS13 9JY | CARRY OUT WORK | Miss Tammy L Blammon | 447402807630 | tammyblammon5@googlemail.com |  | No | 36/690 | 1219891 | JEFF WAY - Make repairs to plaster walls in bathroom and apply sealer to staining on walls .Paint ceiling and walls in anti condensation paint. Fix new plastic skirting around perimeter of walls.
Appointments | Daniel Williams | 02/06/2026 08:00 | Appointment Booked - Staff Allocated | 28B BRUNEL ROAD | BS13 7DZ | COMPLETE DISREPAIR WORKS - ASK SHAN TO ISSUE JOB SHEET | Mr Mohsen Oun | 447880000398 |  | Area 5 - South West | No | 36/1040 | 43926/1 | Complaint works- As per Andy inspection raised by James. Works include decorative finishes flooring and tiling.
Appointments | Oliver Maurice Shore | 02/06/2026 08:00 | Appointment Booked - Staff Allocated | 28B BRUNEL ROAD | BS13 7DZ | COMPLETE DISREPAIR WORKS - ASK SHAN TO ISSUE JOB SHEET | Mr Mohsen Oun | 447880000398 |  | Area 5 - South West | No | 36/1040 | 43926/1 | Complaint works- As per Andy inspection raised by James. Works include decorative finishes flooring and tiling.
Appointments | Glen Norman | 02/06/2026 08:00 | Appointment Booked - Staff Allocated | 13A WYNDHAM CRESCENT | BS4 4SX | COMPLETE WORKS AS PER JOB SHEET - ASK SHAN TO SEND IF CANT SEE | Miss Anna Bochen | 447724925681 | anna.bochen@gmail.com | Area 4 - South East | No | 36/1251 | 81980/1 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled
Appointments | Christopher Mcgregor | 02/06/2026 08:00 | Appointment Started | 44 Wharnecliffe Gardens, Whitchurch | BS14 9JP | CARRY OUT WORK | Miss Jodie Hibbs | 447768957561 | jodeschinzano@gmail.com |  | No | 36/863 | 32869/1 | JW - Ian O - WORKS OUTSTANDING FROM PREVIOUS ORDER : RE POINT PATIO THAT WAS POORLY DONE / MISSING PASSIVE VENT , FILLING INSIDE FRONT DOOR , CLOSE OFF DUCTING BEHIND KITCHEN
Appointments | Jessie Parsons | 02/06/2026 08:00 | Appointment Booked - Staff Allocated | 53 RISDALE ROAD | BS3 2RA | CARRY OUT WORK | Mr John Windridge | 447727998367 | JOHN_WINDRIDGE@LIVE.COM | Area 5 - South West | No | 36/1164 | 65788/1 | JEFFWAY - Renew defective Plasterboard wall in lobby and rooms and make good. FAO John Oyeniyi
Appointments | Jamie Hunt | 02/06/2026 08:00 | Appointment Started | 75 TORRINGTON AVENUE | BS4 1EQ | DISREPAIR - PLEASE COME SEE SHAN FOR PAPER WORK OF WORKS | Ms Rachel Reeves | 447982939319 | rachel84reeves@hotmail.co.uk | Area 4 - South East | No | 36/1054 | 32908/1 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors.
Appointments | Jack Slade | 02/06/2026 08:00 | Appointment Booked - Staff Allocated | 24 Bangrove Walk | BS11 0EY | 2 X FAN INSTALLS/REPLACEMENT - DISREPAIR | Miss Ewelina Graczkowska | 447873205783 | graczkowska@yahoo.co.uk | Area 1 - North West | No | 36/1043 | 39214/1 | Complaint disrepair works / as per G Squared site survey
Appointments | David Cottrell | 02/06/2026 08:00 | Appointment Started | 37 MAYNARD ROAD | BS13 0AX | Repairs to ceiling | Miss Joanna Coles | 447824427329 | jocoles@blueyonder.co.uk | Area 5 - South West | No | 36/1155 | 64574/1 | JEFF WAY-AS PER ROB D: WHERE ABSENT , FIT NEW NEWEL POST, HANDRAIL AND BALUSTERS TO STAIRCASE RHS. CURRENTLY HHSRS HAZARD WITH YOUNG CHILDREN IN PROPERTY.
Appointments | Sam Benden | 02/06/2026 08:00 | Appointment Booked - Staff Allocated | 71b Salcombe Road, Knowle | BS4 1AG | CARRY OUT WORK | Miss Kaci Saunders | 447340180998 | kacisaunders@yahoo.com |  | No | 36/1329 | 59411/2 | JEFF WAY - AS PER ROB DOIDGE - REFIX LOOSE BANNISTER RAIL TO COMMUNAL STAIRWAY - MD Booked in with Rob D 23/04/2026 08:00 - 12:00pm via text Hallway
Appointments | James Stephens | 02/06/2026 08:00 | N/A | Millmead House, 1 Silcox Road | BS13 0JL | PAINT NEW PLASTER | Miss Sarah Rowe | 447849997283 | important40@outlook.com | Area 5 - South West | No | 36/907 | 31414/1 | Complaints works - lounge and hallway - re-raised due to jobs being handed back from WMS
Appointments | Glen Norman | 02/06/2026 07:00 | Appointment Ended - Second Visit Required | 56 Sherrin Way, Withywood, | BS13 8RS | CARRY OUT WORK | Mrs Angela Gilmartin | 447837628663 | agilmartin@email.com |  | No | 36/1393 | 70105/2 | Jeff Way - Crack repair to Bedroom wall and ceiling, and redecoration as per John Oyeniyi.
Appointments | Sam Benden | 01/06/2026 17:00 | Appointment Booked - Staff Allocated | 15 HOLLIDGE GARDENS | BS3 1AQ | CARRY OUT WORK | Mrs Gloria Benkhelifa | 447780118151 | stevenson488@hotmail.co.uk | Area 5 - South West | No | 36/1198 | 35087/4 | Jeff Way - as per John Oyeniyi: Redecoration works to wall and kitchen in bathroom, mould wash ceiling in kitchen.
Appointments | Sam Benden | 01/06/2026 14:00 | N/A | 15 HOLLIDGE GARDENS | BS3 1AQ | repairs | Mrs Gloria Benkhelifa | 447780118151 | stevenson488@hotmail.co.uk | Area 5 - South West | No | 36/1198 | 35087/4 | Jeff Way - as per John Oyeniyi: Redecoration works to wall and kitchen in bathroom, mould wash ceiling in kitchen.
Appointments | Sahib Singh | 01/06/2026 14:00 | Works Completed | 213 GATEHOUSE AVENUE | BS13 9AQ | install bathroom fan | Miss Lacey Reader | 447951056330 | laceyloreader@icloud.com | Area 5 - South West | No | 36/1184 | 29066/2 | Jeffway- as per Jeff N- Apply mould wash to side of PVC windows in front and rear bedrooms. Overhaul all PVC windows. Cut and fix plasterboard across existing window cills and clad over in in PVC cill to form insulation bridge Fix new fan in external bat
Appointments | Jamie Hunt | 01/06/2026 13:00 | Appointment Ended - Follow On Work Required | 3 Mowcroft Road, Hartcliffe | BS13 0LE | repairs | Miss Leanne Derrick | 447340995741 | leaderrick1990@gmail.com |  | No | 36/854 | 31982/1 | JW - As per Jeff - Various works required throughout property, See SOR comments for specific location details Hack off damage plaster work to the sides and behind ground floor toilet and reskim to match existing levels. Remove rotten timber skirting at th
Appointments | Jamie Hunt | 01/06/2026 12:00 | Appointment Ended - No Access | 5 Englishcombe Road | BS13 0NW | COMPLETE PAINTING OF BEDROOM | Mr Kavell Gayle | 07503401703 | kavellgayle@gmail.com | Area 5 - South West | No | 36/984 | 3697/2 | Disrepair works - James Bailey (surveyor) Bedroom - strip back damaged plaster, treat brick, replaster, mist coat, anticondensation paint Kitchen - d+m wash pipes Living room - - strip back damaged plaster, treat brick, replas
Appointments | James Stephens | 01/06/2026 12:00 | Appointment Ended - No Access | 31 Maynard Close | BS13 0AS | CARRY OUT WORK | Mr Thomas Parslow | 447491231553 | thomas.parslow@hotmail.co.uk | Area 5 - South West | No | 36/927 | 36534/1 | JW - AS PER JOHN O: PLEASE FIX WALL TILES ON WALL ABOVE BATH AND REPAIR SPOT ON BATH
Appointments | Timothy Cotter | 01/06/2026 12:00 | Appointment Booked - Staff Allocated | 12 Chelvey Close, Hartcliffe | BS13 0PJ | CARRY OUT WORK | Miss Lara Mckeating | 447921335186 | mckeatinglara@yahoo.com |  | No | 36/1301 | 81035/2 | JEFF WAY - AS PER ROB D: VACUUM GUTTER CLEARANCE FRONT & REAR, RENEWAL OF REAR KITCHEN COOKER EXTRACTOR VENT COVER AS SQUIRRELS ACCESSING. COVER OVER NEW VENT WITH A METAL MESH/ GRATE AS EXTRA PROTECTION
Appointments | Glen Norman | 01/06/2026 12:00 | Appointment Booked - Staff Allocated | 17 MILLPOOL COURT | BS10 6AX | STAINBLOCK KITHEN CEILING AND PAINT NEW PLASTER | Mr Steven Bendall | 447498020555 | stevebendall19@gmail.com | Area 1 - North West | No | 36/1229 | 76933/1 | PD1 - Please carry out works as listed.
Appointments | Clayton Burbridge | 01/06/2026 12:00 | Appointment Booked - Staff Allocated | LOT1 - 38 St Bernards Road, Shirehampton | BS11 9UR | COMPLETE TILING TO BATHROOM | Mrs Saeda Yusuf | 447445694323 | saedamy@yahoo.com |  | No | 36/974 | 40454/1 | JEFF WAY - AS PER DARRYL 07733831884 BATHROOM WORKS & MAKE GOOD KIDS BEDROOM & LOFT INSPECTION
Appointments | Jamie Hunt | 01/06/2026 11:00 | Appointment Started | 3 Mowcroft Road, Hartcliffe | BS13 0LE | repairs | Miss Leanne Derrick | 447340995741 | leaderrick1990@gmail.com |  | No | 36/854 | 31982/1 | JW - As per Jeff - Various works required throughout property, See SOR comments for specific location details Hack off damage plaster work to the sides and behind ground floor toilet and reskim to match existing levels. Remove rotten timber skirting at th
Appointments | Jessie Parsons | 01/06/2026 11:00 | Appointment Booked - Staff Allocated | 8 Felton Grove, Bedminster Down | bs13 7ef | CARRY OUT WORK | Mrs Felicity Mcquiness | 447757162878 | fizmcguinness@virginmedia.com |  | No | 36/1303 | 76772/2 | Jeffway- as per Jeff N-Cut damage wallpaper to head and sides of 1st floor rear bedroom window to expose loose plasterwork. hack off and apply skim finish to match existing levels. Apply emulsion paint to new plasterwork only. Overhaul all PVC windows le
Appointments | Oliver Maurice Shore | 01/06/2026 11:00 | Appointment Booked - Staff Allocated | 8 Felton Grove, Bedminster Down | bs13 7ef | CARRY OUT WORK | Mrs Felicity Mcquiness | 447757162878 | fizmcguinness@virginmedia.com |  | No | 36/1303 | 76772/2 | Jeffway- as per Jeff N-Cut damage wallpaper to head and sides of 1st floor rear bedroom window to expose loose plasterwork. hack off and apply skim finish to match existing levels. Apply emulsion paint to new plasterwork only. Overhaul all PVC windows le
Appointments | Darren Whitchurch | 01/06/2026 09:00 | Appointment Started | 17 Dancey Mead | BS13 8DG | SEND TEXT | Mr Stephen John Brine | 447512474312 | stevebinnie2@yahoo.com |  | No | 36/875 | 7166/4 | AS PER NICHOLAS CORY JW TO SKIM WALLS IN STAIRWELL AND DECTORATE.
Appointments | Jamie Hunt | 01/06/2026 09:00 | Appointment Completed | 4 CLONMEL ROAD | BS4 1PW | DISREPAIR WORKS - TO COMPLETE | Mr Mohammed Kamran Adil | 447479557078 | kamiadil1971@gmail.com | Area 4 - South East | No | 36/1176 | 69496/1 | Complaint works- Replace both extractor fans. overhaul and repair windows through out. repair / replace door lock. replace fence panels.
Appointments | Clayton Burbridge | 01/06/2026 08:00 | Appointment Completed | 19 POUNTNEY DRIVE | BS5 0XF | DISREPAIR - COMPLETE WORKS AS PER NOTES | Ms Euthlyn Douglas | 447990810818 |  |  | No | 36/1035 | 38851/1 | Complaint disrepair works / as per CG
Appointments | Glen Norman | 01/06/2026 08:00 | Appointment Completed | 3 HENBURY COURT | BS10 7QL | PAINT NEW PLASTER TO HALLWAY | Miss Lyore Felix | 447459004297 |  | Area 1 - North West | No | 36/1308 | 63699/2 | CARRY OUT WORKS - DISREPAIR
Appointments | Jamie Hunt | 01/06/2026 08:00 | N/A | 3 Mowcroft Road, Hartcliffe | BS13 0LE | repairs | Miss Leanne Derrick | 447340995741 | leaderrick1990@gmail.com |  | No | 36/854 | 31982/1 | JW - As per Jeff - Various works required throughout property, See SOR comments for specific location details Hack off damage plaster work to the sides and behind ground floor toilet and reskim to match existing levels. Remove rotten timber skirting at th