## Works Instructions
Received Date and Time | Description of Work | Appointment Date | Next appointment date | Completed | Type of Work | Property Reference | Address | Client Order Reference | Works Status | Financial Status | Our Works Instruction Number | Started | Time Allowed | Cancelled Reason | Cancelled Date | Recorded By | Latest Completion Date | In Time | Administrative Status | Handover date | Ready to handover | QS Reviewed | Internal Notes | BCC Tracker Status | Job Value
2026-07-03 09:40:00 | JW - AS PER ROB DOIDGE - PATH REPAIRS TO FRONT AND SIDE OF PROPERTY, HAVE USED SQM SORS TO COVER ALL PATCHES, SEE EDITED PHOTOS SENT OVER |  |  |  | Routine Repairs | 1277050 | 57 Elmtree Drive, Withywood, Bristol | 125001/1 | New Works Instruction | ACE Agreed | 36/1722 |  | 35 days |  |  | Lainie Lavin | 20/08/2026 09:40 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 249.98
2026-07-01 14:40:00 | Renew WC pan, renew bathroom flooring, repair wall cracks, redecorate. Tenant has thoughts of harming people. |  |  |  | Routine Repairs | 1307988 | 24 Millmead House | 101843/2 | New Works Instruction | Awaiting Cost Estimate | 36/1718 |  | 35 days |  |  | Cybix AI | 18/08/2026 14:40 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 789.41
2026-07-01 09:40:00 | JW - AS PER IAN OGBORNE - AN OVERHAULS / PAINT DOORS/ DOOR OVERHAUL /KITCHEN OVERHAUL /CLIP 15MM PIPE WORK |  |  |  | Routine Repairs | 1223809 | 119 Kenmare Road | 124036/1 | New Works Instruction | Awaiting Cost Estimate | 36/1713 |  | 35 days |  |  | Cybix AI | 18/08/2026 09:40 |  | Pre-works Items To Complete |  |  |  |  | Next Appointment Needed | 299.64
2026-07-01 08:40:00 | JW - AS PER ROB DOIDGE - RENEW BATH PANEL WITH ACRYLIC, TNT REPORTS BOTH WC AND BATH DRAIN/ FLUSH VERY SLOWLY. OVERHAUL / REPAIR AS REQUIRED / WHILE BATH PANEL OFF |  |  |  | Routine Repairs | 1315271 | 14 Walwyn Gardens | 123967/1 | New Works Instruction | Awaiting Cost Estimate | 36/1712 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 228.87
2026-07-01 08:40:00 | JW - AS PER JOHN OYENIYI - RENEW WC, RENEW SILICONE TO BATH, SCRAPE BACK ALL LOOSE PAINT TO THE BATHROOM WINDOW REVEAL MOULD TREAT AND PAINT WITH MOULD RESISTANT BATHROOM PAINT |  |  |  | Routine Repairs | 1248346 | 8 Hastings Road | 123980/1 | New Works Instruction | Awaiting Cost Estimate | 36/1714 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting appointment date | 492.59
2026-07-01 08:40:00 | JW - AS PER DAVE PALMER- VARIOUS WORKS THROUGHOUT PROPERTY - REPAIRS TO LONGE WALL, DOORFRAME/MAKE GOOD PLASTER WORKS TO BEDROOM, FAN OVERHAUL, EXTERNAL REPAIRS SEE COMMENTS |  |  |  | Routine Repairs | 1250222 | 12 Howard Road | 123969/1 | New Works Instruction | Awaiting Cost Estimate | 36/1715 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting asbestos report | 589.06
2026-07-01 08:40:00 | JW - AS PER JOHN OYENIYI - Crack repair on outdoor shed, Overhaul shed door |  |  |  | Routine Repairs | 1306974 | 12 Meriet Avenue | 123985/1 | New Works Instruction | Awaiting Cost Estimate | 36/1716 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 271.03
2026-07-01 08:40:00 | Fix PVC trim on 1 bedroom window and re-silicone window |  |  |  | Routine Repairs | 1095 | 31 Elder Avenue | 123988/1 | New Works Instruction | Awaiting Cost Estimate | 36/1717 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 127.38
2026-07-01 08:40:00 | JW - AS PER JOHN OYENIYI -crack repair to Living room wall and ceiling; patch paving repairs to make safe |  |  |  | Routine Repairs | 1317120 | 65 Wroughton Drive | 123990/1 | New Works Instruction | Awaiting Cost Estimate | 36/1719 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Pre-completion Items To Complete |  |  |  | 03/07 - Asbestos report received an uploaded. Asbestos report requested - CL | Awaiting appointment date | 439.91
2026-07-01 08:40:00 | JW - AS PER ROB DOIDGE - RENEW BATH PANEL WITH ACRYLIC, WHILE OFF, CHECK AND FILL VERMIN HOLES UNDER BATH. REMOVE KITCHEN CORNER UNIT TO FILL VERMIN HOLES BEHIND TO KITCHEN WALLS ALSO |  |  |  | Routine Repairs | 1271574 | 27 Arthurswood Road | 123964/1 | New Works Instruction | Awaiting Cost Estimate | 36/1720 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 203.81
2026-07-01 08:40:00 | Patch plaster repair at Rear attached shed and channel drainage grate |  |  |  | Routine Repairs | 1244366 | 51 Church Lane | 123979/1 | New Works Instruction | Awaiting Cost Estimate | 36/1721 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:40 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 200.38
2026-07-01 08:30:00 | AS PER NICHOLAS CORY JW TO HACK OFF PLASTER , IN LIVING ROOM UNDER WINDOW , BEDROOM LOW LEFT WALL AND RIGHT SIDE HIGH UP REMOVE SKIRTING BOARDBACK TO BRICK WORK , BITUMEN PAINT , SAND/CEMENT SKIM FINISH AND PAINT |  |  |  | Routine Repairs | 1110890 | 35 Fremantle House | 117034/3 | New Works Instruction | Awaiting Cost Estimate | 36/1711 |  | 35 days |  |  | Cybix AI | 18/08/2026 08:30 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 1045.15
2026-06-30 17:50:00 | Jeff Way - as per Jeff Neck: Works to 1st floor front bedroom as per sor descriptions. |  |  |  | Routine Repairs | 1286051 | 152 Newland Road, Withywood | 114656/2 | New Works Instruction | ACE Agreed | 36/1701 |  | 35 days |  |  | Lainie Lavin | 17/08/2026 17:50 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting asbestos report | 1178.38
2026-06-30 11:50:00 | Inspect outhouse for remedial repairs to cracks in structure and replace approx. 4m2 of concrete path adjacent to front Door |  |  |  | Routine Repairs | 1276499 | 85 Dangerfield Avenue | 71960/4 | New Works Instruction | Awaiting Cost Estimate | 36/1708 |  | 35 days |  |  | Cybix AI | 17/08/2026 11:50 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 720.68
2026-06-30 11:00:00 | Carpenter External contractor Jeff wat to renew garage door and frame complete with Garador Horizon in white |  |  |  | Routine Repairs | 1148078 | 36 Hayes Close | 121798/2 | New Works Instruction | Awaiting Cost Estimate | 36/1709 |  | 35 days |  |  | Cybix AI | 17/08/2026 11:00 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 1121.7
2026-06-30 10:10:00 | Jeff Way - as per Jeff Neck: Works as per sors descriptions. |  |  |  | Routine Repairs | 1294753 | 11 Borver Grove | 123014/1 | New Works Instruction | Awaiting Cost Estimate | 36/1710 |  | 35 days |  |  | Cybix AI | 17/08/2026 10:10 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 5240.79
2026-06-29 17:40:00 | Jeff Way - as per Jeff Neck: Works as per sors descriptions. Tenant has learning disability. |  |  |  | Routine Repairs | 1300738 | 18 Fulford Walk, Hartcliffe | 60800/2 | New Works Instruction | ACE Agreed | 36/1700 |  | 35 days |  |  | Lainie Lavin | 14/08/2026 17:40 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting asbestos report | 756.03
2026-06-29 14:10:00 | AS PER GERRY RYAN = after Asbestos removal by Envirocall of floor tiles to the Hallway- bathroom - W.C please renew |  |  |  | Routine Repairs | 1249667 | 2 Holroyd House, Somerset Terrace, Windmill Hill | 122688/1 | New Works Instruction | ACE Agreed | 36/1699 |  | 35 days |  |  | Lainie Lavin | 14/08/2026 14:10 |  | Pre-completion Items To Complete |  |  |  | asbestos survey needed | Awaiting asbestos report | 415.95
2026-06-29 12:10:00 | Jeff Way - As per Jeff Neck: Replace 2no 600mm kitchen wall doors, 1no 300mm wall door and 1no 400mm base door. |  |  |  | Routine Repairs | 1304025 | 9 Hellier Walk, Hartcliffe | 96795/2 | New Works Instruction | ACE Agreed | 36/1696 |  | 35 days |  |  | Lainie Lavin | 14/08/2026 12:10 |  | Pre-works Items To Complete |  |  |  | held until asbestos survey received - 29/6. | Awaiting asbestos report | 161.24
2026-06-29 10:00:00 | Jeff Way - as per Jeff Neck: Works as per sors descriptions. |  |  |  | Routine Repairs | 1272179 | 675 Bishport Avenue | 92834/2 | New Works Instruction | Awaiting Cost Estimate | 36/1694 |  | 35 days |  |  | Cybix AI | 14/08/2026 10:00 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting asbestos report | 2477.89
2026-06-29 09:41:00 | As per EH Works to kitchen including re-plaster and re-dec, utility room replaster and re dec, kitchen handles/re-fix units and window handle main bedroom |  |  |  | Routine Repairs | 1281283 | 8 Hersey Gardens, Withywood | 122048/1 | New Works Instruction | ACE Agreed | 36/1697 |  | 35 days |  |  | Lainie Lavin | 14/08/2026 09:41 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting asbestos report | 1751.67
2026-06-29 08:40:00 | JOINT ROOF INSPECTION WITH BCC SURVEYOR IAN OGBORNE. JEFF WAY TO PROVIDE LADDER. |  |  |  | Routine Repairs | 1246511 | 37 Gathorne Road | 122320/1 | New Works Instruction | Awaiting Cost Estimate | 36/1693 |  | 35 days |  |  | Cybix AI | 14/08/2026 08:40 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 88.5
2026-06-29 08:40:00 | As per EH Various works throughout property. Priority to refix floor boards/bathroom flooring and socket to front room. Second order to be raised on rest |  |  |  | Routine Repairs | 1300738 | 18 Fulford Walk, Hartcliffe | 122187/1 | New Works Instruction | Awaiting Cost Estimate | 36/1695 |  | 35 days |  |  | Cybix AI | 14/08/2026 08:40 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 721.94
2026-06-29 08:40:00 | Complaint works- over haul rear door. repair trim along skirting. overhaul fan. |  |  |  | Routine Repairs | 1112556 | 62 Halston Drive | 122161/1 | New Works Instruction | Awaiting Cost Estimate | 36/1698 |  | 35 days |  |  | Cybix AI | 14/08/2026 08:40 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 179.61
2026-06-25 18:01:00 | Jeffway-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 03/08/26. 10 DAY PERIOD ENDS 17/08/26. | 2026-06-29 14:45:00 | 2026-06-29 | 2026-06-29 08:49:00 | Routine Repairs | 1283416 | 47 Keble Avenue | 121556/3 | Works Completed | ACE Agreed | 36/1642 |  | 35 days |  |  | Lainie Lavin | 12/08/2026 18:01 |  | Pre-completion Items To Complete |  | Yes |  | eicr test booked due 29/6. | Complete | 143.59
2026-06-25 14:41:00 | Jeffway- PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 28/07/26. 10 DAY PERIOD ENDS 11/08/26. |  |  |  | Routine Repairs | 1290239 | 14 Turtlegate Avenue | 121443/3 | New Works Instruction | ACE Agreed | 36/1643 |  | 35 days |  |  | Lainie Lavin | 12/08/2026 14:41 |  | Pre-completion Items To Complete |  |  |  | 30/6 - Attempted to call, no answer. | Awaiting asbestos report | 143.59
2026-06-25 14:15:00 | Complaint works- over haul fan. replace missed units. unblock sink | 2026-07-16 08:00:00 | 2026-07-16 |  | Disrepair | 1259843 | 18 Proctor House | 121705/1 | New Works Instruction | ACE Agreed | 36/1649 |  | 35 days |  |  | Shannon Slade | 12/08/2026 14:15 |  | Pre-works Items To Complete |  |  |  |  | Appointment booked | 722.72
2026-06-25 11:20:00 | Jeffway- PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 29/07/26. 10 DAY PERIOD ENDS 12/07/26. | 2026-07-03 12:00:00 | 2026-07-03 |  | Routine Repairs | 1276319 | 36 Dangerfield Avenue | 121429/2 | New Works Instruction | Awaiting Cost Estimate | 36/1692 |  | 35 days |  |  | Cybix AI | 12/08/2026 11:20 |  | Pre-works Items To Complete |  |  |  |  | Appointment booked | 143.59
2026-06-24 16:01:00 | Clearance of front and rear gardens including brambles, vegetation, Ash tree, including all roots, and grass cutting, to enable drainage repairs and ground stabilisation works to property |  |  |  | Routine Repairs | 1284997 | 12 Molesworth Close, Withywood, | 121040/1 | New Works Instruction | ACE Agreed | 36/1641 |  | 35 days |  |  | Lainie Lavin | 11/08/2026 16:01 |  | Pre-works Items To Complete |  |  |  |  | Complete | 1460.81
2026-06-24 15:00:00 | stain block ceiling to living room and hall under the stairs |  |  |  | Routine Repairs | 266 | 3 Ashton Rise | 121044/1 | New Works Instruction | Awaiting Cost Estimate | 36/1669 |  | 35 days |  |  | Cybix AI | 11/08/2026 15:00 |  | Pre-works Items To Complete | [5 empty] | 158.32
2026-06-24 08:40:00 | Please attend to investigate issues with the shower not working. when switched on water comes on for 2 secs and then cuts out and beeps. only shower in property. |  |  |  | Routine Repairs | 1262540 | 60 Southbow House | 120636/1 | New Works Instruction | Awaiting Cost Estimate | 36/1691 |  | 35 days |  |  | Cybix AI | 11/08/2026 08:40 |  | Suspended: Awaiting asbestos info | [5 empty] | 46.8
2026-06-24 07:21:00 | AS PER ROB DOIDGE - NEW ORDER FOR DEMOLISHING WALL AND REBUILDING FENCE TO 6 BLACKTHORNE ROAD - J.W |  |  |  | Routine Repairs | 1306521 | 33 Maynard Road | 92739/2 | New Works Instruction | Awaiting Cost Estimate | 36/1640 |  | 35 days |  |  | Carlene Lynette Lynch | 11/08/2026 07:21 |  | Pre-works Items To Complete | [5 empty] | 0.0
2026-06-23 13:35:00 | JEFFWAY- replace the shower supply from the board to the shower switch. please respond to responseelectrical@bristol.gov.uk | 2026-06-24 11:15:00 | 2026-06-24 | 2026-06-24 11:16:00 | Emergency Repair | 1056844 | 1 HOME GROUND | 119980/1 | Works Completed | ACE Agreed | 36/1638 |  | 24 hours |  |  | Shannon Slade | 24/06/2026 13:40 |  | Pre-completion Items To Complete |  | No |  | ALAN IS ATTENDING TOMORROW. | Complete | 46.8
2026-06-23 12:30:00 | Complaint works- Please see email and Report | 2026-07-03 13:45:00 | 2026-07-03 |  | Routine Repairs | 1218139 | 30 Downton Road | 71356/1 | Works Started | Awaiting Cost Estimate | 36/1688 | 2026-07-02 14:00:00 | 35 days |  |  | Cybix AI | 10/08/2026 12:30 | No | Pre-completion Items To Complete |  |  |  | 03/07 - Review needed by manager to assess remaining work needed - CL | Manager review needed | 3520.78
2026-06-22 15:31:00 | JW-ROB D - EXTERNAL REPAIRS TO PATH, REPLACE 1 X SLAB, RENEW BATH PANEL WITH ACRYLIC BREAK UP AND RENEW SECTION OF PATH APPROX 3 LIN M LONG NEXT TO NEWER SHED PATH. HAS DROPPED AND TRIP HAZARDS. REPLACE 1 X MISSING SLAB TO AREA RHS OF THIS NEW PATH. BREAK AND RELEVEL 2 X CRACKS TO SIDE PATH / ALLEY, ONE AT EITHER END. REMOVE SCREWS IN FLOOR AND MAKE GOOD IN ALLEY ALSO, RENEW BATH PANEL WITH ACRYLIC |  |  |  | Routine Repairs | 1300034 | 24 Fulford Road, Hartcliffe, | 120006/1 | New Works Instruction | ACE Agreed | 36/1639 |  | 35 days |  |  | Lainie Lavin | 07/08/2026 15:31 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 519.3
2026-06-22 12:02:00 | Jeffway-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 01/07/26. 10 DAY PERIOD ENDS 15/07/26 | 2026-06-22 12:15:00 | 2026-06-22 | 2026-06-22 07:18:00 | Urgent Repair | 1284646 | 16 Millground Road, Withywood, Bristol BS13 8NF | 119766/3 | Works Completed | ACE Agreed | 36/1635 |  | 5 days |  |  | Shannon Slade | 26/06/2026 12:02 |  | Post-completion Items To Complete |  | Yes |  | 29/06 - Cert being completed 30/06 - 23/06 - EICR complete awaiting cert to be issued, variations need to be added - CL | Complete | 143.59
2026-06-22 07:24:00 |  | 2026-06-26 08:00:00 | 2026-06-26 | 2026-06-26 12:18:00 | Routine Repairs | 1281283 | 8 Hersey Gardens, Withywood | 115755/2 | Works Completed | ACE In Progress | 36/1637 |  | 35 days |  |  | Christopher Barclay | 07/08/2026 07:24 |  | Pre-completion Items To Complete |  | Yes |  | 30/06 - Updated needed from operative - CL | Complete | 855.84
2026-06-19 15:02:00 | JW - AS PER JOHN OYENIYI - Take up a section of Bedroom Laminated flooring up, latex floor to remove lumps, and refix floor |  |  |  | Routine Repairs | 1249510 | 16 HOLLIDGE GARDENS | 119014/1 | New Works Instruction | ACE Agreed | 36/1620 |  | 35 days |  |  | Shannon Slade | 06/08/2026 15:02 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 345.36
2026-06-19 14:16:00 | JEFFWAY to attend: ER: no hot water since Jeffway have done some work changing the battery, tnt without hot water for one week |  |  |  | Emergency Repair | 1107626 | Carolina House, 104 Dove Street | 117349/1 | New Works Instruction | ACE Agreed | 36/1611 |  | 24 hours |  |  | Shannon Slade | 20/06/2026 14:17 |  | Pre-completion Items To Complete |  |  |  | JWE ATTENDING. |  | 46.8
2026-06-19 14:10:00 | PD1 - Please carry out works as listed. |  |  |  | Disrepair | 1009650 | 58 BROADLANDS DRIVE | 118975/1 | New Works Instruction | ACE Agreed | 36/1648 |  | 35 days |  |  | Shannon Slade | 06/08/2026 14:10 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting appointment date | 1751.59
2026-06-19 14:07:00 | Direpair Claims works that was not raised Works are required urgently so we can finally sign off the property and get a completed post inspection/closing down the LOC. | 2026-07-27 08:00:00 | 2026-07-27 |  | Disrepair | 1231545 | 2 Saunton Walk | 118575/1 | New Works Instruction | ACE Agreed | 36/1647 |  | 35 days |  |  | Shannon Slade | 06/08/2026 14:07 |  | Suspended: Awaiting asbestos info |  |  |  |  | Appointment booked | 1250.54
2026-06-19 13:41:00 | JEFF WAY - PLEASE CARRY OUT QUITED WORKS AS PER JAMIE & TOM |  |  | 2026-06-15 14:52:00 | Routine Repairs | 1027572 | 11 OAKHANGER DRIVE | 118960/1 | Works Completed | ACE Agreed | 36/1636 |  | 35 days |  |  | Shannon Slade | 06/08/2026 13:41 |  | Post-completion Items To Complete | 2026-06-22 |  |  |  | Complete | 794.99
2026-06-18 14:56:00 | AS PER NICHOLAS CORY JW TO REMOVE RIVIVI7 FAN IN KITCHEN AND REPLACE WITH HIT AND MISS VENT COVER AND COVER ON OUTSIDE WALL | 2026-06-25 10:00:00 | 2026-06-25 | 2026-06-25 11:14:00 | Routine Repairs | 1265709 | 18 Stanley Street North, Bedminster | 27368/6 | Works Completed |  | 36/1615 |  | 35 days |  |  | Shannon Slade | 05/08/2026 14:56 |  | Pre-works Items To Complete |  | Yes |  | FUSE REMOVED, JACK ATTENDING 25/06 | Complete | 58.72
2026-06-18 14:47:00 | JW - AS PER JOHN OYENIYI - Renew Kitchen Floor, Renew plinth to units, Redecorate walls |  |  |  | Routine Repairs | 1304445 | 11 HOLBROOK CRESCENT | 118136/1 | New Works Instruction | ACE Agreed | 36/1614 |  | 35 days |  |  | Shannon Slade | 05/08/2026 14:47 |  | Pre-works Items To Complete | [5 empty] | 777.88
2026-06-18 14:01:00 | Complaint Works - see report for full details and photos - (Charlotte Houldcroft) |  |  |  | Disrepair | 1219541 | 5 Galway Road | 118332/1 | New Works Instruction | ACE Agreed | 36/1646 |  | 35 days |  |  | Shannon Slade | 05/08/2026 14:01 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 1293.06
2026-06-18 13:59:00 | JW to treat mould in WC and front door. Gloss paint front door. Paint bed1 ceiling complete. Hack off and replaster around front door area + decorate. Thermal board WC wall by alley + dec. |  |  |  | Disrepair | 1070082 | 40 STANTON ROAD | 118296 | New Works Instruction | ACE Agreed | 36/1645 |  | 35 days |  |  | Shannon Slade | 05/08/2026 13:59 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting appointment date | 767.94
2026-06-17 14:43:00 | Jeff Way to Reinstate Bathroom Light and Shower please respond to responseelectrical@bristol.gov.uk |  |  | 2026-06-18 10:40:00 | Emergency Repair | 1103533 | 16b Argyle Road | 118005/1 | Works Completed | ACE Agreed | 36/1613 |  | 24 hours |  |  | Shannon Slade | 20/06/2026 14:44 |  | Pre-completion Items To Complete |  | No |  |  | Complete | 46.8
2026-06-17 14:21:00 | ELE - ESC- Electric shower hot water leaking from behind the shower monitor on the wall. Making unusual noises and electric shocks when the shower is on |  |  |  | Emergency Repair | 1163902 | 61 ASHMEAD HOUSE | 117464/1 | New Works Instruction | ACE Agreed | 36/1612 |  | 24 hours |  |  | Shannon Slade | 20/06/2026 14:25 |  | Pre-completion Items To Complete |  |  |  | JWE COMPLETING |  | 46.8
2026-06-17 14:11:00 | JEFFWAY to attend: ER: Vulnerable tnt, had an electrical test done last week but cooker hasn't worked since - please investigate |  |  |  | Emergency Repair | 1205965 | 26 Tarnock Avenue | 117283/1 | New Works Instruction | ACE Agreed | 36/1610 |  | 24 hours |  |  | Shannon Slade | 20/06/2026 14:12 |  | Pre-completion Items To Complete |  |  |  | JWE HAS COMPLETED |  | 67.08
2026-06-17 13:57:00 | Complaint works - No mould currently present - Preventative - Please see surveyor report for details (Charlotte Houldcroft) |  |  |  | Disrepair | 1238864 | 170 ASHTON DRIVE | 117333/1 | New Works Instruction | ACE Agreed | 36/1644 |  | 35 days |  |  | Shannon Slade | 04/08/2026 13:57 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 1266.82
2026-06-17 11:55:00 | ELE- Water dripping from the light fixture in the kitchen - make safe | 2026-06-18 08:00:00 | 2026-06-18 |  | Emergency Repair | 1140325 | 34 BAYNTON HOUSE | 117381/1 | Works Started | ACE Agreed | 36/1591 | 2026-06-18 09:00:00 | 24 hours |  |  | Shannon Slade | 18/06/2026 12:07 | No | Pre-completion Items To Complete | [5 empty] | 46.8
2026-06-16 09:06:43 | Plaster crack repairs to internal walls; and Redecoration works, Renew WHB, and Bath Panel |  |  |  | Routine Repairs | 1282800 | 238 Ilchester Crescent | 116510/1 | New Works Instruction | ACE Agreed | 36/1580 |  | 35 days |  |  | Cybix AI | 03/08/2026 09:06 |  | Pre-works Items To Complete |  |  |  |  | RESPONSIVE | 573.38
2026-06-16 09:06:43 | CLEAR GUTTERING WITH VAC SYSTEM, REPLACE 1 GUTTER UNION JOINT AS PER SURVEY PHOTOS - DAVE PALMER |  |  |  | Routine Repairs | 1298539 | 139 Crosscombe Drive | 116407/1 | New Works Instruction | Awaiting Cost Estimate | 36/1581 |  | 35 days |  |  | Cybix AI | 03/08/2026 09:06 |  | Pre-completion Items To Complete |  |  |  |  | RESPONSIVE | 111.64
2026-06-15 15:04:00 | renew a collapsed front door porch ceiling due to water damage ( roof being renewed ) |  |  | 2026-04-17 15:21:00 | Routine Repairs | 100000 | 14 Miles Road, | 58169/1 | Works Completed | ACE Agreed | 36/1578 |  | 35 days |  |  | Carlene Lynette Lynch | 31/07/2026 15:04 |  | Suspended: Awaiting asbestos info |  | No |  |  | Complete | 594.68
2026-06-15 11:03:33 | RENEWAL OF BROKEN / SUNK SECTION OF GARDEN PATH RHS OF BACK DOOR. DRAIN SURVEY SHOWS NO COLLAPSE OR DRAINAGE ISSUES. APPROX 2M2 |  |  |  | Routine Repairs | 1315497 | 278 Whitchurch Lane | 115588/1 | New Works Instruction | Awaiting Cost Estimate | 36/1573 |  | 35 days |  |  | Cybix AI | 31/07/2026 11:03 |  | Pre-works Items To Complete |  |  |  |  | RESPONSIVE | 249.98
2026-06-15 10:53:00 | PD1 - Please carry out works as listed |  |  |  | Disrepair | 1279410 | 25 FOUR ACRES CLOSE | 115736/1 | New Works Instruction | ACE Agreed | 36/1590 |  | 35 days |  |  | Shannon Slade | 31/07/2026 10:53 |  | Suspended: Awaiting asbestos info | [5 empty] | 757.6
2026-06-15 10:47:00 | Disrepair Claims works required WC & Hallway Works are to be placed on hold until until the ACM reports are returned and the investigation process is completed. The works will go ahead but may require other works to be completed prior to this order. |  |  |  | Disrepair | 1299714 | 22 FABER GROVE | 115893/1 | New Works Instruction | ACE Agreed | 36/1589 |  | 35 days |  |  | Shannon Slade | 31/07/2026 10:47 |  | Pre-works Items To Complete | [5 empty] | 799.67
2026-06-15 10:44:00 | Disrepair Claims works required These works can be undertaken whilst awaiting investigation works of other areas please proceed with this order. | 2026-07-01 12:30:00 | 2026-07-01 |  | Disrepair | 1299714 | 22 FABER GROVE | 115821/1 | New Works Instruction | ACE Agreed | 36/1588 |  | 35 days |  |  | Shannon Slade | 31/07/2026 10:44 |  | Pre-works Items To Complete |  |  |  | 02/07 - Review needed by manager for remaining work - CL | Manager review needed | 1765.72
2026-06-15 08:51:00 | Overhaul ext fan in bathroom and patch repair to floor (cap & cove) |  |  |  | Routine Repairs | 1036619 | 59 TRYM SIDE | 85618/1 | New Works Instruction | Awaiting Cost Estimate | 36/1625 |  | 35 days |  |  | Cybix AI | 31/07/2026 08:51 |  | Suspended: Awaiting asbestos info |  |  | 0 |  | RESPONSIVE | 29.36
2026-06-15 08:51:00 | JW to treat mould in WC and front door. Gloss paint front door. Paint bed1 ceiling complete. Hack off and replaster around front door area + decorate. Thermal board WC wall by alley + dec. | 2026-06-26 08:00:00 | 2026-07-17 |  | Routine Repairs | 1070082 | 40 STANTON ROAD | 118296/1 | New Works Instruction | Awaiting Cost Estimate | 36/1634 |  | 35 days |  |  | Cybix AI | 31/07/2026 08:51 |  | Suspended: Awaiting asbestos info |  |  |  | 30/06 - Unable to contact tenant, voicemail left - CL 29/06 - Asbestos report requested - CL 25/06 - Appointment confirmed with tenant - CL | WIP | 767.94
2026-06-11 10:36:00 | Complaints works - please see surveyors report and email for details (Charlotte Houldcroft) |  |  |  | Disrepair | 1286937 | 132 Queens Road | 115104/1 | New Works Instruction | ACE Agreed | 36/1587 |  | 35 days |  |  | Shannon Slade | 29/07/2026 10:36 |  | Pre-completion Items To Complete | [5 empty] | 2248.65
2026-06-11 10:28:00 | PD1 - Please carry out works as listed |  |  |  | Disrepair | 1187866 | 57 ST DAVIDS CRESCENT | 115147/1 | New Works Instruction | ACE Agreed | 36/1586 |  | 35 days |  |  | Shannon Slade | 29/07/2026 10:28 |  | Suspended: Awaiting asbestos info | [5 empty] | 1665.92
2026-06-11 10:18:00 | Disrepair - repairs throughout property |  |  |  | Disrepair | 1114745 | 44 MOGG STREET | 115067/1 | New Works Instruction | ACE Agreed | 36/1585 |  | 35 days |  |  | Shannon Slade | 29/07/2026 10:18 |  | Suspended: Awaiting asbestos info | [5 empty] | 7223.75
2026-06-10 09:44:00 | JW - AS PER JOHN OYENIYI - Renew Kitchen Flooring, Renew Extractor Fan to Bathroom, Mould wash Bathroom ceiling, Bedroom 1, and Living Room, Gutter repairs | 2026-06-24 12:00:00 | 2026-07-17 |  | Routine Repairs | 1295927 | 4 Broadstone Walk, Hartcliffe | 114250/1 | New Works Instruction | ACE Agreed | 36/1562 |  | 35 days |  |  | Lainie Lavin | 28/07/2026 09:44 |  | Pre-works Items To Complete |  |  |  | 26/06 - FF to attend on 02/07 and 03/07 - CL 22/06 - PO sent to FF - CL | WIP | 1362.96
2026-06-10 08:57:00 |  |  |  |  | Routine Repairs | 1846624 | 4-26 CROSSCOMBE DRIVE | 114487/1 | New Works Instruction | ACE Agreed | 36/1564 |  | 35 days |  |  | Shannon Slade | 28/07/2026 08:57 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 112.9
2026-06-09 13:42:00 | JW - AS PER ROB DOIDGE - RENEWAL OF FRONT AND REAR TIMBER FASCIA / SOFFITS WITH UPVC IF APPLICABLE. RENEWAL OF GUTTERING ALSO FRONT AND REAR AND DOWNPIPES | 2026-07-08 08:00:00 | 2026-07-07 |  | Routine Repairs | 1310481 | 21 Pavey Road, Hartcliffe | 113952/1 | New Works Instruction | ACE Agreed | 36/1561 |  | 35 days |  |  | Carlene Lynette Lynch | 27/07/2026 13:42 |  | Pre-works Items To Complete |  |  |  |  | Appointment booked | 3914.54
2026-06-09 11:50:00 | JW- AS PER JEFF NECK - DIG OUT TRENCH ACROSS GARDEN TO TAKE DRAINAGE PIPEWORK TO DRAIN UNDER EXISTING TIMBER FENCE ONTO WASTELAND |  |  |  | Routine Repairs | 0001053 | 188 Airport Road | 113660/1 | New Works Instruction | ACE Agreed | 36/1560 |  | 35 days |  |  | Carlene Lynette Lynch | 27/07/2026 11:50 |  | Suspended: Awaiting asbestos info |  |  |  | 16/06 - PO sent to AG Builders - CL |  | 1873.15
2026-06-09 11:18:00 | Jeffway- John O-LIVING ROOM - Paint wall after tap maintenance | 2026-07-02 12:00:00 | 2026-07-02 |  | Routine Repairs | 0001063 | 168 Airport Road | 61652/2 | Works Started | ACE Agreed | 36/1557 | 2026-07-02 12:00:00 | 35 days |  |  | Carlene Lynette Lynch | 27/07/2026 11:18 | No | Suspended: Awaiting asbestos info |  |  |  |  | Appointment booked | 138.27
2026-06-09 10:11:00 | Complaint Work - Please see e-mail and report | 2026-06-24 08:00:00 | 2026-06-24 |  | Disrepair | 1252911 | 162 Luckwell Road | 114211/1 | New Works Instruction | ACE Agreed | 36/1584 |  | 35 days |  |  | Shannon Slade | 27/07/2026 10:11 |  | Suspended: Awaiting asbestos info |  |  |  | 24/6 - Mould wash. 23/06 - Unable to get hold of tenant, voicemail left - CL | Appointment booked | 863.0
2026-06-09 10:03:00 | Direpair Claims works required These works are to proceed with full supervisor engagement with Tristan where investigations have been identified. Suggest using a company IES in Wales for your cavity reporting |  |  |  | Disrepair | 1224664 | 43 KINGSHILL ROAD | 114066/1 | New Works Instruction | ACE Agreed | 36/1583 |  | 35 days |  |  | Shannon Slade | 27/07/2026 10:03 |  | Suspended: Awaiting asbestos info | [5 empty] | 831.67
2026-06-08 12:54:00 | CAR - Jeffway Garage No.2. to be replaced with Garador Horizon up and over quoted Mr Darren Brinble 07590518469. please provide after pictures BCC contact Luke Pomphrey |  |  |  | Routine Repairs | 1852331 | Gaywood House Garage Site, North Street | 79434/2 | New Works Instruction | ACE Agreed | 36/1549 |  | 35 days |  |  | Lainie Lavin | 24/07/2026 12:54 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 1417.36
2026-06-08 09:58:00 | Complaint Work - Please see e-mail and report | 2026-06-26 12:00:00 | 2026-06-26 |  | Disrepair | 1262744 | 12 SPENCER HOUSE | 112615/1 | New Works Instruction | ACE Agreed | 36/1582 |  | 35 days |  |  | Shannon Slade | 24/07/2026 09:58 |  | Suspended: Awaiting asbestos info |  |  |  |  | Appointment booked | 1260.37
2026-06-08 07:42:00 | JW - AS PER JEFF NECK - Site inspection to verify all works in flat, as per our Email to Chris Barcley |  |  |  | Routine Repairs | 1313195 | 38 STILLINGFLEET ROAD | 112322/1 | Works Cancelled | Works Cancelled | 36/1552 |  | 35 days | 4: Other | 2026-06-25 11:56:48 | Carlene Lynette Lynch | 24/07/2026 07:42 |  | Works Cancelled |  |  |  | 25/06 - Order cancelled and a new WO to be raised once tenant have been removed - CL 09/06 - Email sent to tenant. Phone numbers provided are not in service, email sent to IO for additional contact information. Can be verbally aggressive, visits in 2's, high verbal aggression - CL | Cancelled | 62.83
2026-06-08 07:38:00 | CAR external contractor Jeffway to arrange renewal of garage door and frame Garador horizon complete BCC contact Luke Pomphrey tnt lives at 105 Littlecross |  |  |  | Routine Repairs | 1354138 | Little Cross House Garage 2 | 112778/1 | New Works Instruction | Awaiting Cost Estimate | 36/1551 |  | 35 days |  |  | Carlene Lynette Lynch | 24/07/2026 07:38 |  | Pre-works Items To Complete |  |  |  | COMPLETED | Complete | 0.0
2026-06-08 07:33:00 | JW - AS PER JEFF NECK - Please arrange roof inspection now scaffold move to front elevation to check front chimney and flashings. As per Darren | 2026-07-02 18:30:00 | 2026-07-08 |  | Routine Repairs | 1244968 | 223 Coronation Road, Southville | 112815/1 | Works Started | ACE Agreed | 36/1550 | 2026-06-24 12:00:00 | 35 days |  |  | Carlene Lynette Lynch | 24/07/2026 07:33 | No | Post-completion Items To Complete |  |  |  | 25/06 - Tim to return to replace 2 roof tiles RHS of bay window - CL 16/06- Job on hold until Variation for works received 11/06 - DW to carry out site visit with JN - CL 09/06 - Email sent to JN regarding site visit - CL | WIP | 840.89
2026-06-05 07:31:00 | JW - AS PER JEFF NECK - Move existing plastic storage box and excavate soil to suit existing concrete slabs. Lay new slabs to suit existing levels. |  |  |  | Routine Repairs | 1271234 | 17 Acresbush Close | 111471/1 | New Works Instruction | Awaiting Cost Estimate | 36/1544 |  | 35 days |  |  | Carlene Lynette Lynch | 23/07/2026 07:31 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 0.0
2026-06-04 19:02:02 | KITCHEN REPAIRS , BATHROOM FLOORING AND PANEL , OUT BUILDING ROOF AND REPAIRS |  |  |  | Routine Repairs | 1282651 | 139 Ilchester Crescent | 1351034 | New Works Instruction | Awaiting Cost Estimate | 36/1526 |  | 35 days |  |  | Cybix AI | 22/07/2026 19:02 |  | Suspended: Awaiting asbestos info |  |  |  |  | RESPONSIVE | 0.0
2026-06-04 19:02:02 | replace concrete outside front door creating gradient so water flows towards aco drain. Fit x1 gully cover and clear/clean aco drain. |  |  |  | Routine Repairs | 1204633 | 58 Showering Road, Stockwood, Bristol BS14 8DN | 1501545 | New Works Instruction | Awaiting Cost Estimate | 36/1530 |  | 35 days |  |  | Cybix AI | 22/07/2026 19:02 |  | Suspended: Awaiting asbestos info |  |  |  |  | RESPONSIVE | 0.0
2026-06-04 14:22:43 | Renew Gate to front garden | 2026-07-01 11:15:00 |  |  | Routine Repairs | 1316478 | 2 Woodmead Gardens | 109711/1 | Works Started | ACE Agreed | 36/1523 | 2026-06-30 13:30:00 | 35 days |  |  | Cybix AI | 22/07/2026 14:22 | No | Suspended: Awaiting Client Action/Response |  |  |  | 01/06 - Gate needs to be order and additional cost required. VO will be sent once costs have been worked out. CB to attend once approved and order received- CL 30/06 - Operative unable to complete work needs a manager to review - CL | Held BCC | 112.23
2026-06-04 07:34:00 | JW - AS PER JEFF NECK - Remove and refix damage kitchen draws and doors to suit |  |  |  | Routine Repairs | 1314198 | 29 Totshill Drive | 111059/1 | New Works Instruction | Awaiting Cost Estimate | 36/1535 |  | 35 days |  |  | Carlene Lynette Lynch | 22/07/2026 07:34 |  | Pre-works Items To Complete |  |  |  |  | Awaiting appointment date | 0.0
2026-06-04 07:30:00 | JW - JEFF NECK - Remove and clear water damage cupboard under sink, check and overhaul waste and pipework under sink, overhaul bath tap, fix new bath panel, replace broken toilet cistern. | 2026-07-21 08:00:00 | 2026-07-21 |  | Routine Repairs | 1261467 | 49 Silbury Road | 111069/1 | New Works Instruction | ACE Agreed | 36/1534 |  | 35 days |  |  | Carlene Lynette Lynch | 22/07/2026 07:30 |  | Suspended: Awaiting asbestos info |  |  |  | 24/06 - Email sent to JN and CM for asbestos report - CL | Appointment booked | 381.91
2026-06-04 07:24:00 | AS PER NICHOLAS CORY JEFFWAY TO ADD TILES ABOVE EXISTING TILES USING 8X6 TO MATCH AS BEST AROUND PERIMETER OF BATH TO CEILING HEIGHT |  |  |  | Routine Repairs | 1174807 | 50 Eccleston House | 79554/2 | New Works Instruction | ACE Agreed | 36/1533 |  | 35 days |  |  | Carlene Lynette Lynch | 22/07/2026 07:24 |  | Suspended: Awaiting Client Action/Response |  |  |  | 24/06 - Tenant informed me that work has been completed already, email sent to NC on how to proceed - CL | Held BCC | 491.64
2026-06-03 18:44:25 | Rebuild retaining wall in Rear Garden and patch repair paving |  |  |  | Routine Repairs | 1287792 | 81 REDFORD CRESCENT | 109373/1 | New Works Instruction | Awaiting Cost Estimate | 36/1491 |  | 35 days |  |  | Cybix AI | 21/07/2026 18:44 |  | Pre-completion Items To Complete |  |  |  | 05/06 - PO sent to BS for work - CL | Awaiting appointment date | 845.48
2026-06-03 13:34:00 | Complaint Work - Please see e-mail and report | 2026-07-01 08:00:00 | 2026-07-01 |  | Disrepair | 1156770 | 15 ROPEWALK HOUSE | 109390/1 | Works Started | ACE Agreed | 36/1521 | 2026-07-01 08:00:00 | 35 days |  |  | Shannon Slade | 21/07/2026 13:34 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Review needed by manager on outstanding work required. Dan only completed ceiling repair to kitchen - CL 30/06 - Appointment confirmed with tenant - CL | Manager review needed | 2243.43
2026-06-02 13:29:00 | staircase Hack off wall to right off staircase and replaster & Strip wall to right off staircase - Kitchen BED 2- repair crack to kitchen wall and bed 2 ceiling & Overhaul kitchen fan - |  |  |  | Disrepair | 1142241 | 50 CHELSEA ROAD | 109175/1 | New Works Instruction | ACE Agreed | 36/1520 |  | 35 days |  |  | Shannon Slade | 20/07/2026 13:29 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting appointment date | 977.48
2026-06-02 13:21:00 | NEEDS TO BE COMPELTED WITHIN 60 DAYS Disrepair works - URGENT - decorating and plaster works |  |  |  | Disrepair - Tomlin | 1103533 | 16b Argyle Road | 109180/1 | New Works Instruction | ACE Agreed | 36/1515 |  | 35 days |  |  | Shannon Slade | 20/07/2026 13:21 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 2958.38
2026-06-02 11:01:00 | JW - As per KPD/Chloe - Jeffway to issue order to Dobbins for completed deep clean @ 49a station road (WO issued for £216.00 with JW Mark up , JW to pay Dobbins £180.00 quoted works from Dobbins) |  |  | 2026-06-04 07:44:00 | Routine Repairs | 1034237 | 49a Station Road | 108832/1 | Works Completed | Invoiced | 36/1497 |  | 35 days |  |  | Shannon Slade | 20/07/2026 11:01 |  | Fully Complete | 2026-06-08 |  |  | PO ISSUED TO DOBBINS - WAITING FOR RESPONSE FROM CHLOE REGARDING SHUTTING DOWN ORDER | Complete | 216.0
2026-06-01 13:16:00 | PD1 - Board up the flooring and seal around pipe work in hallway cupboard. Please do this on the same appointment as Kitchen cupboards. |  |  | 2026-06-10 12:00:00 | Disrepair | 1104796 | 89, FLAT 10 ASHLEY ROAD | 108654/1 | Works Completed | ACE Agreed | 36/1514 |  | 35 days |  |  | Shannon Slade | 17/07/2026 13:16 |  | Pre-completion Items To Complete |  | No |  | 15/06 - WORKS COMPLETED, PICTURES ON WORKS ORDER 34878/1, WILL SIGN OFF TOGETHER. WORKS BEING COMPLETED ALONGSIDE OTHER APPOINTMENT 09/06 | Complete | 131.38
2026-06-01 07:03:00 | PD1 - Carryout overhaul whilst conducting other works | 2026-06-11 09:30:00 | 2026-06-15 | 2026-06-15 14:24:00 | Disrepair | 1014557 | 1 Failand Crescent (KS1985) | 108445/1 | Works Completed | ACE Agreed | 36/1532 |  | 35 days |  |  | Shannon Slade | 17/07/2026 07:03 |  | Suspended: Awaiting asbestos info |  | No |  |  | Appointment booked | 95.17
2026-05-29 13:01:00 | Complaint works- Please see email and report ( works to rectify leak damage thought address) | 2026-06-10 09:15:00 | 2026-06-19 |  | Disrepair | 1045632 | 41 Charfield Road | 107205/1 | Works Started | ACE Agreed | 36/1511 | 2026-06-10 09:15:00 | 35 days |  |  | Shannon Slade | 16/07/2026 13:01 | No | Suspended: Awaiting Client Action/Response |  |  |  | 02/07- awaiting confirmation from BCC removal has taken place IVY REMOVAL BOOKED FOR 19TH JUNE | Appointment booked | 3495.15
2026-05-29 11:25:00 | Chimney Scaffold to be erected so I can investigate what/why it is leaking around the stack |  | 2026-06-08 |  | Routine Repairs | 1232195 | 79 Somerdale Avenue | 106548/1 | New Works Instruction | ACE Agreed | 36/1483 |  | 35 days |  |  | Shannon Slade | 16/07/2026 11:25 |  | Pre-completion Items To Complete |  |  |  | 12/06 - Awaiting to make contact with MRF - CL 10/06 - Scaffolding unable to go up as neighbour needs to move car from drive - CL 01/06 - SCAFFOLDING BEING ERECTED 8TH JUNE | Held BCC | 1119.41
2026-05-29 10:10:00 | JW - ROB D - REPAIR / RESEALING TO FRONT DOOR FRAME RHS AND TOP AND WINDOWFRAME LHS OF DOOR WHERE SEALANT FALLEN OUT SILL AND TOP. RUB DOWN AND REGLOSS WINDOW , FRAME AND DOOR | 2026-06-23 10:45:00 | 2026-06-23 | 2026-06-23 08:04:00 | Routine Repairs | 1297218 | 53 Coleshill Drive, Hartcliffe, Bristol | 106836/1 | Works Completed | ACE Agreed | 36/1496 |  | 35 days |  |  | Lainie Lavin | 16/07/2026 10:10 |  | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPi request sent - CL | Complete | 125.64
2026-05-28 14:41:00 | inspection of bathroom for leak | 2026-05-29 11:00:00 | 2026-05-29 |  | Routine Repairs | 1281534 | 3 Highmead Gardens | 106540/1 | New Works Instruction | ACE In Progress | 36/1460 |  | 35 days |  |  | Carlene Lynette Lynch | 15/07/2026 14:41 |  | Pre-completion Items To Complete |  |  |  | 18/06 - DP confirmed and will update once removed - CL DW visited site, identified artex on walls containing ACM, awaiting response from DP 15/06 - Awaiting JIS - CL 12/06 - Site visit carried out on 29/05, order has been varied . Awaiting job sheet to book in work - CL 03/06 - Asbestos report received and uploaded. Asbestos report requested. VO approve, amended WO uploaded - CL 01/06 - VO sent for approval - CL 30/05 - Awaiting Vo to be added - CL 28/05 - DW to meet PW at property for a site visit 29/05 - CL | Held BCC | 4193.16
2026-05-28 12:55:00 | Complaint Work - Please see e-mail and report | 2026-07-06 08:00:00 | 2026-07-06 |  | Disrepair | 1096793 | 147 RODBOURNE ROAD | 104455/1 | New Works Instruction | ACE Agreed | 36/1455 |  | 35 days |  |  | Shannon Slade | 15/07/2026 12:55 |  | Pre-completion Items To Complete |  |  |  | 03/07 - Appointment confirmed with tenant - CL | Appointment booked | 1635.4
2026-05-28 12:53:00 | Complaint Work - Please see e-mail and report | 2026-07-09 08:00:00 | 2026-07-08 |  | Disrepair | 1244048 | 18 CHATTERTON HOUSE | 106653/1 | New Works Instruction | ACE Agreed | 36/1510 |  | 35 days |  |  | Shannon Slade | 15/07/2026 12:53 |  | Suspended: Awaiting asbestos info |  |  |  |  | Appointment booked | 842.99
2026-05-28 12:47:00 | Complaint works- please see email and report |  |  |  | Disrepair | 1147371 | 93 HASSELL DRIVE | 106375/1 | New Works Instruction | ACE Agreed | 36/1509 |  | 35 days |  |  | Shannon Slade | 15/07/2026 12:47 |  | Pre-completion Items To Complete |  |  |  |  | Awaiting appointment date | 2686.97
2026-05-27 13:49:00 | AS PER GERRY RYAN = EMMA HIND = Remove wall and put back rooms after hidden grow room behind Airing cupboard and also inspected loft for damage | 2026-07-02 08:00:00 | 2026-07-07 |  | Routine Repairs | 1213361 | 8 Campian Walk, Inns Court | 105847/1 | Works Started |  | 36/1456 | 2026-07-02 10:00:00 | 35 days |  |  | Lainie Lavin | 14/07/2026 13:49 | No | Pre-completion Items To Complete |  |  |  | 03/07 - Review needed from manager to formulate a plan as job requirements has changed. Operatives attended 02/07 to start work - CL 17/06 - Asbestos report received and uploaded - CL 01/06 - Follow on appointments booked with tenant for 18/06, 02/07,03/07 and 07/07 - CL | Manager review needed | 2231.77
2026-05-27 13:30:00 | JW - AS PER JOHN OYENIYI - Renew sealing gasket to windows, renew their handles, overhaul exit door and reglaze patio door | 2026-07-24 12:00:00 | 2026-07-24 |  | Routine Repairs | 1282480 | 12 Huntingham Road, Withywood | 105859/1 | New Works Instruction |  | 36/1457 |  | 35 days |  |  | Lainie Lavin | 14/07/2026 13:30 |  | Pre-completion Items To Complete |  |  |  | 03/07 - NA on 02/07, appointment rescheduled with tenant - CL 04/06 - Approval received PO sent to WSG - CL 01/06 - Glazing sent to WSG unable to send PO until commercial has set the pricing - CL | Manager review needed | 896.44
2026-05-27 13:30:00 | JW - AS PER ROB DOIDGE - RENEWING 2 X SLABS TO MAKE A WIDER AREA OUTSIDE BACK DOOR, THEN INSTALL KEE KLAMP RAIL TO LHS OF NEW SLABS , 1M APPROX. 3 SLABS OUT FROM WALL | 2026-07-03 08:00:00 | 2026-07-03 |  | Routine Repairs | 1280508 | 1 Gatehouse Way, Withywood | 105867/1 | Works Started | ACE Agreed | 36/1458 | 2026-07-03 08:00:00 | 35 days |  |  | Lainie Lavin | 14/07/2026 13:30 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment confirmed with tenant - CL | Held BCC | 166.44
2026-05-27 13:10:00 | JW - AS PER IAN - COMPLAINT WORKS URGENT - BATHROOM WORKS / D&M DECORATIONS / PLUMBING / KITCHEN PLINTHS /MASONARY / WINDOW OVERHAUL | 2026-07-03 08:00:00 | 2026-07-06 |  | Routine Repairs | 1307762 | 2 Millmead House, Silcox Road, Hartcliffe | 105824/1 | Works Started | ACE Agreed | 36/1459 | 2026-07-03 08:00:00 | 35 days |  |  | Lainie Lavin | 14/07/2026 13:10 | No | Pre-completion Items To Complete |  |  |  | 03/07 - Unable to get hold of tenant, voicemail left - CL 25/06 - Spoke with tenant and confirmed appointment dates and wen through the works to carried out - CL | Appointment booked | 724.47
2026-05-27 13:10:00 | JW - AS PER JOHN OYNEIYI - Renew Bath panel; skim and redecorate wall behind WC; Renew plasterboard ceiling to staircase and redecorate | 2026-07-09 12:00:00 | 2026-07-09 |  | Routine Repairs | 1303088 | 5 Hartgill Close, Hartcliffe | 105842/1 | Works Started | ACE Agreed | 36/1461 | 2026-07-01 08:00:00 | 35 days |  |  | Lainie Lavin | 14/07/2026 13:10 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Bath panel done, remove toilet cistern and painted behind. Ceiling above stairs not plastered and return visit to plaster and paint once dry - CL 30/06 - Update needed from operative - CL 25/06 - Unable to get hold of tenant, voicemail left and text sent - CL | WIP | 490.24
2026-05-27 13:10:00 | JW - AS PER ROB DOIDGE - REPAIR/ RENEWAL TO PATCH OF KITCHEN FLOOR WHERE LATEX / TILES BROKEN UP AND MISSING, SMALL AREA UNDER SINK UNIT ALSO | 2026-07-10 10:00:00 | 2026-07-10 |  | Routine Repairs | 1305460 | 7 Lasbury Grove, Hartcliffe | 105830/1 | New Works Instruction |  | 36/1462 |  | 35 days |  |  | Lainie Lavin | 14/07/2026 13:10 |  | Pre-works Items To Complete |  | Yes |  | 03/07 - Post inspection booked for IE to attend on 10/07 - CL 30/06 - Flooring completed. Email sent to FF for update on flooring - CL 17/06 - FF to attend on 24/06 and 25/06 - CL 15/06 - Amended PO sent to FF - awaiting a date - CL 09/06 - VO sent to RD and EH - CL 01/06 - PO sent to FF - CL | Appointment booked | 1030.0
2026-05-27 13:10:00 | JW- ROB DOIDGE - CRUMBLING SEALANT / SKIM AROUND PIPES TO BED 2 CEILING AND BED 1 WALL. REPAIR AND RESEAL AROUND PIPES. BASIN TO BATHROOM DRAINS SLOWLY, REPAIR AS REQUIRED daughter anna - 07901912822 or louise - 07443480677 - please contact one of them prior to appointment to assist with booking etc | 2026-06-29 12:00:00 | 2026-06-29 | 2026-06-29 07:54:00 | Routine Repairs | 1262448 | 49 Southbow House, Duckmoor Road | 105809/1 | Works Completed | ACE Agreed | 36/1463 | 2026-06-29 12:00:00 | 35 days |  |  | Lainie Lavin | 14/07/2026 13:10 | Yes | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI request sent - CL | Complete | 68.18
2026-05-27 12:49:00 | REPAIR CHIP IN ENAMEL BATH, REPLACE LEAKING PAN CONNECTOR, PREP AND PAINT BATHROOM SKIRTING BEHIND TOILET AND SINK, RENEW ANTI SLIP FLOORING TO BATHROOM. | 2026-07-27 08:00:00 | 2026-07-27 |  | Routine Repairs | 1285707 | 67 NEWLAND ROAD | 116515/1 | New Works Instruction | Awaiting Cost Estimate | 36/1579 |  | 35 days |  |  | Cybix AI | 14/07/2026 12:49 |  | Pre-completion Items To Complete |  |  |  | 26/06 - NA on 25/06, appointment rebooked - CL | Appointment booked | 378.26
2026-05-27 12:29:00 | Plaster crack repairs to internal walls; and Redecoration works | 2026-07-13 08:00:00 | 2026-07-13 |  | Routine Repairs | 1276740 | 31 Eastlyn Road | 109856/1 | New Works Instruction | Awaiting Cost Estimate | 36/1522 |  | 35 days |  |  | Cybix AI | 14/07/2026 12:29 |  | Pre-completion Items To Complete |  |  |  | 05/06 - Asbestos report received and uploaded. Asbestos report requested - CL | Appointment booked | 480.1
2026-05-26 15:30:00 | Roof works |  |  |  | Routine Repairs | 1563151 | Second Floor Flat, 14 Miles Road | 105427/1 | New Works Instruction |  | 36/1482 |  | 35 days |  |  | Lainie Lavin | 13/07/2026 15:30 |  | Pre-completion Items To Complete |  |  |  | 24/06 - PO sent to BS - CL | Awaiting appointment date | 3146.63
2026-05-26 12:39:00 | Disrepair Claim - Damaged to plasterboard ceiling and stud wall in kitchen and bathroom/WC |  |  |  | Disrepair | 1249656 | Holroyd House, 1 Somerset Terrace | 105224/1 | New Works Instruction | ACE Agreed | 36/1508 |  | 35 days |  |  | Shannon Slade | 13/07/2026 12:39 |  | Pre-completion Items To Complete | [5 empty] | 983.6
2026-05-26 07:17:00 | Wall:Take down external one block wall and remove spoil - two levels in rear garden |  |  | 2026-06-12 13:14:00 | Routine Repairs | 1290217 | 12 TURTLEGATE AVENUE | 105263/1 | Works Completed | Invoiced | 36/1454 |  | 35 days |  |  | Shannon Slade | 13/07/2026 07:17 |  | Fully Complete | 2026-06-17 |  |  | 11/06 - SHEPS HAS CONFIRMED HE WILL TAKE ON WORKS - COMPLETING NEXT WEEK. 05/06 - WORKS ISSUED TO SHEPS, WAITING FOR CONFIRMATION | Complete | 1223.17
2026-05-22 10:34:00 | Daniel Allen - HHSRS issue with fall height in garden. Wall to be demolished and garden graded up to slope |  |  |  | Routine Repairs | 1235149 | 41 Torrington Avenue, Knowle | 104543/1 | New Works Instruction | ACE Agreed | 36/1447 |  | 35 days |  |  | Shannon Slade | 10/07/2026 10:34 |  | Pre-completion Items To Complete |  |  |  | 24/06 - Awaiting an appointment date from AG Builders - CL 16/06 - PO sent to AG Builders - CL 03/06 - ASBESTOS REPORT RECEIVED. | Awaiting appointment date | 658.63
2026-05-22 09:10:00 | As per Daniel Allen - Clear guttering front and rear of dwelling |  |  |  | Routine Repairs | 1201736 | 19 Manston Close | 95945/1 | New Works Instruction | ACE Agreed | 36/1438 |  | 35 days |  |  | Charlie Higginson | 10/07/2026 09:10 |  | Pre-completion Items To Complete |  |  |  | 26/06 - Email sent to Elite to make contact - CL 25/06 - Elite have been unable to make contact with tenant, I called and informed her that Elite will be calling to arrange an appointment - CL 23/06 - Email sent to Elite for update - CL 16/06 - Emails sent to Elite regarding gutter clean - CL 22/05 - Works issued to Gutter Team, awaiting date confirmation. | Awaiting appointment date | 92.28
2026-05-21 10:54:00 | Renew WC Suites at Rear Toilet. Re align Roof Gutters both front and Rear and replace damaged brackets |  |  |  | Routine Repairs | 1282753 | 216 ILCHESTER CRESCENT | 115977/1 | New Works Instruction | ACE Agreed | 36/1572 |  | 35 days |  |  | Cybix AI | 09/07/2026 10:54 |  | Pre-completion Items To Complete |  |  |  |  | RESPONSIVE | 1506.25
2026-05-21 10:54:00 | JW - AS PER ROB DOIDGE - SCRAPE OFF AND RESKIM WETROOM CEILING AFTER LEAKIN FULL, 2 X COATS OF PAINT AND MIST COAT AFTERWARDS. RUB DOWN, STAINBLOCK AND REPAINT BOXING TO RISERS ALSO IN FULL. |  |  |  | Routine Repairs | 1255909 | 3 MAWDELEY HOUSE | 115583/1 | New Works Instruction | ACE Agreed | 36/1576 |  | 35 days |  |  | Cybix AI | 09/07/2026 10:54 |  | Pre-completion Items To Complete |  |  |  | 24/06 - Unable to get hold of tenant, voicemail left - CL | RESPONSIVE | 192.89
2026-05-21 10:31:00 | Jeffway- as per Jeff N-Overhaul PVC windows leave in working order, apply waterproofing seal to spar on rear elevation to a height 1200mm above ground on kitchen wall and rear gable end | 2026-07-06 12:15:00 | 2026-07-06 |  | Routine Repairs | 1245370 | 19 ELMDALE ROAD | 98050/2 | Works Started | ACE Agreed | 36/1446 | 2026-06-30 12:30:00 | 35 days |  |  | Shannon Slade | 09/07/2026 10:31 | No | Pre-completion Items To Complete |  |  |  | 03/07 - Unable to get hold of tenant, voicemail left - CL 29/06 - Appointment confirmed with tenant - CL | WIP | 172.89
2026-05-21 10:27:00 | Jeffway-as per Jeff N-: Cut out cracks in plaster work at positions thus ground floor kitchen / front room / 1st floor landing / top floor side wall , tenant to verify positions | 2026-06-29 08:00:00 | 2026-06-29 | 2026-06-29 12:00:00 | Routine Repairs | 1267089 | 17 Warden Road | 74150/2 | Works Completed | ACE Agreed | 36/1445 | 2026-06-29 08:00:00 | 35 days |  |  | Shannon Slade | 09/07/2026 10:27 | Yes | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPi requested - CL 30/06 - Completion form needs to be assessed DW to add a VO - CL 03/06 - ASBESTOS REPORT RECEVIED AND UPLOADED. 29/05 - Asbestos report requested - CL | Complete | 262.0
2026-05-21 10:24:00 | Jeffway- as per Jeff N-With remove disconnect sink , remove water damage base unit , refix new unit and door. Cut and fix new plinth to suit kitchen. Apply anti condensation paint to ceiling and all walls. | 2026-07-03 08:00:00 | 2026-07-03 |  | Routine Repairs | 1309451 | 15 MURFORD WALK | 74219/2 | Works Started | ACE Agreed | 36/1444 | 2026-06-30 08:00:00 | 35 days |  |  | Shannon Slade | 09/07/2026 10:24 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment confirmed with tenant - CL 29/06 - Appointment confirmed with tenant - CL 02/06 - Asbestos report received and uploaded - CL 01/06 - Asbestos report requested - CL | WIP | 680.97
2026-05-21 10:14:00 | Rebuild retaining wall in Rear Garden |  |  |  | Routine Repairs | 1272226 | 701 Bishport Avenue | 109370/1 | New Works Instruction | Awaiting Cost Estimate | 36/1490 |  | 35 days |  |  | Cybix AI | 09/07/2026 10:14 |  | Pre-completion Items To Complete |  |  |  | 24/06 - Awaiting approval of quote request - CL 16/06 - Quote received and sent to CH - CL 05/06 - PO sent to BS - CL | Awaiting appointment date | 616.2
2026-05-21 10:14:00 | BCC need to issue letter to private tenant, please place on hold until instructed |  |  |  | Routine Repairs | 1306805 | 24 Mellent Avenue, Hartcliffe | 115189/1 | New Works Instruction | Awaiting Cost Estimate | 36/1571 |  | 35 days |  |  | Cybix AI | 09/07/2026 10:14 |  | Suspended: Awaiting Client Action/Response |  |  |  |  | RESPONSIVE | 816.64
2026-05-20 15:15:00 | JEFF WAY A? PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 10/06/26. 10 DAY PERIOD ENDS 24/06/26. | 2026-06-18 12:15:00 | 2026-06-18 | 2026-06-18 14:53:00 | Routine Repairs | 1255658 | 28 Martock Road, Bedminster | 103681/3 | Works Completed | ACE Agreed | 36/1548 | 2026-06-18 12:15:00 | 35 days |  |  | Lainie Lavin | 08/07/2026 15:15 | Yes | Pre-completion Items To Complete |  | No |  |  | Complete | 529.75
2026-05-20 13:46:00 | Complaint Work - Please see e-mail and report | 2026-06-08 12:00:00 | 2026-07-16 |  | Disrepair | 1103920 | 24 ARMADA HOUSE | 103696/1 | New Works Instruction | ACE Agreed | 36/1453 |  | 35 days |  |  | Shannon Slade | 08/07/2026 13:46 |  | Pre-completion Items To Complete |  |  |  | 15/06 - D&M COMPLETED. PLASTERING WORKS BOOKED FOR 16TH JULY, REMANING WORKS BOOEKD FOR 22ND AND 23RD JULY. 05/06 - MOULD WASH BOOKED FOR 8TH JUNE. | Appointment booked | 4193.84
2026-05-19 11:03:00 | AS PER NICHOLAS CORY JW TO NEW X3 RADS, NEW TRVS, BATHROOM FLR CAP&COVE, VENT COVER IN BACK BEDROOM , X3 NEW INTERNAL DOOR, hack of pla right side of living room chimney, wallpaper reglue front bedroom rightside | 2026-07-13 08:00:00 | 2026-07-13 |  | Routine Repairs | 1244902 | 95 Coronation Road | 102496/2 | Works Started | ACE Agreed | 36/1437 | 2026-06-26 08:00:00 | 35 days |  |  | Shannon Slade | 07/07/2026 11:03 | No | Pre-completion Items To Complete |  |  |  | 29/06 - Follow on appointment to compete the plumbing - CL 25/06 - Unable to get hold of the tenant, voicemail and text reminder sent - CL 02/06 - PO sent to FF - CL | WIP | 1888.35
2026-05-18 14:29:00 | Jeffway - As per Ian O - PLASTERING AND PB / PLUMBING / EXTRACTION IN KITCHEN AND BATHROOM IN GLAZING | 2026-07-17 15:15:00 | 2026-07-17 |  | Routine Repairs | 1281272 | 7 HERSEY GARDENS | 101990/1 | New Works Instruction | ACE Agreed | 36/1443 |  | 35 days |  |  | Christopher Barclay | 06/07/2026 14:29 |  | Pre-completion Items To Complete |  |  |  | 24/05 asbestos report from 2012 new on to be requested | Appointment booked | 1208.8
2026-05-18 13:05:00 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled lottie.smart@bristol.gov.uk | 2026-06-24 12:45:00 | 2026-07-13 |  | Disrepair | 1109451 | 106a Cotham Brow | 102216/1 | Works Started | ACE Agreed | 36/1452 | 2026-06-24 12:45:00 | 35 days |  |  | Shannon Slade | 06/07/2026 13:05 | No | Pre-completion Items To Complete |  |  |  | 26/06- SOUTH WEST VOIDS COMPLETING WORKS W/C 13TH JULY. 15/06 - WORKS ISSUED TO SUBCONTRACTOR, WAITING FOR DATES. WORKS ISSUED TO SUBCONTRACTOR - DARREN MEETING THEM WEDNESDAY@ 10AM | WIP | 5800.89
2026-05-18 12:05:02 | Various works to kitchen, bathroom and hallway following complaint | 2026-06-29 08:00:00 | 2026-07-01 |  | Routine Repairs | 1215743 | 36 Cossington Road | 102245/1 | Works Started | ACE Agreed | 36/1402 | 2026-06-11 07:00:00 | 35 days |  |  | Cybix AI | 06/07/2026 12:05 | No | Pre-completion Items To Complete |  |  |  | 30/06 - Bathroom painted living room stained blocked. Rebook a plumber to inspect soil pipe for any leaks, And plasterer to return and replaster - CL 15/06 - Kitchen booked to be replaced on 23/06, confirmed with tenant - CL 03/06 - FF to attend 18/06 and 19/06 - CL 02/06- Some works completed under order 76796/1 29/05 - Fans booked for the 04/06, follow on appointments for 10/06 and 11/06. PO sent to FF and WSG - CL | Appointment booked | 2743.11
2026-05-18 12:05:00 | RENEW ALL PLINTHS AS REQUIRED, APPROX 3 LIN M AND RENEW KIT FLOORING APPROX 4M2 WITH BCC VINYL TILES. 1 X WALL TILE RHS OF COOKER TO MATCH / RENEW ALSO, CREAM. | 2026-06-26 12:00:00 | 2026-06-26 | 2026-06-26 18:15:00 | Routine Repairs | 1279330 | 17 FOUR ACRES CLOSE | 102227/1 | Works Completed | ACE Agreed | 36/1403 | 2026-06-26 17:00:00 | 35 days |  |  | Cybix AI | 06/07/2026 12:05 | Yes | Post-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI requested- CL 25/06 - Appointment confirmed with tenant - CL 16/06 - Email sent to FF for an update - CL 03/06 - PO sent to FF - CL | WIP | 226.41
2026-05-18 11:10:00 | JW - AS PER ROB D- RENEW POORLY CUT TILES TO LHS AND RHS OF NEW BOILER. REGROUT/SILICON THE WORKTOP/TILE JOINT BEHIND SINK. RENEW 2 X SHELVES TO SINK UNIT , RENEW PLINTH AND RAISE DOOR HINGE TO SAME UNIT, RENEW EXTRACTOR FAN ALSO | 2026-06-16 12:00:00 | 2026-06-16 | 2026-06-16 07:49:00 | Routine Repairs | 1297683 | 4 Crosscombe Drive | 102266/1 | Works Completed | ACE Agreed | 36/1498 | 2026-06-16 10:00:00 | 35 days |  |  | Carlene Lynette Lynch | 06/07/2026 11:10 | Yes | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI requested - CL | Complete | 714.26
2026-05-18 11:05:06 | 1 X DIAGONAL CRACK TO FRONT BEDROOM TO FILL AND PATCH PAINT. WILL MONITOR FOR FURTHER MOVEMENT GOING FORWARD | 2026-07-20 14:00:00 | 2026-07-20 |  | Routine Repairs | 1296146 | 1 Chelvey Close | 102260/1 | Works Started | ACE Agreed | 36/1409 | 2026-06-22 14:30:00 | 35 days |  |  | Cybix AI | 06/07/2026 11:05 | No | Pre-completion Items To Complete |  |  |  | 23/06 - NA access on 22/06 - CL | Appointment booked | 69.62
2026-05-18 | JEFF WAY - MAIN WORKS. VOID WORKS. KEYSAFE: 9163. SWES AREA |  |  |  | Routine Repairs | 123123 | fakestreet | 64293/4 | New Works Instruction | Awaiting Cost Estimate | 36/1396 |  | 35 days |  |  | Cybix AI | 06/07/2026 00:00 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting asbestos report | 20.32
2026-05-15 14:15:00 | JEFF WAY-AS PER ROB D:RENEWAL OF BATH PANEL WITH ACRYLIC, WHILE PANEL OFF FILL RODENT HOLES UNDER BATH & PHOTOGRAPH. ALSO FILL HOLES AROUND BATHROOM PIPEWORK NEXT TO WC & SMALL HOLES TO BEDROOM CORNER & COMMUNAL LOBBY | 2026-06-12 10:00:00 | 2026-06-12 | 2026-06-12 07:51:00 | Routine Repairs | 1296384 | 2 Chestnut House | 72741/2 | Works Completed | ACE Agreed | 36/1442 | 2026-06-12 10:00:00 | 35 days |  |  | Christopher Barclay | 03/07/2026 14:15 | Yes | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI request sent - CL | Complete | 120.62
2026-05-15 13:48:00 | HEATER:RESITE AND RECONNECT - Heater:Isolate supply, disconnect and resite night storage heater, including dismantle and reassemble, move to new site, secure to wall and make all connections, reconnect electricity supply, electrical tests and leave in working order and remove waste and debris. | 2026-06-30 13:15:00 | 2026-07-07 |  | Routine Repairs | 1282071 | 19 HILLS BARTON | 71393/2 | Works Started | ACE Agreed | 36/1439 | 2026-06-30 13:15:00 | 35 days |  |  | Christopher Barclay | 03/07/2026 13:48 | No | Pre-completion Items To Complete |  |  |  | 29/06 - Appointment confirmed with tenant - CL | Appointment booked | 327.33
2026-05-15 | Jeff Way - as per John Oyeniyi: Renew handles to 2nos kitchen unit; Renew handle to 1no door; Renew taps to Bath and Sink and renew water cistern. | 2026-06-30 12:00:00 | 2026-06-30 | 2026-06-30 12:43:00 | Routine Repairs | 1301877 | 44 GREENDITCH AVENUE | 71422/2 | Works Completed | ACE Agreed | 36/1440 | 2026-06-30 12:00:00 | 35 days |  |  | Christopher Barclay | 03/07/2026 00:00 | Yes | Pre-completion Items To Complete |  | No |  | 29/06 - Appointment confirmed with tenant - CL | Complete | 437.72
2026-05-15 | JEFF WAY-AS PER ROB D: BEDROOM CEILING/ WALL/ WINDOW REVEAL. OLD ROOF LEAK NOW FIXED. PATCH REPAIR ARTEX CEILING & STAINBLOCK/ PAINT AS REQUIRED OTHER PATCHES TO WALL/ WINDOW. COLOUR MATCH ALSO |  |  |  | Routine Repairs | 1296964 | 60 BISHPORT AVENUE | 72099/2 | New Works Instruction | Awaiting Cost Estimate | 36/1441 |  | 35 days |  |  | Christopher Barclay | 03/07/2026 00:00 |  | Client Works Description Received |  |  |  |  | Awaiting asbestos report | 0.0
2026-05-14 12:58:00 | Complaint works- please see email and report- Bedroom 1 Stain-block affected section of ceiling Repaint ceiling (small section) Bedroom 2 Decorate ceiling Hack off damaged sections of wall and make good Sink sections of wall as required Room size: 2.4m x 2.6m, height 2.4m Approx. 5m² of wall repairs and making good Bedroom 3 Paint ceiling Fill holes to walls and make good to allow the tenant to decorate Possible hacking off and skimming of walls (subject to inspection) Bathroom Hack off wall tiles and reinstate from bath to ceiling, including reveals Install stub screen Clean out fan Renew bathroom flooring Kitchen Boxing damaged following leak - renew boxing Overhaul fan Toilet Room Stain-block ceiling and repaint Overhaul fan Landing Repair loose handrail Hack off damaged wall at top of stairs, renew and decorate Fix stairs to wall and renew kite tread Paint section at bottom of stairs Address cracking to ceiling and repaint Living Room - Make good the walls following removal of the dado rail Hack off damaged sections of wall as required Repair and make good all affected areas Complete necessary decorations to finish the room to a good standard Renew wall vent. | 2026-05-26 08:00:00 | 2026-06-17 |  | Disrepair | 1083869 | 24 DORCHESTER ROAD | 100636/1 | New Works Instruction | ACE Agreed | 36/1451 |  | 35 days |  |  | Shannon Slade | 02/07/2026 12:58 |  | Pre-completion Items To Complete |  |  |  | 04/06 - REMAINING WORKS BOOKED FOR 12TH JUNE, 16TH AND 17TH JUNE | WIP | 3273.36
2026-05-14 12:53:00 | BEDR1 , BEDR 2 BATHR EXTERNAL HALLWAY KITCH | 2026-06-30 09:45:00 |  |  | Disrepair | 1162421 | 16 WHITSON HOUSE | 101095/1 | Works Started | ACE Agreed | 36/1450 | 2026-06-30 09:45:00 | 35 days |  |  | Shannon Slade | 02/07/2026 12:53 | No | Fully Complete |  |  |  | 1/7 - Awaiting response from FF regarding flooring works. 25/05 - WORKS BOOKED FOR 3RD AND 4TH OF JUNE. | WIP | 1553.39
2026-05-14 11:16:00 | Jeff Way - as per Jeff Neck: Fix timber battens across ceilings in 1st floor rear bedroom/ front bedroom and landing ceilings... ¦ 72PT413307 x21 CEILING:FIX NE 12.5MM PLASTERBOARD 3MM SKIM COAT - Ceiling:Supply; 72JR395103 x1 CEILING HATCH:RENEW BLOCKBOARD ACCESS HATCH - Ceiling Hatch:Renew; 72PA442001 x21 WALLS AND CEILINGS:APPLY MIST 2 COATS EMULSION - Walls and Ceilin - NO ASBESTOS REPORT WITH ORDER | 2026-07-13 08:00:00 | 2026-07-06 |  | Routine Repairs | 1306601 | 47 MAYNARD ROAD | 100909/1 | New Works Instruction | ACE Agreed | 36/1434 |  | 35 days |  |  | Christopher Barclay | 02/07/2026 11:16 |  | Pre-completion Items To Complete |  |  |  | 03/07 - Email sent to RD and JN to send over a varied order for the additional work requested. Appointment confirmed with tenant - CL 04/06 - Confirmation not a CT from CM - CL 02/06 - Email sent to JN,CM and EH regarding CT - CL | Appointment booked | 1086.69
2026-05-14 10:48:00 | JEFF WAY-as per Jeff N: Hack off damage plaster work to window surround in ground floor bathroom & reskim window wall & side return. Apply anti condensation paint to ceiling & walls. ¦ 72PT411107 x4 WALL:RENEW APPLY 3MM SKIM COAT PLASTER - Wall:Renew defective or ; 72PA442203 x9 CEILINGS:APPLY 2 COATS OF ANTI CONDENSATION PAINT - Ceilings:Wash; 72PL630573 x1 WC CISTERN/PAN:OVERHAUL ANY TYPE - WC Cistern/Pan:Overhaul any ty - NO ASBESTOS REPORT WITH ORDER | 2026-07-02 12:00:00 | 2026-07-02 |  | Routine Repairs | 1295621 | 23 BRISCOES AVENUE | 100877/1 | New Works Instruction | ACE Agreed | 36/1433 |  | 35 days |  |  | Christopher Barclay | 02/07/2026 10:48 |  | Pre-completion Items To Complete |  |  |  |  | Appointment booked | 253.03
2026-05-14 09:44:00 | JW - As per Jeff Neck - Bellcast repairs, remove existing PVC moulding across window head/opening, new silicone seal - Copy of WO information emailed to JW 14.05.2026 ¦ 72PT423007 x5 RENDER REPAIRS:RENEW BELLCAST FEATURE - Render Repairs:Renew bell; 72JR318179 x5 WINDOW:REPOINT SILICONE TO PVCU FRAME - Window:Rake out, prepare ; 72JR318181 x5 WINDOW:RENEW QUADRANT FILLET TO PVCU - Window:Renew cellular PVCu; 72PT421024 x2 WALL:APPLY ROUGHCAST RENDER DUB OUT - Wall:Apply 12mm cement and - NO ASBESTOS REPORT WITH ORDER |  | 2026-06-17 | 2026-06-17 08:27:00 | Routine Repairs | 1285263 | 4 MOW BARTON | 100812/1 | Works Completed | ACE Agreed | 36/1432 |  | 35 days |  |  | Christopher Barclay | 02/07/2026 09:44 |  | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI request sent - CL | Complete | 271.26
2026-05-13 15:32:00 | Jeffway-As per John O-Reglaze 1 window ¦ 72GL551005 x1 DOUBLE; 72EL842001 x1 DOMESTIC - NO ASBESTOS REPORT WITH ORDER | 2026-06-08 08:00:00 | 2026-06-05 | 2026-06-05 13:04:00 | Routine Repairs | 1243023 | 13 Chalcroft House | 69352/2 | Works Completed |  | 36/1419 |  | 35 days |  |  | Christopher Barclay | 01/07/2026 15:32 |  | Pre-completion Items To Complete | 2026-06-30 | Yes |  | 30/06 - KPI request sent. Email sent to WSG for completion photos - CL 15/06 - Unable to contact tenant, voicemail left - CL 03/05 - VO approved - CL 28/05 - VO sent to JO for approval. Email sent to WSG - CL | Complete | 236.87
2026-05-13 14:17:00 | DA - Make good external render around any pipe, brackets, other projections and the like, fill holes, make good render. Old kitchen waste hole ¦ 72PT423009 x1 DWELLING REPAIR:MAKE GOOD AROUND PIPE ETC - Dwelling:Make good an - NO ASBESTOS REPORT WITH ORDER | 2026-06-23 09:00:00 | 2026-06-23 | 2026-06-23 08:00:00 | Routine Repairs | 1309235 | 77 Murford Avenue, Hartcliffe | 100551/1 | Works Completed | ACE Agreed | 36/1430 | 2026-06-23 09:00:00 | 35 days |  |  | Christopher Barclay | 01/07/2026 14:17 | Yes | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI request sent - CL | Complete | 50.0
2026-05-13 14:17:00 | DA - Skirting:Renew any size softwood plain, moulded or chamfered skirting plugged to brickwork, including all ends and angles and prepare for redecoration, and remove waste and debris. ¦ 72JR381001 x1 SKIRTING:RENEW - NO ASBESTOS REPORT WITH ORDER | 2026-07-14 14:00:00 | 2026-07-14 | 2026-06-23 08:02:00 | Routine Repairs | 1309235 | 77 Murford Avenue, Hartcliffe | 100563/1 | Works Completed | ACE Agreed | 36/1431 | 2026-06-23 08:00:00 | 35 days |  |  | Christopher Barclay | 01/07/2026 14:17 | Yes | Pre-completion Items To Complete |  | Yes |  |  | Complete | 27.19
2026-05-13 12:53:00 | Jeffway- as per John O-Renew silicone to Vinyl sheet flooring, bath and door frame in bathroom; Fix PVC skirting to bath panel ¦ 72FL433001 x20 SEALANT; 72JR318201 x1 DOOR; 72PL631501 x1 SEALANT:RENEW; 72FL432703 x3 SKIRTING:RENEW - NO ASBESTOS REPORT WITH ORDER | 2026-07-23 08:00:00 | 2026-07-23 |  | Routine Repairs | 1312545 | 61 Rowan House | 90073/2 | Works Started | ACE Agreed | 36/1426 | 2026-06-24 12:15:00 | 35 days |  |  | Christopher Barclay | 01/07/2026 12:53 | No | Pre-completion Items To Complete |  |  |  | 25/06 - NA 24/06, appointment rebooked - CL 17/06 - Appointment rescheduled due to op unavailable - CL | Appointment booked | 145.46
2026-05-13 12:50:00 | Direpair Claims works required |  |  |  | Disrepair | 1111780 | 67 GROSVENOR ROAD | 100019/1 | New Works Instruction | ACE Agreed | 36/1449 |  | 35 days |  |  | Shannon Slade | 01/07/2026 12:50 |  | Suspended: Awaiting asbestos info | [5 empty] | 1699.73
2026-05-13 12:47:00 | Jeffway-as per John O-Paving patch repair by entrance; Clear rubbles from Collapsed blockwork fence in the Rear garden and replace with fence panels ¦ 72GR011001 x5 PAVING:TEMPORARY; 72BL101111 x10 WALL:DEMOLISH; 72FE017304 x10 FENCING:ERECT; 72BL102719 x2 HOLE:MAKE - NO ASBESTOS REPORT WITH ORDER |  |  |  | Routine Repairs | 1292326 | 4 Bellamy Avenue | 84568/2 | New Works Instruction | ACE Agreed | 36/1424 |  | 35 days |  |  | Christopher Barclay | 01/07/2026 12:47 |  | Pre-completion Items To Complete |  |  |  | 24/06 - Awaiting quote to be reviewed by CH - CL 08/06 - Quote received from BS - CL 04/06 - Email sent to BS chasing quote - CL 28/05 - Email sent to BS - CL | Awaiting appointment date | 1505.7
2026-05-13 12:33:00 | Direpair Claims works required | 2026-06-09 12:00:00 | 2026-07-06 |  | Disrepair | 1227947 | 148 NEWQUAY ROAD | 100263/1 | New Works Instruction | ACE Agreed | 36/1448 |  | 35 days |  |  | Shannon Slade | 01/07/2026 12:33 |  | Pre-completion Items To Complete |  |  |  | 03/07 - Appointment confirmed with tenant - CL | Appointment booked | 3103.97
2026-05-13 11:20:00 | Jeffway- as per Dave Palmer-BATHROOM WORKS TO INCLUDE HACK OFF TILES, FITTING OF ACRYLIC LINING BOARD TO BATH SURROUND. STAIN BLOCK AND ANTI CONDENSATION PAINT. ¦ 72WF431003 x1 WALL; 72JR350017 x5 LINING; 72PA435121 x6 STAIN; 72PA442001 x9 WALLS; +5 more SORs - NO ASBESTOS REPORT WITH ORDER | 2026-07-14 08:00:00 | 2026-07-13 |  | Routine Repairs | 1293147 | 396 BISHPORT AVENUE | 54190/2 | New Works Instruction | ACE Agreed | 36/1412 |  | 35 days |  |  | Christopher Barclay | 01/07/2026 11:20 |  | Pre-completion Items To Complete |  |  |  | 09/06 - Appointments confirmed with tenant - CL | WIP | 1339.05
2026-05-13 06:59:00 | Scaffold for access to roof |  | 2026-07-03 |  | Routine Repairs | 1316478 | 2 Woodmead Gardens | 75475/1 | New Works Instruction |  | 36/1394 |  | 35 days |  |  | Shannon Slade | 01/07/2026 06:59 |  | Pre-works Items To Complete |  |  |  | 17/06 - PO sent to Ag Builders. Update provided from MRF and varied order received, uploaded and variations added - CL 16/06 - MRF to provide update on work required as confirmed by CM - CL 03/06 - Email sent to MF regarding scaffolding - CL Scaffold up for BCC roof inspection | Appointment booked | 6053.74
2026-05-12 11:37:00 | PD1 - Please carry out works as listed. |  |  |  | Disrepair | 1016600 | 68 HENACRE ROAD | 99847/1 | New Works Instruction | ACE Agreed | 36/1407 |  | 35 days |  |  | Shannon Slade | 30/06/2026 11:37 |  | Pre-completion Items To Complete |  |  |  | 02/07 make POW and send to BCC for start of august | Awaiting appointment date | 4118.8
2026-05-12 11:28:00 | Treat mould in bathroom - photo | 2026-05-26 12:00:00 |  | 2026-05-26 21:35:00 | Disrepair | 1151639 | 11 Lansdowne Court | 99794/1 | Works Completed | Invoiced | 36/1406 | 2026-05-26 12:00:00 | 35 days |  |  | Shannon Slade | 30/06/2026 11:28 | Yes | Fully Complete | 2026-06-12 |  |  | 19/05 - WORKS ISSUED TO DAMP AND MOULD. | Complete | 108.05
2026-05-12 10:59:00 | Jeff Way - as per John Oyeniyi: Redecorate Bathroom walls and ceiling; Mould wash bedroom ceiling. ¦ 72PT411107 x3 WALL:RENEW APPLY 3MM SKIM COAT PLASTER - Wall:Renew defective or ; 72PA442001 x2 WALLS AND CEILINGS:APPLY MIST 2 COATS EMULSION - Walls and Ceilin; 72WF431025 x4 WALL TILES:RAKE OUT AND REGROUT - Wall Tiles:Rake out and regrout; 72PA435121 x4 STAIN BLOCK:APPLY ONE COAT - Stain Block:Apply one coat of stain ; +2 more SORs - NO ASBESTOS REPORT WITH ORDER | 2026-07-16 08:00:00 | 2026-07-16 |  | Routine Repairs | 1280315 | 18 GATEHOUSE CLOSE | 68975/2 | Works Started | ACE Agreed | 36/1418 | 2026-06-26 08:00:00 | 35 days |  |  | Christopher Barclay | 30/06/2026 10:59 | No | Pre-completion Items To Complete |  |  |  | 25/06 - Unable to get hold of tenant voicemail left and text sent - CL 03/06 - Asbestos report received and uploaded. Asbestos report requested - CL | WIP | 375.57
2026-05-11 10:37:00 | Jeff Way - Crack repair to Bedroom wall and ceiling, and redecoration as per John Oyeniyi. | 2026-06-09 08:00:00 | 2026-06-09 | 2026-06-09 11:08:00 | Routine Repairs | 1289005 | 56 Sherrin Way, Withywood, | 70105/2 | Works Completed | ACE Agreed | 36/1393 | 2026-06-03 13:15:00 | 35 days |  |  | Lainie Lavin | 29/06/2026 10:37 | Yes | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL | Complete | 428.91
2026-05-08 16:50:00 | JEFF WAY-AS PER ROB D: RENEWAL OF ACRYLIC BATH PANEL, RUB DOWN, PREP & REGLOSS SKIRTING & RE ATTATCH TO BATH PANEL AFTER, SEAL ANY REQUIRED JOINTS TO FLOOR / SKIRTING AFTER | 2026-07-14 11:45:00 | 2026-07-14 |  | Routine Repairs | 4582858 | Flat 2, 1 Risdale Road, Ashton Vale | 64925/2 | New Works Instruction | ACE Agreed | 36/1389 |  | 35 days |  |  | Lainie Lavin | 26/06/2026 16:50 |  | Pre-works Items To Complete |  |  |  |  | Appointment booked | 95.49
2026-05-08 16:50:00 | Jeff Way - as per John Oyeniyi: Remove laminated floor in kitchen, remove bumps & latex, refix laminated floor. Repair & hairline cracks in bedroom ceiling Overhaul Living room | 2026-07-16 08:00:00 | 2026-07-16 |  | Routine Repairs | 1254177 | 18 Malago Road, Bedminster | 74158/2 | New Works Instruction | ACE Agreed | 36/1390 |  | 35 days |  |  | Lainie Lavin | 26/06/2026 16:50 |  | Pre-completion Items To Complete |  |  |  | 26/06 - Op attended on 25/06 but could not complete work as tenant has to go out to hospital. Appointment needs to be rebooked. Flooring being investigated by DW - CL 01/06 - Email sent to JO chasing decision - CL 29/05 - Email sent to JO regarding laminated flooring - CL | Appointment booked | 365.92
2026-05-08 16:10:00 | Jeff Way - as per John Oyeniyi: Hack off bad rendering and renew to Toilet wall (external) and redecorate. | 2026-07-09 08:00:00 | 2026-07-09 |  | Routine Repairs | 1282797 | 234 Ilchester Crescent, Bedminster Down | 85301/2 | New Works Instruction | ACE Agreed | 36/1388 |  | 35 days |  |  | Lainie Lavin | 26/06/2026 16:10 |  | Pre-completion Items To Complete |  |  |  | 29/06 - Appointment confirmed with tenant - CL 15/06 - Appointment rescheduled due to op held up on first job - CL 04/06 - Asbestos report received and uploaded - CL | Appointment booked | 261.51
2026-05-08 15:20:00 | Jeffway-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 03/06/2026. 10 DAY PERIOD ENDS 17/06/26. Booked in with Dan A 3/06/26 8-12pm via VM | 2026-05-29 14:30:00 |  | 2026-05-29 09:20:00 | Routine Repairs | 1210931 | 56 Barnstaple Road, Knowle | 98699/3 | Works Completed |  | 36/1387 | 2026-05-29 12:12:00 | 35 days |  |  | Lainie Lavin | 26/06/2026 15:20 | Yes | Pre-completion Items To Complete | 2026-06-04 | Yes |  | 04/06 - KPI requested and VO sent - CL 01/06 - EICR completed on 29/05, awaiting cert from MF - CL | Complete | 188.59
2026-05-08 14:50:00 | Daniel Allen - apply treatment to window surrounds in front bedrooms 1 and 2 | 2026-06-12 08:00:00 | 2026-06-12 | 2026-06-12 07:59:00 | Routine Repairs | 1309235 | 77 Murford Avenue, Hartcliffe | 98689/1 | Works Completed | ACE Agreed | 36/1386 |  | 35 days |  |  | Lainie Lavin | 26/06/2026 14:50 |  | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI request sent - CL | Complete | 86.44
2026-05-08 14:10:00 | Daniel Allen - Please renew bath and fittings | 2026-06-18 08:00:00 | 2026-06-18 | 2026-06-18 13:36:00 | Routine Repairs | 1235149 | 41 Torrington Avenue, Knowle | 98660/1 | Works Completed | ACE Agreed | 36/1384 |  | 35 days |  |  | Lainie Lavin | 26/06/2026 14:10 |  | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI requested - CL 02/06 - Asbestos report received and uploaded - CL 29/05 - Asbestos report requested - CL | Complete | 631.96
2026-05-08 13:33:00 | Complaint Job - Rodents within property - Work with Orbis to remove waste below bathroom flooring - Various works see other comments - Brick up Old vent hole - Replace Base unit and wall unit - Remove Toilet pan and Floorboards for orbis access to clear rodents waste - Overhaul Extractor in bathroom - Refix Hand rail on stairs - Window replacement Glazing only 2no windows - | 2026-05-14 08:00:00 |  |  | Routine Repairs | 1215743 | 36 Cossington Road | 76796/1 | Works Started |  | 36/1378 | 2026-05-14 08:00:00 | 35 days |  |  | Carlene Lynette Lynch | 26/06/2026 13:33 | No | Suspended: WSG to be booked |  |  |  | 30/06 - PO sent to WSG, awaiting appointent date - CL 24/06 - Email sent to WSG for update - CL 15/06 - Quote request sent to WSG - CL 08/06 - VO sent to JN and EH - CL 29/05 - VO sent to EH and CH - CL 26/05/update left to do *Downstairs landing ceiling to be Reboarded and skimed after leak has damaged area. /Shower screen to be fitted (customer has supplied and is onsite). Please note shower screen works are additional works agreed By BBC Jeff the surveyor. /Bath panel and toliet system to be silicone sealed once Flooring has been applied. / Mould wash to bath ceiling to be applied * Paint hallway ceiling repair and 1M2 in the living room where the leak has come through. 18/5 - awaiting date from BB for clearence. | Next Appointment Needed | 1603.36
2026-05-08 12:30:00 | JEFF WAY - as per Jeff Neck: URGENT - Dismantle Scaffolding on rear elevation at the above address and re erect across front elevetion giving access to complete eave level with hand railing up to chimney | 2026-06-26 12:00:00 |  | 2026-06-09 08:24:00 | Routine Repairs | 1244968 | 223 Coronation Road, Southville | 98547/1 | Works Completed | ACE Agreed | 36/1381 |  | 35 days |  |  | Lainie Lavin | 26/06/2026 12:30 |  | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI request sent - CL 16/06/26- Marked as completed due to new order raised by BCC 03/06 - Email sent to JN and EH informing scaffolding has been moved - CL | Complete | 943.81
2026-05-08 09:50:00 | JEFF WAY - As per Sean P : Skim around pipe in bedroom LHS by door. Redecorate whole celling after leak from flat. - TENANT REFUSED WORKS |  |  |  | Routine Repairs | 1303486 | 14 Hayleigh House, Silcox Road | 7254/1 | New Works Instruction | ACE Agreed | 36/1379 |  | 35 days |  |  | Lainie Lavin | 26/06/2026 09:50 |  | Suspended: Awaiting Client Action/Response |  |  |  | 03/06 - EMAIL ISSUED TO SURVEYOR AS TENANT REFUSED WORKS. WAITING FOR CONFIRMATION | Held BCC | 50.0
2026-05-08 08:26:00 | Complaint works- Clear guttering around walkway. inspect loft and do what's necessary. over haul all fans. refit kitche unit doors. Replace bath panel | 2026-06-12 13:15:00 | 2026-07-13 |  | Disrepair | 1162410 | 15 WHITSON HOUSE | 98769/1 | New Works Instruction | ACE Agreed | 36/1383 |  | 35 days |  |  | Shannon Slade | 26/06/2026 08:26 |  | Pre-completion Items To Complete |  |  |  | 16/06 - PART WORKS COMPLETED. ELECTRICAL WORKS COMPLETED. REMAINING WORKS BOOKED FOR 13TH JULY. 20/05 - WORKS BOOKED FOR 12TH JUNE, JWE ISSUED FAN WORKS. LOFT INSULATION GIVEN TO CONTRACTOR WAITING FOR DATE. | WIP | 388.31
2026-05-08 08:13:00 | Complaint works- bathroom repair leak, replace broken window lock. stain block patch in kitchen replace cracked glass. | 2026-05-19 17:00:00 |  | 2026-05-19 15:16:00 | Disrepair | 1267830 | 82 WARING HOUSE | 98642/1 | Works Completed | ACE Agreed | 36/1382 | 2026-05-19 17:00:00 | 35 days |  |  | Shannon Slade | 26/06/2026 08:13 | Yes | Pre-completion Items To Complete |  | No |  | COMPLETED - WAITING FOR PHOTOS OF WINDOW HANDLE TO SIGN OFF | Complete | 366.68
2026-05-08 08:10:00 | Complaint Work - Please see e-mail and report | 2026-06-17 09:00:00 | 2026-06-17 |  | Disrepair | 1250733 | 28A KNOWLE ROAD | 98472/1 | New Works Instruction | ACE Agreed | 36/1380 |  | 35 days |  |  | Shannon Slade | 26/06/2026 08:10 |  | Pre-works Items To Complete |  |  |  | 02/07 - awaiting azzy report from bcc 01/07/26 -Tenant didn't want mould wash carried out due to windows being replaced. | Held BCC | 496.7
2026-05-07 13:07:00 | Touch up chip in bath. (tnt wants to keep the bath) | 2026-06-09 08:00:00 |  | 2026-06-09 14:54:00 | Disrepair | 1151731 | 21 Lansdowne Court | 97924/1 | Works Completed | Invoiced | 36/1364 |  | 35 days |  |  | Shannon Slade | 25/06/2026 13:07 |  | Suspended: Awaiting asbestos info | 2026-06-15 |  |  |  | Complete | 53.03
2026-05-07 12:58:00 | Specilist Projects - Demolish and Rebuild Retaining Wall to Rear Garden |  |  | 2026-06-15 12:18:00 | Disrepair | 1177566 | 43 Harewood Road | 92280/1 | Works Completed |  | 36/1363 |  | 35 days |  |  | Shannon Slade | 25/06/2026 12:58 |  | Pre-completion Items To Complete |  | Yes |  | WIP - DARREN TO CARRY OUT SITE VISIT WITH ED | Complete | 7198.47
2026-05-07 12:56:00 | PD1 - Please carry out works as listed. Any questions, the surveyor is James Bailey | 2026-06-15 12:00:00 | 2026-06-23 | 2026-06-23 15:42:00 | Disrepair | 1245096 | 37 COTSWOLD ROAD | 97885/1 | Works Completed | ACE Agreed | 36/1362 |  | 35 days |  |  | Shannon Slade | 25/06/2026 12:56 |  | Pre-completion Items To Complete |  | Yes |  | 17/06 - PART WORKS COMPLETE, PAINTING BOOKED FOR 23RD JUNE. | Complete | 187.55
2026-05-07 12:40:00 | JEFF WAY - AS PER ROB D: RENEWAL OF HAND BASIN/ SPLASHBACK / PEDESTAL, FLOORBOARDS AS REQUIRED, BATH PANEL WITH ACRYLIC AND THEN RENEW FLOORING IN FULL TO BATHROOM | 2026-06-26 08:00:00 | 2026-06-30 |  | Routine Repairs | 1273376 | 5 Brunel Road, Bedminster Down | 96603/2 | Works Started | ACE Agreed | 36/1377 | 2026-06-26 08:00:00 | 35 days |  |  | Lainie Lavin | 25/06/2026 12:40 | No | Pre-completion Items To Complete |  |  |  | 30/06 - Email received from FF as they have been unable to contact tenant and left various message. I have been unable to contact tenant voicemail and text sent - CL 29/06 - Email sent to FF informing them we have completed work - CL 25/06 - Unable to get hold of tenant, voicemail and text message sent - CL 29/05 - PO sent to FF - CL | Manager review needed | 576.82
2026-05-07 11:20:00 | JJEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? DANIEL ALLEN ATTENDING 21/05/26. 10 DAY PERIOD ENDS 05/06/26. | 2026-06-04 08:00:00 | 2026-06-04 | 2026-06-04 12:35:00 | Routine Repairs | 1051883 | 4 Edington Grove, Henbury, | 97921/3 | Works Completed | Invoiced | 36/1376 | 2026-06-04 08:00:00 | 35 days |  |  | Lainie Lavin | 25/06/2026 11:20 | Yes | Pre-completion Items To Complete | 2026-06-12 | Yes |  | 18/06 - KPI received and uploaded - CL 12/06 - KPI request sent - CL | Complete | 143.59
2026-05-07 10:40:00 | Jeff Way - as per John Oyeniyi: Patch Paving repairs |  |  |  | Routine Repairs | 1306816 | 25 Mellent Avenue, Hartcliffe | 97911/1 | New Works Instruction | ACE Agreed | 36/1373 |  | 35 days |  |  | Lainie Lavin | 25/06/2026 10:40 |  | Pre-completion Items To Complete |  |  |  | 24/06 - Awaiting appointment date from AG Builders - CL 16/06 - PO sent to AG Builders - CL | Awaiting appointment date | 573.2
2026-05-07 10:40:00 | Jeff Way - Crack repair on external render on front elevation and mould wash bedroom walls as per John Oyeniyi. | 2026-06-05 13:15:00 | 2026-06-26 | 2026-06-26 13:39:00 | Routine Repairs | 1285990 | 138 Newland Road, Withywood | 96904/2 | Works Completed | ACE Agreed | 36/1374 | 2026-06-05 13:00:00 | 35 days |  |  | Lainie Lavin | 25/06/2026 10:40 | No | Pre-completion Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI requested - CL 25/06 - Appointment confirmed with tenant - CL | Complete | 354.5
2026-05-07 10:40:00 | Jeff Way - as per John Oyeniyi: Fit extractor fan on Bathroom window, Fill hairline crack in entrance hallway & redecorate entrance hallway (wall & ceiling); Resilicone door (internal face) Booked in with John Oyeniyi 27/04/26 8-12pm via text | 2026-07-14 08:00:00 | 2026-07-14 |  | Routine Repairs | 1279669 | 12 Gatehouse Avenue | 59752/2 | New Works Instruction | ACE Agreed | 36/1375 |  | 35 days |  |  | Lainie Lavin | 25/06/2026 10:40 |  | Pre-completion Items To Complete |  |  |  | 02/07 - CH to review door and contact BCC. Tenant refused work until issue resolved, see smart form - CL 30/06 - Appointment confirmed with tenant - CL | Manager review needed | 551.28
2026-05-06 11:30:00 | Jeff Way - as per John Oyeniyi: Patch repair to tarmac on accessible ramp. John Oyeniyi booked to attend 30/04/26. | 2026-06-25 11:00:00 | 2026-06-25 | 2026-06-25 10:54:00 | Routine Repairs | 4586952 | Greenway Bush Lane Site, Greenway Bush Lane | 87948/2 | Works Completed | ACE Agreed | 36/1371 | 2026-06-12 13:00:00 | 35 days |  |  | Lainie Lavin | 24/06/2026 11:30 | No | Pre-completion Items To Complete |  | No |  | 30/06 - Awaiting for completion photos from operative - CL 29/05 - Site report requested from JO - CL | Complete | 374.34
2026-05-06 11:30:00 | Jeff Way - as per John Oyeniyi: Hole on plasterboard wall to be blocked in communal laundry. |  |  |  | Routine Repairs | 1845325 | 1-64 Chestnut House, Bishport Avenue, Hartcliffe | 82255/2 | Works Cancelled | Works Cancelled | 36/1372 |  | 35 days | 3: Omitted from Contract | 2026-06-08 15:34:08 | Lainie Lavin | 24/06/2026 11:30 |  | Works Cancelled |  |  |  | order cancelled EH 08/06 | Cancelled | 67.61
2026-05-06 10:30:00 | JEFF WAY - AS PER JEFF NECK: SCAFFOLD TO FRONT ELAVATION |  | 2026-06-04 |  | Routine Repairs | 1261207 | 27 Sidmouth Road, Bedminster | 97230/1 | New Works Instruction | ACE Agreed | 36/1370 |  | 35 days |  |  | Lainie Lavin | 24/06/2026 10:30 |  | Suspended: Awaiting Client Action/Response |  |  |  | 11/06 - Job put on hold awaiting instruction from JN once he has attended - CL 08/06 Awaiting JEFF Neck inspection 01/06 - SCAFFOLD TO BE ERECTED 4TH JUNE. - JUST BELOW SOFFITS - REPAIR. | Held BCC | 742.85
2026-05-05 13:15:00 | Jeff Way - as per Jeff Neck: Cut and lift existing vinyl sheet in patch in ground floor rear kitchen .Apply two coats of latex to sloping patch area only. Remove timber skirting to side and end of bath, scribe to suit floor level and refix to suit. Fix new 600mm wide wall cupboard to suit kitchen walling. JEFF WAY - as per Jeff Neck: Works to Kitchen and Bathroom emailed over full description. ¦ 72FL432301 x4 FLOOR TILES:HACK UP SINGLE VINYL TILE PER TILE; 72FL431315 x4 SCREED:LATEX SELF LEVEL; 72JR381003 x3 SKIRTING:TAKE OFF AND REFIX; 72JR371057 x1 KITCHEN UNIT:RENEW SINGLE WALL 600X300 900MM HIGH - NO ASBESTOS REPORT WITH ORDER | 2026-07-14 08:00:00 | 2026-07-14 |  | Routine Repairs | 1252864 | 142 Luckwell Road | 96909/1 | New Works Instruction | ACE Agreed | 36/1358 |  | 35 days |  |  | Charlie Higginson | 23/06/2026 13:15 |  | Pre-completion Items To Complete |  |  |  | 18/06 - PO sent to FF - CL | Appointment booked | 282.9
2026-05-05 13:06:00 | Jeff Way - as per Jeff N: Works in bathroom, emailed over full description ¦ 72FL432500 x3 SHEET FLOORING:HACK UP VINYL TILES; 72JR305501 x3 FLOORING:SUPPLY AND LAY HARDBOARD; 72FL432507 x3 SHEET FLOORING:LAY NEW VINYL AND SUB-BASE; 72JR388013 x1 BATH PANEL:RENEW ACRYLIC SIDE; +1 more SORs - NO ASBESTOS REPORT WITH ORDER | 2026-06-30 08:00:00 | 2026-07-02 |  | Routine Repairs | 1287850 | 89 REDFORD CRESCENT | 47044/2 | Works Started | Awaiting Cost Estimate | 36/1357 | 2026-06-25 08:00:00 | 35 days |  |  | Charlie Higginson | 23/06/2026 13:06 | No | Post-completion Items To Complete |  |  |  | 29/06 - Appointment confirmed with tenant - CL 15/06 - FF confirmed will be attending 01/07 and 02/07 - CL | WIP | 387.46
2026-05-05 13:00:00 | Jeff Way - as per Jeff Neck: Lay new vinyl sheet flooring and sub base to rear dining / kitchen floor. JEFF NECK ATTENDING 16/4/26 BETWEEN 8-12PM - TEXT SENT Kitchen |  | 2026-06-26 | 2026-06-29 09:09:00 | Routine Repairs | 1290273 | 23 Turtlegate Avenue, Withywood | 46478/2 | Works Completed | ACE Agreed | 36/1369 |  | 35 days |  |  | Lainie Lavin | 23/06/2026 13:00 |  | Pre-works Items To Complete | 2026-07-03 | Yes |  | 03/07 - KPI request sent - CL 30/06 - Email sent to FF for an update - CL 10/06 - Flooring booked for 26/06 and 29/06. Email sent FF for an update - CL 01/06 - PO sent to FF - CL | Complete | 364.74
2026-05-05 10:10:00 | Jeff Way to renew 3x ceilings , 10.5 m2 Bed 2 , 9.0m2 Kitchen and 14.0m2 Liv room, 16 x lin m 125mm coving required to living room. DEC & ELE parts included R.M | 2026-07-16 14:30:00 | 2026-06-30 |  | Routine Repairs | 1310481 | 21 Pavey Road, Hartcliffe | 95466/1 | Works Started | ACE Agreed | 36/1368 | 2026-06-19 10:30:00 | 35 days |  |  | Lainie Lavin | 23/06/2026 10:10 | No | Pre-completion Items To Complete |  |  |  | 25/06 - Kitchen ceiling plaster boarded follow on appointment to continue work 25/06 - CL | Appointment booked | 2419.25
2026-05-05 09:50:00 | JEFF WAY - FAO DARREN WHITCHURCH : REBUILD BRICK WALL INC SURVEY FOOTINGS / AUTHORISED BY STRUCTURAL AS PER IAN OGBORNE. |  |  |  | Routine Repairs | 1271085 | 2 Acresbush Close, Withywood | 96575/1 | New Works Instruction | ACE Agreed | 36/1367 |  | 35 days |  |  | Lainie Lavin | 23/06/2026 09:50 |  | Pre-completion Items To Complete |  |  |  | 24/06 - Awaiting appointment date from AG Builders - CL 18/06 - Awaiting a response from AG Builders - CL 16/06 - PO sent to AG Builders - CL | Awaiting appointment date | 2260.3
2026-05-01 17:58:00 | Jeffway- as per Ian O- FAO DARREN WHITCHURCH :REMOVE AND REPLACE FENCING |  |  |  | Routine Repairs | 1271085 | 2 Acresbush Close, Withywood | 96268/1 | New Works Instruction | ACE Agreed | 36/1366 |  | 35 days |  |  | Lainie Lavin | 22/06/2026 17:58 |  | Pre-works Items To Complete |  |  |  | 24/06 - Awaiting appointment date from AG Builder - CL 18/06 - PO sent to AG builders - CL | Awaiting appointment date | 3895.23
2026-05-01 12:26:00 | Complaint Work - Please see e-mail and report | 2026-05-28 14:15:00 | 2026-05-28 |  | Disrepair | 1221416 | 6 Hurst Road | 96226/1 | Works Started | ACE Agreed | 36/1361 | 2026-05-28 14:15:00 | 35 days |  |  | Shannon Slade | 22/06/2026 12:26 | No | Pre-completion Items To Complete | [5 empty] | 2782.17
2026-05-01 11:44:00 | Jeffway-AS PER DAVE PALMER - FILL VARIOUS SMALL HOLES AROUND THE PROPERTY WHERE MICE HAVE BEEN ENTERING, TENANT TO ADVISE ON WHERE. FILL HOLE OUTSIDE IN FRONT COMMUNAL GRASS AREA WHERE TRAFFIC CONE IS PLACED | 2026-07-02 08:00:00 | 2026-07-02 |  | Routine Repairs | 1301242 | 63 Gatcombe Road | 82807/2 | New Works Instruction | ACE Agreed | 36/1353 |  | 35 days |  |  | Carlene Lynette Lynch | 22/06/2026 11:44 |  | Pre-completion Items To Complete |  |  |  | 02/07 - Tenant only available Thursday or Friday - CL 01/05 - Survey photos added. Additional contact - Mr Jesse Silk - 07402864634 - jessesk1997@icloud.com | Appointment booked | 80.19
2026-05-01 11:07:00 | Jeffway-AS PER DAVE PALMER - EXTRACTOR OVERHAUL TO BATHROOM, RENEW SAFETY FLOORING IN BATHROOM, ROOM REDEC TO DOWNSATAIS BACK ROOM. | 2026-07-02 10:00:00 | 2026-07-06 |  | Routine Repairs | 1297649 | 75 Collinson Road | 62738/2 | Works Started | ACE Agreed | 36/1352 | 2026-06-19 08:00:00 | 35 days |  |  | Carlene Lynette Lynch | 22/06/2026 11:07 | No | Pre-completion Items To Complete |  |  |  | 03/07 - Appointment confirmed with tenant - CL Review needed by manager to assess outstanding work - CL 01/07 - Appointment confirmed with tenant - CL 30/06 - FF to attend 15/07 and 16/07 - CL 26/06 - Follow on appointments booked for decs to be completed, and fan overhauled. PO sent to FF - CL 15/06 - NA on 12/06 - CL 28/05 - Follow on appointment for decs booked for 19/06 - CL 01/05 - Asbestos report received and uploaded. Asbestos report requested as the report sent by DP was unable to open - CL | WIP | 522.81
2026-04-30 17:28:00 | Car External contractor Jeffway to renew Garador Horizon Steel Door BCC contact Luke Pomphrey tnt 55 Chalcroft House Damian 07587128567 please provide before and after pictures |  |  |  | Routine Repairs | 1354149 | Little Cross House Garage 3, Phipps Street, Southville | 93930/2 | New Works Instruction | ACE Agreed | 36/1351 |  | 35 days |  |  | Lainie Lavin | 19/06/2026 17:28 |  | Pre-completion Items To Complete |  |  |  | 30/06 - Amended PO sent to UP&Over, awaiting an appointment date - CL 24/06 - Email sent to UP & Over for an update - CL 18/06 - PO sent - CL | Awaiting appointment date | 1121.7
2026-04-30 14:52:00 | Jeffway-AS PER ROB DOIDGE - STAINBLOCKING TO BACK BED WALLS AND CEILINGS AFTER OLD LEAK. REPAINT CEILING IN FULL 9M2 AND PATCH TREAT/ PAINT SMALL BIT OF MOULD TO EXTERNAL WALL 1M2. | 2026-07-03 08:00:00 | 2026-07-03 |  | Routine Repairs | 1306576 | 40 Maynard Road | 73455/2 | Works Started | Awaiting Cost Estimate | 36/1354 | 2026-07-03 09:00:00 | 35 days |  |  | Carlene Lynette Lynch | 19/06/2026 14:52 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Unable to get hold of tenant, voicemail left - CL 16/06 - Appointment rescheduled due to op being held up on job - CL 01/05 -Photos from surveyor added. Additional contact details on WO if needed - CL | Appointment booked | 0.0
2026-04-30 13:22:00 | JEFFWAY DN786139 RRO - Overhaul/inspect bath for leaks. Replace water damaged floor in bathroom including rescreeding. Any additional works to be agreed. Melissa Edwards 07442675013. | 2026-04-01 10:00:00 |  | 2026-04-01 14:24:00 | Routine Repairs | 1015970 | 4 Henacre Road lawrnce weston | 106587/1 | Works Completed | Invoiced | 36/1250 |  | 35 days |  |  | Lainie Lavin | 19/06/2026 13:22 |  | Fully Complete | 2026-04-13 | Yes |  | 13/04 - KPI requested - CL | Complete | 50.0
2026-04-30 12:38:00 | Re seal Kitchen and living room windows - Overhaul Bedroom window (not opening) - Adjust and clean all windows in property | 2026-05-08 08:00:00 |  | 2026-06-08 12:14:00 | Routine Repairs | 1194145 | 7 Cowling Drive, Stockwood | 76840/1 | Works Completed | Invoiced | 36/1350 |  | 35 days |  |  | Lainie Lavin | 19/06/2026 12:38 |  | Fully Complete | 2026-06-02 |  |  |  | Complete | 208.64
2026-04-30 12:02:00 | COMPLAINT WORKS | 2026-06-10 08:00:00 | 2026-07-02 |  | Disrepair | 1265549 | 52 St Peters House | 95672/1 | New Works Instruction | ACE Agreed | 36/1360 |  | 35 days |  |  | Shannon Slade | 19/06/2026 12:02 |  | Pre-completion Items To Complete |  |  |  | 03/07 - JP to be contacted regarding the condition of the property - CL 01/07 - Tenants phone switched off and no facility to leave voicemail, text sent - CL | Appointment booked | 2406.2
2026-04-29 10:30:00 | Complaint works- Timerwize quote |  |  | 2026-05-29 09:21:00 | Disrepair | 1180434 | 28 LEWIN STREET | 94850/1 | Works Completed | ACE Agreed | 36/1359 |  | 35 days |  |  | Shannon Slade | 18/06/2026 10:30 |  | Fully Complete | 2026-06-16 |  |  |  | Complete | 2240.27
2026-04-28 16:01:00 | Jeff Way - As per John Oyeniyi: Crack repair at Entrance lobby and Bath repair. John Oyeniyi booked to attend 24/04/26 8am-12pm - text sent | 2026-07-06 09:00:00 | 2026-07-06 |  | Routine Repairs | 1248302 | 4 Hastings Road, Bedminster, | 64260/2 | New Works Instruction |  | 36/1349 |  | 35 days |  |  | Lainie Lavin | 17/06/2026 16:01 |  | Pre-completion Items To Complete |  |  |  | 03/07 - Variation request sent. Appointment confirmed with tenant - CL 15/06 - Appointment rescheduled as requested by tenant - CL | Appointment booked | 1921.37
2026-04-28 15:01:00 | Attend Property - Remove sink unit to gain access for possible pest proof internal of the property. | 2026-07-06 12:00:00 | 2026-07-06 |  | Routine Repairs | 1302541 | 51 Hareclive Road | 80828/1 | Works Started | ACE Agreed | 36/1348 | 2026-06-09 10:00:00 | 35 days |  |  | Carlene Lynette Lynch | 17/06/2026 15:01 | No | Post-completion Items To Complete |  |  |  | 03/07 - Unable to get hold of tenant, voicemail left - CL 29/05 - Appointment rescheduled to 08/05 as requested by KD. Appointment booked for 18/05 - CL | WIP | 635.35
2026-04-27 14:01:00 | Complaints: New one to Kitchen -BL to provide aperture; new front door | 2026-05-28 13:15:00 | 2026-06-23 |  | Disrepair | 1195342 | 2 DURWESTON WALK | 93957/1 | New Works Instruction | ACE Agreed | 36/1346 |  | 35 days |  |  | Shannon Slade | 16/06/2026 14:01 |  | Suspended: Awaiting asbestos info | [5 empty] | 1111.18
2026-04-27 14:00:00 | Jeffway- as per John O-Hack off vinyl tiles in Kitchen, latex and renew sheet flooring |  | 2026-06-08 | 2026-06-09 11:28:00 | Routine Repairs | 1272113 | 663 Bishport Avenue, Withywood | 71383/2 | Works Completed | ACE Agreed | 36/1340 |  | 35 days |  |  | Lainie Lavin | 16/06/2026 14:00 |  | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL 10/06- Email sent to FF for confirmation works completed - CL 01/06 - FF to attend on 8-9/06. Emails sent to FF chasing work - CL awaiting FF to give a date -15/4 LL. | Complete | 874.8
2026-04-27 13:58:00 | Complaints; Dining Room damp repairs to follow external works WO93846 |  |  |  | Disrepair | 1146743 | 1 Hamilton Road | 93864/1 | New Works Instruction | ACE Agreed | 36/1345 |  | 35 days |  |  | Shannon Slade | 16/06/2026 13:58 |  | Pre-completion Items To Complete | [5 empty] | 1167.53
2026-04-27 13:56:00 | Complaints: Gable corner rear elevation to cover downpipe repairs & refix plus, tower front left Party Wall |  |  |  | Disrepair | 1146743 | 1 Hamilton Road | 93846/1 | New Works Instruction | ACE Agreed | 36/1344 |  | 35 days |  |  | Shannon Slade | 16/06/2026 13:56 |  | Pre-completion Items To Complete | [5 empty] | 2148.65
2026-04-27 09:50:00 | Ceiling patch in communal lounge repair required after leak As above | 2026-07-24 09:15:00 | 2026-07-24 |  | Routine Repairs | 1838604 | 2-33 Chard Court, Fortfield Road | 93675/1 | Works Started |  | 36/1339 | 2026-06-08 08:00:00 | 35 days |  |  | Lainie Lavin | 16/06/2026 09:50 | No | Pre-completion Items To Complete |  |  |  | 12/06 - Email sent to PW informing unable to locate where loft insulation is needed awaiting repsonse - CL 09/06 - Plastering already completed, email sent to PW and EH to provided clarification - CL | Appointment booked | 105.88
2026-04-24 13:54:00 | Complaint Work - Please see e-mail and report |  |  |  | Disrepair | 1199673 | 85 Hungerford Road | 93427/1 | New Works Instruction | ACE Agreed | 36/1343 |  | 35 days |  |  | Shannon Slade | 15/06/2026 13:54 |  | Suspended: Awaiting asbestos info |  |  |  | 02/07- ease and adjust door 20/05 - awaiting update from BCC regarding correct SORS | Held BCC | 123.06
2026-04-24 13:52:00 | Complaint works throughout property; Renew kitchen and bathroom extract fans; resecure hot tap on kitchen sink; replace window handle (with key) in bathroom as per Tom Taylor | 2026-06-11 12:00:00 | 2026-07-07 |  | Disrepair | 1240159 | 9 BERRYCROFT | 93362/1 | New Works Instruction | ACE Agreed | 36/1342 |  | 35 days |  |  | Shannon Slade | 15/06/2026 13:52 |  | Suspended: Awaiting asbestos info |  |  |  | 17/06 - EMAIL ISSUED TO BCC REGARDING ISSUES IN PROPERTY. WAITING FOR RESPONSE. 15/06 - NO ACCESS ON 11TH JUNE, ELECTRICIAN REBOOKED FOR 16TH JUNE, OTHER WORKS BOOKED FOR 7TH JULY. (TENANT DOESNT ANWSER PHONE, SO CONFIRMATION HAS BEEN SENT VIA TEXT) 20/05 - WORKS BOOKED FOR 11TH JUNE | Held BCC | 655.78
2026-04-24 13:50:00 | Jeffway- as per John O-Stitch up cracks on party wall in Rear Garden Booked in with Mike and Pete 16/04/2026 08:00 - 17:30 |  |  |  | Routine Repairs | 1300716 | 16 Fulford Walk, Hartcliffe | 78674/2 | New Works Instruction | ACE Agreed | 36/1332 |  | 35 days |  |  | Lainie Lavin | 15/06/2026 13:50 |  | Pre-completion Items To Complete |  |  |  | 24/06 - Quote received from BS, forwarded to CH for review - CL 17/06 - Email sent to BS chasing work - CL 29/05 - PO sent to BS - CL | Awaiting appointment date | 568.44
2026-04-24 13:50:00 | Jeffway- as per John O-: Renew double base unit (beneath sink) and paint walls | 2026-07-08 13:00:00 | 2026-07-08 |  | Routine Repairs | 1284191 | 30 Latchmoor House, Banwell Close | 47331/2 | Works Started | ACE Agreed | 36/1334 | 2026-06-22 08:00:00 | 35 days |  |  | Lainie Lavin | 15/06/2026 13:50 | No | Pre-completion Items To Complete |  |  |  | 03/07 - DW attended to measure sink units and order for installation on 08/07 - CL 30/06 - Site visit booked for Darren to attend and measure kitchen unit and appointment confirmed with tenant for repairs to be carried out on 08/07 - CL 25/06 - Tenant refused op access to carry out repair, she wanted her bathroom unit changed and not the kitchen. I was unable to get hold of tenant on the phone, left a voicemail to make contact to discuss the matter - CL 28/05 - Appointment confirmed with tenant - CL | Appointment booked | 438.73
2026-04-24 13:49:00 | PD1 - Please carry out works as listed. Access to be arranged through surveyor James Bailey | 2026-06-29 12:30:00 |  |  | Disrepair | 1268128 | 24, FIRST FLOOR FLAT WEST MALL | 93183/1 | New Works Instruction | ACE Agreed | 36/1341 |  | 35 days |  |  | Shannon Slade | 15/06/2026 13:49 |  | Suspended: Awaiting asbestos info |  |  |  | 30/06 - Job put on hold awaiting asbestos report and confirmation from JB on how he would like to proceed - CL 08/06 - WORKS BOOKED FOR CLAYTON 29TH AND 30TH JUNE. | Held BCC | 892.6
2026-04-24 13:20:00 | Jeffway- as per John O-Patch repair wall rendering at Rear elevation | 2026-07-31 08:00:00 | 2026-07-27 |  | Routine Repairs | 1292020 | 62 Aldwick Avenue, Hartcliffe | 87514/2 | Works Started | ACE Agreed | 36/1331 | 2026-07-27 11:29:00 | 35 days |  |  | Lainie Lavin | 15/06/2026 13:20 | No | Pre-completion Items To Complete |  |  |  | 28/05 - Email sent to EH and KD regarding extension (see notes) . Extension granted - CL 27/05 - Extension applied for as tenant works in a school and is only available after 22/07 - CL | Appointment booked | 486.87
2026-04-24 10:00:00 | Jeff Way - As per Rob Doidge: Renewal of w.c in full, renewal of basin & bath taps & renew non slip floor covering to bathroom. Please liaise with h/o Lisa Taylor regarding appts / access. | 2026-06-22 08:45:00 |  |  | Routine Repairs | 1306145 | 18 Maynard Close | 81339/2 | New Works Instruction | ACE Agreed | 36/1319 |  | 35 days |  |  | Carlene Lynette Lynch | 15/06/2026 10:00 |  | Pre-completion Items To Complete |  |  |  | 25/06 - PO sent to FF for dates they will be able to attend as has to go through support worker - CL 11/06 - Appointment confirmed with housing officer - CL 03/06 - Asbestos report received and uploaded. Email sent to LT (dealing with tenant) with 2 dates for work to be carried out . Asbestos report requested - CL | Next Appointment Needed | 503.49
2026-04-24 10:00:00 | JEFF WAY - AS PER ROB DOIDGE - REFIX LOOSE BANNISTER RAIL TO COMMUNAL STAIRWAY - MD Booked in with Rob D 23/04/2026 08:00 - 12:00pm via text Hallway | 2026-06-02 08:00:00 | 2026-06-02 | 2026-06-02 08:46:00 | Routine Repairs | 1231227 | 71b Salcombe Road, Knowle | 59411/2 | Works Completed | Invoiced | 36/1329 | 2026-06-02 08:00:00 | 35 days |  |  | Lainie Lavin | 15/06/2026 10:00 | Yes | Pre-completion Items To Complete | 2026-06-05 | Yes |  | 11/06 - KPI received and uploaded - CL 05/06 - KPI requested - CL | Complete | 75.56
2026-04-24 10:00:00 | JEFF WAY - AS PER ROB DOIDGE - RENEW BOTTOM STAIR WINDER / TREAD IN FULL, FALLING DOWN TOWARDS WALL AT BACK CORNER Booked in with Rob D 23/04/2026 08:00-12pm via text | 2026-06-23 10:00:00 | 2026-06-23 | 2026-06-23 07:46:00 | Routine Repairs | 1216520 | 39 Creswicke Road, Knowle | 58616/2 | Works Completed | ACE Agreed | 36/1330 | 2026-06-23 10:00:00 | 35 days |  |  | Lainie Lavin | 15/06/2026 10:00 | No | Pre-completion Items To Complete |  | Yes |  | 29/05 - Tenant on holiday requested to call back next week to arrange appointment - CL | Complete | 66.34
2026-04-23 14:29:00 | AS PER ROB DOIDGE - GARDEN WALL REPLACEMENT WITH POST AND PANEL FENCE TO 6 BLACKTHORNE. EICR TO OUTBUILDING IN GARDEN |  |  |  | Routine Repairs | 1306521 | 33 Maynard Road | 92739/1 | New Works Instruction |  | 36/1313 |  | 35 days |  |  | Carlene Lynette Lynch | 12/06/2026 14:29 |  | Pre-completion Items To Complete |  |  |  | 23/06- Quote sent to RD and EH. - CL JW to send Shepps quote to BCC 15/06 - Quote received from BS, sent to CH for reviewing - CL 12/06 - PO sent to BS - CL 04/06 - EH asked for job to be put on hold - CL 03/06 - Tenant refused any further work being done on her property, email sent to RD and EH to assist - CL 12/5 - sheps couldnt complete job, emailed CL on how to proceed? (LL). 11/5 - chased up sheps with email (LL) , 05/05 - Awaiting quote from Shepps - CL 28/04 - Received approval to proceed with work - CL 23/04 - Tenant refused EICR, email sen | Awaiting appointment date | 201.36
2026-04-23 13:43:00 | CAR jeffway group - renew garage door with GArador horizon Up and over sent email to quote Garage No.11 wide open, as door hinges have snapped. Unsecured garage. Caretaker Harvey Holliday - 07548665507 bcc contact Luke Pomphrey |  |  | 2026-05-29 10:47:00 | Routine Repairs | 1851963 | Gilton House Garage Site | 79144/2 | Works Completed | ACE Agreed | 36/1315 |  | 35 days |  |  | Carlene Lynette Lynch | 12/06/2026 13:43 |  | Pre-completion Items To Complete |  | Yes |  | 12/06 - works completed 29th may. 29/05 - PO sent to Up & Over - CL | Complete | 1417.36
2026-04-23 13:20:00 | Jeffway-as per John O-Renew 2 panels of fence at Rear Elevation | 2026-07-20 12:15:00 | 2026-07-20 |  | Routine Repairs | 1295563 | 11 Briscoes Avenue, Hartcliffe | 92694/1 | New Works Instruction | ACE Agreed | 36/1328 |  | 35 days |  |  | Lainie Lavin | 12/06/2026 13:20 |  | Pre-completion Items To Complete |  |  |  | 23/06 - NA on 22/06, appointment rescheduled - CL | Appointment booked | 451.7
2026-04-23 11:10:00 | Jeffway- John O-2m2 paving repair to the entrance paving slab John Oyeniyi booked to attend 22/04/26 10am-2pm - text sent External | 2026-06-22 08:30:00 | 2026-06-22 | 2026-06-22 07:27:00 | Routine Repairs | 1278860 | 187 Four Acres, Withywood | 63837/2 | Works Completed | ACE Agreed | 36/1327 |  | 35 days |  |  | Lainie Lavin | 12/06/2026 11:10 |  | Pre-completion Items To Complete |  | Yes |  |  | Complete | 114.64
2026-04-23 11:00:00 | Jeffway-as per Ian O-Paint Living room ceiling and Kitchen walls John Oyeniyi booked to attend 22/04/26 between 12-5.30pm - text sent Property | 2026-07-16 12:00:00 | 2026-07-16 |  | Routine Repairs | 1299394 | 36 Englishcombe Road, Hartcliffe | 64468/2 | New Works Instruction | ACE Agreed | 36/1326 |  | 35 days |  |  | Lainie Lavin | 12/06/2026 11:00 |  | Pre-completion Items To Complete |  |  |  |  | Appointment booked | 335.72
2026-04-22 15:29:00 | RESPONSE REWIRE |  |  | 2026-01-30 10:26:00 | Routine Repairs | TBC | 121 Lansdowne Court | 59832/2 | Works Completed | Invoiced | 36/1310 |  | 35 days |  |  | Carlene Lynette Lynch | 11/06/2026 15:29 |  | Suspended: Awaiting asbestos info | 2026-04-28 |  |  | 28/04 - KPI requested - CL | Complete | 7210.83
2026-04-22 14:49:00 | As per Aaron Watkins FAO SUPERVISOR. meet on site to discuss works required call 07831121336 before booking in appointment. |  |  |  | Routine Repairs | 1012313 | 22 Commonfield Road, Lawrence Weston | 92296/1 | Works Cancelled | Works Cancelled | 36/1324 |  | 35 days | 3: Omitted from Contract | 2026-06-16 11:51:38 | Lainie Lavin | 11/06/2026 14:49 |  | Suspended: Awaiting asbestos info |  |  |  | 03/06- AW and SH meeting on site today 15/05 - BCC cant get hold of tenant to arrange awaiting update from Aaron | Cancelled | 377.81
2026-04-22 12:31:00 | JEFF WAY - AS PER ROB D: LOG BURER REMOVED, SMOKE TEST & SAFETY CHECK TO CHIMNEY/ FLUE PIPE PRIOR TO BLOCKING UP OPENING & FITTING ELECTRIC FIRE TO EXISTING SURROUND ETC. |  |  |  | Routine Repairs | 1293987 | 2 Blagrove Close | 83207/2 | New Works Instruction | ACE Agreed | 36/1309 |  | 35 days |  |  | Carlene Lynette Lynch | 11/06/2026 12:31 |  | Suspended: Awaiting asbestos info |  |  |  | 02/07 - EH to chase CASA - CL 25/06 CASA attended EH will confirm - CL 16/06 - CASA to attend on 22/06 - CL 03/06 - Email sent to OB chasing response - CL 22/04 - PO sent to OB to carry out smoke safety check. Asbestos report requested - CL | Awaiting asbestos report | 664.32
2026-04-22 11:40:00 | Jeffway-FAODARREN- as per Ian O- EXT PAINTING , WALKWAY PATCH REPAIRS , BRICK REPAIR AND SEALANT | 2026-05-12 08:00:00 |  | 2026-05-29 11:20:00 | Routine Repairs | 1841801 | 1-10 Berrycroft, Catherine Mead Street | 92149/1 | Works Completed | ACE Agreed | 36/1322 |  | 35 days |  |  | Lainie Lavin | 11/06/2026 11:40 |  | Pre-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI requested- CL | Complete | 1569.11
2026-04-21 14:36:00 | Overhaul of valley gutter and assocated works |  |  | 2026-05-11 13:42:00 | Disrepair | 1234044 | 10 TAVISTOCK WALK | 91761/1 | Works Completed | ACE Agreed | 36/1318 |  | 35 days |  |  | Shannon Slade | 10/06/2026 14:36 |  | Pre-completion Items To Complete |  | Yes |  | 14/05 - WORKS ARE COMPLETED WAITING FOR BCC TO COMPLETE SITE INSPECTION. 21/04 - WORKS ISSUED TO LMT WHO ARE CURRENTLY ON SITE. | Complete | 1980.0
2026-04-21 11:20:00 | Jeffway- as per Jeff N-Hack off water damage render/ plasterwork to head and sides to ground floor living room window. cut out rotten damage timber work forming casement surrounds window opening. refix new timber to suit and undercoat and gloss to suit. Fix PVC cill over existing tiled cill. Apply epoxy wood filler to external split on window. Fill cracks in stone cill and window head |  |  |  | Routine Repairs | 1273116 | 39 Borleyton Walk, | 72999/2 | New Works Instruction | ACE Agreed | 36/1314 |  | 35 days |  |  | Lainie Lavin | 10/06/2026 11:20 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting asbestos report | 514.63
2026-04-21 07:53:00 | In first floor bathroom -Remove existing and lay nonslip flooring and subbase. |  |  | 2026-05-21 21:36:00 | Disrepair | 1055089 | 176 Greystoke Avenue | 91841/1 | Works Completed | ACE Agreed | 36/1320 |  | 35 days |  |  | Shannon Slade | 10/06/2026 07:53 |  | Post-completion Items To Complete | 2026-06-12 |  |  | 07/05 - FF ATTENDING 20TH AND 21ST MAY. 28/04 - WORKS ISSUED TO FANTASY FLOORING. | Complete | 292.6
2026-04-20 15:43:00 | Jeff Way - as per Jeff Neck: Works as per email sent on 20/04/26. Major Rep 35 days. Expected Completion 10/06/2026 • Job Description: Lay new vinyl sheet flooring in hallway and utility room, Make good cracking around door frames in hallway. fix timber architrave to living / front internal door frame, replace existing glass in utility room with toughened. Apply skim plaster to all walls in hallway, Apply emulsion paint to all walls in hallway, fix white tiles to side and end of bath, seal to side and end of bath, overhaul bath and basin taps, replace double power socket and boxes in living room and bedroom. apply caulk gun filler around cracking on bedroom ceiling, rehang kitchen cupboard door, apply emulsion paint to kitchen ceiling, satin block kitchen walls , apply emulsion paint to kitchen walls. | 2026-07-03 08:00:00 | 2026-07-03 |  | Routine Repairs | 1313606 | 120 Stillingfleet Road | 53053/2 | Works Started |  | 36/1305 | 2026-06-15 08:00:00 | 35 days |  |  | Carlene Lynette Lynch | 09/06/2026 15:43 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment confirmed with tenant - CL 23/06 - Tenant denied access to decorator, citing that she wanted other work completed first. JN to speak with tenant - CL 17/06 - Variation sent to JN and EH - CL 16/06 -CB to attend on 17/06 to fix door. DW to carry out site visit to assess work carried out yesterday - CL 07/05 - Email sent to JN and EH regarding the utility room door. Tenant called back and appointments booked for 15/06, 19/06 and 22/06 - CL Unable to get hold of tenant, voicemail and text sent - CL 22/04 - Asbestos report received and uploaded - CL 20/04 | Appointment booked | 1693.84
2026-04-20 11:40:00 | As per darryls (07733831884) - Repoint where mortar missing and crumbling - refer to pics | 2026-06-18 13:00:00 | 2026-06-18 |  | Routine Repairs | 1014911 | 1 Gorham Close | 90676/1 | Works Started | ACE Agreed | 36/1304 | 2026-05-21 16:45:00 | 35 days |  |  | Carlene Lynette Lynch | 09/06/2026 11:40 | No | Pre-completion Items To Complete |  |  |  | 11/06 -Following site visit additional brick work and pointing booked in for 18/06. Unable to handover job until site visit between DW and DJ on 11/06 - CL 09/06 - Site inspection requested by DJ regarding work carried out - CL 05/06 - KPI requested - CL 20/04 - Pictures uploaded, DJ queried whether an asbestos report is needed. Email sent for pics and asbestos report - CL | Complete | 186.47
2026-04-20 08:02:00 | Jeff Way - as per Jeff Neck: Apply plaster skim to all damage walls in 1st floor front bedroom. | 2026-06-09 11:15:00 | 2026-06-09 | 2026-06-09 07:58:00 | Routine Repairs | 1277049 | 55 Elmtree Drive | 61595/2 | Works Completed | ACE Agreed | 36/1307 | 2026-06-09 08:00:00 | 35 days |  |  | Carlene Lynette Lynch | 09/06/2026 08:02 | Yes | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL 22/04 - Asbestos report received and uploaded - CL 21/04 - Asbestos report requested - CL | Complete | 536.55
2026-04-20 07:52:00 | Jeff Way - as per Jeff Neck: Disconnect water & waste supplies remove water damage base unit & fix new to suit, refix existing doors & overhaul all doors & draws. |  |  |  | Routine Repairs | 1274722 | 2 Cornleaze | 36678/2 | Works Cancelled | Works Cancelled | 36/1306 |  | 35 days | 4: Other | 2026-06-17 13:30:16 | Carlene Lynette Lynch | 09/06/2026 07:52 |  | Works Cancelled |  |  |  | 08/06 - Email sent to JN on how to proceed as tenant has informed me she is getting a new kitchen. CL 21/04 - Asbestos report requested - CL | Cancelled | 535.47
2026-04-17 11:56:00 | Jeff Way - as per John Oyeniyi: Renew 1no double Kitchen unit and renew 1no handle to kitchen unit | 2026-06-25 09:00:00 | 2026-06-25 | 2026-06-25 07:31:00 | Routine Repairs | 1311746 | 52 Redwood House, | 41343/2 | Works Completed | ACE Agreed | 36/1300 | 2026-06-24 12:30:00 | 35 days |  |  | Lainie Lavin | 08/06/2026 11:56 | No | Pre-completion Items To Complete |  | Yes |  | 25/06 - Most work completed, handles to be replaced 25/06 - CL 15/06 - Appointment rescheduled due to op being held on first job. New appointment booked with tenants carer - CL CL 30/04 - Appointment booked, email and letter sent. Email sent to CM for additional contact details as number provided does not work - CL | Complete | 308.57
2026-04-16 14:20:00 | PD1 - Please carry out works as listed. |  | 2026-07-02 |  | Disrepair | 1174261 | 145 EASTWOOD ROAD | 89296/1 | New Works Instruction | ACE Agreed | 36/1316 |  | 35 days |  |  | Shannon Slade | 05/06/2026 14:20 |  | Pre-completion Items To Complete |  |  |  | 03/07 - Unable to repair drainage system. confirmation if glazing unit installation needed - CL 01/07 - Tenant informed me that he is unable to do AM appointments. Will reschedule and confirm - CL 30/06 - Unable to contact tenant, voicemail left - CL 08/06 - WORKS BOOKED FOR 2ND JULY, PLEASE DO NOT ATTEND ALONE DUE TO CREDIBLE THREAT. 27/02 - ASBESTOS AND INVESTIGATION REPORT REQUESTED. PROPERTY IS CREDIBLE THREAT I BELIEVE | Manager review needed | 824.81
2026-04-16 14:06:00 | Jeffway-AS PER DAVE PALMER - RENEW TILES TO VARIOUS AREAS IN THE FOYER AND LAUNDRY ROOM, RENEW TILES IN TOILET, REMOVE SINK, REMOVE CLEAN AND REFIX TILES TO WALL WHERE SINK IS FIXED.AS PER SURVEY PHOTOS | 2026-05-22 09:00:00 | 2026-06-10 | 2026-05-25 12:13:00 | Routine Repairs | 1845392 | 1-62 Millmead House, | 89315/1 | Works Completed | ACE Agreed | 36/1293 | 2026-06-10 09:00:00 | 35 days |  |  | Carlene Lynette Lynch | 05/06/2026 14:06 | Yes | Pre-completion Items To Complete |  | Yes |  | 29/05 - Works started need to be finished, bathroom tiles need to be finished and sink refitted | Complete | 251.88
2026-04-16 13:26:00 | Jeffway- as per Jeff N-Cut damage wallpaper to head and sides of 1st floor rear bedroom window to expose loose plasterwork. hack off and apply skim finish to match existing levels. Apply emulsion paint to new plasterwork only. Overhaul all PVC windows leave in working order | 2026-06-01 12:00:00 | 2026-06-08 | 2026-06-08 09:00:00 | Routine Repairs | 1277754 | 8 Felton Grove, Bedminster Down | 76772/2 | Works Completed |  | 36/1303 | 2026-06-01 11:00:00 | 35 days |  |  | Lainie Lavin | 05/06/2026 13:26 | No | Pre-completion Items To Complete | 2026-06-30 | Yes |  | 30/06 - KPI resent as errors found - CL 29/06 - KPI requested - CL 24/04 - Follow appointment booked for 08/06 - CL | Complete | 211.09
2026-04-16 11:30:00 | Please carry out disrepair works as listed | 2026-05-26 09:15:00 | 2026-06-22 |  | Disrepair | 1151322 | 3 LANGTON HOUSE | 47071/4 | New Works Instruction | ACE Agreed | 36/1296 |  | 35 days |  |  | Shannon Slade | 05/06/2026 11:30 |  | Pre-completion Items To Complete |  |  |  | 08/06 - ELECTRICAL WORKS COMPLETED, MOULD WASH COMPLETED, REMAINING WORKS BOOKED FOR 22ND JUNE. ASBESTOS REPORT REQUIRED - ATTEMPTED TO CALL TENANT 23RD AND 24TH - MESSAGE LEFT. 12/05 -NO ANWSER FROM TENANT ON 5TH MAY FOR D&M TREATMENT TO BE COMPLETED, ELECTRICAL WORKS BOOKED IN FOR 21ST MAY. WORKS TO BE REBOOKED, EMAIL ISSUED TO TENANT | Appointment booked | 1437.58
2026-04-16 11:28:00 | PD1 - Please carry out works as listed |  |  | 2026-05-07 10:09:00 | Disrepair | 1211014 | 70 Barnstaple Road | 89221/1 | Works Completed | ACE Agreed | 36/1295 | 2026-05-07 10:09:00 | 35 days |  |  | Shannon Slade | 05/06/2026 11:28 | Yes | Post-completion Items To Complete | 2026-05-13 |  |  | 22/04 - WORKS BOOKED FOR 7TH MAY. | Complete | 126.32
2026-04-16 10:43:00 | CARRY OUT WORKS - DISREPAIR |  |  | 2026-06-01 10:31:00 | Disrepair | 1055976 | 3 HENBURY COURT | 63699/2 | Works Completed | ACE Agreed | 36/1308 |  | 35 days |  |  | Shannon Slade | 05/06/2026 10:43 |  | Post-completion Items To Complete | 2026-06-12 |  |  | 27/05 - NA on 26/05. Job to be rebooked. Appointment rebooked with tenant- CL | Complete | 68.72
2026-04-15 13:26:00 | JEFF WAY - AS PER ROB D: VACUUM GUTTER CLEARANCE FRONT & REAR, RENEWAL OF REAR KITCHEN COOKER EXTRACTOR VENT COVER AS SQUIRRELS ACCESSING. COVER OVER NEW VENT WITH A METAL MESH/ GRATE AS EXTRA PROTECTION | 2026-06-01 12:00:00 | 2026-06-12 | 2026-06-12 10:44:00 | Routine Repairs | 1296237 | 12 Chelvey Close, Hartcliffe | 81035/2 | Works Completed | ACE Agreed | 36/1301 | 2026-06-01 12:00:00 | 35 days |  |  | Lainie Lavin | 04/06/2026 13:26 | No | Pre-completion Items To Complete | 2026-06-23 |  |  | 23/06 - KPI requested - CL 15/06 - Email sent to Elite for update - CL 24/04 - Appointment booked for 01/06, awaiting gutter clean appointment date. Email sent to Elite - CL | Complete | 180.38
2026-04-15 13:26:00 | JEFF WAY - AS PER ROB D: MOULD/ CONDENSATION DRIP TREATMENT & REPAINT WITH HALOPHEN PAINT TO FULL WINDOW WALL & REVEAL & FULL SINK WALL IN KITCHEN | 2026-05-18 12:00:00 | 2026-06-30 |  | Routine Repairs | 1243750 | 87 Chalcroft House, Lower Sidney Street | 83580/2 | New Works Instruction | ACE Agreed | 36/1302 |  | 35 days |  |  | Lainie Lavin | 04/06/2026 13:26 |  | Pre-completion Items To Complete |  |  |  | 29/06 - Unable to contact tenant as landline phone number disconnected. Voicemail left on mobile - CL 10/06 - NA 09/06, appointment rescheduled for 16/06 - CL 22/05 Tenant cancelled appointment due to feeling unwell 07/05 - Appointment booked through BCC RD and Maya. Unable to get hold of tenant, voicemail left - CL 30/04 - NA on 29/04. Awaiting a new date from compliance - CL 24/04 - Awaiting date from compliance for job to be carried out - CL | Appointment booked | 129.66
2026-04-14 11:56:00 | JEFF WAY - AS PER DAVE PALMER: RENEW SURROUND TO INSPECTION COVER & RENEW BACK INLET GULLY. | 2026-06-30 08:15:00 | 2026-06-30 | 2026-06-30 14:15:00 | Routine Repairs | 1280779 | 37 Gay Elms Road, Withywood | 40520/2 | Works Completed | ACE Agreed | 36/1297 | 2026-06-29 08:00:00 | 35 days |  |  | Lainie Lavin | 03/06/2026 11:56 | No | Post-completion Items To Complete |  | Yes |  | 30/06 - Operative re attended on 30/06 as pipe broke, DW to add VO for extra pipe - CL 29/05 - Email sent to DP requesting photos and site audit - CL | Complete | 192.43
2026-04-14 11:56:00 | Jeffway- as per John O-Renew tap to Kitchen sink | 2026-06-04 14:30:00 | 2026-06-25 | 2026-06-04 12:30:00 | Routine Repairs | 1291903 | 4 Aldwick Avenue, Hartcliffe | 50243/3 | Works Completed | ACE Agreed | 36/1298 |  | 35 days |  |  | Lainie Lavin | 03/06/2026 11:56 |  | Pre-completion Items To Complete |  | No |  | 30/04 - Unable to make contact with tenant, voicemail and text sent - CL | Appointment booked | 118.33
2026-04-14 11:18:00 | Complaint works- works to address mould within the hallway. | 2026-06-23 11:15:00 | 2026-06-23 | 2026-06-23 15:09:00 | Disrepair | 1174089 | 90 EASTWOOD CRESCENT | 87412/1 | Works Completed | ACE Agreed | 36/1294 |  | 35 days |  |  | Shannon Slade | 03/06/2026 11:18 |  | Pre-completion Items To Complete |  | No |  | 16/06 - WORKS COMPLETED, DRAUGHT EXCLUDER TO BE FITTED BOOKED FOR 23RD JUNE 17/04 - BOOK DAN WILLIAMS FOR 2 HOURS TO COMPLETE WORKS. 20/04 - WE ATTEMPTED TO GAIN ACCESS TO THE PROPERTY BY KNOCKING DOOR BY TENANT REFUSED ENTRY DUE TO NO SURVEYOR ATTENDING, EMAIL ISSUED TO TOM LEAR.12/05 - WORKS BOOKED FOR 4TH JUNE | Appointment booked | 163.85
2026-04-10 16:44:00 | JEFF WAY - Crack repair to Rear Elevation wall and Mould wash bedroom 1 FAO JOHN OYENIYI | 2026-07-08 12:00:00 | 2026-07-08 |  | Routine Repairs | 1291903 | 4 Aldwick Avenue, Hartcliffe | 50243/2 | Works Started | ACE Agreed | 36/1287 | 2026-06-26 08:00:00 | 35 days |  |  | Lainie Lavin | 01/06/2026 16:44 | No | Pre-completion Items To Complete |  |  |  | 03/07 - Op unable to attend due to being held up on job - CL 01/07 - Unable to contact tenant , voicemail left and text sent - CL 26/06 - Second visit required to tyrolene - CL 17/06 - WORKS BOOKED FOR 25TH JUNE 30/04 - Unable to make contact with tenant, voicemail and text sent - CL | Appointment booked | 668.9
2026-04-10 15:14:00 | As per Ches Blackett, please install fan in kitchen and install fan in bathroom DGU. |  |  |  | Routine Repairs | 1292020 | 62 Aldwick Avenue, Hartcliffe | 80463/2 | New Works Instruction | ACE Agreed | 36/1288 |  | 35 days |  |  | Lainie Lavin | 01/06/2026 15:14 |  | Suspended: Awaiting Client Action/Response |  |  |  | 23/06 - Email sent to CB on how to proceed - CL 16/06 - WSG informed us that the tenant has refused to have the DGUs fitted. Unable to get hold of tenant, voicemail left and text message sent - CL 27/05 - PO sent to WSG for DGU install - CL 14/04 - Variation request sent - CL | Held BCC | 1050.72
2026-04-10 10:51:00 | JEFF WAY - AS PER ROB DOIDGE - FOLLOWING PROPERTY FIRE - SMOKE CLEAN WHERE REQUIRED TO PROPERTY FOLLOWING FIRE. REPAIR / RENEWAL AS REQUIRED TO STAIRCASE, DOWNSTAIRS DOORFRAMES AND METER CUPBOARD UNDER STAIRS | 2026-06-15 08:00:00 | 2026-06-15 |  | Routine Repairs | 1294753 | 11 Borver Grove | 86409/1 | Works Started | ACE Agreed | 36/1285 | 2026-05-09 08:00:00 | 35 days |  |  | Carlene Lynette Lynch | 01/06/2026 10:51 | No | Pre-works Items To Complete |  |  |  | 25/06 - Order to be KPI and new order has been raised - CL 16/06 - Awaiting VOs from EH and RD, and further instruction - CL 11/06 - EH and RD to site visit Monday - CL10/6 - awaiting dates from sub contractor. 05/06- Staircase installation starting on Monday 08/06/26 - 18/5 - on held as awaiting contractor app date.13/05 Plastering works completed. 01/04 - Appointment booked for plastering to commence on 09/05 after rewire completed by JWE - CL 30/04 - VO sent to RD and PO sent to BB - CL 28/04 - RD confirmed in house electrical team will be carrying out rewire. SH to confirm a plan to carry out the | Complete | 5992.79
2026-04-09 16:47:00 | Car Jeffway to replace the whole curtain on the roller at Gilton House, please proivide after pictures up and over already quoted for repair BCC contact Luke Pomphrey |  | 2026-05-29 | 2026-05-29 08:14:00 | Routine Repairs | 1837032 | 2-47 Gilton House, Glenarm Walk | 79027/2 | Works Completed | ACE Agreed | 36/1290 |  | 35 days |  |  | Lainie Lavin | 29/05/2026 16:47 |  | Pre-completion Items To Complete |  | Yes |  | 03/06 - Completed on 29/05 - CL 27/05 - Email sent to UO chasing completion date - CL 13/05 Email sent to UO chasing date 28/04 - PO sent to UO - CL | Complete | 950.49
2026-04-09 16:27:00 | Car Jeffway to renew 2041/1851 Garador Horizon garage door in white Up and over have already been out and quoted please provide after pictures BCC contact Luke Pomphrey |  | 2026-06-08 |  | Routine Repairs | 1164712 | 125 Barrow Road, Barton Hill | 70215/2 | New Works Instruction | ACE Agreed | 36/1289 |  | 35 days |  |  | Lainie Lavin | 29/05/2026 16:27 |  | Suspended: Awaiting asbestos info |  |  |  | 12/06 - WORKS COMPLETED 10/06 - Email sent to Up and Over for update - CL 29/05 - PO sent to UP & Over | Complete | 1417.36
2026-04-09 15:27:00 | Scaffold tower required up and around stack as per pictures to demolish stack and make good roof. |  |  |  | Routine Repairs | 1278826 | 183 Four Acres, Withywood | 82127/2 | New Works Instruction | ACE Agreed | 36/1263 |  | 35 days |  |  | Lainie Lavin | 29/05/2026 15:27 |  | Suspended: Awaiting Client Action/Response |  |  |  | 09/06- VO requested 28/05 - Quote requested from BS - CL 07/05 - Email sent to BS - CL | Held BCC | 3047.95
2026-04-09 11:21:00 | COMPLAINT WORKS - FOR CHARLOTTE SMART Lottie.Smart@bristol.gov.uk | 2026-06-04 09:30:00 | 2026-07-02 |  | Disrepair | 1237941 | 90 Willinton Road | 84946/1 | Works Started | ACE Agreed | 36/1286 | 2026-05-21 12:30:00 | 35 days |  |  | Shannon Slade | 29/05/2026 11:21 | No | Pre-completion Items To Complete |  |  |  | 26/06 - FF WERE UNABLE TO COMPLETE DUE TO ROTTED FLOORBOARDS. FLOORBOARDS BEING RENEWED 2ND JULY AND THEN FF TO REBOOK. 16/06 - FLOORING WORKS REMAINING. CHASER EMAIL SENT TO FF TO CONFIRM DATE. 08/06 - WORKS ALL COMPLETED. FLOORING WORKS ISSUED TO FF, WAITING FOR DATE. 13/05 - PART WORKS COMPLETED. GLOSSING WORKS TO BE COMPLETED 27TH MAY | WIP | 3224.43
2026-04-08 17:18:00 | Jeffway - As per Joe Cottrell - Lift and relay slabs and cut back shrubs - tenant to contact HO regarding drive due to tenants need with sister(not current tenant) | 2026-07-09 08:00:00 | 2026-07-09 |  | Routine Repairs | 1285774 | 81 Newland Road, Withywood | 85153/1 | Works Started | ACE Agreed | 36/1264 | 2026-05-14 08:00:00 | 35 days |  |  | Lainie Lavin | 28/05/2026 17:18 | No | Pre-completion Items To Complete |  |  |  | 02/06 - Awaiting quote to send WO as works far exceed description 18/5 - On held as awaiting update from chloe regarding vo ..15/05 - Meterage and spec needs altering SH to send VO to Emma and Chloe. | Appointment booked | 256.52
2026-04-08 17:18:00 | Jeffway - As per Joe Cottrell - Concrete repair to concrete slab area | 2026-06-16 12:00:00 |  | 2026-06-19 14:39:00 | Routine Repairs | 1253072 | 16 Lynton Road, Bedminster | 85150/1 | Works Completed | ACE Agreed | 36/1266 |  | 35 days |  |  | Lainie Lavin | 28/05/2026 17:18 |  | Post-completion Items To Complete | 2026-06-25 |  |  | 23/06 - AG Builders to attend next week to remove shuttering and cut expansions in - CL 22/06 - AG completed 19/06, completion photos requested - CL 16/06 - WORKS ISSUED TO A&G TO COMPLETE FRIDAY. 12/05 approval given continue with works 30/04 - VO sent to CM and EH for approval - CL 28/04 - Site visit arranged with tenant for SH to attend - CL | Complete | 1844.12
2026-04-08 17:18:00 | Jeffway - As per Joe Cottrell - Rebuild a block wall to rear garden - contractor to advise works needed for steps. |  |  |  | Routine Repairs | 1271825 | 9 Billand Close, Withywood | 85148/1 | New Works Instruction | ACE Agreed | 36/1267 |  | 35 days |  |  | Lainie Lavin | 28/05/2026 17:18 |  | Suspended: Awaiting Client Action/Response |  |  |  | 23/06 - Jeff Neck attending 23/0618/06 - Email sent to EH chasing VO - CL 08/06 - Awaiting approval for VO from EH sent on 04/06 - CL03/06 - Quote received from BS - CL 28/05 - Email sent to BS to provide a quote for the work required - CL | Cancelled | 3591.33
2026-04-08 15:48:00 | PRE INSPECT - Kitchen floor tiles are lifting. This is causing issues as tenant has mobility issues. She says she was told about a year ago that kitchen, and flooring would be replaced due to damp issues. |  |  |  | Routine Repairs | 1186056 | 19 Ripon Road, St Annes | 23868/1 | New Works Instruction | ACE Agreed | 36/1268 |  | 35 days |  |  | Lainie Lavin | 28/05/2026 15:48 |  | Pre-completion Items To Complete |  |  |  |  | Complete | 998.9
2026-04-08 11:45:00 | Complaint works - paint over black staining from old firs place. scrape and repaint bathroom ceiling from old leak | 2026-06-29 08:00:00 | 2026-06-29 | 2026-06-29 11:48:00 | Disrepair | 1288159 | 4 Rusham Sherrin Way | 84934/1 | Works Completed | ACE Agreed | 36/1284 |  | 35 days |  |  | Shannon Slade | 28/05/2026 11:45 |  | Pre-works Items To Complete |  | Yes |  | 30/06 - Works complete awaiting completion photos from operative - CL WORKS BOOKED FOR 29TH JUNE | Complete | 845.84
2026-04-08 09:01:00 | Scrape loose paint work in ground floor bathroom ceiling. Remove existing wall heater and apply plaster skim to side wall and window head. Apply anti condensation paint to completed ceiling and reskimmed wall. | 2026-07-29 12:00:00 | 2026-07-29 |  | Routine Repairs | 1289050 | 61 Sherrin Way | 24570/1 | Works Started |  | 36/1261 | 2026-06-12 12:00:00 | 35 days |  |  | Carlene Lynette Lynch | 28/05/2026 09:01 | No | Pre-completion Items To Complete |  |  |  | 02/07 - GF to to meet JN to attend property for Review - CL 25/06 - BCC CALLED TO RE-ARRANGE APPOINTMENT. SPOKE WITH TENANT AND REARRANGED FOR 29TH JULY AT TENANT REQUEST. 25/06 - Jeff to confirm with tenant above to be available and allow access to electrician George to call Jeff when on route - CL 23/06 - Email sent to JN for site visit to inspect electricals - CL 12/06 - Electrician attended to disconnect heater and found an issue with wiring. The property may need to be rewired - CL 07/05 - Variation request sent to JN and EH - CL 06/05 - Variations to be added and sent for approval following site visit from SH - CL 24/04 - Spoke with tenant, SH to attend and carry out site visit - CL 14/04 - Contact details updated. Email sent to CM | Appointment booked | 711.28
2026-04-07 16:46:00 | Jeff Way - FAO John O: Repair works to Floorboards, Plastering and decorating works | 2026-07-21 08:00:00 | 2026-07-21 |  | Routine Repairs | 1255443 | 16 Martock Crescent, Bedminster | 84531/1 | New Works Instruction | ACE Agreed | 36/1270 |  | 35 days |  |  | Lainie Lavin | 27/05/2026 16:46 |  | Pre-completion Items To Complete |  |  |  |  | Appointment booked | 486.11
2026-04-07 14:10:00 | Jeff Way - FAO John O - Renew trickle air vent to Window in bedroom 1 and overhaul vent in bathroom | 2026-06-12 08:00:00 | 2026-06-12 | 2026-06-12 07:47:00 | Routine Repairs | 1312045 | 10 Rowan House, Bishport Avenue | 84362/1 | Works Completed | ACE Agreed | 36/1271 | 2026-06-12 08:00:00 | 35 days |  |  | Lainie Lavin | 27/05/2026 14:10 | No | Pre-completion Items To Complete |  | Yes |  |  | Complete | 64.07
2026-04-07 12:04:00 |  | 2026-04-17 08:00:00 | 2026-04-17 |  | Urgent Repair | 1215641 | 25 Cossington Road |  | Works Started | Awaiting Cost Estimate | 36/1260 | 2026-04-17 08:00:00 | 5 days |  |  | Linda Maby | 13/04/2026 12:04 | No | Pre-completion Items To Complete | [5 empty] | 0.0
2026-04-07 09:12:00 | DISREPAIR WORKS | 2026-06-30 08:00:00 | 2026-07-07 |  | Disrepair | 1264411 | 18 ST JOHNS LANE | 39290/1 | Works Started | ACE Agreed | 36/1262 | 2026-06-04 11:30:00 | 35 days |  |  | Shannon Slade | 27/05/2026 09:12 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment confirmed with tenant - CL 29/09 - Unable to contact tenant, voicemail left and text sent - CL WIP - WORKS TO BE CARRIED ON 7TH JULY. | WIP | 1379.73
2026-04-02 16:00:00 | DN786139 RESPONSIVE REPAIRS OVERFLOW - JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 16/4/26 - 10 DAY PERIOD ENDS 30/4/26 | 2026-06-09 09:15:00 | 2026-06-09 | 2026-06-09 12:17:00 | Routine Repairs | 1021574 | 142 Long Cross, Lawrence Weston | 83660/3 | Works Completed | ACE Agreed | 36/1272 |  | 35 days |  |  | Lainie Lavin | 26/05/2026 16:00 |  | Pre-completion Items To Complete |  | No |  |  | Complete | 143.59
2026-04-02 11:38:00 | Repairs throughout property - | 2026-06-09 08:00:00 | 2026-07-10 |  | Disrepair | 1299736 | 24 Faber Grove | 83392/1 | New Works Instruction | ACE Agreed | 36/1283 |  | 35 days |  |  | Shannon Slade | 26/05/2026 11:38 |  | Pre-completion Items To Complete |  |  |  | 15/06- SCAFFOLD BEING ALTERED 22ND JUNE .EXTERNAL BOOKED WITH CONTRACTOR FOR THAT WEEK. INTERNALS REARRANGED DUE TO TENANT NOT BEING HOME - 10TH, 14TH AND 7TH JULY. 08/06 - NO ACCESS 8TH JUNE, WILL TRY AGAIN ON 9TH JUNE | Appointment booked | 7848.01
2026-04-02 11:36:00 | the window is currently nailed shut. | 2026-05-20 14:00:00 |  |  | Disrepair | 1209525 | 7 Alard Road | 83504/1 | Works Started |  | 36/1282 | 2026-05-20 14:00:00 | 35 days |  |  | Shannon Slade | 26/05/2026 11:36 | No | Pre-completion Items To Complete |  |  |  | 15/06 - WAITING FOR UPDATE FROM BCC REGARDING QUOTED WORKS. 19/05 - NO ACCESS IN APRIIL. WORKS BOOKED FOR 20TH MAY. 22/04 - APPOINTMENT ARRANGED FOR TUESDAY 28TH - 8.30AM | WIP | 208.22
2026-04-01 11:33:00 | Repairs throughout property | 2026-08-07 08:00:00 | 2026-07-27 |  | Disrepair | 1302507 | 43 Hareclive Road | 78797/1 | New Works Instruction | ACE Agreed | 36/1281 |  | 35 days |  |  | Shannon Slade | 22/05/2026 11:33 |  | Pre-completion Items To Complete |  |  |  | 25/06 - Unable to get hold of tenant, voicemail left to make contact to confirm appointments - CL | Appointment booked | 3028.13
2026-04-01 10:38:00 | Replacing window mounted unit; please report back if new glazing required: Jim Langford 07345 766709. Plus additional D&M works |  | 2026-07-15 |  | Disrepair | 1160130 | 34 Tyndall House Great Ann Street | 82848/1 | New Works Instruction | ACE Agreed | 36/1279 |  | 35 days |  |  | Shannon Slade | 22/05/2026 10:38 |  | Pre-completion Items To Complete |  |  |  | JWC AN ELECTRICIAN BOOKED FOR 15TH JULY | Appointment booked | 876.54
2026-03-30 17:20:00 | Jeff Way - As per Rob Doidge; Make safe to rear garden wall as per site visit with Steve, removal of up to 5 rows of blockwork in areas. photo sent with approx works. | 2026-05-05 10:15:00 |  | 2026-05-05 09:27:00 | Routine Repairs | 1306805 | 24 Mellent Avenue, Hartcliffe | 82604/1 | Works Completed | Invoiced | 36/1274 | 2026-05-01 08:00:00 | 35 days |  |  | Lainie Lavin | 20/05/2026 17:20 | Yes | Pre-completion Items To Complete | 2026-06-11 | Yes |  | 11/06 - KPI request sent - CL 06/05 - Awaiting photos from Dan W - CL 01/05 - Appointment rescheduled due to illness - CL 13/04 - Email sent to RD for VO - CL | Complete | 656.48
2026-03-30 17:00:00 | Jeff Way - Provide additional loft insulation to meet required standard as per John Oyeniyi. | 2026-05-11 08:00:00 |  | 2026-05-13 14:23:00 | Routine Repairs | 1303102 | 7 Hartgill Close, Hartcliffe | 82071/1 | Works Completed | Invoiced | 36/1273 |  | 35 days |  |  | Lainie Lavin | 20/05/2026 17:00 |  | Pre-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI received and uploaded. KPI requested - CL 13/05 - Works completed | Complete | 1013.35
2026-03-30 13:56:00 | Remove defective patch to Stairwell and allow for inspection prior to repair: Jim Langford 07345 766709 | 2026-05-08 08:00:00 |  |  | Disrepair | 1111780 | 67 GROSVENOR ROAD | 81819/1 | Works Started | ACE Agreed | 36/1257 | 2026-05-08 08:00:00 | 35 days |  |  | Shannon Slade | 20/05/2026 13:56 | No | Suspended: Awaiting asbestos info |  |  |  | 19/03- WORKS ON HOLD, WAITING FOR ASBESTOS REPORT. | Held BCC | 1579.87
2026-03-30 13:53:00 | Overhaul Kitchen/Bathroom linked system | 2026-05-13 08:00:00 |  |  | Disrepair | 1111780 | 67 GROSVENOR ROAD | 81814/1 | New Works Instruction | ACE Agreed | 36/1256 |  | 35 days |  |  | Shannon Slade | 20/05/2026 13:53 |  | Suspended: Awaiting asbestos info |  |  |  | 19/05 - JOB ON HOLD,WAITING FOR ASBESTOS REPORT. TASK ISSUED TO D&M TO BOOK FANS. | Held BCC | 88.08
2026-03-30 13:51:00 | Porch type Hall wall/floor join | 2026-05-08 12:00:00 |  |  | Disrepair | 1111780 | 67 GROSVENOR ROAD | 81809/1 | New Works Instruction |  | 36/1255 |  | 35 days |  |  | Shannon Slade | 20/05/2026 13:51 |  | Suspended: Awaiting asbestos info |  |  |  | 19/03 - JOB ON HOLD, WAITING FOR ASBESTOS REPORT. | Held BCC | 366.51
2026-03-30 13:39:00 | complaint works- please see email and report- Jeremy Price | 2026-06-09 12:00:00 |  |  | Disrepair | 1237827 | 74 Willinton Road | 81613/1 | New Works Instruction | ACE Agreed | 36/1254 |  | 35 days |  |  | Shannon Slade | 20/05/2026 13:39 |  | Pre-completion Items To Complete | [5 empty] | 2395.87
2026-03-30 11:59:00 | Take out Bath and rectify leak; refix; followed by extractor |  |  |  | Disrepair | 1264499 | 174 ST JOHNS LANE | 81885/1 | New Works Instruction | ACE Agreed | 36/1259 |  | 35 days |  |  | Shannon Slade | 20/05/2026 11:59 |  | Pre-completion Items To Complete | [5 empty] | 479.31
2026-03-30 11:36:00 | Bed4; Smallest bedroom overlooking the front elevation | 2026-07-17 12:00:00 | 2026-07-17 |  | Disrepair | 1280484 | 35 Gatehouse Close | 81835/1 | New Works Instruction |  | 36/1258 |  | 35 days |  |  | Shannon Slade | 20/05/2026 11:36 |  | Pre-completion Items To Complete |  |  |  | 15/06 - RAD TO BE CHANGED ON FRIDAY 19TH JUNE. WSG WORKS BOOKED FOR 11TH JUNE. TENANT HAS REFUSED PLASTERING WORKS AND DOESNT WANT RAD RENEWED, JUST REMOVED. EMAIL ISSUED TO BCC TO CONFIRM HOW TO MOVE FORWARD. | Appointment booked | 422.88
2026-03-30 11:00:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 9/4/26. 10 DAY PERIOD ENDS 23/4/26 | 2026-05-27 12:15:00 |  |  | Routine Repairs | 1304150 | 1 Herridge Road, Hartcliffe | 81716/3 | Works Cancelled | Works Cancelled | 36/1235 |  | 35 days | 4: Other | 2026-06-16 13:48:32 | Lainie Lavin | 20/05/2026 11:00 |  | Works Cancelled |  |  |  | 16/06 - Job cancelled by BCC - Cl 28/05 - Tenant informed LM that no longer exchanging, Email sent to EM & CM - CL | Cancelled | 143.59
2026-03-30 10:39:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 09/04/26. 10 DAY PERIOD ENDS 23/4/26 |  |  | 2026-04-27 14:11:00 | Routine Repairs | 1293078 | 386 Bishport Avenue, Hartcliffe | 81677/3 | Works Completed | Invoiced | 36/1236 |  | 35 days |  |  | Lainie Lavin | 20/05/2026 10:39 |  | Pre-completion Items To Complete | 2026-05-06 | Yes |  | 06/05 - KPI received and uploaded. KPI request sent - CL | Complete | 143.59
2026-03-30 10:36:00 | PD1 - Please carry out works as listed | 2026-05-14 08:00:00 |  |  | Disrepair | 1152734 | 121 LANSDOWNE COURT | 82120/1 | New Works Instruction | ACE Agreed | 36/1278 |  | 35 days |  |  | Shannon Slade | 20/05/2026 10:36 |  | Suspended: Awaiting asbestos info |  |  |  |  | Complete | 138.55
2026-03-30 10:33:00 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled | 2026-06-19 12:00:00 | 2026-06-19 |  | Disrepair | 1292655 | 326 Bishport Avenue, Hartcliffe | 82059/1 | New Works Instruction | ACE Agreed | 36/1277 |  | 35 days |  |  | Shannon Slade | 20/05/2026 10:33 |  | Pre-completion Items To Complete |  |  |  | 08/06 - PLASTERING BOOKED FOR 19TH JUNE. TENANT DOESN'T WANT DECS DONE AS SHE IS GOING TO DECORATE HERSELF WAITING FOR REPORT FROM CASA. | Appointment booked | 152.45
2026-03-30 10:32:00 | Follow on works; making good after Bathroom leak: See WO81885 |  | 2026-07-10 |  | Disrepair | 1264499 | 174 ST JOHNS LANE | 81899/1 | New Works Instruction | ACE Agreed | 36/1276 |  | 35 days |  |  | Shannon Slade | 20/05/2026 10:32 |  | Pre-completion Items To Complete |  |  |  | WORKS BOOKED FOR 10TH AND 15TH JULY | Appointment booked | 452.14
2026-03-30 10:29:00 | Kitchen 1.5 and Hall 1sqm; tanking added |  | 2026-07-10 |  | Disrepair | 1264499 | 174 ST JOHNS LANE | 81868/1 | New Works Instruction | ACE Agreed | 36/1275 |  | 35 days |  |  | Shannon Slade | 20/05/2026 10:29 |  | Pre-completion Items To Complete |  |  |  | 15/06 - WORKS BOOKED FOR 10TH AND 15TH JULY. GUTTER ISSUED TO CONTRACTOR | Appointment booked | 824.32
2026-03-30 08:35:00 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled | 2026-05-29 11:15:00 |  |  | Disrepair | 1191351 | 13A WYNDHAM CRESCENT | 81980/1 | Works Started | ACE Agreed | 36/1251 | 2026-05-29 11:15:00 | 35 days |  |  | Shannon Slade | 20/05/2026 08:35 | No | Suspended: Awaiting Client Action/Response |  |  |  | JWC WORKS ARE COMPLETED, ELECTRICIAN UNABLE TO FIT FAN ABOVE KITCHEN WINDOW DUE TO EXTERNAL CABLES JUST ABOVE WINDOW. ADVISE IS TO RUN DUCTING THROUGH KITCHEN STORE ROOM OVER 1M OF DUCTING 2X CORE HOLES. PLEASE LET ME KNOW HOW TO PROCEED? | Held BCC | 572.08
2026-03-30 07:59:00 | PD1 - Please carry out works as listed. | 2026-06-01 12:00:00 | 2026-06-18 |  | Disrepair | 1062346 | 17 MILLPOOL COURT | 76933/1 | Works Started | ACE Agreed | 36/1229 | 2026-05-26 09:00:00 | 20 days |  |  | Shannon Slade | 28/04/2026 07:59 | No | Pre-completion Items To Complete |  |  |  | READY TO BOOK, ATTEMPTED TO CALL TENANT NO ANWSER EMAIL SENT. TENANT CALLED BACK WORKS BOOKED FOR 26TH MAY AND 1ST OF JUNE. JWE 4TH JUNE. | Complete | 193.74
2026-03-27 15:19:00 | Jeffway-AS PER AARON WATKINS 07831121336 - FOA DARREN WHITCHURCH. REMAINING WORKS FOR PROPERTY, BOTH ORDER TO BE TREATED AS ONE. WORKS TO BATHROOM, LOUNGE REPAIRS, PAINTING |  |  | 2026-04-30 11:59:00 | Routine Repairs | 81481/1 | 26 Maynard Close, Hartcliffe | 81481/1 | Works Completed |  | 36/1237 |  | 35 days |  |  | Lainie Lavin | 19/05/2026 15:19 |  | Pre-completion Items To Complete | 2026-06-05 |  |  | 05/06 - KPI requested - CL 05/05 - RC to send completion photos - CL 28/04 - All works complete RC to carry out flooring on 29/04-30/04 - CL Works ongoing with NJE works expected to be complete 24/04 | Complete | 3938.49
2026-03-27 12:29:00 | Jeffway-AS PER DAVE PALMER - FAO DARREN WHITCHURCH, J WAY TO CARRY OUT WORKS AS DISCUSSED ON SITE, (TENANT RECHARGE ORDER) SEE NOTES FOR FURTHER INFORMATION |  |  | 2026-04-30 13:07:00 | Routine Repairs | 81386/1 | 26 Maynard Close, Hartcliffe | 81386/1 | Works Completed | ACE Agreed | 36/1239 |  | 35 days |  |  | Lainie Lavin | 19/05/2026 12:29 |  | Pre-completion Items To Complete | 2026-05-13 | Yes |  | 23/06 - KPI resent -CL 05/05 - Update needed from DW - CL Works on going with NJE on site, expecting completion - 24/04 speak with Darren on dates- 17/04 | Complete | 2410.75
2026-03-27 12:20:00 | JEFFWAY-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? TOM WALKER ATTENDING 03/04/26. 10 DAY PERIOD ENDS 17/04/26. | 2026-05-05 08:30:00 |  | 2026-05-05 09:23:00 | Routine Repairs | 1316605 | 15 Woodmead Gardens, Hartcliffe | 81319/3 | Works Completed | ACE Agreed | 36/1240 | 2026-05-05 10:04:00 | 35 days |  |  | Lainie Lavin | 19/05/2026 12:20 | Yes | Pre-completion Items To Complete | 2026-06-11 | Yes |  | 11/06 - KPI requested - CL 03/06 - EICR received and uploaded. Awaiting EICR - CL 06/05 - Awaiting EICR cert - CL | Complete | 143.59
2026-03-27 11:16:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 1/4/26. 10 DAY PERIOD ENDS 15/4/26 | 2026-06-25 12:00:00 | 2026-06-25 |  | Routine Repairs | 1316934 | 45 Wroughton Drive | 81266/2 | Works Cancelled | Works Cancelled | 36/1223 |  | 25 days | 3: Omitted from Contract | 2026-06-23 11:15:15 | Carlene Lynette Lynch | 05/05/2026 11:16 |  | Works Cancelled |  |  |  | EICR couldn't be completed, due to Error circuit 3 needs c.p.c reading lowering | Cancelled | 143.59
2026-03-27 11:12:00 | JEFFWAY-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR -TOM WALKER ATTENDING 13/04/26. 10 DAY PERIOD ENDS 27/04/26. | 2026-04-23 10:45:00 |  | 2026-04-23 14:48:00 | Routine Repairs | 1058420 | 19 Lanercost Road | 81242/3 | Works Completed | Invoiced | 36/1222 |  | 25 days |  |  | Carlene Lynette Lynch | 05/05/2026 11:12 |  | Fully Complete | 2026-05-22 |  |  |  | Complete | 143.59
2026-03-26 12:20:00 | Jeffway- as per Joe C-Scrape back loose paint prep surface and decorate - overhaul extractor and grill | 2026-06-17 08:00:00 | 2026-06-23 | 2026-06-23 07:44:00 | Routine Repairs | 1289583 | 45 Spartley Drive, Highridge | 64289/2 | Works Completed | ACE Agreed | 36/1246 | 2026-06-23 13:15:00 | 35 days |  |  | Lainie Lavin | 18/05/2026 12:20 | No | Pre-completion Items To Complete |  | No |  | 18/06 - Tenant refused access and wants BCC to reattend. Email sent to EH and CM. - CL | Complete | 444.94
2026-03-24 14:20:00 | Jeffway-Rob D-AS PER ROB DOIDGE - RENEWAL OF SMALL SKIRTING TO KIT CUPBOARD. MAKING GOOD TO BOTTOM OF WALLS AND HOLE IN LATEX FLOORING FIRST | 2026-06-08 12:15:00 | 2026-06-11 | 2026-06-11 11:45:00 | Routine Repairs | 1302994 | 557 Hareclive Road, Hartcliffe | 79995/1 | Works Completed | ACE Agreed | 36/1248 | 2026-06-11 08:00:00 | 35 days |  |  | Lainie Lavin | 14/05/2026 14:20 | No | Post-completion Items To Complete |  | Yes |  | 2804 - Follow on appointment booked for 11/06 - CL | Complete | 89.92
2026-03-24 13:59:00 | Jeffway-Jeff N-Repair water damage ceiling in living room and apply emulsion paint to complete ceiling. Lay new vinyl sheet cut to suit bathroom floor Note existing flooring removed. Fix PVC skirting to side of bath and new flooring. Throughout Property | 2026-05-01 12:00:00 | 2026-05-19 | 2026-05-19 17:14:00 | Routine Repairs | 1311757 | 53 Redwood House, Bishport Avenue | 15824/2 | Works Completed | ACE Agreed | 36/1249 | 2026-05-19 10:51:00 | 35 days |  |  | Lainie Lavin | 14/05/2026 13:59 | No | Pre-works Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI requested - CL 05/05 - Flooring sent to FF, awaiting appointment date. Tenant refused painting only allowed to treat areas - CL Paint and repair booked in for 1/5/26. Once completed, send FF and return jeffway to complete bath works. -23/4. 01/05 - TENANT HAS CONFIRMED | Complete | 431.64
2026-03-24 12:07:00 | PD1 - Please carry out works as listed | 2026-06-25 09:00:00 | 2026-06-25 |  | Disrepair | 1283085 | 5 KEBLE AVENUE | 79765/1 | New Works Instruction |  | 36/1238 |  | 35 days |  |  | Shannon Slade | 14/05/2026 12:07 |  | Pre-completion Items To Complete |  |  |  | 15/06 - DEHUM IN PLACE, PLASTERING COMPLETED. NEXT APPOINTMENT IN 16TH JUNE. 04/06 - WORKS BOOKED FOR DAN 10TH AND 11TH JUNE, CLAYTON 16TH AND 17TH JUNE, FLOORING 17TH AND 18TH JUNE. 27/05 - NA needs to be rebooked - CL | WIP | 2717.66
2026-03-24 09:29:00 | JEFF WAY - Fix new round plastic gully grill to drain on rear elevation . Apply stain block to water damage kitchen ceiling and repaint area. FAO JEFF NECK | 2026-06-03 08:00:00 | 2026-06-03 | 2026-06-03 11:45:00 | Routine Repairs | 1299032 | 1 Dyers Close, Hartcliffe | 79714/1 | Works Completed | ACE Agreed | 36/1245 | 2026-06-03 08:00:00 | 35 days |  |  | Lainie Lavin | 14/05/2026 09:29 | No | Fully Complete | 2026-06-11 | Yes |  | 11/06 - KPI requested - CL 24/04 - Unable to contact tenant, voicemail and text sent - CL | Complete | 122.88
2026-03-24 09:20:00 | JEFF WAY - Note tenant to lift bedroom and landing carpets to allow access to loose flooring. Secure loose floor board as shown by tenant. Overhaul sink and basin taps . Replace damage latch on living room door. FAO JEFF NECK BOOKED WITH JEFF NECK 9/3/26 8-11AM - CONFIRMED OVER PHONE Property | 2026-07-06 10:15:00 | 2026-07-06 |  | Routine Repairs | 4552447 | 10 Buttercup Walk, Ashton Vale | 35188/2 | New Works Instruction | ACE Agreed | 36/1244 |  | 35 days |  |  | Lainie Lavin | 14/05/2026 09:20 |  | Pre-completion Items To Complete |  |  |  | 03/07 - Unable to get hold of tenant, voicemail left - CL 04/06 - Na on 03/06, appointment rescheduled - CL 24/04 - Appointment booked for 03/06 - CL | Appointment booked | 122.0
2026-03-23 13:49:00 | JEFF WAY - Overhaul front and rear timber doors leave in working order. Fix new external vents grill fix over existing to prevent water ingress FAO JEFF NECK | 2026-06-03 10:30:00 | 2026-06-03 | 2026-06-03 08:06:00 | Routine Repairs | 1297172 | 41 Coleshill Drive, Hartcliffe | 79292/1 | Works Completed | ACE In Progress | 36/1243 | 2026-06-03 10:58:00 | 35 days |  |  | Lainie Lavin | 13/05/2026 13:49 | No | Pre-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI requested - CL | Complete | 475.81
2026-03-23 11:00:00 | Jeff Way - As per John Oyeniyi: Overhaul extractor fan, redecorate bathroom ceiling. | 2026-05-26 10:15:00 |  | 2026-05-26 11:20:00 | Routine Repairs | 1274857 | 15 Cornleaze, Withywood | 42565/2 | Works Completed | ACE Agreed | 36/1242 | 2026-05-27 13:30:00 | 35 days |  |  | Lainie Lavin | 13/05/2026 11:00 | No | Pre-completion Items To Complete | 2026-06-04 | Yes |  | 04/06 - KPI requested and VO sent - CL 30/04 - Fan booked in for 21/05. Compliance to arrange mould clean - CL | Complete | 429.25
2026-03-23 08:18:00 | PD1 - Please carry out works as listed |  | 2026-07-21 |  | Disrepair | 1057052 | 29 HOME GROUND | 79441/1 | New Works Instruction | ACE Agreed | 36/1233 |  | 20 days |  |  | Shannon Slade | 21/04/2026 08:18 |  | Suspended: Awaiting asbestos info |  |  |  | 16/06 - JWC AND GLAZING WORKS BOOKED FOR 21ST JULY AT TENANTS REQUEST 21/04 - SPOKE WITH TENANT WHO HAS CONFIRMED THAT SHE ISNT ALLOWED AT THE PROPERTY DUE TO AN INVESTIGATION. ASKED ME TO CALL HER BACK ON THE 11TH MAY. | Appointment booked | 383.53
2026-03-20 09:30:00 | Jeffway- John O-Renew Toilet bowl and cistern; and overhaul kitchen sink | 2026-06-03 08:00:00 | 2026-06-03 | 2026-06-03 12:41:00 | Routine Repairs | 1239981 | 17 Berchel House | 71497/2 | Works Completed | ACE Agreed | 36/1312 | 2026-06-03 08:00:00 | 35 days |  |  | Carlene Lynette Lynch | 12/05/2026 09:30 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL 23/04 - Asbestos report requested - CL | Complete | 410.12
2026-03-20 08:15:00 | Complaints work / KITCHEN: O/HAUL/RENEW EXTRACTOR FAN / BATHROOM: PAINT CEILING ONLY. 5 X WINDOWS NEED TO BE OVERHAULED NOT SPECIFIED | 2026-05-20 08:00:00 |  |  | Disrepair | 1271483 | 7 Arthurswood Road | 78802/1 | New Works Instruction | ACE Agreed | 36/1232 |  | 20 days |  |  | Shannon Slade | 20/04/2026 08:15 |  | Pre-completion Items To Complete |  |  |  | 08/6 - TENANT HAS CALLED TO SAY THAT THEY HAVE CANCER AND WILL BE IN HOSPITAL FOR A FEW WOOKS. REMOVED APPOINTMENTS AS TENANT DOESNT KNOW WHEN HE WILL BE HOME. | Held Tenant | 579.01
2026-03-20 08:08:00 | Complaints work / KITCHEN: O/HAUL / RENEW BASE UNITS, BOTH TAPS, GLASS AND O/H WINDOW FITTINGS, FIX HEAT DETECTOR. BATHOOM: RENEW FAN, REGLAZE WINDOW. HALL: FILL HOLE BY LIGHT SWITCH AND MATCH PAINT. EXTERNAL: CLEAN GUTTERING, | 2026-07-02 11:00:00 | 2026-07-08 |  | Disrepair | 1010771 | 248 BROADLANDS DRIVE | 78657/1 | New Works Instruction |  | 36/1231 |  | 20 days |  |  | Shannon Slade | 20/04/2026 08:08 |  | Pre-completion Items To Complete |  |  |  | 03/ 07 - DW attended to measure kitchen unit appointment booked to carry out 08/07 -13/07 - CL 01/07 - Variation request sent Darren booked in to attend on 02/07 to measure kitchen units. Works rescheduled with tenant for remedial work to be carried out on 08/07 and 09/07. Fan booked in to be installed on 13/07. Quote request sent to WSG and PO sent to Elite to carry out a gutter clean- CL 18/06 - WORKS REBOOKED FOR 16TH AND 17H JULY. 15/06 - OPERATIVE LEFT. WORKS CANCELLED. TO BE REBOOKED. 20/05 - WORKS BOOKED FOR 8TH AND 9TH JUNE | Appointment booked | 2259.69
2026-03-19 15:09:00 | Jeff Way - As per Jeff Neck: Works to living room, bedroom and bathroom as per email description. | 2026-05-07 08:00:00 |  | 2026-05-07 14:26:00 | Routine Repairs | 1313720 | 56 Tewther Road, Hartcliffe, Bristol | 77088/1 | Works Completed |  | 36/1219 |  | 25 days |  |  | Lainie Lavin | 24/04/2026 15:09 |  | Pre-works Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI request - CL 12/05- Invoice for completed works and kpi 11/5 - still awaiting confirmation of roof works (LL). 08/05 - Job now on hold awaiting confirmation roofing work has been completed by BCC - CL 14/04 - Appointment booked with tenant for fan install. Tenant is | Complete | 378.82
2026-03-19 14:11:00 | Complaint works- Damp Survey and works. |  |  | 2026-05-29 09:23:00 | Disrepair | 1180434 | 28 LEWIN STREET | 74589/1 | Works Completed | ACE Agreed | 36/1216 |  | 20 days |  |  | Shannon Slade | 17/04/2026 14:11 |  | Post-completion Items To Complete | 2026-06-16 |  |  | WORKS ISSUED TO TIMBERWISE, AWAITING DATE OF ATTENDNACE. 13/04 - CONFIRMED TO TENANT THAT BCC REQUIRE SECOND OPINION, WAITING FOR TIMBERWISE TO CONFIRM APPOINTMENT. 17/04 - WORKS ARRANGED WITH TENANT AND TIMBERWISE FOR 22ND APRIL.01/05 - TIMBERWISE ARE AT | Complete | 222.01
2026-03-19 12:32:00 | Jeff Way - As per Tom Walker: Patch skim living room ceiling | 2026-05-22 12:00:00 | 2026-05-22 | 2026-05-22 11:06:00 | Routine Repairs | 1306316 | 40 Maynard Close | 76745/1 | Works Completed |  | 36/1205 |  | 25 days |  |  | Shannon Slade | 24/04/2026 12:32 |  | Pre-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI requested - CL 24/04 - Appointment booed for the 11/05 - CL 07/04 - Asbestos reports received from CM and added to file. Email sent to TW chasing asbestos report. CM cc'd in - CL | Complete | 45.48
2026-03-19 12:31:00 | Jeffway-AS PER ROB DOIDGE - RENEWAL OF SILICON WHERE FALLING OUT / MISSING ON JOINT FROM SOFFIT AND WALL TO FRONT , REAR AND SIDE ELEVATIONS . REPOINT CEMENT FILLET FULL LENGTH FRONT ELEVATION AND WHERE CRACKED / BREAKING TO SIDE ELEVATION ALSO. REMOVAL OF WEEDS / GROWTH PRIOR TO RENEWING. | 2026-05-29 12:00:00 | 2026-05-29 |  | Routine Repairs | 1312705 | 22 SAMPSONS ROAD | 70565/2 | Works Started | ACE Agreed | 36/1204 | 2026-05-29 12:00:00 | 25 days |  |  | Shannon Slade | 24/04/2026 12:31 | No | Pre-completion Items To Complete |  |  |  |  | Complete | 304.18
2026-03-19 12:22:00 | Jeffway- as per John O-Overhaul windows; Paint Bathroom ceiling | 2026-06-10 14:00:00 |  | 2026-05-27 07:56:00 | Routine Repairs | 1281409 | 23 Hersey Gardens, Withywood | 70046/2 | Works Completed | Invoiced | 36/1203 | 2026-04-29 12:00:00 | 25 days |  |  | Shannon Slade | 24/04/2026 12:22 | No | Post-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI received and uploaded. KPI requested - CL 30/04 - Follow on appointment booked for 01/05 to complete electrical work - CL 16/04 - Asbestos report received and uploaded. Follow on appointments booked for 20/05 and 27/05 - CL | WIP | 529.75
2026-03-19 11:59:00 | Jeff Way - As per Tom Walker: Over board and plaster skim Kitchen ceiling | 2026-06-05 08:00:00 | 2026-06-05 | 2026-06-05 12:23:00 | Routine Repairs | 1279501 | 34 Four Acres Close, Withywood | 59378/4 | Works Completed | ACE Agreed | 36/1391 | 2026-06-05 09:23:00 | 35 days |  |  | Lainie Lavin | 11/05/2026 11:59 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL | Complete | 194.22
2026-03-19 08:02:00 | Disrepair - repairs throughout property - DN786139 - Responsive Repairs Overflow | 2026-06-05 08:00:00 |  |  | Disrepair | 1302187 | 42 Grinfield Avenue | 77090/1 | Works Started | ACE Agreed | 36/1230 | 2026-05-29 08:00:00 | 20 days |  |  | Shannon Slade | 17/04/2026 08:02 | No | Pre-completion Items To Complete |  |  |  | 15/06 - TILE UPDATED WAITING FOR UPDATE FROM JAMIE REGARDING IN HOUSE TEAM. 08/06 - OPERATIVE(PLUMBER) NEEDS TO RETURN TO ADDRESS AIR LOCK IN PIPES. WORKS BOOKED FOR 29TH MAY, 3RD JUNE AND 5TH JUNE | WIP | 644.16
2026-03-19 07:54:00 | Fill all cracks in kitchen | 2026-06-10 09:30:00 | 2026-06-29 | 2026-05-07 14:48:00 | Disrepair | 1093829 | 41 MONTREAL AVENUE | 76659/1 | Works Completed | ACE Agreed | 36/1227 | 2026-05-07 08:00:00 | 20 days |  |  | Shannon Slade | 17/04/2026 07:54 | No | Pre-completion Items To Complete |  | Yes |  | 30/06 - NA on 29/06 not carded - CL | WIP | 131.0
2026-03-19 | Complaint - Please carry out works as listed. | 2026-05-22 12:00:00 | 2026-07-01 | 2026-07-01 07:47:00 | Disrepair | 1106123 | 25 Burnell Drive, St Pauls | 53830/2 | Works Completed |  | 36/1228 |  | 20 days |  |  | Shannon Slade | 17/04/2026 00:00 |  | Pre-works Items To Complete |  | Yes |  | 29/06 - Appointment confirmed with tenant - CL 15/06 - TENANT WASNT HOME ON PREVIUS APPOINTMENT, WORKS REBOOKED FOR 30TH JUNE. 08/06 - REMAINING WORKS BOOKED FOR 10TH JUNE. ALONGSIDE ELECTRICIAN. 13/05 - D&M TREATMENT COMPLETED, WORKS BOOKED FOR 22ND MAY. | Complete | 1415.54
2026-03-18 12:18:00 | JEFF WAY - AS PER ROB D: FOLLOWING LEAK/ WATER ISSUE ABOVE. STAINBLOCK & REPAINT TO MATCH EXISTING THE AREAS OF CEILING/ WALLS TO MIDDLE BEDROOM & HALL CUPBOARD. ALLOWED FOR 4M2 BUT SMALLER AREA. CONCRETE CEILINGS WITH SKIM | 2026-04-22 08:00:00 |  | 2026-04-22 08:24:00 | Routine Repairs | 1307477 | 44 MIDDLEFORD HOUSE | 43025/2 | Works Completed | Invoiced | 36/1202 | 2026-04-23 08:00:00 | 25 days |  |  | Shannon Slade | 23/04/2026 12:18 | Yes | Pre-completion Items To Complete | 2026-04-28 | Yes |  | 29/04 - KPI received and uploaded - CL 28/04 - KPI request sent - CL 20/04 - Appointment booked for 22/04, email sent to RD informing him of the appointment - CL | Complete | 100.04
2026-03-18 10:51:00 | Jeffway-: AS PER ROB D - FOLLOWING LEAK FROM ABOVE FLAT, NOW FIXED. REDECORATE AFFECTED AREAS OF KIT AND BATHROOM WALLS / CEILINGS AS REQUIRED. MATCH IN PAINT COLOURS. APPROX 14M2 TOTAL AREA | 2026-06-25 12:00:00 | 2026-06-25 | 2026-06-25 09:32:00 | Routine Repairs | 1251350 | 13 LITTLECROSS HOUSE | 58367/2 | Works Completed | ACE Agreed | 36/1200 | 2026-04-29 12:00:00 | 25 days |  |  | Shannon Slade | 23/04/2026 10:51 | No | Pre-completion Items To Complete |  | Yes |  | 06/05 - Contact details requested as number supplied is incorrect - CL | Complete | 271.34
2026-03-18 08:29:00 | Repairs to ceiling cracks and external wall insulation - some additional minor works | 2026-05-05 09:00:00 | 2026-06-22 |  | Disrepair | 1313300 | 60 Stillingfleet Road | 63929/1 | New Works Instruction | ACE Agreed | 36/1234 |  | 20 days |  |  | Shannon Slade | 16/04/2026 08:29 |  | Pre-completion Items To Complete |  |  |  |  | Appointment booked | 2069.49
2026-03-17 10:45:00 | Jeffway - As Per Rob D - Various works to downstairs WC (see email sent with full job description 17.03.2026) - DOWNSTAIRS WC, HACK OFF LOOSE PLASTER TO WC WALL AND WINDOW WALL AS REQUIRED AND REPLASTER, HAVE ALLOWED FOR 2M2 BUT UNKNOWN TOTAL AMOUNT. HAVE ALLOWED FOR WC TO COME OFF TOO. RENEW LATEX TO FLOOR IN WC ALSO. OVERHAUL WC CISTERN AND ALSO REPAIR FLOORBOARD TO CORNER OF BACK BEDROOM WHERE MISSING | 2026-05-19 12:00:00 | 2026-06-12 | 2026-06-12 13:22:00 | Routine Repairs | 1278382 | 88 Four Acres | 75911/1 | Works Completed | ACE Agreed | 36/1199 | 2026-05-19 16:15:00 | 25 days |  |  | Shannon Slade | 23/04/2026 10:45 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL 30/04 - Follow on appointment confirmed with tenant for 19/05 - CL | Complete | 498.85
2026-03-17 07:51:00 | Kitchen works- replace missing plinth, install extractor in current vent hole and refit loose dummy draw front. | 2026-06-08 08:00:00 |  | 2026-06-08 12:36:00 | Disrepair | 1297707 | 8 Crosscombe Drive | 75900/1 | Works Completed | ACE Agreed | 36/1226 | 2026-06-08 08:00:00 | 20 days |  |  | Shannon Slade | 16/04/2026 07:51 | No | Pre-completion Items To Complete |  | Yes |  | 15/04 - FAN WORKS BOOKED FOR 12.30PM 15TH APRIL. | Complete | 472.37
2026-03-16 10:26:00 | Jeff Way - as per John Oyeniyi: Redecoration works to wall and kitchen in bathroom, mould wash ceiling in kitchen. | 2026-06-26 12:00:00 | 2026-06-26 | 2026-06-26 10:44:00 | Routine Repairs | 1249509 | 15 HOLLIDGE GARDENS | 35087/4 | Works Completed | ACE Agreed | 36/1198 | 2026-06-01 12:30:00 | 25 days |  |  | Shannon Slade | 22/04/2026 10:26 | No | Pre-completion Items To Complete |  | Yes |  | 30/06 - Awaiting completion photos - CL 25/06 - Appointment confirmed with tenant - CL 21/04 - Follow on appointment booked for 11/05 - CL | Complete | 215.2
2026-03-13 07:46:00 | Complaints work / BATHROOM: REMOVE AND REPLACE CEILING, REDECORATE ENTIRE ROOM, O/H FAN, REPLACE PANEL WITH PVC, RENEW CISTERN, RENEW VINYL FLOOR, REPLACE SEALANT ON BASIN & BATH | 2026-06-30 13:00:00 | 2026-07-02 |  | Disrepair | 1282877 | 35 INNOX GARDENS | 74551/1 | Works Started | ACE Agreed | 36/1225 | 2026-06-30 13:00:00 | 20 days |  |  | Shannon Slade | 14/04/2026 07:46 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Toilet frame and bath panel complete. Manger needs to review outstanding work needed - CL 01/07 - Appointment confirmed with tenant - CL 30/06 - Unable to contact, voicemail left - CL 29/06 - Appointment confirmed with tenant - CL WAITING FOR JOB SHEET. | Manager review needed | 849.98
2026-03-13 07:24:00 | Complaint works- Snags to be undertaken | 2026-04-28 08:00:00 | 2026-07-16 |  | Disrepair | 1299667 | 17 FABER GROVE | 74490/1 | Works Started | ACE Agreed | 36/1224 | 2026-04-28 09:00:00 | 20 days |  |  | Shannon Slade | 14/04/2026 07:24 | No | Pre-completion Items To Complete |  |  |  | 16/06 - INSULATION BOOKED FOR 16TH JUL. 19/05 - ALL OTHER WORKS COMPLETED, INSULATION BOOKED FOR 22ND MAY. 22/04 - WORKS BOOKED FOR 28/04. | Appointment booked | 175.72
2026-03-12 14:06:00 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled | 2026-05-12 14:15:00 |  | 2026-05-12 11:40:00 | Disrepair | 1311837 | 61 Redwood House | 74058/1 | Works Completed | Invoiced | 36/1215 | 2026-05-12 12:00:00 | 20 days |  |  | Shannon Slade | 13/04/2026 14:06 | No | Fully Complete | 2026-06-11 |  |  | 05/06 - EMAIL ISSUED TO LOTTIE TO SEE IF WE CAN OMIT PAINTING AND SIGN OFF. 19/03 - WORKS COMPLETED AS FAR AS WE CAN GO. EMAIL ISSUED TO LOTTIE, AS TENANT DIDNT WANT PAINTING TO BE COMPELTED AND DOMESTIC DRAINS NEED TO ATTEND, WAITING FOR RESPONSE. WORKS BOOKED FOR 12TH MAY | Complete | 50.0
2026-03-12 13:13:00 | Complaints work / ROOFING / INSULATION |  |  | 2026-03-30 13:16:00 | Disrepair | 1237941 | 90 Willinton Road | 74294/1 | Works Completed | Invoiced | 36/1253 |  | 35 days |  |  | Shannon Slade | 05/05/2026 13:13 |  | Fully Complete | 2026-04-02 | Yes |  |  | Complete | 2899.29
2026-03-11 14:01:00 | Part of planned works. please speak with James Bailey if any questions. *DO NOT CALL TENANT* |  |  |  | Disrepair | 1014557 | 1 Failand Crescent (KS1985) | 73519/1 | New Works Instruction | ACE Agreed | 36/1214 |  | 20 days |  |  | Shannon Slade | 10/04/2026 14:01 |  | Suspended: Awaiting Client Action/Response |  |  |  | 02/07 - awaiting order from BCC for decorating 30/06 - All work completed - CL WAITING FOR PLANNED TO GIVE ME DATES |  | 6297.22
2026-03-10 10:13:00 | AS PER GERRY RYAN - PLM to remove cistern and hand basin, pla to skim damage walls and renew tiles to the basin and tap end of bath - dec to paint bahtroom and paint not emulsion ele to over haul bathroom | 2026-06-25 08:00:00 | 2026-06-25 | 2026-06-25 07:42:00 | Routine Repairs | 1224937 | 6 LAMBERT PLACE | 69916/1 | Works Completed | ACE Agreed | 36/1196 | 2026-06-25 08:00:00 | 25 days |  |  | Shannon Slade | 16/04/2026 10:13 | No | Pre-completion Items To Complete |  | Yes |  | 23/06 - Unable to get hold of tenant, voicemail left - CL | Complete | 860.77
2026-03-09 09:52:00 | JEFFWAY - Install Vent cover on extractor fan; skim wall around extractor fan and overhaul extractor fan - John Oyeniyi | 2026-04-16 13:45:00 |  | 2026-04-16 08:40:00 | Routine Repairs | 1271870 | 14 Billand Close, Withywood | 72398/1 | Works Completed | Invoiced | 36/1194 | 2026-03-25 08:00:00 | 15 days |  |  | Carlene Lynette Lynch | 30/03/2026 09:52 | No | Pre-completion Items To Complete | 2026-04-28 | Yes |  | 30/04 - KPI received and uploaded - CL 28/04 - KPI requested - CL | Complete | 160.02
2026-03-06 13:55:00 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled | 2026-05-08 08:00:00 | 2026-06-22 | 2026-06-22 15:51:00 | Disrepair | 1245325 | 72 Dunkerry Road | 71961/1 | Works Completed | ACE Agreed | 36/1213 | 2026-05-08 08:00:00 | 20 days |  |  | Shannon Slade | 07/04/2026 13:55 | No | Pre-completion Items To Complete |  | Yes |  | 12/06 - WORKS BOOKED FOR ELECTRICIAN AND MULTI TO ATTEND 22ND JUNE. TENANT HAS MENTIONED FLOORING ISSUES WHICH ISNT ON THE ORDER. 20/05 - TENANT IS ON HOLIDAY AND GOING TO CALL WHEN SHES BACK. SCAFFOLDING BEING ERECTED 4TH MAY, SITE VISIT 6TH MAY, ELECTRICAL WORKS BOOKED FOR 7TH MAY AND INTERNAL DECORATING BOOKED FOR 8TH MAY. RENDER WORKS TO BE BOOKED FOLLOWING SITE VISIT. | Complete | 2694.01
2026-03-06 13:51:00 | Complaint works- living room,kitchen and bathroom. scrape off peeling paint on walls seal and repaint. replace glass units in livingroom. treat pipes in bathroom, replace broken down pipe | 2026-07-27 12:00:00 | 2026-07-27 |  | Disrepair | 1312750 | 32 Sampsons Road, Hartcliffe | 71807/1 | New Works Instruction | ACE Agreed | 36/1212 |  | 20 days |  |  | Shannon Slade | 07/04/2026 13:51 |  | Pre-completion Items To Complete |  |  |  | 19/03 - INCOMPLETE WORKS SCHEULED TO BE COMPELTED 15TH JUNE. | Appointment booked | 954.72
2026-03-06 12:06:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 12/3/26. 10 DAY PERIOD ENDS 26/3/26 | 2026-05-20 12:00:00 |  | 2026-05-20 12:02:00 | Routine Repairs | 1276499 | 85 Dangerfield Avenue | 71960/3 | Works Completed | ACE Agreed | 36/1193 |  | 15 days |  |  | Shannon Slade | 27/03/2026 12:06 |  | Suspended: Awaiting asbestos info |  | No |  |  | Complete | 143.59
2026-03-05 13:41:00 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled | 2026-05-05 09:15:00 |  | 2026-05-21 07:41:00 | Disrepair | 1249850 | 23 HOLROYD HOUSE | 71310/1 | Works Completed | Invoiced | 36/1210 |  | 20 days |  |  | Shannon Slade | 02/04/2026 13:41 |  | Fully Complete | 2026-05-29 |  |  | 19/03 - WORKS BOOKED FOR 21ST MAY. | Complete | 467.73
2026-03-05 13:38:00 | COMPLAINT AS PER CHARLOTTE SMART- Various works required please advise when this is scheduled | 2026-05-07 09:00:00 | 2026-06-05 | 2026-06-05 14:51:00 | Disrepair | 1308129 | 38 MILLMEAD HOUSE | 71309/1 | Works Completed | ACE Agreed | 36/1209 |  | 20 days |  |  | Shannon Slade | 02/04/2026 13:38 |  | Pre-completion Items To Complete |  | No |  | WORKS BOOKED FOR 6TH AND 7TH OF MAY | Appointment booked | 934.26
2026-03-05 11:24:00 | Jeff Way - As per John Oyeniyi: Redecorate Kitchen ceiling; Part of wall and Living Room Ceiling | 2026-07-14 08:00:00 | 2026-07-14 |  | Routine Repairs | 1282082 | 20 Hills Barton | 61846/2 | New Works Instruction | ACE Agreed | 36/1192 |  | 15 days |  |  | Shannon Slade | 26/03/2026 11:24 |  | Pre-completion Items To Complete |  |  |  | 18/06 - Needs a follow on appointment to paint 20M2 ceiling. Vo needed- CL 05/06 - Appointment rescheduled with tenant - CL 04/06- NA on 04/06, unable to make contact with tenant, voicemail left - CL | WIP | 357.58
2026-03-04 13:36:00 | PD1 - Please carry out works as listed | 2026-04-23 14:00:00 |  | 2026-05-01 13:48:00 | Disrepair | 1229885 | 12 POYNTZ ROAD | 70931/1 | Works Completed | ACE Agreed | 36/1208 |  | 20 days |  |  | Shannon Slade | 01/04/2026 13:36 |  | Pre-completion Items To Complete |  | No |  | WORKS BOOKED FOR 23RD APRIL. FLOORING ISSUED TO FF. 24/04 - FLOORING WORKS TO BE COMPLETED TODAY, PLUMBER ATTENDING DUE TO LEAK UNDER SINK. TENANT HAS GONE MENTAL REGARDING KITCHEN WORKS? 12/05 - FF HAS ATTEMPTED TO GAIN ACCESS ON TWO OCCASIONS WITH NO SU | Complete | 487.38
2026-03-04 10:43:00 | JEFF WAY - Prime and oil paint (Gloss) Kitchen exit door ( external face), improve loft insulation FAO JOHN OYENIYI | 2026-04-10 12:00:00 |  | 2026-04-10 07:39:00 | Routine Repairs | 1305584 | 7 LUCKLEY AVENUE | 38618/2 | Works Completed | Invoiced | 36/1190 | 2026-04-10 12:00:00 | 15 days |  |  | Shannon Slade | 25/03/2026 10:43 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL | Complete | 347.7
2026-03-03 10:35:00 | Jeffway - replace concrete outside front door creating gradient so water flows towards aco drain. Fit x1 gully cover and clear/clean aco drain. Melissa Edwards 07442675013 |  |  | 2026-04-13 14:04:00 | Routine Repairs | 1204633 | 58 Showering Road, Stockwood, Bristol BS14 8DN | 6011/2 | Works Completed | Invoiced | 36/1189 | 2026-04-13 11:54:00 | 15 days |  |  | Shannon Slade | 24/03/2026 10:35 | No | Suspended: Awaiting asbestos info | 2026-04-15 | Yes |  | 28/05 - Amended KPI received and uploaded - CL 28/04 - KPI received and uploaded - CL 15/04 - KPI requested - CL 27/02 - Awaiting date from contractor - CL Extra SORs required as per Darrens conversation with ME. works in progress 13/04 | Complete | 1576.64
2026-03-02 13:31:00 | Please carry out disrepair works as listed. |  |  |  | Disrepair | 1091550 | 48 LANDSEER AVENUE | 42065/2 | Works Cancelled | Works Cancelled | 36/1207 |  | 20 days | 4: Other | 2026-06-25 08:20:59 | Shannon Slade | 30/03/2026 13:31 |  | Suspended: Awaiting asbestos info |  |  |  |  | Cancelled | 4316.2
2026-03-02 10:27:00 | Jeffway- as per John O-Renew elbow joint to shower drain pipe on the Rear Elevation, overhaul windows, Renew lead flashing to entrance canopy & other works. Renew water cistern, pvc trims to window cill, tile up splashback above bath, and renew bath panel Renew bend to shower waste pipe BEDROOM 1 - Overhaul Tilt turn mechanism to window BATHROOM - Fix new glazed tiles on wall above bath to ceiling BATHROOM - Renew Bath Panel KITCHEN - Renew friction stay to window BATHROOM - Mould wash and paint damp stains on ceiling and wall by window BEDROOMS ,Provide PVCu cill to all 3nos Bedroom windows... Bedroom 1, 2 and 3, measuring 2m each making 6m in total | 2026-06-09 10:15:00 | 2026-06-25 | 2026-05-29 08:55:00 | Routine Repairs | 1288999 | 55 SHERRIN WAY | 63719/2 | Works Completed | Invoiced | 36/1183 | 2026-05-26 08:00:00 | 15 days |  |  | Shannon Slade | 23/03/2026 10:27 | No | Post-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI received and uploaded. KPI requested - CL | Complete | 1191.55
2026-03-02 08:25:00 | JEFFWAY to carry out off peak rewire - requested by Ciaran O'Bern - any issues please email ciaran.o'bern@bristol.gov.uk |  |  |  | Routine Repairs | 1143277 | 63 CROYDON STREET | 70043/1 | New Works Instruction | ACE Agreed | 36/1188 |  | 15 days |  |  | Shannon Slade | 23/03/2026 08:25 |  | Suspended: Awaiting asbestos info |  |  |  |  | Awaiting asbestos report | 7235.17
2026-03-02 08:13:00 | Jeffway- As per Joe C-Remove toilet/overhaul and investigation on water leak near soil pipe | 2026-03-24 09:45:00 |  | 2026-03-24 14:09:00 | Routine Repairs | 1226717 | 2 MORPETH ROAD | 60921/2 | Works Completed | Invoiced | 36/1186 | 2026-03-24 09:45:00 | 15 days |  |  | Shannon Slade | 23/03/2026 08:13 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 16/04 - KPI received and uploaded - CL 15/04 - KPI request sent - CL | Complete | 214.05
2026-03-02 08:08:00 | Jeffway-AS PER ROB DOIDGE - REMOVE / REFIX CORNER KITCHEN BASE UNIT TO TREAT, STERILIZE AND PAINT MOULD TO CORNER EXTERNAL WALL. APPROX 2M2 FROM TNTTS DESCRIPTION | 2026-04-28 08:00:00 |  |  | Routine Repairs | 1277254 | 13 ELVARD ROAD | 34655/2 | Works Cancelled | Works Cancelled | 36/1185 |  | 15 days | 1: Refusal | 2026-06-03 09:05:21 | Shannon Slade | 23/03/2026 08:08 |  | Works Cancelled |  |  |  | 29/05 - Tenant Doesnt us to remove new kitchen units, not willing to sign disclaimer. email sent to RD | Cancelled | 98.68
2026-03-02 07:45:00 | Jeffway- as per Jeff N- Apply mould wash to side of PVC windows in front and rear bedrooms. Overhaul all PVC windows. Cut and fix plasterboard across existing window cills and clad over in in PVC cill to form insulation bridge Fix new fan in external bathroom wall. | 2026-06-01 14:15:00 | 2026-06-03 | 2026-06-03 16:29:00 | Routine Repairs | 1280075 | 213 GATEHOUSE AVENUE | 29066/2 | Works Completed |  | 36/1184 |  | 15 days |  |  | Shannon Slade | 23/03/2026 07:45 |  | Suspended: Awaiting asbestos info | 2026-06-04 |  |  | 04/06 - VO sent to JN and EH - CL 11/05 - Awaiting photos of complete work from JS. Appointment to be scheduled once vents come in - CL Sent to compliance to carry out the mould wash and fan installation. Will book remaining work once appointment confirmed. Asbestos report request sent to | Complete | 1037.12
2026-02-27 10:18:00 | Jeffway-as per John O-Repair to Plasterboard ceiling in Kitchen, Refix Handrails to wall, Overhaul 3nos door, Renew loft hatch | 2026-06-19 12:00:00 |  |  | Routine Repairs | 1240171 | 72 Birch Road, Southville, Bristol BS3 1PF | 65004/2 | Works Started | ACE Agreed | 36/1181 | 2026-04-14 13:00:00 | 15 days |  |  | Shannon Slade | 20/03/2026 10:18 | No | Pre-completion Items To Complete |  |  |  | 23/06 - NA on 19/6, tenant said she will make contact to arrange another appointment once she knows her work rota, email sent to JO - CL 16/04 - Asbestos report received and uploaded - CL 15/04 - Asbestos report requested. Decs booked in for 21/05 - CL | Awaiting appointment date | 673.06
2026-02-27 10:15:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. JOE COTTRELL ATTENDING 4/3/26. 10 DAY PERIOD ENDS 18/3/26 | 2026-05-21 12:00:00 |  | 2026-05-21 14:53:00 | Routine Repairs | 695 | 58 Ashton Rise | 69267/2 | Works Completed | ACE Agreed | 36/1180 | 2026-05-21 14:53:00 | 15 days |  |  | Shannon Slade | 20/03/2026 10:15 | No | Pre-works Items To Complete | 2026-06-04 |  |  | 03/06 - EICR received and uploaded - CL 06/05 -Appointment booked with tenant for 21/05 - CL Updated details received from BCC 15/04 - No Access - 16/04Tenant not answering calls. Attempted to call , no answer - 27/4 & 28/4 (LL). Sent to surveyor, BCC emailed now awaiting call from tenant, up | Complete | 143.59
2026-02-27 10:14:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. JOE COTTRELL ATTENDING 03/03/26. 10 DAY PERIOD ENDS 17/03/26 |  | 2026-03-11 | 2026-03-13 08:50:00 | Routine Repairs | 1290217 | 12 TURTLEGATE AVENUE | 69136/3 | Works Completed | Invoiced | 36/1179 |  | 15 days |  |  | Shannon Slade | 20/03/2026 10:14 |  | Pre-completion Items To Complete | 2026-03-16 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 143.59
2026-02-27 09:25:00 | Complaint works- Replace both extractor fans. overhaul and repair windows through out. repair / replace door lock. replace fence panels. | 2026-05-11 08:00:00 |  | 2026-06-01 12:17:00 | Disrepair | 1214364 | 4 CLONMEL ROAD | 69496/1 | Works Completed |  | 36/1176 | 2026-05-07 11:15:00 | 20 days |  |  | Shannon Slade | 27/03/2026 09:25 | No | Post-completion Items To Complete | 2026-06-12 |  |  | 19/03 - FENCING AND ELECTRICAL WORKS COMPLETED. INTERNAL WORKS BOOKED FOR 1ST OF JUNE. ELECTRICAL WORKS ISSUED TO JWE - WAITING FOR DATE. EXTERNAL WORKS BOOEKD FOR 7TH MAY AND INTERNALS FOR 8TH MAY | Complete | 1747.59
2026-02-27 09:20:00 | Disrepair - property repairs throughout - DN786139 - Responsive Repairs Overflow | 2026-07-28 08:00:00 | 2026-07-20 |  | Disrepair | 1285309 | 19 MOW BARTON | 69288/1 | New Works Instruction | ACE Agreed | 36/1175 |  | 20 days |  |  | Shannon Slade | 27/03/2026 09:20 |  | Pre-completion Items To Complete |  |  |  | 16/06 - WORKS BOOKED FOR 20TH, 21ST, 23RD 24TH AND 28TH JULY. SCAFFOLD ERECTED. | Appointment booked | 3230.79
2026-02-27 08:58:00 | Complaint disrepair works : guttering clear water ways. Front elevation inspect and renew gully cover on front. Bathroom reseal joint in the waste pipe | 2026-06-25 13:00:00 | 2026-07-08 |  | Disrepair | 1267103 | 24 Warden Road | 69097/1 | New Works Instruction | ACE Agreed | 36/1174 |  | 20 days |  |  | Shannon Slade | 27/03/2026 08:58 |  | Pre-completion Items To Complete |  |  |  | 26/06 - TOP COAT OF PLASTERING BEING COMPLETED 8TH JULY AND PAINTING 13TH JULY. ROOF WORKS ARE COMPLETED. 16/06 - DARREN IS COMPLETING INSPECTION TODAY. 22/04 - DARREN IS SOR'S UP ROOFING WORKS TO ISSUE TO LOTTIE | WIP | 6604.52
2026-02-26 08:45:00 | Description: Complaint works- Hall water stain repaint. kitchen plinths refit. overhaul back door. refit rad in livingroom. replace blown DG units. | 2026-05-14 08:00:00 |  |  | Disrepair | 1217681 | 14 DELIUS GROVE | 68852/1 | Works Started | ACE Agreed | 36/1173 | 2026-05-14 08:00:00 | 20 days |  |  | Shannon Slade | 26/03/2026 08:45 | No | Suspended: Awaiting Client Action/Response |  |  |  | 16/06 - JWC WORKS COMPLETED. SPOKE WITH TENANT REGARDING OUTSTANDING GLAZING WORKS AND SHE IS VERY POORLY. SHE IS GOING TO CONTACT WSG REGARDING GETTING A DATE. 15/05 - WORKS ISSUED TO GLAZING COMPANY. CARPENTER BOOKED FOR 27TH MAY TO COMPLETE PLINTHS AND OVERHAUL OF FRONT DOOR. | Held BCC | 678.98
2026-02-24 09:25:00 | Remove loose artex from ceilings to make safe, leave clean and tidy. Living Room and main Bedroom - and check for other areas. Leave cracks for inspection. Call Jo P any issues or concerns after removal | 2026-04-02 13:30:00 |  | 2026-04-02 14:48:00 | Routine Repairs | 1290524 | 5 TURTLEGATE WALK | 67952/1 | Works Completed | Invoiced | 36/1165 | 2026-04-02 14:48:00 | 15 days |  |  | Shannon Slade | 16/03/2026 09:25 | No | Post-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL 07/04 - Email sent requesting JP availability and asbestos report requested - CL works completed, awaiting visit from BCC before carrying on. job placed on hold until outcome received | Complete | 262.0
2026-02-24 08:27:00 | Complaint work- Re render the back of the house., Cupboard/ store room over board and insulate walls and ceiling. bedroom install skirting. bathroom replace extractor. 2 dg units to replace in property. | 2026-04-01 08:00:00 |  |  | Disrepair | 1264535 | 240 ST JOHNS LANE | 63225/1 | Works Started | Invoiced | 36/1172 | 2026-04-01 08:00:00 | 20 days |  |  | Shannon Slade | 24/03/2026 08:27 | No | Pre-completion Items To Complete |  |  |  | 30/06 - Fan and fascia cut hole completed - CL 15/06 - ALL JWC WORKS COMPELTED, CHASED MARK FOR UPDATE ON FLOORING.JWE AND CLAYTON BOOKED TO COMPLETE ELECTRICAL WORKS ON 29TH JUNE. 13/05 - WAITING FOR FF TO CONFIRM DATE OF ATTEDNANCE/ SCAFFOLDING BEING ERECTED 19TH MARH - RENDERING BOOKED FOR 20TH MARCH. PAINTING BOOKED FOR 20TH MARCH. 30/03 - EXTERNAL WORKS COMPLETED, INTERNAL WORKS BOOKED FOR 24TH, 29TH AND 30TH APRIL. FLOORING TO | Next Appointment Needed | 13735.52
2026-02-23 09:23:00 | JEFFWAY - Renew defective Plasterboard wall in lobby and rooms and make good. FAO John Oyeniyi | 2026-06-03 08:00:00 | 2026-06-08 | 2026-06-08 09:22:00 | Routine Repairs | 3785293 | 53 RISDALE ROAD | 65788/1 | Works Completed | ACE Agreed | 36/1164 | 2026-06-02 08:00:00 | 15 days |  |  | Shannon Slade | 13/03/2026 09:23 | No | Pre-completion Items To Complete |  | Yes |  | 28/04 - Follow on appointments booked for 03/06 and 08/06. Tenant has informed me that he does a school run at 11am and is happy for operative to stay in property until he returns - CL 24/04 - CASA has confirmed BCC should receive the report from them on | Complete | 745.32
2026-02-23 09:21:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 26/2/26/26. 10 DAY PERIOD ENDS 12/3/26 |  | 2026-03-05 | 2026-03-06 10:58:00 | Routine Repairs | 1290795 | 40 TYNTESFIELD ROAD | 65830/3 | Works Completed | Invoiced | 36/1163 |  | 15 days |  |  | Shannon Slade | 13/03/2026 09:21 |  | Post-completion Items To Complete | 2026-03-06 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 143.59
2026-02-23 09:18:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 26/2/26. 10 DAY PERIOD ENDS 12/3/26 |  | 2026-03-06 | 2026-03-05 10:48:00 | Routine Repairs | 1308732 | 67 MOWCROFT ROAD | 65806/3 | Works Completed | Invoiced | 36/1162 |  | 15 days |  |  | Shannon Slade | 13/03/2026 09:18 |  | Post-completion Items To Complete | 2026-03-11 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 143.59
2026-02-23 09:15:00 | AS PER ROB DOIDGE - FIT EXT FAN TO KIT WALL IN PLACE OF VENT. REMOVE WINDOW FAN AND REGLAZE WINDOW. FIT WINDOW FAN TO BATHROOM WINDOW. RUB DOWN AND REPAINT BATH RADIATIOR WITH GLOSS. RENEW STAIR TREAD TO 3RD STEP IN STAIRCASE. REPAIR DAMAGED FLOORBOARDS UNDER CARPET TO LANDING X 3. REPLACE VENTS IN W.C AND D/S BEDROOM WITH UPVC SLIDERS | 2026-06-09 08:00:00 |  | 2026-06-09 10:13:00 | Routine Repairs | 1305835 | 17 MACEYS ROAD | 65774/1 | Works Completed | Invoiced | 36/1161 | 2026-04-20 08:00:00 | 15 days |  |  | Shannon Slade | 13/03/2026 09:15 | No | Pre-completion Items To Complete | 2026-06-11 | Yes |  | 16/06 - KPI received and uploaded - CL 11/06 - KPI requested - CL 08/06 - PO sent to WSG - CL 05/06 - KPI requested - CL 24/04 - Fans booked in to be installed on 29/05 as tenant will be on holiday. PO sent to WSG to install glazing units - CL 23/04 - On hold awaiting approval of variation, Asbestos report received and uploaded. Email sent to RD regarding new location of f | Complete | 1038.38
2026-02-23 09:06:00 | CCTV SURVEY TO REAR GULLEY BY LEAN-TO SHED. CLEAR OUT THE STONE DRAINAGE CHANNELNEXT TO IT AND CHECK CONDITION OF WALL / FLOOR SLAB FOR POSSIBLE WATER INGRESS TO W.C FLOORING. FILL HOLE TO CLADDING WITH CEMENT/ FILLER ALSO. |  |  |  | Routine Repairs | 1261605 | 80 SILBURY ROAD | 65737/1 | Works Cancelled | Works Cancelled | 36/1160 |  | 15 days | 3: Omitted from Contract | 2026-06-23 11:13:17 | Shannon Slade | 13/03/2026 09:06 |  | Suspended: Awaiting Client Action/Response |  |  |  | 23/06- Cancel works as per meeting on 23/06 08/05 - Quote received and sent to QS - CL 07/05 - Email sent to masters chasing the quote - CL 28/04 - follow up email sent 24/04 - Email sent to contractors chasing quote - CL 21/04 - Quote request sent for survey - CL | Cancelled | 367.83
2026-02-20 07:39:00 | JEFF WAY-AS PER ROB D: URGENT MOULD TREATMENT & PAINTING TO WC FULL ROOM, BATHROOM WALLS & CEILING IN FULL, WALLS ABOVE DADO IN D/S BEDROOM. LHS WALL OF FRONT DOOR, RHS WALL BY PIPES IN KITCHEN & INSIDE OF FRONT & BACK DOORS | 2026-03-30 11:00:00 |  | 2026-03-30 10:43:00 | Routine Repairs | 1305835 | 17 MACEYS ROAD | 62433/2 | Works Completed | Invoiced | 36/1159 | 2026-03-31 12:00:00 | 15 days |  |  | Shannon Slade | 12/03/2026 07:39 | No | Pre-completion Items To Complete | 2026-04-09 | Yes |  | Works completed 30/03 by compliance team | Complete | 345.76
2026-02-20 07:36:00 | Jeff Way - As per Mike Roe-French: Scaffold to the rear and side of building |  |  |  | Routine Repairs | 1245461 | 15 FAIRFIELD PLACE | 64666/1 | New Works Instruction | ACE Agreed | 36/1158 |  | 15 days |  |  | Shannon Slade | 12/03/2026 07:36 |  | Pre-completion Items To Complete |  |  |  | 30/06 - BS to assess works needed - CL 26/03 - SCAFFOLD ERECTED 10/03. MIKE ROE FRENCH HAS BEEN INFORMED. | WIP | 4754.44
2026-02-20 07:32:00 | Jeff Way - As per John Oyeniyi: Rear Garden pavement to be made safe; Redecoration works to bathroom; Kitchen unit repairs; hairline crack repair in bedroom. | 2026-05-27 08:00:00 |  | 2026-05-27 08:10:00 | Routine Repairs | 1291823 | 50 Wrington Crescent | 48205/2 | Works Completed | Invoiced | 36/1157 | 2026-05-27 08:00:00 | 15 days |  |  | Shannon Slade | 12/03/2026 07:32 | No | Pre-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI received and uploaded. KPI requested - CL 06/05 - Tenant called back and arrange follow on appointment for 27/05. Unable to make contact with tenant, Voicemail and text sent - CL 05/05 - Unable to make contact with tenant, Voicemail and text sent. Update needed from CM - CL 24/04 - Appointment bo | Complete | 805.2
2026-02-20 07:27:00 | DISREPAIR WORKS | 2026-06-10 12:00:00 | 2026-07-01 | 2026-07-01 07:44:00 | Disrepair | 1026319 | 4 MOOR GROVE | TBC | Works Completed | ACE Agreed | 36/1147 | 2026-07-01 08:00:00 | 20 days |  |  | Shannon Slade | 20/03/2026 07:27 | No | Pre-completion Items To Complete |  | Yes |  | 29/06 - Appointment confirmed with tenant - CL 16/06 - JWC WORKS COMPLETED, JWE BOOKED FOR 30TH TO COMPLETE FAN. WORKS BOOKED TO BE COMPLETED 19TH AND 20TH MAY. | Complete | 2021.4
2026-02-20 07:25:00 | JEFF WAY-AS PER ROB D: WHERE ABSENT , FIT NEW NEWEL POST, HANDRAIL AND BALUSTERS TO STAIRCASE RHS. CURRENTLY HHSRS HAZARD WITH YOUNG CHILDREN IN PROPERTY. | 2026-06-16 13:15:00 | 2026-06-16 | 2026-06-16 07:31:00 | Routine Repairs | 1306554 | 37 MAYNARD ROAD | 64574/1 | Works Completed |  | 36/1155 | 2026-05-05 08:00:00 | 15 days |  |  | Shannon Slade | 12/03/2026 07:25 | No | Pre-completion Items To Complete |  | Yes |  | 24/03 - resident cancelled job, only wants work booked for Tuesdays. booked for 31/03/26 | Complete | 682.55
2026-02-19 15:15:00 | Overlay existing loft insulation to front and rear elevations to a further width of approximately 500mm |  |  |  | Disrepair | 1230042 | 3 PURCELL WALK | 64151/1 | New Works Instruction | ACE Agreed | 36/1171 |  | 20 days |  |  | Shannon Slade | 19/03/2026 15:15 |  | Suspended: Awaiting Client Action/Response |  |  |  | 14/05 - TENANT HAS REFUSED WORKS, EMAIL ISSUED TO TOM TAYLOR. | Held BCC | 412.0
2026-02-19 14:55:00 | JEFF WAY - AS PER IAN O: CLEAR ANY BUILDING WASTE IN LOFT , STAIN BLOCK ,STOP COCK , DRAINAGE REAR , DRAINAGE FRONT .WEATHER | 2026-07-16 08:00:00 | 2026-07-15 |  | Routine Repairs | 1279103 | 215 FOUR ACRES | 64479/1 | Works Started |  | 36/1153 | 2026-05-12 08:00:00 | 15 days |  |  | Shannon Slade | 11/03/2026 14:55 | No | Pre-completion Items To Complete |  |  |  | 18/06 - Order may need varying once Tim has attended. Staining blocking and painting omitted from order as tenant refused. BCC to contact tenant regarding stop clock. Email sent to IO regarding the soakaway and stop clock - CL 08/06 - Appointment reschedule due to illness - CL | Appointment booked | 194.21
2026-02-19 08:11:00 | JEFF WAY-AS PER ROB D: MOULD TREATMENT & PAINTING TO COAL SHED WALLS & CEILING AS REQUIRED. ALSO TO BOTTOM OF UTILITY ROOM EXTERNAL DOOR. FOT 2 X AIRBRICKS TO SODE WALLS OF COAL SHED AS IN PHOTOS SENT TO AID VENTILATION. | 2026-04-30 08:00:00 |  |  | Routine Repairs | 1301424 | 124 Gatcombe Road | 58835/2 | Works Cancelled | Works Cancelled | 36/1152 | 2026-04-15 11:00:00 | 15 days | 2: No Access | 2026-06-02 07:26:55 | Shannon Slade | 11/03/2026 08:11 | No | Works Cancelled |  |  |  | 29/05 - 3 times no access in person, email sent to BCC for clarity on how to proceed | Cancelled | 226.4
2026-02-19 08:10:00 | JEFF WAY - AS PER ROB D: RENEW 2 X MISSING PLINTHS TO MATCH EXISTING TO KITCHEN UNITS. OVERHAUL DOORS / HINGES WHERE DROPPED / HANGING OFF AS REQUIRED | 2026-06-26 14:15:00 | 2026-06-26 | 2026-06-26 14:14:00 | Routine Repairs | 1276604 | 34 Derham Road | 14985/2 | Works Completed | ACE Agreed | 36/1151 | 2026-06-04 08:00:00 | 15 days |  |  | Shannon Slade | 11/03/2026 08:10 | No | Pre-completion Items To Complete |  | No |  | 30/06 - Awaiting completion photos - CL 25/06 - Appointment confirmed with tenant - CL 05/04 - Tenant for got about appointment, appointment rescheduled - CL 30/04 - Appointment rescheduled due to availability - CL | Complete | 152.97
2026-02-19 07:20:00 | JEFF WAY - AS PER IAN O: KITCHEN OVERHAUL, ELECTRICAL SOCKET | 2026-04-29 07:00:00 | 2026-04-29 | 2026-04-29 11:55:00 | Routine Repairs | 1290660 | 3 TYNTESFIELD ROAD | 64529/1 | Works Completed |  | 36/1154 | 2026-04-15 14:00:00 | 15 days |  |  | Shannon Slade | 11/03/2026 07:20 | No | Pre-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI requested - CL Works due 15/4 - elec 29/4 - multi. | Complete | 110.17
2026-02-18 14:58:00 | Disrepair Works - James Bailey (surveyor) Roof - carry out roof inspection (flat roof will need to arrange access) Livingroom- scrape back chimney, scrape back chimney, treat brick, replaster, mist coat and stain block Kitchen - Damp and mould wash around window reveal. | 2026-03-20 10:00:00 | 2026-06-10 |  | Disrepair | 1037703 | 64 Vincent Close | 4654/2 | New Works Instruction | ACE Agreed | 36/1169 |  | 20 days |  |  | Shannon Slade | 18/03/2026 14:58 |  | Pre-completion Items To Complete |  |  |  | SITE VISIT COMPLETED BY DARREN - EMAIL ISSUED TO JAMES. 24/04 - DARREN INFORMED MO OF ISSUES AT THE ABOVE ADDRESS IN MEETING, WAITING FOR UPDATE FROM BCC. NEED UPDATE FROM REGARDING ASHCROFT AND WHO'S GOT KEY TO LOFT? SENT EMAIL TO JB TODAY ASKING HIM TO |  | 519.16
2026-02-18 14:55:00 | Disrepair Works - James Bailey (surveyor) Plumber/ Gas engineer to carry out checks for leaks in flat and to water heater. Living room/ boiler cupboard/ cupboard - remove damaged plaster, replaster, apply 2 mist coats and 2 coats of emulsion. Doors - supply and fit 2 x flush doors to (1 x kitchen, 1 x bathroom). Kitchen - Damp and mould wash to affected areas, supply and fit new extractor | 2026-04-30 13:00:00 | 2026-07-22 |  | Disrepair | 1111359 | 84 FREMANTLE HOUSE | 3719/2 | New Works Instruction | ACE Agreed | 36/1168 |  | 20 days |  |  | Shannon Slade | 18/03/2026 14:55 |  | Pre-completion Items To Complete |  |  |  | 16/06 - PLASTRTER CALLED IN SICK, SO WORKS RE BOOKED FOR 22ND AND 27TH JULY. 12/05 -WORKS REBOOKED FOR 12TH, 17TH AND 23RD OF JUNE.WORKS BOOKED FOR 30TH APRIL, 5TH AND 7TH MAY. 07/05 - OPERATIVE HAS CALLED IN SICK. NEED TO RE BOOK. | Appointment booked | 1964.58
2026-02-18 14:46:00 | Responsive Repairs Overflow - Damp to bathroom and hallway - damp and mould treated by BCC repairs team - DN786139 - | 2026-05-06 09:00:00 |  |  | Disrepair | 1289049 | 60 Sherrin Way | 63253/1 | Works Cancelled | Works Cancelled | 36/1167 |  | 20 days | 4: Other | 2026-06-11 11:16:18 | Shannon Slade | 18/03/2026 14:46 |  | Works Cancelled |  |  |  | 11/06 - BCC HAS CONFIRMED THAT WE CAN CANCEL WORKS ORDER. 19/05 - CHASED BCC FOR UPDATE. 06/05 - Appointment needs to be rescheduled due to operative being ill - CL WORKS BOOKED 28TH AND 29TH APRIL AND 6TH MAY | Cancelled | 1665.76
2026-02-18 12:28:00 | COMPLAINT AS PER CHARLOTTE SMART- Please provide report on roof and what repairs are required scaff already in situ, please advise when scheduled | 2026-04-09 08:00:00 |  | 2026-04-14 12:23:00 | Disrepair | 1237941 | 90 Willinton Road | 63591/1 | Works Completed | Invoiced | 36/1146 |  | 20 days |  |  | Shannon Slade | 18/03/2026 12:28 |  | Fully Complete | 2026-04-02 | Yes |  |  | Complete | 59.0
2026-02-18 09:38:00 | Complaint Works - bathroom remove wall paper treat and paint with anti condensation paint. reseal bath. remove ceiling tiles and paint. repair front door. through out remove paper that's loose and treat mould. | 2026-07-02 08:00:00 | 2026-07-02 |  | Disrepair | 1142285 | 72 CHELSEA ROAD | 61312/1 | Works Started | ACE Agreed | 36/1140 | 2026-04-16 08:00:00 | 20 days |  |  | Shannon Slade | 18/03/2026 09:38 | No | Pre-completion Items To Complete |  |  |  | 03/07 - Completion photos needed from op - CL 02/07 - DW to contact JS to discuss additional work needed in bedroom - CL 01/07 - Appointment confirmed with tenant - CL 30/06 - Appointment confirmed with tenant - CL 19/05 - REMAINING WORKS BOOKED FOR 4TH JUNE. -WORKS BOOKED FOR 16TH AND 17TH APRIL | WIP | 1094.62
2026-02-18 08:08:00 | JEFF WAY - AS PER JEFF NECK: Hack/ cut out loose missing cement brick joints on rear elevation of house. Apply sand/cement & re joint to suit existing brickwork... Job Description: Hack / cut out loose missing cement brick joints on rear elevation of house. Apply sand/cement and re joint to suit existing brickwork. Apply mould wash to internal face of timber garden door. Rub down and apply under/gloss to suit. | 2026-04-24 08:00:00 |  | 2026-04-30 11:54:00 | Routine Repairs | 1252864 | 142 Luckwell Road | 63782/1 | Works Completed | ACE Agreed | 36/1150 |  | 15 days |  |  | Shannon Slade | 10/03/2026 08:08 |  | Pre-completion Items To Complete | 2026-05-06 | Yes |  | 06/05 - KPI requested - CL 05/05 - Update needed from CM - CL 23/04 - Appointment date changed to 24/04 and follow on appointment booked for 30/04 - CL 27/03 - Appointments booked for 02/04 and 07/04 - CL | Complete | 185.78
2026-02-18 08:05:00 | JEFF WAY - WORKS TO HALLWAY AS PER JEFF NECK (EMAIL SENT) | 2026-03-27 12:45:00 |  | 2026-03-27 10:41:00 | Routine Repairs | 1309677 | 22 OAK HOUSE | 22688/2 | Works Completed | ACE Agreed | 36/1149 | 2026-03-13 12:00:00 | 15 days |  |  | Shannon Slade | 10/03/2026 08:05 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI requested - CL Works confirm completed with tenant awaiting photos from operative - CL | Complete | 211.79
2026-02-18 07:58:00 | Fill cracks in Hallway and Kitchen, and patch plaster to Liv Rm wall including expamet, to stabilise - temporary repairs while waiting for decant. | 2026-06-15 12:00:00 |  | 2026-02-20 10:16:00 | Routine Repairs | 1306009 | 53 Maidenhead Road, Hartcliffe | 10162/4 | Works Completed | ACE Agreed | 36/1148 | 2026-02-20 10:17:00 | 15 days |  |  | Shannon Slade | 10/03/2026 07:58 | Yes | Pre-completion Items To Complete | 2026-06-03 |  |  |  | Complete | 176.25
2026-02-17 10:11:00 | PD1 - Please carry out works as listed. | 2026-04-22 12:30:00 | 2026-06-08 |  | Disrepair | 1221916 | 54 ILMINSTER AVENUE | 63374/1 | New Works Instruction | ACE Agreed | 36/1145 |  | 20 days |  |  | Shannon Slade | 16/03/2026 10:11 |  | Pre-completion Items To Complete |  |  |  | 05/06 - FLOORING COMPLETED. POST INSPECTION BOOKED FOR 8TH MAY. 20/05 - WORKS BOOKED FOR 26TH AND 27TH MAY. WORKS BOOEKD FOR 22ND APRIL 23/04 - JWC WORKS COMPLETED, FLOORING WORKS ISSUED TO FF WAITING FOR DATE 05/05 -CHASED FF FOR DATE. 07/05 - FF UNABLE TO GET HOLD OF TENANT, I HAVE LEFT MESSAGE TO RETURN CALL TO FF. | Complete | 952.15
2026-02-17 09:38:00 | JEFF WAY - Renew Kitchen floor, and repair Roof Gutter FAO JOHN OYENIYI | 2026-04-15 10:00:00 |  | 2026-05-29 12:48:00 | Routine Repairs | 1304923 | 29 HONEY GARSTON ROAD | 27081/2 | Works Completed | Invoiced | 36/1138 |  | 15 days |  |  | Shannon Slade | 09/03/2026 09:38 |  | Fully Complete | 2026-06-02 |  |  | 29/05- FF completed works 27/04 - Awaiting confirmation from FF - CL 16/04 - Flooring sent to FF - CL 13/04 - Site visit booked with tenant for DW to attend and assess work required - CL Contact details received from CM and contact number the same. Email sent to tenant to make co | Complete | 583.2
2026-02-16 10:03:00 | Jeffway to install fan in bathroom window. silicone round bath. Ensure kitchen fan in working while there. | 2026-05-08 13:15:00 |  | 2026-05-08 10:42:00 | Disrepair | 1055089 | 176 Greystoke Avenue | 62907/1 | Works Completed |  | 36/1144 | 2026-05-08 13:15:00 | 20 days |  |  | Shannon Slade | 13/03/2026 10:03 | No | Post-completion Items To Complete | 2026-06-05 |  |  | ELECTRICAL WORKS ISSUED TO JWE/WSG WORKS ISSUED - REMAINING WORKS BOOKED FOR 23RD MARCH 23/03 - OPERATIVE WAS SICK FOR TODAYS APPOINTMENT. WORKS RE BOOKED FOR 01/04. 21/04 - FAN BEING INSTALLED ON FRIDAY. SEALANT RE-BOOKED FOR 24TH. 07/05 - ELECTRICIAN WA | Complete | 928.88
2026-02-16 09:34:00 | Jeffway-as per John o-Repair Kitchen Units and Fix new ones | 2026-04-01 11:30:00 |  | 2026-04-01 15:44:00 | Routine Repairs | 1306598 | 46 Maynard Road | 56406/2 | Works Completed | Invoiced | 36/1137 | 2026-04-01 14:30:00 | 15 days |  |  | Shannon Slade | 06/03/2026 09:34 | No | Pre-completion Items To Complete | 2026-04-09 | Yes |  | 13/04 - KPI received and uploaded - CL | Complete | 386.98
2026-02-16 09:28:00 | jeff way - Hack off defective wall and ceiling rendering and renew Plaster, skim, and redecorate fao John Oyeniyi | 2026-06-04 12:15:00 | 2026-06-04 | 2026-06-04 07:43:00 | Routine Repairs | 1283836 | 14 LANGFORD ROAD | 6896/2 | Works Completed | ACE Agreed | 36/1136 | 2026-06-04 08:58:00 | 15 days |  |  | Shannon Slade | 06/03/2026 09:28 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI request sent - CL 24/04 - Follow on appointments booked for 29/05, 04/06 and 11/06 - CL 13/04 - Unable to make contact with tenant , voicemail sent - CL 09/04 - Unable to make contact with tenant, voicemail and text sent - CL Tenant called I to explained the appointments n | Complete | 546.42
2026-02-13 13:38:00 | Repairs throughout property - DN786139 - Responsive Repairs Overflow | 2026-06-04 17:00:00 |  | 2026-06-04 21:16:00 | Disrepair | 1212153 | 29 Broadbury Road | 62114/1 | Works Completed | Invoiced | 36/1131 | 2026-04-17 08:00:00 | 20 days |  |  | Shannon Slade | 12/03/2026 13:38 | No | Fully Complete | 2026-06-08 |  |  | 17/06 - Electrical cert received and uploaded - CL ROOF WORKS HAVE BEEN ISSUED TO SHEPS AND STARTING MONDAY 30/04. INTERNAL WORKS TO BE BOOKED, WAITING FOR UPDATE FROM MO REGARDING DIFF ADDRESS SO I CAN USE DATES. 07/04 - ROOF WORKS COMPLETED. WAITING FOR CONFIRMATION THAT WE CAN OFF-HIRE SCAFFOLD FROM BC | Complete | 6416.87
2026-02-13 12:23:00 | JWAY - INSTALL FELT ROOF COVERING TO REAR LEAN TO / SHED THAT IS LEAKING, 8M2. FILL CRACKS AS REQUIRED FIRST. WHERE SLAB HAS DROPPED AROUND EDGES, REMOVE TENANTS EXP FOAM AND FILL WITH CEMENT AND PAINT TO MATCH EXISTING WHITE, 6 LINM. |  |  |  | Routine Repairs | 1316592 | 14 WOODMEAD GARDENS | 62151/1 | Works Cancelled | Works Cancelled | 36/1130 |  | 15 days | 4: Other | 2026-06-08 12:08:01 | Shannon Slade | 05/03/2026 12:23 |  | Works Cancelled |  |  |  | 08/06 - Wo cancelled as property has now become a VOID. Call tenant who advised she is no longer at the property. Contact details for new tenant requested from RD and CM - CL0 3/06 - Asbestos report received and uploaded. Asbestos report requested - CL | Cancelled | 1018.93
2026-02-13 12:16:00 | JEFF WAY - Bathroom Repairs and redecorations FAO JOHN OYENIYI | 2026-06-24 08:00:00 |  |  | Routine Repairs | 1285810 | 91 NEWLAND ROAD | 61109/1 | Works Started | ACE Agreed | 36/1126 | 2026-04-29 08:00:00 | 15 days |  |  | Shannon Slade | 05/03/2026 12:16 | No | Pre-completion Items To Complete |  |  |  | 25/06 - EH cancelled order will revisit. Held until JO made contact with tenant to discuss matter- CL 24/06 - Tenant not allowing work to be carried out until issue with mould addressed. Email sent to JO - CL 05/06 - NA on 04/06, appointment rescheduled - CL 30/04 - Appointment rescheduled for 04/06 - CL 08/04 - Unable to get hold of tenant voicemail left to make contact to arrange an appointment - CL | Cancelled | 868.56
2026-02-12 12:31:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 23/2/26. 10 DAY PERIOD ENDS 9/3/26 |  | 2026-03-06 | 2026-03-05 10:51:00 | Urgent Repair | 1277447 | 73 FAIR FURLONG | 61545/3 | Works Completed | Invoiced | 36/1128 |  | 5 days |  |  | Shannon Slade | 18/02/2026 12:31 |  | Fully Complete | 2026-03-11 | Yes |  | 30/04 - KPI received and uploaded - CL 07/04 - KPI request added and forwarded to EH - CL | Complete | 143.59
2026-02-12 12:28:00 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF SHRUB / WEED SELF SET IN CHIMNEY STACK & M/G ANY HOLES FROM REMOVING TO STOP WATER INGRESS. REPAIR TO DAMAGED CORNER OF BLACK ACO DRAINAGE BY BK GATE | 2026-05-13 08:00:00 |  |  | Routine Repairs | 1244366 | 51 Church Lane | 61262/1 | Works Started |  | 36/1127 | 2026-05-13 08:00:00 | 15 days |  |  | Shannon Slade | 04/03/2026 12:28 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Review needed on scaffolding variation - CL 23/06 - Variations needed for scaffolding - CL 02/06 - VO sent to RD - CL 18/5 - chased up scaffold with bcc awaiting response. Tenant aware. 15/05 -On hold awaiting scaffold alteration 27/04 - Scaffolding to be erected on 12/05 and repair to be carried out on 13/05. VO approved and works to go ahead - CL 24/04 - Job put on hold as discussed in meeting RD will discuss the matter with Emma. Email sent to RD advising of the chimney growth | Manager review needed | 1739.44
2026-02-12 09:50:00 | PD1 - Please carry out works as listed. | 2026-04-16 11:00:00 |  | 2026-05-19 10:56:00 | Disrepair | 1152734 | 121 LANSDOWNE COURT | 61636/1 | Works Completed | Invoiced | 36/1143 |  | 20 days |  |  | Shannon Slade | 11/03/2026 09:50 |  | Suspended: Awaiting asbestos info | 2026-06-05 |  |  | WORKS BOOKED FOR 16TH APRIL. 23/04 - MOULD WORKS COMPLETED. OPERATIVE WAS OFF FROM 15TH APRIL. WORKS BOOKED FOR 2ND JUNE | Complete | 1431.64
2026-02-12 09:45:00 | Jeffway to carry out complain disrepair works - overhaul two base units, renew two wall unit doors by cooker, renew bath panel, clean/wipe down and service windows in property, treat slight mould in living room, etc... | 2026-05-06 10:15:00 |  | 2026-05-07 13:32:00 | Disrepair | 1082855 | 28 COPLEY GARDENS | 61551/1 | Works Completed | ACE Agreed | 36/1142 | 2026-05-06 08:15:00 | 20 days |  |  | Shannon Slade | 11/03/2026 09:45 | No | Post-completion Items To Complete | 2026-06-12 |  |  | WORKS BOOKED THROUGH BCC - 18TH AND 24TH MARCH 23/03 - PLASTERING WORKS COMPLETED. REMAINING WORKS BOOKED FOR 24TH MARCH. 30/03 - NO ACCESS ON 24TH MARCH - WORKS RE BOOKED FOR 6TH MAY 07/05 - WORKS COMPLETED YESTERDAY, WAITING FOR COMMERCIAL TO CHECK. | Complete | 912.24
2026-02-12 09:41:00 | COMPLAINT AS PER CHARLOTTE SMART- lottie.smart@bristol.gov.uk DN786139 - Responsive Repairs OverflowA?. | 2026-07-03 09:00:00 | 2026-07-07 |  | Disrepair | 1302529 | 47 HARECLIVE ROAD | 61472/2 | New Works Instruction | ACE Agreed | 36/1141 |  | 20 days |  |  | Shannon Slade | 11/03/2026 09:41 |  | Pre-completion Items To Complete |  |  |  |  | Appointment booked | 1182.62
2026-02-12 09:35:00 | PD1 - Please carry out works as listed | 2026-04-20 11:15:00 |  | 2026-04-20 11:23:00 | Disrepair | 1067 | 160 Airport Road | 61317/1 | Works Completed | ACE Agreed | 36/1139 | 2026-04-20 11:15:00 | 20 days |  |  | Shannon Slade | 11/03/2026 09:35 | No | Pre-completion Items To Complete | 2026-04-29 | Yes |  | WORKS BOOKED FOR 20TH APRIL 24/04 - WORKS COMPLETE WAITING FOR COMMERICAL TO ISSUE HANDOVER | Complete | 84.32
2026-02-11 15:01:00 | PD1 - Please carry out works as listed. | 2026-05-12 08:00:00 | 2026-05-27 |  | Disrepair | 1115055 | 158 RICHMOND ROAD | 60332/2 | New Works Instruction | ACE Agreed | 36/1135 |  | 20 days |  |  | Shannon Slade | 10/03/2026 15:01 |  | Pre-completion Items To Complete |  |  |  | WORKS BOOKED FOR 14TH APRIL AND 23RD APRIL - D&M TEAM ARE ATTENDING TO COMPLETE FAN/D&M CLEAN - DATE TO BE CONFIRMED. 24/04 - CHASED DAMP AND MOULD FOR DATE, OPERATIVE WAS SICK YESTERDAY WORKS REBOOKED FOR 13/05. 29/04 FLOORING HAS BEEN ARRANGED FOR 14TH | Appointment booked | 1892.82
2026-02-11 14:53:00 | PD1 - Please carry out works as listed. | 2026-04-15 12:00:00 |  | 2026-04-28 14:48:00 | Disrepair | 1274299 | 36 COBHORN DRIVE | 61033/1 | Works Completed |  | 36/1134 |  | 20 days |  |  | Shannon Slade | 10/03/2026 14:53 |  | Post-completion Items To Complete | 2026-04-29 | Yes |  | WORKS BOOKED FOR 15TH APRIL | Complete | 609.31
2026-02-10 14:29:00 | COMPLAINT WORKS: KITCHEN: FAN REPAIR/RENEW. BATHROOM: FAN REPAIR RENEW, PLASTER HOLES AND ROUND PIPE. BED1: PATCH REPAIR WALLPAPER AND FIX PERKO TYPE TO CONCEALLED DOOR | 2026-05-29 15:30:00 | 2026-06-02 |  | Disrepair | 1221256 | 21 HOME MEAD | 58805/2 | Awaiting Target Start | ACE Agreed | 36/1133 |  | 20 days |  |  | Shannon Slade | 09/03/2026 14:29 |  | Pre-completion Items To Complete |  |  |  | WORKS BOOKED FOR 2ND JUNE | Appointment booked | 133.5
2026-02-10 13:17:00 | Jeffway - As per Rob D - INSTALL WINDOW MOUNTED FANS TO KITCHEN AND BATHROOM , CORNISH TYPE PROPERTY. ALSO RENEW SILICON AROUND BATH IN FULL | 2026-07-02 08:30:00 |  |  | Routine Repairs | 1293330 | 430 Bishport Avenue | 60035/1 | Works Started | ACE Agreed | 36/1129 | 2026-06-25 09:00:00 | 15 days |  |  | Shannon Slade | 02/03/2026 13:17 | No | Suspended: WSG to be booked |  |  |  | 03/07 - Email sent to WSG for a quote to replace external gaskets - CL 01/07 - Site inspection booked with tenant - CL 30/06 -Update need from operative on work completed - CL 01/06 - ATTEMPTED TO CALL TENANT TWICE WITH NO LUCK. TASK ISSUED TO D&M. 18/05- Chased WSG again DGU installed Compliance to book in Fans , 06/05 - WSG planning to install if tenants home on 08/05 - CL 05/05 - Email sent to WSG for update - CL 30/04 - Awaiting date for DGU install - CL 28/04 - Vo approved JW to book works 23/04 - On hold awaiting variation approval - CL awaiting Glazing comp | WIP | 1236.58
2026-02-10 10:32:00 | vJeffway-AS PER ROB DOIDGE - TREATMENT / PAINTING TO SMALL AREAS OF MOULD BY FRONT DOOR, TO BATHROOM WALLS BY W.C AND LIVING ROOM UNDER WINDOW. | 2026-06-25 09:15:00 | 2026-06-24 | 2026-06-24 10:35:00 | Routine Repairs | 1304467 | 14 Holbrook Crescent, Hartcliffe, Bristol BS13 0EU | 60323/1 | Works Completed |  | 36/1124 | 2026-06-24 09:15:00 | 15 days |  |  | Shannon Slade | 02/03/2026 10:32 | No | Pre-completion Items To Complete |  | Yes |  | 30/06 - Tenant confirmed trickle vent already completed - CL 25/06 - Op attended 24/06 tenant said trickle vents been completed, CL to speak with tenant - CL 09/06 - Appointment confirm with tenant for electrical work on 23/06. Spoke with tenant regarding fan and electrical work. - CL 21/04 - NA on 20/01, appointment needs to be rebooked - CL | Complete | 947.29
2026-02-10 09:25:00 | Jeffway-: AS PER ROB DOIDGE - FOLLOWING STRUCTURAL SURVEY, BREAK UP FLOOR SCREED IN LIVING ROOM 200MM FROM PERIMITER AND RENEW AS PER REPORT. INSTALL CHICKEN WIRE INTO SCREED AND ADD FIBRE ADDITIVE. RENEW FLOOR TILES AFTERWARDS | 2026-04-16 10:00:00 |  | 2026-04-23 08:04:00 | Routine Repairs | 1311417 | 19 REDWOOD HOUSE | 60316/1 | Works Completed | Invoiced | 36/1123 | 2026-04-16 08:04:00 | 15 days |  |  | Shannon Slade | 02/03/2026 09:25 | No | Pre-works Items To Complete | 2026-04-28 | Yes |  | 01/05 - KPI received and uploaded - CL 28/04 - KPI requested - CL 24/04 - FF confirmed work completed 23/04. Awaiting confirmation photos - CL 20/04 - Quote request sent to FF. Screeding completed 18/04 - CL Tenant called back and confirmed he is availabl | Complete | 2166.16
2026-02-10 09:22:00 | JW - As per Rob D - RENEW BACK GATE ON EXISTING FRAME, BACKS ONTO MAIN ROAD. CLEAR FLY TIPPED WASTE TO REAR GARDEN - TENANT TO SHOW ITEMS TO GO | 2026-03-25 11:30:00 |  | 2026-03-25 14:35:00 | Routine Repairs | 1252740 | 6 LOMBARD STREET | 60283/1 | Works Completed | Invoiced | 36/1122 | 2026-03-23 12:30:00 | 15 days |  |  | Shannon Slade | 02/03/2026 09:22 | No | Fully Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL | Complete | 366.79
2026-02-10 08:38:00 | Jeffway - Kindly replace damaged/broken floor tiles in the Kitchen, contact John Oyeniyi if there is need to further discuss this. FAO JOHN OYENIYI | 2026-03-31 09:15:00 |  | 2026-03-31 10:00:00 | Routine Repairs | 1282582 | 38 HUNTINGHAM ROAD | 18017/2 | Works Completed | Invoiced | 36/1116 | 2026-03-30 10:45:00 | 15 days |  |  | Shannon Slade | 02/03/2026 08:38 | No | Post-completion Items To Complete | 2026-04-15 | Yes |  | 17/04 - KPI received and uploaded - CL 15/04 - KPI request sent - CL Awaiting completion photos from Sub con | Complete | 101.7
2026-02-09 09:19:00 | JEFFWAY to fit 2-pole isolation switch to an occupied property. Please liaise with the tenant to book this in and please let responseelectrical@bristol.gov.uk know once completed. |  |  | 2026-03-09 10:59:00 | Routine Repairs | 1176369 | 30 GRANVILLE STREET | 59463/1 | Works Completed | Invoiced | 36/1118 | 2026-03-09 10:59:00 | 15 days |  |  | Shannon Slade | 27/02/2026 09:19 | No | Pre-completion Items To Complete | 2026-03-09 | Yes |  | 13/04 - KPI received and uploaded - CL 07/04 - KPI request forwarded to EH - CL | Complete | 259.0
2026-02-09 08:49:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 10/2/26. 10 DAY PERIOD ENDS 24/2/26 |  |  | 2026-02-23 11:23:00 | Routine Repairs | 1279501 | 34 Four Acres Close, Withywood | 59378/3 | Works Completed | Invoiced | 36/1117 |  | 15 days |  |  | Shannon Slade | 27/02/2026 08:49 |  | Post-completion Items To Complete | 2026-02-26 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 143.59
2026-02-06 08:35:00 | carry out GRP roof to 26, 24 Mowcroft as discussed with Steve and Mike, closest codes to get started, Mike agreed to discus techeal spec for Steve and meet on site to ensure works are done to standard .Matt Ford | 2026-06-24 16:45:00 |  | 2026-06-17 08:25:00 | Routine Repairs | 1308629 | 26 MOWCROFT ROAD | 59127/1 | Works Completed | ACE Agreed | 36/1115 |  | 15 days |  |  | Shannon Slade | 26/02/2026 08:35 |  | Pre-completion Items To Complete |  | No |  | 25/06 - WORKS COMPLETED. WAITING FOR ELECTRICIAN TO ATTEND AND REINSTATE SATTELITTE AN THEN SCAFFOLD CAN BE OFF-HIRED. 05/05 - Awaiting quote from roofing contractor - CL01/05 - Variation added and revised WO uploaded - CL 21/04 - Chased SH for quote - CL | Complete | 7731.59
2026-02-06 08:24:00 | JWAY - Strip rear bedroom wallpaper, cut out damaged plasterwork. Dub out w sand/cement to suit existing levels. Reskim complete wall. Make good to reveal timber door frame. Fix new floor double power back box. Overhaul PVC windows - J Neck | 2026-05-28 12:00:00 | 2026-06-02 | 2026-06-02 08:51:00 | Routine Repairs | 1278962 | 198 Four Acres | 58831/1 | Works Completed | ACE Agreed | 36/1114 | 2026-04-15 08:00:00 | 15 days |  |  | Shannon Slade | 26/02/2026 08:24 | No | Post-completion Items To Complete | 2026-06-05 | Yes |  | 05/06 - KPI requested - CL 27/04 - Unable to get hold of tenant, voicemail and text sent - CL 20/04 - Follow on appointment booked for 23/04 - CL | Complete | 439.55
2026-02-06 08:12:00 | Complaint works- New works following leak WO- THOMAS LEAR | 2026-04-08 13:00:00 | 2026-07-10 |  | Disrepair | 1307751 | Millmead House, 1 Silcox Road | 58870/1 | New Works Instruction | ACE Agreed | 36/1113 |  | 20 days |  |  | Shannon Slade | 05/03/2026 08:12 |  | Pre-completion Items To Complete |  |  |  | 16/06 - NO ACCESS DUE TO OPS BEING LOUD. TENANT MAD E COMPLAINT TO BCC, REQUESTED GLEN TO RETURN. WORKS BOOKED FOR 10TH JULY. 05/06 - TENANTHAD TO COLLECT CHILD FROM SCHOOL ON PREVIOUS APPOINTMENT, WORKS RE BOOKED FOR 8TH JUNE. 08/04 - WORKS ARE BEING PROCESSED ON WORKS ORDER 31414/1 | WIP | 872.55
2026-02-05 14:21:00 | Tenants daughters number is - 07501593854 - Brittany - Jeffway to clean and service windows, renew sealant in bathroom, S&F door frame, refix surface mounted box. | 2026-05-01 15:45:00 |  |  | Disrepair | 1275645 | 96 CUTLER ROAD | 58481/1 | New Works Instruction | ACE Agreed | 36/1132 |  | 20 days |  |  | Shannon Slade | 04/03/2026 14:21 |  | Suspended: Awaiting asbestos info |  |  |  | 17/06 - DARREN NEED TO CHECK WITH OP IF ALL WORKS COMPLETED. ELECTRICAL WORK COMPLETED. 14/05 - DATES ISSUED TO YOANNA FOR DATES OF 16TH JUNE. WORKS BOOKED FOR 9TH MARCH 23/03 - NO ACCESS ON THE 9TH MARCH. ATTEMPTED TO CALL TENANT HOWEVER PHONE IS OFF. I HAVE SENT AN EMAIL ASKING TENANT TO CALL ME. 30/03 - WORKS BOOKED FOR 1ST MAY THROUGH BC | WIP | 251.36
2026-02-05 14:05:00 | Renew Bed 2 ceiling tested by CASA , NAD inc ELE / DEC parts R.M | 2026-06-29 09:45:00 | 2026-07-03 |  | Routine Repairs | 1245369 | 42 Eldon Terrace, Windmill Hill | 58180/1 | Works Started | ACE Agreed | 36/1347 | 2026-06-17 08:00:00 | 35 days |  |  | Shannon Slade | 26/03/2026 14:05 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment confirmed with tenant - CL 30/06 - Ceiling bonded, follow on appointment booked for 03/07 - CL 18/06 - Another visit required to plaster bedroom ceiling - CL 17/06 - JP attended on 16/06 - CL | WIP | 943.68
2026-02-05 13:19:00 | Kitchen - Treat area of reported mould on ceiling beside pipework. Board ceiling of cupboard. | 2026-04-23 12:45:00 |  |  | Disrepair | 1097763 | 164 ROMNEY AVENUE | 58393/1 | Works Cancelled | Works Cancelled | 36/1206 |  | 20 days | 4: Other | 2026-03-24 14:51:05 | Shannon Slade | 04/03/2026 13:19 |  | Suspended: Awaiting asbestos info |  |  |  | 23/03 - WORKS BOOKED FOR 17TH APRIL AND 23RD APRIL. ASBESTOS REPORT REQUESTED. | Cancelled | 282.8
2026-02-05 11:01:00 | Jeffway - Demolish severely cracked back garden wall as necessary to make safe, board up to secure. as discussed with Darren W. Melissa Edwards 07442675013 |  |  | 2026-02-20 15:19:00 | Routine Repairs | 1306009 | 53 Maidenhead Road, Hartcliffe | 58501/1 | Works Completed | Invoiced | 36/1112 |  | 15 days |  |  | Shannon Slade | 25/02/2026 11:01 |  | Pre-completion Items To Complete | 2026-04-22 | Yes |  | 11/06 - KPI received and uploaded - CL 22/04 - KPI request sent - CL | Complete | 498.42
2026-02-05 10:58:00 | JEFF WAY - AS PER ROB D: DINING ROOM, STAIN BLOCK PATCHES TO CONCRETE CEILING AFTER LEAK FROM BATHROOM ABOVE THEN REPAINT CEILING IN FULL, SMALL PATCH REPAIR TO BEAM DETAIL BETWEEN KITCHEN ALSO. 10M2 TOTAL AREA, 2M2 STAINBLOCK | 2026-03-13 12:15:00 |  | 2026-03-13 16:05:00 | Routine Repairs | 1282991 | 47 Innox Gardens | 58477/1 | Works Completed | Invoiced | 36/1111 | 2026-03-13 12:50:00 | 15 days |  |  | Shannon Slade | 25/02/2026 10:58 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL | Complete | 171.3
2026-02-05 10:53:00 | JEFF WAY - FAO DARREN: CANOPY, PASSIVE VENT, CRACK REPAIR, PAINTING, D&amp;M AS PER IAN OGBORNE | 2026-07-28 08:00:00 | 2026-07-28 |  | Routine Repairs | 1197860 | 77 Hazelbury Road, Knowle | 58447/1 | New Works Instruction | ACE Agreed | 36/1110 |  | 15 days |  |  | Shannon Slade | 25/02/2026 10:53 |  | Pre-completion Items To Complete |  |  |  |  | Appointment booked | 382.56
2026-02-05 10:45:00 | JEFF WAY - AS PER ROB D: RENEWAL OF BATHROOM & KITCHEN EXTRACTOR FANS WITH HUMIDISTATS. RENEWAL OF NON ASBESTOS BATHROOM FLOORING WITH BCC NON SLIP VINYL - 2M2 | 2026-04-17 08:00:00 |  | 2026-04-17 09:03:00 | Routine Repairs | 1295381 | 1 BRANCHE GROVE | 16768/2 | Works Completed | Invoiced | 36/1109 | 2026-04-17 09:00:00 | 15 days |  |  | Shannon Slade | 25/02/2026 10:45 | No | Pre-completion Items To Complete | 2026-04-28 | Yes |  | 28/04 - KPI requested - CL 24/04 - FF confirmed flooring complete. Awaiting completion pics - CL 20/04 - Fans completed on 17/04, a quote request has been sent to FF - CL | Complete | 708.08
2026-02-04 10:40:00 | Pre response inspection please examine back door and flooring inside, damaged by water coming down from gutters and soffit. | 2026-05-07 08:00:00 |  | 2026-05-07 09:50:00 | Routine Repairs | 1305777 | 4 Lyveden Gardens | 1304/1 | Works Completed | ACE Agreed | 36/1108 |  | 15 days |  |  | Shannon Slade | 24/02/2026 10:40 |  | Pre-completion Items To Complete | 2025-04-29 | Yes |  | 27/03 - Appointment booked for 05/05 and 07/05. Once request will be sent to FF to complete the flooring - CL | Complete | 907.34
2026-02-04 08:32:00 | JEFF WAY - As per John O: Renew extractor fan in bathroom and redecorate ceiling | 2026-05-11 12:15:00 | 2026-05-11 | 2026-05-11 09:59:00 | Routine Repairs | 1306203 | 25 MAYNARD CLOSE | 57726/1 | Works Completed | Invoiced | 36/1106 | 2026-03-31 15:45:00 | 15 days |  |  | Shannon Slade | 24/02/2026 08:32 | No | Pre-completion Items To Complete | 2026-05-13 | Yes |  | 13/04 - Unable to make contact with tenant voicemail and text sent - CL Email sent to JO on how to proceed - CL 08/04 - SA to make a decision on whether a fan can be fitted following Tyler's visit - CL Painting complete, email to confirm new fan location | Complete | 401.03
2026-02-03 08:35:00 | JEFF WAY - AS PER ROB DOIDGE - STAINBLOCKING TO AFFECTED AREAS OF CEILING AND KIT WALLS AFTER LEAK . FILL CRACKS THEN REPAINT CEILING IN FULL AND COOKER / WINDOW WALLS IN FULL, MATCH COLOURS, 12M2 APPROX TOTAL. | 2026-03-26 12:00:00 |  | 2026-03-26 08:29:00 | Routine Repairs | 1313208 | 40 STILLINGFLEET ROAD | 15413/2 | Works Completed | Invoiced | 36/1100 | 2026-03-26 12:00:00 | 15 days |  |  | Shannon Slade | 23/02/2026 08:35 | No | Fully Complete | 2026-04-15 | Yes |  | 16/06 - KPI received and uploaded - CL 15/04 - KPI requested - CL Works completed, awaiting VO approval from BCC -27/3. | Complete | 270.57
2026-02-03 08:31:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. JOE COTTRELL ATTENDING 5/2/26. 10 DAY PERIOD ENDS 19/2/26 |  | 2026-03-05 | 2026-03-05 10:44:00 | Routine Repairs | 1284726 | 31 MILLGROUND ROAD | 55039/3 | Works Completed | Invoiced | 36/1099 |  | 15 days |  |  | Shannon Slade | 23/02/2026 08:31 |  | Post-completion Items To Complete | 2026-03-11 | Yes |  |  | Complete | 143.59
2026-02-03 07:54:00 | JEFF WAY - Remove existing toilet & plastic cistern & refix new to suit existing plumbing. Fix new bath panel. Apply anti condensation paint to walls and complete ceiling. Reseal around bath, FAO JEFF NECK | 2026-07-17 08:00:00 | 2026-07-17 |  | Routine Repairs | 1308152 | 41 MILLMEAD HOUSE | 47517/2 | Works Started | ACE Agreed | 36/1105 | 2026-04-02 08:00:00 | 15 days |  |  | Shannon Slade | 23/02/2026 07:54 | No | Pre-completion Items To Complete |  |  |  | 30/07 - Tenant called to confirm appointment - CL 18/06 - Email sent to JN confirmation of asbestos removal - CL 05/06 - ASBESTOS REMOVAL BOOKED FOR 12.06 11/5 - emailed jeff neck for update (LL). 06/05- BCC arrange asbestos floor removal 28/04 - Email sent to JN to arrange for asbestos floor tiles to be removed - CL 08/04 - Unable to make contact with tenant, voicemail left and text message sent - CL | WIP | 704.06
2026-02-03 07:46:00 | PD1 - Please carry out works as listed. | 2026-05-21 12:00:00 | 2026-05-13 |  | Routine Repairs | 1191124 | 140 Wootton Road | 57149/1 | New Works Instruction | ACE Agreed | 36/1103 |  | 15 days |  |  | Shannon Slade | 23/02/2026 07:46 |  | Suspended: Awaiting Client Action/Response |  |  |  | 15/05 - On hold awaiting confirmation from BCC on how to proceed | Held BCC | 658.97
2026-02-02 08:49:00 | JEFF WAY - AS PER ROB DOIDGE - MOULD TREATMENT WHERE REQUIRED TO DOWNSTAORS WETROOM AND THEN REPAINT ALL WALLS AND CEILING IN FULL WITH HALOPHEN PAINT. APPROX 10M2 TOTAL AREA | 2026-04-22 12:45:00 |  | 2026-04-22 08:35:00 | Routine Repairs | 1306429 | 9 Maynard Road | 56877/1 | Works Completed | Invoiced | 36/1102 | 2026-04-22 12:45:00 | 15 days |  |  | Shannon Slade | 20/02/2026 08:49 | No | Pre-completion Items To Complete | 2026-04-28 | Yes |  | 29/04 - KPI received and uploaded - CL 27/03 - Chased LM for completion photos - CL | Complete | 218.77
2026-01-29 08:29:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. JOE COTTRELL ATTENDING 5/2/26. 10 DAY PERIOD ENDS 19/2/26 |  |  | 2026-02-23 11:33:00 | Routine Repairs | 1293545 | 502 BISHPORT AVENUE | 55021/3 | Works Completed | Invoiced | 36/1098 |  | 15 days |  |  | Shannon Slade | 18/02/2026 08:29 |  | Fully Complete | 2026-02-26 | Yes |  |  | Complete | 143.59
2026-01-29 08:23:00 | Jeffway- as per Jeff Neck-: Scrap loose paint on ground floor front bathroom ceiling. remove light fitting / refix and apply plaster over existing artex to complete ceiling. and various other bathroom works, emailed over. | 2026-04-16 15:00:00 |  | 2026-04-16 08:15:00 | Routine Repairs | 1294491 | 48 BLAGROVE CRESCENT | 54374/2 | Works Completed | Invoiced | 36/1097 | 2026-03-20 08:00:00 | 15 days |  |  | Shannon Slade | 18/02/2026 08:23 | No | Fully Complete | 2026-04-28 | Yes |  | 06/05 - KPI received and uploaded - CL 28/04 - KPI requested - CL | Complete | 379.76
2026-01-28 08:31:00 | JEFF WAY - KITCHEN WORKS , PLASTERING , PAINTING , WINDOW OVERHAUL FAO ROB DOIDGE | 2026-04-28 14:45:00 |  | 2026-04-28 16:00:00 | Routine Repairs | 1314814 | 2 Upjohn Crescent | 53012/1 | Works Completed | ACE Agreed | 36/1081 | 2026-03-26 08:00:00 | 15 days |  |  | Shannon Slade | 17/02/2026 08:31 | No | Post-completion Items To Complete | 2026-06-02 | Yes |  | 03/06 - KPI resent - CL 05/05 - KPI requested - CL Paint works due - 28/4. Elec works due - 23/4/26. | Complete | 945.51
2026-01-28 08:15:00 | Complaint works- Please see email and report. | 2026-06-25 08:00:00 | 2026-07-01 |  | Disrepair | 4257583 | 3 Teal Close | 54414/1 | Works Started | ACE Agreed | 36/1094 | 2026-06-24 08:00:00 | 20 days |  |  | Shannon Slade | 24/02/2026 08:15 | No | Pre-completion Items To Complete |  |  |  | 26/06 - ROOF WORKS COMPLETE, JWC WORKS COMPLETE. JWE BOOKED FOR 1ST JULY. 20/05 - TENANT COULDNT GET TIME OFF WORK FOR PREVIOUS APPOINTMENTS. WORKS RE BOOKED FOR 24TH, 25TH AND 26T JUNE. 14/04 - SCAFFOLD OFFHIRED. WORKS BOOKED FOR 18TH, 19TH AND 20TH MAY. | Appointment booked | 2608.4
2026-01-28 07:33:00 | JEFF WAY - AS PER ROB DOIDGE - REPLACEMENT OF 7 X TRICKLE VENTS TO VARIOUS WINDOWS, TNT WILL SHOW, NONE HAVE A CLOSING MECHANISM | 2026-05-08 15:15:00 |  |  | Routine Repairs | 1271427 | 39 ACRESBUSH CLOSE | 18867/2 | Works Cancelled | Works Cancelled | 36/1091 | 2026-03-30 08:00:00 | 15 days | 4: Other | 2026-06-10 11:05:23 | Shannon Slade | 17/02/2026 07:33 | No | Works Cancelled |  |  |  | 10/06 - Works order cancelled as confirm with BCC. Email sent to RD regarding property now being void - CL 22/05 No access need to reschedule 12/05 - APPOINTMENT ARRANGED FOR 22ND MAY - APPOINTMENT OF 8TH MAY DIDNT GO AHEAD DUE TO OP SICKNESS. | Cancelled | 100.1
2026-01-27 09:46:00 | Jeffway- as per Jeff Neck-: Break out sloping concrete area to the rear of the property draining towards rear kitchen wall and clear and various other works sent over via email | 2026-05-01 10:00:00 |  |  | Routine Repairs | 1239538 | 59 Avonleigh Road, Bedminster | 53627/1 | Works Started | ACE In Progress | 36/1088 | 2026-04-07 08:00:00 | 15 days |  |  | Shannon Slade | 16/02/2026 09:46 | No | Pre-completion Items To Complete |  |  |  | 23/06 - AG to book an appointment next week - CL 18/06 - Awaiting appointment date from AG Builders - CL 16/06 - Emails sent to Ag Builders chasing decision - CL 12/06 - PO sent to AG builders - CL 11/5 - chased up with cl (LL).08/05 - VO sent by HS and SH on 05/05. VO forwarded to EH and CM for reference - CL 05/05 - Awaiting update from SH regarding outstanding work - CL 28/04 - Appointment booked with tenant for SH to do a site visit. Appointment | Awaiting appointment date | 2901.61
2026-01-27 09:39:00 | Complaint works- please see email and report- Thomas Lear | 2026-06-11 08:00:00 | 2026-07-03 |  | Disrepair | 1309020 | 46 MURFORD AVENUE | 46466/1 | Works Started | ACE Agreed | 36/1087 | 2026-03-30 08:00:00 | 20 days |  |  | Shannon Slade | 23/02/2026 09:39 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment rescheduled as requested by tenant - CL 17/06 - Electrical cert received and uploaded - CL 16/06 - NO ACESS ON 12TH JUNE, TENANT PHONE WAS OFF. WORKS RE BOOKED FOR 3RD JULY. 05/06 - OP WAS OFF ON 27TH, WORKS RE BOOKED FOR FRIDAY 12TH JUNE 23/03 - Contact made with tenant, works booked for 30th March for plastering and 13th and 14th April 2026. 15/04 - DECORATING WORKS STARTED 14TH, waiting for planned to come back with another date as tenant had appointments so couldn't allow two days acce | WIP | 6076.72
2026-01-26 09:23:00 | jeffway - supply and fit new kitchen wall cupboards as per SOR | 2026-03-24 11:15:00 |  | 2026-03-24 17:30:00 | Routine Repairs | 1304707 | 2 HONEY GARSTON CLOSE | 53270/1 | Works Completed | Invoiced | 36/1086 | 2026-03-24 12:00:00 | 15 days |  |  | Shannon Slade | 13/02/2026 09:23 | No | Fully Complete | 2026-04-30 | Yes |  | 30/04 - WO already invoiced. KPI received and updated. KPI requested - CL | Complete | 294.02
2026-01-26 09:21:00 | Jeffway prep and paint ceilings in bathroom and bedroom 1 | 2026-03-17 12:00:00 |  | 2026-03-17 10:01:00 | Routine Repairs | 1279421 | 26 Four Acres Close | 53260/1 | Works Completed | Invoiced | 36/1085 | 2026-03-17 12:00:00 | 15 days |  |  | Shannon Slade | 13/02/2026 09:21 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI requested - CL | Complete | 212.75
2026-01-26 09:20:00 | Jeff Way - Overhaul Extractor Fans and Window as pre John Oyeniyi | 2026-05-06 10:00:00 |  | 2026-05-06 07:32:00 | Routine Repairs | 1280928 | 62 Gay Elms Road, Withywood | 53274/1 | Works Completed | Invoiced | 36/1084 |  | 15 days |  |  | Shannon Slade | 13/02/2026 09:20 |  | Pre-completion Items To Complete | 2026-06-03 | Yes |  | 30/04 - Rake and mastic completed 30/04 by CM as screen was unsafe for tenant - CL 20/04 - Follow on appointment booked for repairs to be carried out. Fan book in for 30/04 - CL | Complete | 934.8
2026-01-26 08:52:00 | Jeff Way - Renew silicone to bath, patch plaster repair and redecoration as per John Oyeniyi. | 2026-06-11 09:30:00 | 2026-06-11 |  | Routine Repairs | 1300114 | 36 FULFORD ROAD | 53314/1 | Works Started | ACE Agreed | 36/1083 | 2026-03-26 08:00:00 | 15 days |  |  | Shannon Slade | 13/02/2026 08:52 | No | Post-completion Items To Complete |  |  |  | 12/06 - WSG confirmed job complete. Awaiting cost to issue PO - CL 10/06 - Email sent to WSG chasing work - CL 19/5 - requested quote from WSG regarding glass pane (LL). | Complete | 260.96
2026-01-26 08:35:00 | As per sean p : Install fan through window in kitchen. | 2026-07-02 11:15:00 | 2026-07-02 | 2026-07-02 07:37:00 | Routine Repairs | 1194383 | 20 COWLING ROAD | 53058/1 | Works Completed | ACE Agreed | 36/1082 |  | 15 days |  |  | Shannon Slade | 13/02/2026 08:35 |  | Pre-completion Items To Complete |  | Yes |  | 01/07 - Appointment confirmed with tenant - CL 17/06 - Only book Jack or Alan for electrical jobs at this address - CL 16/06 - NA on 12/06, appointment rescheduled - CL Awaiting appointment date from compliance - CL | Complete | 584.01
2026-01-22 11:37:00 | Jeff Way - Roof repairs : variations to be amended as per John Oyeniyi | 2026-03-06 12:15:00 |  | 2026-03-06 10:17:00 | Routine Repairs | 1285990 | 138 Newland Road, Withywood | 52117/1 | Works Completed | Invoiced | 36/1080 | 2026-03-06 10:18:00 | 15 days |  |  | Shannon Slade | 11/02/2026 11:37 | No | Fully Complete | 2026-04-07 | Yes |  | 07/04 - KPI request sent and forwarded to EH - CL | Complete | 1106.88
2026-01-22 11:30:00 | JEFF WAY - Redecorate Hallway ceiling, part of kitchen and Bathroom FAO JOHN OYENIYI | 2026-03-25 15:45:00 |  | 2026-03-25 14:32:00 | Routine Repairs | 1294060 | 10 Blagrove Close | 17121/2 | Works Completed | Invoiced | 36/1079 |  | 15 days |  |  | Shannon Slade | 11/02/2026 11:30 |  | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI requested - CL Called tenant and booked appointment for works to be completed today (25/03) - CL | Complete | 422.94
2026-01-21 13:44:00 | CPMPLAINTS - Chimney Scaffold to be erected 900mm space all round chimney to remove and check flashings and soakers and to completely Duganitie stack re do flaunchingA?s .PLEASE ADVISE SAM SMART ON 07825906969 WHEN SCAFFOLD ERECTED |  |  | 2026-02-11 13:23:00 | Disrepair | 1284986 | 11 Molesworth Close | 49726/1 | Works Completed | Invoiced | 36/1073 | 2026-01-22 13:56:00 | 20 days |  |  | Shannon Slade | 17/02/2026 13:44 | Yes | Fully Complete | 2026-02-26 | Yes |  | 23/04 - ATTEMPTED TO CALL TENANT REGARDING THE CHIPS IN BATH, PHONES OFF. | Complete | 1119.41
2026-01-21 11:19:00 | Disrepair - Roofing and front elevation works as per Darren. | 2026-02-09 08:15:00 | 2026-06-15 | 2026-05-22 11:55:00 | Disrepair | 1158425 | 17 THOMSON ROAD | 45318/3 | Works Completed | ACE Agreed | 36/1078 |  | 20 days |  |  | Shannon Slade | 17/02/2026 11:19 |  | Pre-completion Items To Complete |  | No |  | 05/06 - PAINTING COMPLETED, HOWEVER, TENANT IS SAYING THAT STAINS ARE APPEARING. BOOKED TO REATTEND 15TH JUNE 20/05 - COMPLETION APPOINTMENT BOOKED FOR 22ND MAY LMT RETURNED TO COMPLETE WORKS AS PER INSTRUCTION FROM DARREN. SCAFFOLD NOW OFF-HIRED. REMAINING WORKS TO BE SCHEDULED. 23/04- INTERNAL WORKS BOOKED FOR 14TH MAY, DECS BOOKED FOR 18TH MAY | WIP | 1554.34
2026-01-21 09:35:00 | Jeff Way - Redecorate Bathroom Ceiling, and overhaul windows as per John Oyeniyi. | 2026-05-01 14:45:00 | 2026-06-15 | 2026-05-01 12:48:00 | Routine Repairs | 1302325 | 7 HARECLIVE ROAD | 16747/2 | Works Completed | ACE Agreed | 36/1077 | 2026-03-19 09:59:00 | 15 days |  |  | Shannon Slade | 10/02/2026 09:35 | No | Pre-completion Items To Complete |  | Yes |  |  | Complete | 314.73
2026-01-20 09:13:00 | JEFF WAY - AS PER ROB DOIDGE - VARIOUS REPAIRS, SEE SORS, HANDRAIL, ARCHITRAVES, PLASTER REPAIRS, FLOOR HOLE / WALL HOLES | 2026-04-08 10:30:00 |  | 2026-04-08 16:22:00 | Routine Repairs | 1291641 | 5 Wraxall Grove | 48813/1 | Works Completed | Invoiced | 36/1075 | 2026-03-10 08:00:00 | 15 days |  |  | Shannon Slade | 09/02/2026 09:13 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 16/04 - KPI received and uploaded - CL 15/04 - KPI requested - CL | Complete | 336.28
2026-01-20 09:03:00 | Jeff Way - Clean and Realign Roof Gutters on the Front Elevation to drain properly to the down pipe as per John Oyeniyi | 2026-04-01 08:00:00 |  | 2026-04-01 11:30:00 | Routine Repairs | 1291914 | 10 Aldwick Avenue | 48789/1 | Works Completed | Invoiced | 36/1074 | 2026-04-01 08:00:00 | 15 days |  |  | Shannon Slade | 09/02/2026 09:03 | No | Post-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI requested - CL Works completed 01/04 | Complete | 495.48
2026-01-19 09:46:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 20/1/26. 10 DAY PERIOD ENDS 3/2/26 | 2026-02-18 12:15:00 | 2026-02-18 | 2026-01-23 11:41:00 | Routine Repairs | 1313093 | 18 STILLINGFLEET ROAD | 48073/3 | Works Completed | Invoiced | 36/1071 | 2026-01-23 11:41:00 | 15 days |  |  | Shannon Slade | 06/02/2026 09:46 | Yes | Fully Complete | 2026-02-03 | Yes |  |  | Complete | 143.59
2026-01-16 08:31:00 | Complaint disrepair works / as per CG | 2026-02-27 08:00:00 | 2026-06-15 | 2026-06-15 13:42:00 | Disrepair | 1169955 | 108 Capgrave Crescent | 38801/2 | Works Completed | ACE Agreed | 36/1068 | 2026-02-23 08:00:00 | 20 days |  |  | Shannon Slade | 12/02/2026 08:31 | No | Pre-completion Items To Complete |  | Yes |  | 05/06 - ALL COMPLETED, FAN NEEDS RECONNECTING. TENANT IS ON HOLIDAY, BOOKED FOR 15TH JUNE. 19/03 - TENANT REFUSED APPOINTMENT ON 8TH MAY, WORKS BOOKED FOR 3RD OF JUNE. PLASTER NOT DRY - WORKS RE BOOKED FOR 13TH MARCH 23/03 - TENANT HAD FAMILY EMERGENCY ON 13TH SO COULDN'T ALLOW ACCESS. WORKS RE BOOKED FOR 9TH APRIL(AT HER REQUEST). 23/04 - PAINTING COMPLETED, ELECTRICIAN AND TILER BOOKED FOR 8TH MAY. | WIP | 682.96
2026-01-15 13:45:00 | Please carry out disrepairs work as listed | 2026-03-17 11:30:00 | 2026-07-10 |  | Disrepair | 1137435 | 18 WAINBROOK DRIVE | 40015/2 | New Works Instruction |  | 36/1065 |  | 20 days |  |  | Shannon Slade | 11/02/2026 13:45 |  | Pre-completion Items To Complete |  |  |  | 16/06 - TOIET WORKS APPROVED BY JAMES BAILEY, WORKS BOOEKD FOR 10TH JULY. 04/06 - EMAIL TO BE ISUSED TO SURVEYOR REGARDING TOILET WORKS, WORKS BOOKED FOR 17TH AND 18TH MARCH - WAITING FOR COMMERICAL TO CHECK COMPLETION 24/04 - MINOR PLASTER REPAIRS TO BE COMPLETED, TRIED TO CALL TENANT TO REBOOK BUT PHONE IS OFF, WILL TRY AGAIN. EMAIL SENT TO JAMES WITH PLUMBING INSPECTION 05/05 - WAITING | WIP | 703.29
2026-01-15 13:22:00 | Disrepair work: - Carry out service of windows to ensure good operation - Install 2 x vents in hallway cupboard doors (located at the top and bottom of the stairs) - paint with anti-fungal paint the inside of the cupboard at the top of the stairs. | 2026-05-12 12:00:00 |  | 2026-05-12 19:24:00 | Disrepair | 1280586 | 1 Gay Elms Road | 8992/1 | Works Completed |  | 36/1064 | 2026-01-30 09:00:00 | 20 days |  |  | Shannon Slade | 11/02/2026 13:22 | No | Suspended: Awaiting asbestos info |  | Yes |  | FIRST LOT OF WORKS COMPLETED - NEED TO ARRANGE APPOINTMENT FOR VARIATION WORKS 23/03 - WORKS BOOKED FOR 26TH MARCH FOR EXTERNAL WORKS. GLAZING WORKS ISSUED TO WSG AND WAITING FOR DATE FROM ELECTRICIANS. 30/03 - EXTERNAL WORKS COMPLETED. ELECTRICIANS BOOKE | Complete | 1148.54
2026-01-15 13:12:00 | JEFFWAY - AS PER ROB DOIDGE - FOLLOWING LEAK FROM ABOVE FLAT, REDEC AIRING CUPBD TO HALL IN FULL AND LHS WALL OF CUPBD BY FRONT DOOR. RENEW BASIN TO BATHROOM..... | 2026-05-29 09:15:00 | 2026-06-11 |  | Routine Repairs | 1296395 | 3 CHESTNUT HOUSE | 47079/1 | Works Started | ACE Agreed | 36/1063 | 2026-05-29 08:00:00 | 15 days |  |  | Shannon Slade | 04/02/2026 13:12 | No | Pre-completion Items To Complete |  |  |  | 01/06 - EMAIL FROM BCC TO CONFIRM CASA ARE ATTENDING ON 11TH JUNE. 21/05- tenant Called to say bathroom being completed by a different team, emailed Rob to confirm so we can cancel. 11/5 - Emailed surveyor asking for update on casa (LL).30/04 - Job put on hold until CASA complete asbestos report - CL 20/04 - RD has ordered an asbestos report from CASA - CL 17/04 - Asbestos report requested - CL | Complete | 676.64
2026-01-15 08:50:00 | JW to Carry out finishing works to plaster on top of window reveal. Decorate to finish, and install tenants blind for them as good-will-gesture. Renew extraction fan in kitchen. | 2026-03-31 10:45:00 |  | 2026-04-15 09:23:00 | Disrepair | 1082322 | 5 CONDER HOUSE | 46959/1 | Works Completed | Invoiced | 36/1062 | 2026-03-31 10:45:00 | 20 days |  |  | Shannon Slade | 11/02/2026 08:50 | No | Fully Complete | 2026-06-12 |  |  | 16/06 - WINDOW TRIM TO BE BOOKED IN. WORKS BOOKED FOR 31ST MARCH AND 10TH APRIL. 13/04 - ELECTRICAL WORKS COMPLETED 10TH APRIL, PAINTING WORKS TO BE COMPLETED 15TH APRIL. | Complete | 420.99
2026-01-15 07:55:00 | Complaint works- Replace bathroom floor, replace fan in bathroom. Replace bath panel. repair render. repair patio door. repair and service all windows |  |  | 2026-03-11 13:45:00 | Disrepair | 1304649 | 41 Hollisters Drive | 47242/1 | Works Completed | ACE Agreed | 36/1067 |  | 20 days |  |  | Shannon Slade | 11/02/2026 07:55 |  | Post-completion Items To Complete | 2026-06-12 |  |  | PHOTOS REQUESTED FROM DARREN WALLIS | Complete | 1061.92
2026-01-15 07:50:00 | Please carry out additional disrepair works as listed. | 2026-06-22 07:45:00 |  | 2026-05-14 19:28:00 | Disrepair | 1209149 | 15 WHITTOCK SQUARE | 34956/2 | Works Completed | ACE Agreed | 36/1066 |  | 20 days |  |  | Shannon Slade | 11/02/2026 07:50 |  | Post-completion Items To Complete | 2026-06-01 |  |  | WINDOW OVERHAUL COMPLETED, FAN UNABLE TO BE FITTED DUE TO PIPE WORK, BOILER FLU TO CLOSE - NEW FAN BIGGER DEPTH THAN EXISITING ONE IN PLAC. EITHER WINDOW FAN OR MOVE PIPEWORK? 30/03 - WINDOW FAN APPROVED. PO SENT TO GLAZING COMPANY TO COMPLETE WINDOW AND | Complete | 995.06
2026-01-14 08:28:00 | JEFF WAY - FAO JEFF NECK RENDER EXT WALL TO BOTTOM OF STAIRS & WORKS TO REAR SHOWER CUBICLE AS PER EMAIL | 2026-06-24 08:00:00 | 2026-07-01 | 2026-07-01 07:36:00 | Routine Repairs | 1281670 | 1 HIGHRIDGE CRESCENT | 8502/2 | Works Completed | ACE Agreed | 36/1061 | 2026-06-24 08:00:00 | 15 days |  |  | Shannon Slade | 03/02/2026 08:28 | No | Pre-completion Items To Complete |  | Yes |  | 30/06 - Appointment confirmed with tenant - CL 17/06 - Spoke with JN to discuss a plan to move the job forward. A joint site visit with DW to form a plan booked for 18/06. Tenant informed. - CL28/05 - Op to attend (28/5) and assess work in bathroom - CL 17/04 - Follow on appointment to carry out decs booked for 27/05. Asbestos report requested - CL | Complete | 350.75
2026-01-14 07:50:00 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF EXT FAN FROM DOWNSTAIRS W.C, PATCH REPAIR CEILING AFTER AND REPAINT. RENEW DRAUGHT STRIPS TO FRONT DOOR, CURRENT ONES STILL LETTING AIR THROUGH | 2026-06-25 13:00:00 | 2026-06-25 |  | Routine Repairs | 4511517 | 2 Buttercup Walk | 46615/1 | Works Started | Invoiced | 36/1060 | 2026-05-15 08:00:00 | 15 days |  |  | Shannon Slade | 03/02/2026 07:50 | No | Fully Complete | 2026-06-29 | Yes |  | 10/09 - KPi received and uploaded - CL 08/06 - KPI requested - CL 27/03 - Appointment booked to renew draught excluders, compliance tasked to book in fan removal. Once complete an appointment to repair hole from fan will be booked in - CL | Complete | 144.95
2026-01-14 07:43:00 | JEFF WAY - FAO Sean - Fit condensation fan to bathrm wall, install in LHS to window & clean mould to sloping celling in front bedrm/top up loft insulation please push into the slope to avoid cold spot. Install end cap to front elevation. | 2026-07-17 08:00:00 | 2026-07-17 |  | Routine Repairs | 1297150 | 29 COLESHILL DRIVE | 9603/2 | New Works Instruction | ACE Agreed | 36/1059 |  | 15 days |  |  | Shannon Slade | 03/02/2026 07:43 |  | Pre-completion Items To Complete |  |  |  | 08/06 - Appointment rescheduled due to illness - CL 30/04 - Follow on appointments booked for 19/05, 20/05 and 08/06 - CL 27/04 - Provisional appointments (19/05 and 08/06) have been booked in, awaiting response from tenant. Fans sent to compliance to book, awaiting a date. Email sent to CM for additional | Appointment booked | 918.95
2026-01-13 08:50:00 | Complaint works- please see email and report | 2026-03-17 08:00:00 | 2026-07-03 |  | Disrepair | 1302916 | 542 Hareclive Road, Hartcliffe, Bristol BS13 0LX | 45204/1 | Works Started | ACE Agreed | 36/1057 | 2026-03-11 08:00:00 | 20 days |  |  | Shannon Slade | 09/02/2026 08:50 | No | Pre-completion Items To Complete |  |  |  | 23/06 - KITCHEN WORKS RE-ISSUED TO FF, WAITING FOR COMPLETION. 19/03 - BATHROOM FAN NOT COMPLETE, ELECTRICIAN ATTENDING 21/05. SUPERVISOR ALSO ATTENDING FOR POST INSPECTION. | WIP | 3488.69
2026-01-13 08:22:00 | Complaint disrepair work - repair finish above front door and paint. Repoint crack in brickwork on front elevation. patch repair plaster by Bed1 and Kitchen and paint to finish. Check radiators and bleed if necessary. | 2026-03-17 08:00:00 | 2026-06-19 |  | Disrepair | 1279192 | 3 FOUR ACRES CLOSE | 45287/1 | New Works Instruction | ACE Agreed | 36/1056 |  | 20 days |  |  | Shannon Slade | 09/02/2026 08:22 |  | Pre-completion Items To Complete |  |  |  | 20/05 - WORKS BOOKED FOR 19TH AND 23RD JUNE. WORKS BOOKED FOR 19TH AND 25TH MARCH 23/03 - NO ACCESS ON 3 OCCASSIONS, EMAIL ISSUED TO CASSIE TO ASSIST WITH BOOKING IN. 30/03 - ATTEMPTED TO CALL TENANT TO RE BOOK WORKS - EMAIL ISSUED TO TENANT 31/03 - WORKS BOOKED FOR 13TH APRIL AND 30TH APRIL. 23/04 | Appointment booked | 299.16
2026-01-12 14:30:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. JOE COTTRELL ATTENDING 13/12/26. 10 DAY PERIOD ENDS 27/1/26 | 2026-05-18 08:00:00 |  | 2026-04-15 11:17:00 | Routine Repairs | 1309235 | 77 Murford Avenue, Hartcliffe | 45181/3 | Works Completed | Invoiced | 36/1055 | 2026-04-15 08:00:00 | 15 days |  |  | Shannon Slade | 30/01/2026 14:30 | No | Fully Complete | 2026-06-03 |  |  | 09/06 - KPI received and uploaded - CL 20/04 - Awaiting confirmation EICR has been completed - CL Awaiting date from contractor - CL | Complete | 143.59
2026-01-12 13:31:00 | jw - AS PER ROB DOIDGE - REPAIRS TO EXTERNAL PATHWAY / GARDEN AROUND DRAIN WHERE CRACKED, APPROX 3M2 | 2026-05-11 10:30:00 |  |  | Routine Repairs | 1317426 | 9 Wymbush Crescent | 44988/1 | Works Started | ACE Agreed | 36/1053 | 2026-05-07 08:00:00 | 15 days |  |  | Shannon Slade | 30/01/2026 13:31 | No | Suspended: Awaiting info Sub Contractor |  |  |  | 22/06 - AG Builders updated and will book appointments in for next week - CL 15/06 - Amended PO sent to AG Builders, awaiting appointment date - CL 12/06 - PO sent to AG Builders - CL 07/05 - Site visit booked SH to meet RD on site to assess work required - CL Email sent to RD notifying him on the condition of the garden path and how he would like to proceed - CL 06/05 - Appointment to be rescheduled due to operative illness - CL Works | Awaiting appointment date | 874.93
2026-01-12 13:26:00 | JW-AS PER ROB DOIDGE - RENEWAL OF BATH, APPROX 1SQM TILES TO SHOWER WALL AND TAPS TO BASIN . FIT EXTRACTOR FAN WHERE PASSIVE VENT IS AND OVERHAUL W.C FOR LEAKS | 2026-06-10 13:00:00 | 2026-06-10 | 2026-06-10 07:45:00 | Routine Repairs | 1292837 | 357 Bishport Avenue | 44995/1 | Works Completed |  | 36/1052 | 2026-04-14 08:00:00 | 15 days |  |  | Shannon Slade | 30/01/2026 13:26 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL | Complete | 1245.57
2026-01-12 13:09:00 | JW- AS PER ROB DOIDGE - RENEWAL OF KITCHEN FLOORING IN FULL, LIKE FOR LIKE WITH VINYL SHEETING, TNT TO CHOOSE COLOUR, APPROX 10M2. N.A.D |  | 2026-01-21 | 2026-01-21 14:00:00 | Routine Repairs | 1311315 | 2 REDWOOD HOUSE | 44984/1 | Works Completed | Invoiced | 36/1051 | 2026-01-20 14:00:00 | 15 days |  |  | Shannon Slade | 30/01/2026 13:09 | Yes | Post-completion Items To Complete | 2026-02-23 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 772.75
2026-01-09 12:32:00 | Carpenter - to repair or renew bifold door to down stairs wc. | 2026-01-29 10:30:00 | 2026-01-29 | 2026-01-29 13:59:00 | Routine Repairs | 1156521 | 2 ROBINSON DRIVE | 62713/1 | Works Completed | Invoiced | 36/1050 | 2026-01-29 10:30:00 | 15 days |  |  | Shannon Slade | 29/01/2026 12:32 | No | Fully Complete | 2026-02-16 | Yes |  |  | Complete | 144.31
2026-01-09 12:25:00 | Jeff Way as per BB Carry out remedila works to porch roof to remedy original defective works carriedby contratcor |  |  |  | Routine Repairs | 1256413 | 14, FIRST FLOOR FLAT MILES ROAD | 44775/1 | New Works Instruction | ACE Agreed | 36/1049 |  | 15 days |  |  | Shannon Slade | 29/01/2026 12:25 |  | Pre-completion Items To Complete |  |  |  |  | Held BCC | 2428.2
2026-01-09 11:55:00 | Complaint disrepair works / as per CG | 2026-03-23 08:00:00 |  | 2026-04-10 10:29:00 | Disrepair | 1132350 | Roegate House, 61 Whitefield Avenue | 38832/1 | Works Completed | ACE Agreed | 36/1034 | 2026-02-23 08:00:00 | 20 days |  |  | Shannon Slade | 05/02/2026 11:55 | No | Post-completion Items To Complete | 2026-04-24 | Yes |  | 20/03 -ARRANGE ELECTRICIAN TO RETURN AND COMPLETE SURFACE BOX. 23/03 - WORKS BOOKED FOR 10TH APRIL. | Complete | 628.63
2026-01-08 13:49:00 | COMPLAINT - FOLLOW ON WORKS |  | 2026-06-30 | 2026-03-24 08:27:00 | Routine Repairs | 1841925 | BK 14 MILES ROAD | TBC | Works Completed | ACE Agreed | 36/1024 |  | 15 days |  |  | Shannon Slade | 28/01/2026 13:49 |  | Pre-works Items To Complete | 2026-06-15 | Yes |  | 15/06 - KPI requested - CL | Complete | 4633.42
2026-01-08 13:46:00 | JW - As Per Sean P : Hack off and renew plaster. LHS of the door in the living room . | 2026-01-22 09:00:00 | 2026-01-22 | 2026-01-22 14:48:00 | Routine Repairs | 1205523 | 258 STURMINSTER ROAD | 44193/1 | Works Completed | Invoiced | 36/1023 | 2026-01-14 08:00:00 | 15 days |  |  | Shannon Slade | 28/01/2026 13:46 | Yes | Fully Complete | 2026-01-22 | Yes |  |  | Complete | 465.12
2026-01-08 13:44:00 | JW - As per Jeff Neck - Repair hairline crack in kitchen ceiling and repaint to suit | 2026-03-12 08:00:00 |  | 2026-03-18 09:48:00 | Routine Repairs | 1310969 | 68 PAWLETT ROAD | 44182/1 | Works Completed | ACE Agreed | 36/1022 | 2026-03-18 08:00:00 | 15 days |  |  | Shannon Slade | 28/01/2026 13:44 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI Requested - CL | Complete | 151.0
2026-01-08 13:39:00 | JW - As per Jeff N - Hack off damage plasterwork above living room doorhead and apply plaster skim to match existing levels, tenant to redecorate to suit | 2026-02-24 11:15:00 |  | 2026-02-24 09:39:00 | Routine Repairs | 1284395 | 4 LULSGATE ROAD | 44179/1 | Works Completed | ACE Agreed | 36/1021 | 2026-02-24 11:15:00 | 15 days |  |  | Shannon Slade | 28/01/2026 13:39 | No | Pre-completion Items To Complete | 2026-03-31 | Yes |  |  | Complete | 75.75
2026-01-08 13:20:00 | JW - As per Jeff N - Check seal on living room window head overhaul and leave in working order | 2026-02-26 15:00:00 |  | 2026-03-16 13:48:00 | Routine Repairs | 1313720 | 56 Tewther Road, Hartcliffe, Bristol | 44187/1 | Works Completed | ACE Agreed | 36/1019 | 2026-02-26 15:00:00 | 15 days |  |  | Shannon Slade | 28/01/2026 13:20 | No | Post-completion Items To Complete | 2026-03-23 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 50.0
2026-01-08 13:16:00 | JW - As per Jeff N - Cut out cracked brickwork at low level rear elevation and refix new rejointed to match existing | 2026-03-05 12:00:00 |  | 2026-03-06 13:44:00 | Routine Repairs | 1278360 | 85 FOUR ACRES | 44174/1 | Works Completed | Invoiced | 36/1018 |  | 15 days |  |  | Shannon Slade | 28/01/2026 13:16 |  | Fully Complete | 2026-03-19 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 189.48
2026-01-08 13:11:00 | Jeffway -As per John O - Scrape back plaster work in Lounge Ceiling, skim and paint; Latex floor in lounge and Landing. Paint woodwork in Bathroom, Overhaul fan to kitchen | 2026-07-01 08:00:00 | 2026-06-24 |  | Routine Repairs | 1317084 | 60 WROUGHTON DRIVE | 44148/1 | Works Started | ACE Agreed | 36/1016 | 2026-03-30 09:40:00 | 15 days |  |  | Shannon Slade | 28/01/2026 13:11 | No | Suspended: Awaiting Client Action/Response |  |  |  | 23/06 - Tenant called to cancel appointment due to ceiling having collapsed from leak in loft. Email sent to JO and EH - CL06/05 - Follow on appointment booked for 03/06 - CL Fans booked in to overhaul on 30/03, plastering booked for 14/04 and decs booked for 28/04 - CL | Held BCC | 569.72
2026-01-08 11:07:00 | JW- As Per Ian O - PLASTERING , PAINTING , LEAK AROUND DORMA , RE FIX PENDANT , DOOR LOCKS , ROOFING | 2026-07-20 09:00:00 | 2026-07-20 |  | Routine Repairs | 1292257 | 9 Barbour Gardens | 44451/1 | New Works Instruction | ACE Agreed | 36/1027 |  | 15 days |  |  | Shannon Slade | 28/01/2026 11:07 |  | Pre-completion Items To Complete |  |  |  | 29/05 - Extension request sent - CL 07/05 - Unable to get hold of tenant, voicemail and text sent - CL 21/04 - Asbestos report received and uploaded - CL | Appointment booked | 782.89
2026-01-08 11:03:00 | JW-AS PER ROB DOIDGE - OVERHAUL FRONT AND BACK DOORS FOR DRAUGHTS AND SECURITY. REPAIR WALL BY RHS CORNER OF BACK DOOR AND REFIX / SEAL BACK UPVC TRIM TO FRONT DOOR RHS | 2026-07-02 17:15:00 | 2026-07-02 | 2026-07-02 07:50:00 | Routine Repairs | 1297069 | 12 COLESHILL DRIVE | 44450/1 | Works Completed | ACE Agreed | 36/1026 | 2026-07-01 11:15:00 | 15 days |  |  | Shannon Slade | 28/01/2026 11:03 | No | Pre-completion Items To Complete |  | Yes |  | 30/06 - Appointment confirmed with tenant - CL | Complete | 282.86
2026-01-08 10:54:00 | JW- As per Sean P : there is a hole in the T&G/ chipboard flooring. Please cut out and renew to patch in with existing to living room floor. | 2026-07-22 12:30:00 | 2026-07-22 |  | Routine Repairs | 1195580 | 42 DURWESTON WALK | 44155/1 | Works Started | ACE Agreed | 36/1025 | 2026-06-23 12:00:00 | 15 days |  |  | Shannon Slade | 28/01/2026 10:54 | No | Suspended: Awaiting asbestos info |  |  |  | 24/06 - NA on 23/06, appointment rebooked - CL | Appointment booked | 80.76
2026-01-08 10:31:00 | JEFF WAY - FAO DARREN : SCAFFOLD TO BE ERRECTED ASAP TO GAIN ACCESS FOR REMOVAL OF CHIMNEY STACK AND MAKE GOOD . AS PER DISCUSSION POSSIBLE MAKE GOOD TEMP TO RESOLVE WATER INGRESS AS PER IAN OGBORNE | 2026-01-23 08:00:00 |  | 2026-02-19 13:45:00 | Routine Repairs | 1279103 | 215 FOUR ACRES | 33980/2 | Works Completed | Invoiced | 36/1003 | 2026-01-20 08:00:00 | 15 days |  |  | Shannon Slade | 28/01/2026 10:31 | No | Fully Complete | 2026-02-26 | Yes |  |  | Complete | 2463.26
2026-01-07 12:28:00 | Complaint works- As per Andy inspection raised by James. Works include decorative finishes flooring and tiling. | 2026-07-01 08:00:00 | 2026-07-01 |  | Disrepair | 1273434 | 28B BRUNEL ROAD | 43926/1 | New Works Instruction | ACE Agreed | 36/1040 |  | 20 days |  |  | Shannon Slade | 03/02/2026 12:28 |  | Pre-completion Items To Complete |  |  |  | 02/07 - Review needed to identify outstanding work needed - CL 30/06 - Tenant not advised of appointment - CL 16/06 - PRT WORKS COMPLETED, NEED TO RETURN GLOSS AND SAND DOWN FRONT DOOR. BOOKED FOR 1ST JULY 08/06 - TENANT DIDNT ALLOW PLASTERERS BACK IN, MULTITRADE ON SITE 08/06, PLASTERERS TO BE REBOOKED | Manager review needed | 4551.31
2026-01-06 13:08:00 | As per Darryl's (07733 831 884) request - renew flaunching to inspection chamber (closest SOR). Meet on site to discuss concerete plinths to shed at the back. Many thanks | 2026-03-16 08:00:00 | 2026-03-16 | 2026-03-17 12:27:00 | Routine Repairs | 1272497 | 826 Bishport Avenue | 36688/1 | Works Completed | Invoiced | 36/1015 | 2026-03-17 12:27:00 | 15 days |  |  | Shannon Slade | 26/01/2026 13:08 | No | Pre-completion Items To Complete | 2026-03-25 | Yes |  |  | Complete | 85.67
2026-01-06 13:04:00 | Jeffway - As per John O: Repair Kitchen worktop, overhaul and resilicone window | 2026-06-09 09:00:00 | 2026-07-02 |  | Routine Repairs | 1304990 | 40 HONEY GARSTON ROAD | 43366/1 | Works Started | ACE Agreed | 36/1014 | 2026-07-02 08:00:00 | 15 days |  |  | Shannon Slade | 26/01/2026 13:04 | No | Suspended: Awaiting Client Action/Response |  |  |  | 03/07 - NA on 02/07 order to be returned to BCC email sent to EH and IO - CL - CL 09/06 - Unable to get hold of tenant voicemail left informing of cancelled appointment - CL 28/04 - Contacted by housing officer as the number provided was hers sent by mistake. She advised that tenant is a CT as he can be temperamental. Contact details updated and appointment booked for 09/06 - CL 09/04 - Unable to make contact with tenant, vo | Appointment booked | 312.25
2025-12-31 14:31:00 | JEFF WAY - AS PER ROB DOIDGE - 1M2 PATCH REPAIR TO PLASTERBOARD CEILING IN BACK BEDROOM. PATCH PAINT ALSO. LEAK NOW FIXED | 2026-04-07 08:00:00 |  | 2026-04-07 14:35:00 | Routine Repairs | 1294242 | 4 BLAGROVE CRESCENT | 13134/2 | Works Completed | Invoiced | 36/1010 | 2026-03-31 07:45:00 | 15 days |  |  | Shannon Slade | 22/01/2026 14:31 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL | Complete | 216.4
2025-12-31 13:01:00 | JEFF WAY - FAO R DOIDGE - REMOVAL OF CORNER KITCH UNIT & UNIT RHS OF COOKER TO FILL PEST HOLES AROUND PIPEWORKE TAKE PHOTOS OF HOLES FILLED DUE TO FOLLOW ON. ENSURE PLINTHS ARE FIXED BK SECURELY. HAVE USED FIRE FOAM SOR FOR THE FILLING | 2026-05-21 10:30:00 | 2026-05-21 | 2026-05-21 14:51:00 | Routine Repairs | 1252706 | 2 LOMBARD STREET | 9448/2 | Works Completed | Invoiced | 36/1013 | 2026-03-30 08:00:00 | 15 days |  |  | Shannon Slade | 22/01/2026 13:01 | No | Pre-completion Items To Complete | 2026-06-08 | Yes |  | 10/09 - KPI received and uploaded - CL 08/06 - KPI requested - CL | Complete | 135.13
2025-12-31 12:40:00 | JEFF WAY - FAO JOHN OYENIYI - Scaffold up for Roof Inspection |  |  | 2026-03-11 13:49:00 | Routine Repairs | 1285990 | 138 Newland Road, Withywood | 42542/1 | Works Completed | Invoiced | 36/1012 |  | 15 days |  |  | Shannon Slade | 22/01/2026 12:40 |  | Pre-completion Items To Complete | 2026-03-25 | Yes |  |  | Complete | 973.32
2025-12-31 12:36:00 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF OLD MOULD GROWTH IN BACK BEDROOM , ROOF HAS BEEN RENEWED AND AREA DRIED OUT. REPAIR CEILING AS REQUIRED. ALSO OVERHAUL FRONT LIVING ROOM WINDOW, TENANT AFRAID TO OPEN AFTER HINGE IS LOOSE. - PLEASE CALL TENANT WHILE OUTSIDE SO SHE CAN REMOVE DOG FROM PROPERTY. | 2026-05-18 17:45:00 | 2026-05-18 | 2026-05-18 17:49:00 | Routine Repairs | 1312829 | 8 SHORTWOOD ROAD | 42551/1 | Works Completed | ACE Agreed | 36/1011 | 2026-04-28 08:00:00 | 15 days |  |  | Shannon Slade | 22/01/2026 12:36 | No | Pre-completion Items To Complete | 2026-06-08 | Yes |  | 08/06 - KPI requested - CL 29/04 - Unable to contact tenant, voicemail and text sent - CL 08/04 - D&M to rebook appointment, no access. Issued to d&m team to re-book -10/4. App booked 24/04 | Complete | 152.47
2025-12-31 12:27:00 | JEFF WAY - AS PER ROB DOIDGE - WINDOW OVERHAUL TO PROPERTY , VARIOUS INCLUDING LIVING ROOM , BALCONY AND BEDROOMS ARE DRAUGHTY, LIKELY HINGE ISSUES | 2026-06-12 12:00:00 |  | 2026-03-18 11:51:00 | Routine Repairs | 1293045 | 384 BishportAvenue | 12541/2 | Works Completed | Invoiced | 36/1009 | 2026-03-18 14:00:00 | 15 days |  |  | Shannon Slade | 22/01/2026 12:27 | No | Pre-completion Items To Complete | 2026-03-25 | Yes |  |  | Complete | 212.04
2025-12-31 12:16:00 | JEFF WAY - AS PER ROB DOIDGE - DRY SCRAPE, PREP, SEAL AND REPAINT BOTH LIVING ROOM AND BATHROOM CEILINGS IN FULL. NOT ALL NEEDS SCRAPING, PREVIOUS LEAKS TO BALCONY AREA AND BATHROOM CEILING. 30M2 AREA TOTAL | 2026-07-27 15:30:00 | 2026-07-27 |  | Routine Repairs | 1252080 | 92 LITTLECROSS HOUSE | 12157/2 | Works Started | ACE Agreed | 36/1007 | 2026-05-19 08:00:00 | 15 days |  |  | Shannon Slade | 22/01/2026 12:16 | No | Pre-completion Items To Complete |  |  |  | Bathroom Decs completed. tenant is sleeping in living room, rebook in living room decs 07/04 | WIP | 454.8
2025-12-31 12:07:00 | Please renew 15m2 ceiling in liv room 2, TEX NAD | 2026-07-16 08:00:00 | 2026-07-09 |  | Routine Repairs | 1264160 | 34 St Johns Crescent | 42396/1 | Works Started | ACE Agreed | 36/1006 | 2026-03-20 09:00:00 | 15 days |  |  | Shannon Slade | 22/01/2026 12:07 | No | Pre-completion Items To Complete |  |  |  | 29/04 - Tenant called and rescheduled her appointment on 11/05 to 20/05. Follow on appointment s booked for 11/05 and 03/06 - CL Follow on appointments booked for 29/04 and 30/04 - CL | WIP | 992.87
2025-12-30 16:22:00 | renew first course of felt and batten 3 sides, insulating slopping ceilings between the eves and installing eves trays, new fascia, soffits, guttering and down pipes - Matt Ford |  |  | 2026-03-02 08:43:00 | Routine Repairs | 1233847 | 35 Tavistock Road | 42373/1 | Works Completed | Invoiced | 36/1005 |  | 15 days |  |  | Shannon Slade | 21/01/2026 16:22 |  | Fully Complete | 2026-03-25 | Yes |  |  | Complete | 9905.6
2025-12-29 10:36:00 | JEFF WAY - AS PER ROB DOIDGE - RENEWAL OF 2 X MISSING BATH TILES, FILLING OF SMALL CRACK TO BATHROOM WALL. RENEWAL OF 5 X BALUSTRADES TO STAIRCASE WHERE MISSING | 2026-05-21 18:00:00 | 2026-06-04 | 2026-06-04 12:24:00 | Routine Repairs | 1303282 | 44 HARTGILL CLOSE | 11705/2 | Works Completed | ACE Agreed | 36/1004 | 2026-05-21 18:00:00 | 15 days |  |  | Shannon Slade | 20/01/2026 10:36 | No | Pre-completion Items To Complete |  | No |  | 21/04 - Appointment rescheduled to 11/05 - CL Asbestos report request sent to RD and appointment rescheduled to 20/04 - CL | Complete | 129.45
2025-12-29 09:50:00 | JEFF WAY - FAO JEFF NECK - BATHROOM WORKS AS PER WORKS ORDER SENT | 2026-02-17 08:00:00 |  | 2026-02-23 08:57:00 | Routine Repairs | 1303088 | 5 Hartgill Close, Hartcliffe | 41904/1 | Works Completed | ACE Agreed | 36/1002 | 2026-02-05 08:00:00 | 15 days |  |  | Shannon Slade | 20/01/2026 09:50 | No | Pre-completion Items To Complete | 2026-03-25 | Yes |  |  | Complete | 911.32
2025-12-24 12:04:00 | JEFF WAY - AS PER ROB DOIDGE - RENEWAL OF BATH PANEL AND TIMBER PANEL TO DUCTING / SERVICES | 2026-03-27 08:00:00 |  | 2026-03-27 10:21:00 | Routine Repairs | 1313548 | 108 STILLINGFLEET ROAD | 10825/2 | Works Completed | Invoiced | 36/1001 | 2026-03-27 08:00:00 | 15 days |  |  | Shannon Slade | 19/01/2026 12:04 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL | Complete | 133.53
2025-12-23 14:00:00 | cover over porch and bay roof, with GRP flat roof, use 150mm lead flashing, sor codes best that could be found |  |  | 2026-03-31 08:00:00 | Routine Repairs | 1204586 | 37 SHOWERING ROAD | 41571/1 | Works Completed | Invoiced | 36/999 |  | 15 days |  |  | Shannon Slade | 16/01/2026 14:00 |  | Fully Complete | 2026-04-09 | Yes |  | 09/04 - KPI received and uploaded - CL Works complete 01/04 | Complete | 2487.77
2025-12-23 14:00:00 | Scaffolding required upto gutter height at front and rear of property. Roofers to renew first course of felt and batten, installing eves trays and insulating sloping ceilings with 50mm rock wool slabs Matt Ford |  |  | 2026-03-24 11:47:00 | Routine Repairs | 1222226 | 97 ILMINSTER AVENUE | 41504/1 | Works Completed | Invoiced | 36/1000 |  | 15 days |  |  | Shannon Slade | 16/01/2026 14:00 |  | Fully Complete | 2026-03-26 | Yes |  |  | Complete | 2311.33
2025-12-23 12:55:00 | DISREPAIR - JEFF WAY TO CARRY OUT WORKS RAISED BY CHARLOTTE SMART 07920616045 | 2026-06-18 12:15:00 |  |  | Disrepair | 1161611 | 61 WALKER CLOSE | 41375/1 | Works Started | ACE Agreed | 36/1041 | 2026-03-16 08:00:00 | 20 days |  |  | Shannon Slade | 23/01/2026 12:55 | No | Pre-completion Items To Complete |  |  |  | 16/06 - JWC WORKS COMPLETED, NO ACCESS ON 8TH FOR D&M. WAITING FOR CONFIRMATION DATE FROM D&M. 20/05 - BATHROOM WORKS TO BE COMPLETED 3RD JUNE. TASK ISSUED TO DARREN TO LET ME KNOW WHAT WORKS NEED TO BE COMPLETED. | WIP | 1738.88
2025-12-23 11:31:00 | complaint works- see report and email- WO- Thomas Lear | 2026-03-05 08:00:00 | 2026-06-05 | 2026-06-03 22:03:00 | Disrepair | 1263010 | 39 SPENCER HOUSE | 37917/1 | Works Completed | ACE Agreed | 36/996 | 2026-03-06 08:00:00 | 20 days |  |  | Shannon Slade | 23/01/2026 11:31 | No | Pre-completion Items To Complete |  | No |  | 19/05 - KITCHEN WORKS COMPLETED, PLASTERING COMPLETED, PAINTING AND SILICONE BOOKED FOR 5TH JUNE | Appointment booked | 507.01
2025-12-23 10:43:00 | complaint works- Thomas Lear- please see report and email. | 2026-05-18 10:00:00 | 2026-06-22 |  | Disrepair | 1309462 | 16 MURFORD WALK | 37119/1 | New Works Instruction | ACE Agreed | 36/992 |  | 20 days |  |  | Shannon Slade | 23/01/2026 10:43 |  | Suspended: Awaiting Client Action/Response |  |  |  | 02/07- awaiting environmental clean confirmation from BCC 25/06 - Spoke with tenants mother who confirmed he is not currently living in the property as it is infested with rats - CL As20/05 - NO ACCESS, WORKS BOOKED FOR 22ND, 23RD AND 26TH JUNE | Appointment booked | 650.56
2025-12-22 11:03:00 | Please carry out additional disrepair works as listed out | 2026-05-27 08:00:00 |  |  | Disrepair | 1104796 | 89, FLAT 10 ASHLEY ROAD | 34878/1 | Works Started | ACE Agreed | 36/986 | 2026-03-12 08:00:00 | 20 days |  |  | Shannon Slade | 22/01/2026 11:03 | No | Pre-completion Items To Complete |  |  |  | 15/06 - JWC WORKS COMPLETED, WAITING FOR DATE THAT FF ARE ATTENDING. 01/06 - WORKS RE BOOKED FOR 9TH AND 10TH JUNE TENANT REFUSED ACCESS ON 12TH MARCH DUE TO COLOUR OF KITCHEN- EMAIL ISSUED TO JAMES, WAITING FOR UPDATE FROM BCC 17/04 - WORKS BOOKED FOR 27TH AND 28TH MAY | WIP | 1709.38
2025-12-19 13:55:00 | Living room ceiling partially collapsed, now made safe, requires mortar removing/boarding and skimming, ELE and DEC parts included R.M | 2026-06-16 08:00:00 | 2026-06-16 | 2026-02-19 07:44:00 | Routine Repairs | 1245369 | 42 Eldon Terrace, Windmill Hill | 40478/1 | Works Completed | Invoiced | 36/982 | 2026-06-16 08:00:00 | 15 days |  |  | Lainie Lavin | 14/01/2026 13:55 | No | Fully Complete | 2026-02-26 | Yes |  | 07/04 - KPI request added and forwarded to EH - CL- Works complete JWC to reattend to trim up bay window 09/04 | Complete | 1138.05
2025-12-19 13:55:00 | AS PER GERRY RYAN = To remove bathroom suit = so you can renew the bathroom old lath plaster walls and in the bedroom due to water damage from shower / install shower board around the bath / fix back bathroom suit / re-decorate both rooms | 2026-03-24 11:00:00 |  | 2026-03-23 14:39:00 | Routine Repairs | 1176610 | 41 Grove Park Road, Brislington | 40750/1 | Works Completed | Invoiced | 36/983 | 2026-03-18 08:00:00 | 15 days |  |  | Lainie Lavin | 14/01/2026 13:55 | No | Fully Complete | 2026-04-15 | Yes |  | 27/04 - KPI received and uploaded - CL 15/04 - KPI requested - CL Variation request sent to GR - CL | Complete | 2726.86
2025-12-19 13:44:00 | Complaint works- WO- Thomas Lear- please see email and complaint report | 2026-07-08 08:00:00 | 2026-07-08 |  | Disrepair | 1221347 | 30 Home Mead, Creswicke Road | 40673/1 | Works Started | ACE Agreed | 36/1048 | 2026-06-09 08:00:00 | 20 days |  |  | Shannon Slade | 21/01/2026 13:44 | No | Pre-completion Items To Complete |  |  |  | 30/06 - Follow on appointment needs to be booked for sanding, painting and skirting - CL 29/06 - Appointment conformed with tenant - CL 15/06 - PLASTERING/EXTERNAL WORKS COMPLETED. INTERNALS BOOKED FOR 30TH JUNE, EMAIL SENT TO BCC TO SEND ACCESS LETTER. | WIP | 1554.77
2025-12-19 13:14:00 | Complaint- Charlotte Smart As per SOW, charlotte.smart2@bristol.gov.uk Please advise when this is scheduled. | 2026-05-19 08:00:00 |  | 2026-04-02 12:55:00 | Disrepair | 1301913 | 48 GREENDITCH AVENUE | 40770/1 | Works Completed | Invoiced | 36/1042 |  | 20 days |  |  | Shannon Slade | 21/01/2026 13:14 |  | Fully Complete | 2026-04-15 | Yes |  |  | Complete | 1519.39
2025-12-19 09:15:00 | Jeffway - Extractor Fan repairs, Redecoration and Window Reglazing. | 2026-05-19 12:15:00 |  | 2026-06-01 07:45:00 | Routine Repairs | 1244413 | 2 Clift Road, Ashton Gate, | 40560/1 | Works Completed | ACE Agreed | 36/978 | 2026-04-01 08:00:00 | 15 days |  |  | Lainie Lavin | 14/01/2026 09:15 | No | Pre-completion Items To Complete | 2026-07-01 | Yes |  | 01/07 - KPI resent - CL 29/06 - KPI requested - CL 10/06 - Email sent to WSG update on glazing unit - CL 01/06 - AWAITING ELECTRICAL CERTS FROM JACK. works complete from RR, Fan overhaul no access on the 01/04 - awaiting appointment date from compliance regarding fan overhaul 07/04. No answer from tenant tried multiple times - 10/4. | Complete | 1206.55
2025-12-18 13:42:00 | Complaint works. repair bathroom Floor, James Saunders raised via Alvaro's notes. | 2026-02-17 12:00:00 |  | 2026-03-26 15:19:00 | Disrepair | 1244286 | 43 Chatterton House, Ship Lane | 40330/1 | Works Completed | Invoiced | 36/1047 |  | 20 days |  |  | Shannon Slade | 20/01/2026 13:42 |  | Fully Complete | 2026-04-15 | Yes |  | WORKS BOOKED FOR 25TH AND 26TH MARCH. 30/03 - FF WAS UNABLE TO TAKE UP TILES AND ADHESIVE. MY OP HAS NOW COMPLETED WORKS, ASKED FF TO RETURN TO COMPLETE FLOORING. | Complete | 498.51
2025-12-17 14:41:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. TOM WALKER ATTENDING 8/1/26. 10 DAY PERIOD ENDS 22/1/26 |  | 2026-01-21 | 2026-01-21 14:51:00 | Routine Repairs | 1030371 | 2 Richmond Terrace, Avonmouth | 40101/3 | Works Completed | Invoiced | 36/972 | 2026-01-21 11:24:00 | 15 days |  |  | Lainie Lavin | 12/01/2026 14:41 | No | Fully Complete | 2026-02-03 | Yes |  |  | Complete | 158.34
2025-12-17 11:31:00 | Jeffway- as per Joe Cotrell- Various works at property including flooring. Please see email for full works description | 2026-06-16 08:00:00 | 2026-06-16 | 2026-03-30 15:45:00 | Routine Repairs | 1255443 | 16 Martock Crescent, Bedminster | 39947/1 | Works Completed | Invoiced | 36/971 | 2026-03-13 10:30:00 | 15 days |  |  | Lainie Lavin | 12/01/2026 11:31 | No | Post-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL 09/04 - Email sent for completion photos of demolition - CL Appointment booked with tenant for Tim to attend on 30/03 - CL | Complete | 1506.38
2025-12-17 09:11:00 | JW - As per Ian - RE FIT LOW LEVEL GUTTERING AT REAR / REPLACE POORLY FITTED INTERNAL WINDOW BOARD IN BEDROOM / PATIO DOOR OVERHAUL / FILLING AND SANDING INTERNAL | 2026-04-13 16:15:00 |  | 2026-04-13 08:22:00 | Routine Repairs | 1196663 | 14 Eastcote Park, Whitchurch | 32813/2 | Works Completed | Invoiced | 36/969 | 2026-04-13 08:00:00 | 15 days |  |  | Lainie Lavin | 12/01/2026 09:11 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 16/06 - KPI received and uploaded - CL 15/04 - KPI request sent - CL Appointment booked with tenant for repair to window cill. Tenant has refused all other work. Email sent to IO advising of refusal - CL | Complete | 439.55
2025-12-16 14:01:00 | JEFF WAY- BRICKWORK , EXTRACTOR FANS PLEASE ENSURE ALL FANS ARE DUCTED WITH EXTERNAL GRILLES | 2026-05-22 13:00:00 | 2026-05-22 | 2026-05-22 16:47:00 | Routine Repairs | 1299463 | 47 Englishcombe Road, Hartcliffe | 39721/1 | Works Completed | ACE Agreed | 36/967 | 2026-05-22 13:00:00 | 15 days |  |  | Lainie Lavin | 09/01/2026 14:01 | No | Pre-completion Items To Complete | 2026-06-11 | Yes |  | 11/06 - KPI requested - CL 30/04 - Appointment booked with tenant to complete fan install - CL 27/04 - Hole under bath completed, awaiting dates from Compliance with Fans dates | Complete | 848.82
2025-12-16 13:40:00 | Complaint disrepair works - KITCHEN: DOOR OVERHAUL, EXTERNAL:GUTTER CLEAN, ROOF: BRICK REPOINT ON CHIMNEY, RENEW LEAD FLASHING ON ROOF, BAHROOM: WINDOW EASE AND ADJUST | 2026-04-28 08:00:00 |  | 2026-05-26 11:16:00 | Disrepair | 1222022 | 71 Ilminster Avenue | 39505/1 | Works Completed | Invoiced | 36/1046 |  | 20 days |  |  | Shannon Slade | 16/01/2026 13:40 |  | Fully Complete | 2026-05-29 |  |  |  | Complete | 1446.33
2025-12-16 13:38:00 | Front door - overhaul Front and back door - prep and paint with gloss paint inside of doors - in 3rd bedroom - renew blown window panes - renew extraction fans | 2026-03-02 11:30:00 |  |  | Disrepair | 1235434 | 73 Torrington Avenue | 39515/1 | New Works Instruction | ACE Agreed | 36/1045 |  | 20 days |  |  | Shannon Slade | 16/01/2026 13:38 |  | Suspended: Awaiting Client Action/Response |  |  |  | 1606 - TENANT REFUSING WORKS TO FRONT DOOR, EMAIL ISSUED TO CASS. WORKS BOOKED FOR 15TH APRIL. 23/04 - OPERATIVES WAS SICK ON 15TH APRIL - APPOINTMENT REARRANGED FOR 29TH MAY, DUE TO TENANT STARTING NEW JOB | Held BCC | 911.9
2025-12-16 13:01:00 | Jeffway - As Per John O: Kindly realign the Gutters to slope properly to the down pipe on both front and rear elevations Please ensure this is properly realigned to the down pipe. Call John to meet on Site. | 2026-04-25 08:00:00 |  |  | Routine Repairs | 1292473 | 281 Bishport Avenue, Hartcliffe | 39656/1 | Works Started | Works Cancelled | 36/966 | 2026-04-25 08:00:00 | 15 days |  | 2026-06-16 12:18:05 | Lainie Lavin | 09/01/2026 13:01 | No | Suspended: Awaiting Client Action/Response |  |  |  | 02/07 - Awaiting direction from EH - CL 25/06 - BCC confirmed that scaffold was not approved and will investigate on if BCC plumbing - CL 27/04 - Jeffway Attended site but works already complete- | Held BCC | 2500.39
2025-12-16 07:21:00 | Complaint works- New bathroom. replacing dg units x4, minor mould treatment. skirting, draft excluders and over haul external doors. | 2026-07-06 08:00:00 | 2026-07-03 |  | Disrepair | 1235456 | 75 TORRINGTON AVENUE | 32908/1 | Works Started | ACE Agreed | 36/1054 | 2026-03-30 08:00:00 | 20 days |  |  | Shannon Slade | 16/01/2026 07:21 | No | Pre-completion Items To Complete |  |  |  | 26/06 - WIP, CHASED GLAZING COMPANY. WAITING FOR UPDATE WITH REGARDS TO WINDOWS. SIMON BOOKED TO COMPLETE SNAGGING WORKS 29TH, ELECTRICIAN BOOKED FOR 29TH. 25/06 - Decs completed 24/06 - CL 16/06 - RADS TO BE COMPLETED, DECS TO BE COMPLETED AND THEN FLOORING. 05/06 - JAMIE RETURNNG TO CARRY ON WITH WORKS. SPOKE WITH TENANT TO UPDATE - WORKS BOOKED FOR 18TH MARCH - WORKS BOOKED FOR 30TH AND 31ST TO COMPLETE BATHROOM. - 07/04 - BOOK IN REMAINING WORKS. 24/04 - DARREN WHITCHURCH TO COMPLETE SITE VISIT ON MONDAY AT 10AM TO ASSESS IF WORKS ARE COMPLETED13/05 - | WIP | 4152.59
2025-12-15 14:41:00 | lounge / shower room and bedroom works | 2026-03-27 14:00:00 | 2026-01-15 | 2026-01-15 09:39:00 | Routine Repairs | 1280928 | 62 Gay Elms Road, Withywood | 39337/1 | Works Completed | Invoiced | 36/963 | 2026-01-14 08:00:00 | 15 days |  |  | Lainie Lavin | 08/01/2026 14:41 | No | Fully Complete | 2026-02-16 | Yes |  |  | Complete | 576.43
2025-12-15 13:35:00 | Complaint disrepair works / as per G Squared site survey. | 2026-06-18 08:00:00 | 2026-06-18 |  | Disrepair | 1036824 | 91 TRYM SIDE | 39385/1 | Works Started | ACE Agreed | 36/1044 | 2026-06-18 08:00:00 | 20 days |  |  | Shannon Slade | 15/01/2026 13:35 | No | Pre-completion Items To Complete |  |  |  | 27/05 - Appointment rescheduled for 18/06, as requested by tenant as his wife suffers from a nervous disposition and he only has Thursdays off. NA needs to be rebooked - CL | Appointment booked | 950.53
2025-12-15 13:28:00 | Complaint disrepair works / as per G Squared site survey |  | 2026-06-02 | 2026-06-02 10:46:00 | Disrepair | 1007256 | 24 Bangrove Walk | 39214/1 | Works Completed | ACE Agreed | 36/1043 | 2026-06-02 10:46:00 | 20 days |  |  | Shannon Slade | 15/01/2026 13:28 | No | Pre-completion Items To Complete |  | Yes |  | 17/06 - Electrical cert received and uploaded - CL 14/05 - WORKS BOOKED VIA EMAIL DUE TO NO CONTACT ON MULTIPLE OCCASINS VIA PHONE. | Complete | 463.32
2025-12-15 12:23:00 | Complaint disrepair works / as per G Squared site survey | 2026-05-19 12:00:00 | 2026-07-20 |  | Disrepair | 1119795 | 51 CLAVERHAM ROAD | 39230/1 | New Works Instruction | ACE Agreed | 36/1039 |  | 20 days |  |  | Shannon Slade | 15/01/2026 12:23 |  | Suspended: Awaiting asbestos info |  |  |  | 17/06 - WORKS BOOKED FOR 20TH AND 21ST AND 23RD, AND THEN FF TO BE CONFIRMED. 15/06 - SITE VISIT BOOKED FOR 16TH JUNE TO LOOK AT BATHROOM WORKS. 19/05 - No access for surveyor to asses bathroom works, need rebooking | Appointment booked | 1836.52
2025-12-12 12:17:00 | Complaint disrepair works / as per CG | 2026-07-02 10:00:00 | 2026-07-02 |  | Disrepair | 1125902 | 93 GORSE HILL | 38923/1 | Works Started | ACE Agreed | 36/1038 | 2026-03-18 08:00:00 | 20 days |  |  | Shannon Slade | 14/01/2026 12:17 | No | Pre-completion Items To Complete |  |  |  | 29/06 - Appointment confirmed with tenant - CL 22/06- OP BOOKED FOR 30TH JUNE TO COMPLETE DECS OF NEW PLASTER IN L/ROOM 15/06 - WIP, PLSTERING IN PROGRESS 15TH JUNE, OTHER WORKS TO BE RE BOOKED. 28/04 - TIMBERWISE ATTENDING 4TH JUNE ISSUE WORKS TO TIMBERWISE. 20/05 - TW REPORT ISSUED TO CASSIE. WAITING FOR RESPONSE. SEE NOTES SECTION, | WIP | 3313.2
2025-12-12 12:14:00 | Complaints work/G Squared report (WO raised by A Williams) | 2026-05-20 12:00:00 |  |  | Disrepair | 1012153 | 21 CLAPTON WALK | 38867/1 | Works Started | ACE Agreed | 36/1037 | 2026-05-20 12:00:00 | 20 days |  |  | Shannon Slade | 14/01/2026 12:14 | No | Pre-completion Items To Complete |  |  |  | 16/06 - CHASED CONTRACTOR FOR DATE AS THEY WERE UNABLE TO ATTEND ON 2ND JUNE. 20/05 - JWE WORKS BOOKED FOR 20TH MAY. WORKS ISSUED TO CONTRACTOR, BILLY TO ATTEND 2ND JUNE WORKS ISSUED TO SUBCONTRACTOR AND JWE TO BOOK WORKS. DATE TO BE CONFIRMED | WIP | 668.46
2025-12-12 12:11:00 | Complaint disrepair works / as per CG |  | 2026-05-28 | 2026-05-29 12:00:00 | Disrepair | 1070082 | 40 STANTON ROAD | 38865/1 | Works Completed | ACE Agreed | 36/1036 |  | 20 days |  |  | Shannon Slade | 14/01/2026 12:11 |  | Suspended: Awaiting asbestos info |  | No |  | 15/05 - FLOORING WORKS BOOKED FOR 28TH AND 29TH MAY. WORKS BOOKED FOR 20TH AND 21ST APRIL. 24/04 - JWC WORKS COMPLETED, FLOORING WORKS ISSUED TO FF, WAITING FOR CONFIRMATION OF DATE. 05/05 - CHASED FF FOR DATE. 07/05 - SPOKE WITH FF WHO HAS CONFIRMED TH | WIP | 1600.3
2025-12-12 12:01:00 | Complaint disrepair works / as per CG | 2026-01-28 08:00:00 | 2026-06-01 | 2026-04-17 08:41:00 | Disrepair | 1154605 | 19 POUNTNEY DRIVE | 38851/1 | Works Completed | ACE Agreed | 36/1035 | 2026-02-03 08:00:00 | 20 days |  |  | Shannon Slade | 14/01/2026 12:01 | No | Post-completion Items To Complete | 2026-05-07 | Yes |  | PART WORKS COMPLETED, REMAINING WORKS BOOKED FOR 17TH APRIL. - 24/04 - COMPLETE, WAITING FOR PICTURES | Complete | 609.93
2025-12-12 11:51:00 | Complaint disrepair works / as per G Squared site survey | 2026-07-13 09:00:00 | 2026-07-13 |  | Disrepair | 1044935 | 8 CHALLENDER AVENUE | 38722/1 | New Works Instruction | ACE Agreed | 36/1033 |  | 20 days |  |  | Shannon Slade | 14/01/2026 11:51 |  | Pre-works Items To Complete |  |  |  | 3/7 - fan and socket works. 02/07- complete all other works and omit plastering 20/05 - ON HOLD DUE TO BCC ATTENDING IN MID JUNE TO COMPLTE ROOF WORKS AND THEN WE CAN GO AHEAD WITH OTHER WORKS. 15/04 - PLASTERING AND WINDOW WORKS REMOVED FROM ORDER AS MO CONFIRMED THAT BCC ARE COMPLETING THESE WORKS INHOUSE. EMAIL ISSUED TO MO TO CONFIRM DATES OF WHEN BCC ARE ATTENDING. SO WORKS CAN BE BOOKED AROUND THESE WORKS. | Appointment booked | 5081.27
2025-12-12 11:48:00 | Complaint disrepair works / as per CG |  |  | 2026-03-09 09:26:00 | Disrepair | 1165373 | 62 BARTON HOUSE | 38825/1 | Works Completed | ACE Agreed | 36/1032 |  | 20 days |  |  | Shannon Slade | 14/01/2026 11:48 |  | Post-completion Items To Complete | 2026-03-10 | Yes |  |  | Complete | 50.0
2025-12-12 09:48:00 | Scaffolding required front and rear of property, , just below guttering height, Roofers to renew first course of felt and batten, insulating the eves, install eve trays. Install new fascia boards and new guttering, front and rear. | 2026-01-09 08:00:00 |  | 2026-03-06 12:00:00 | Routine Repairs | 1222511 | 129 Ilminster Avenue | 38971/1 | Works Completed | Invoiced | 36/962 | 2026-01-08 08:00:00 | 15 days |  |  | Shannon Slade | 07/01/2026 09:48 | No | Fully Complete | 2026-03-20 | Yes |  |  | Complete | 5933.82
2025-12-12 08:32:00 | Concrete roof on out building, leaking, causing damp on inside, needs covering with Tuff Stuff/liquid sealant | 2026-05-18 10:15:00 | 2026-05-18 | 2026-05-18 17:43:00 | Routine Repairs | 1316592 | 14 WOODMEAD GARDENS | 39024/1 | Works Completed | ACE Agreed | 36/961 | 2026-05-18 08:00:00 | 15 days |  |  | Shannon Slade | 07/01/2026 08:32 | No | Pre-completion Items To Complete | 2026-06-08 | Yes |  | 08/06 - KPI requested - CL 05/05 - Appointment needs to be rescheduled due to sickness - CL Appointment rescheduled to 29/04 and follow on appointment to complete work 30/04 - CL | Complete | 224.08
2025-12-11 11:45:00 | DISREPAIR WORKS / AS PER G SQUARED SITE SURVEY | 2026-04-30 10:30:00 | 2026-06-22 |  | Disrepair | 1020300 | 29 LONG CROSS | 38624/1 | Works Started | ACE Agreed | 36/1031 | 2026-04-27 08:45:00 | 20 days |  |  | Shannon Slade | 13/01/2026 11:45 | No | Pre-completion Items To Complete |  |  |  | 16/06 - PAINTING TO BE COMPLETED MONDAY 22ND JUNE. 19/03 - OPERATIVE WAS SICK ON 6TH MAY, WORKS RE BOOKED FOR 10TH JUNE | Appointment booked | 1733.69
2025-12-11 11:41:00 | Complaint disrepair works / as per G Squared site survey | 2026-06-04 10:15:00 | 2026-06-19 |  | Disrepair | 1010373 | 174 BROADLANDS DRIVE | 38606/1 | Works Started | ACE Agreed | 36/1030 | 2026-06-04 10:15:00 | 20 days |  |  | Shannon Slade | 13/01/2026 11:41 | No | Pre-completion Items To Complete |  |  |  | 16/06 - JWC WORKS COMPLETED, GUTTERING COMPANY ATTENDING BY END OF THE WEEK. | Appointment booked | 498.41
2025-12-11 11:33:00 | Please carry out disrepairs works as listed out. | 2026-06-24 09:00:00 | 2026-06-26 |  | Routine Repairs | 1177566 | 43 Harewood Road | 34769/2 | Works Started | ACE Agreed | 36/1029 | 2026-03-04 09:15:00 | 15 days |  |  | Shannon Slade | 06/01/2026 11:33 | No | Pre-completion Items To Complete | 2026-04-29 | Yes |  | 24/6 - Issued po to wsg, awaiting a response. 29/04 - KPI requested - CL UNABLE TO INSTALL HEATER IN RECOMMENDED PLACE DUE TO REGULATIONS 30/03 - JAMES BAILEY HAS ASKED FOR ELECTRICIAN TO GIVE HIM A CALL. ASKED DAR TO CALL AND EXPLAIN. 08/04 - WORKS BOOKED FOR D&M ELECTRCIANS TO COMPLETE 13TH APRIL. | Complete | 1099.81
2025-12-11 09:51:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? TOM WALKER ATTENDING 17/12/25. 10 DAY PERIOD ENDS 31/12/25. | 2026-01-12 12:00:00 | 2026-01-12 | 2026-01-12 10:46:00 | Routine Repairs | 0001925 | 8 St Peters Way, Horfield | 38445/2 | Works Completed | Invoiced | 36/951 | 2026-01-12 12:00:00 | 15 days |  |  | Lainie Lavin | 06/01/2026 09:51 | No | Pre-completion Items To Complete | 2026-02-12 | Yes |  |  | Complete | 143.59
2025-12-10 14:41:00 | JEFF WAY - PRE MUTUAL EXCHANGEELECTRIC TEST. TOM WALKER ATTENDING 15/12/25. 10 DAY PERIOD ENDS 29/12/25 |  |  | 2026-03-06 09:44:00 | Routine Repairs | 1297058 | 11 Coleshill Drive, Hartcliffe | 38335/3 | Works Completed | Invoiced | 36/943 | 2026-03-06 09:45:00 | 15 days |  |  | Lainie Lavin | 05/01/2026 14:41 | No | Post-completion Items To Complete | 2026-03-11 | Yes |  |  | Complete | 143.59
2025-12-10 11:42:00 | Inspection of loft insulation and overlaying to 270mm as per Tom Taylor | 2026-01-05 12:00:00 |  | 2026-01-05 10:13:00 | Disrepair | 1313979 | 9 The Brambles Grinfield Avenue | 38381/1 | Works Completed | Invoiced | 36/998 |  | 20 days |  |  | Shannon Slade | 12/01/2026 11:42 |  | Fully Complete | 2026-01-07 | Yes |  |  | Complete | 500.08
2025-12-09 13:11:00 | JEFF WAY - As per Darryl (07733 831 884)- WORKS TO BATHROOM, M/G WALLS IN KIDS BEDROOM, CARRY OUT LOFT INSPECTION - SEE EMAIL WITH FULL DESCRIPTION | 2026-05-28 15:15:00 |  |  | Routine Repairs | 1033803 | LOT1 - 38 St Bernards Road, Shirehampton | 16790/2 | Works Started | ACE Agreed | 36/958 | 2026-04-09 09:00:00 | 15 days |  |  | Lainie Lavin | 02/01/2026 13:11 | No | Pre-completion Items To Complete |  |  |  | 02/06 - FLOORING WORKS BOOKED FOR 15TH AND 16TH JUNE. 29/05- Email sent to BCC about contact info as FF are struggling to contact tenant 18/5 - awaiting date from FF to attend.14/05 - Tiling around the window revil needs re-booking in as tenant buying own tiles , once they have we will book - 06/05 - Follow on appointment to complete work on 13/05 - CL 20/04 - Appointment booked for CM to complete work 05/05. Awaiting appointment date from FF - CL Follow on appointment to carry out plastering booked for 10/04 - CL | WIP | 3220.4
2025-12-09 11:36:00 | Complaint works. repair leaking rad, wc built falso wall and install close coupled toilet, repair ceiling, replace floor. bathroom, replace floor and bath panel. Install extractor fans - James Saunders | 2026-07-03 15:00:00 | 2026-07-03 |  | Disrepair | 1299849 | 35 FABER GROVE | 38011/1 | Works Started | ACE Agreed | 36/997 | 2026-04-30 08:00:00 | 20 days |  |  | Shannon Slade | 09/01/2026 11:36 | No | Pre-completion Items To Complete |  | No |  | 3/7 - Fan booked. 18/05 - FF ATTENDING THE 1ST AND 2ND JUNE. 13/05 - FLOORING WORKS ISSUED TO FF, ELECTRICIAN BOOKED FOR 2ND JUNE. - WORKS BOOKED FOR 23RD AND 24TH MARCH - NO ACCESS DUE TO DAUGHTER RECENTLY HAVING AN OP. WORKS RE BOOKED FOR 30TH APRIL AND 1ST OF MAY. | WIP | 1749.24
2025-12-06 11:05:00 | Please carry out disrepair works as listed. | 2026-04-28 09:45:00 | 2026-04-28 | 2026-05-05 13:35:00 | Disrepair | 1291481 | 27 Whiting Road, Withywood | 37298/1 | Works Completed | ACE Agreed | 36/994 | 2026-02-17 08:00:00 | 20 days |  |  | Shannon Slade | 08/01/2026 11:05 | No | Post-completion Items To Complete |  | Yes |  | WALLS PREPPED FOR DECS - CAN WE INSTALL SMALLER CUPBOARD TO ALLOW FOR FAN TO BE FITTED IN EXISITING PLACE DUE TO REGULATIONS THE OPTIONS ARE PUT IN WINDOW OR REDUCE UNIT SIZE? 30/03 - CHANGE OF UNIT BOOKED FOR 14TH APRIL, FAN TO BE FITTED 20TH APRIL. 23/0 | Complete | 1757.97
2025-12-05 10:57:00 | Contact Andrew Griffiths | 2026-04-16 08:00:00 | 2026-07-03 |  | Disrepair | 1107580 | 100 Carolina House | 27925/2 | New Works Instruction | ACE Agreed | 36/993 |  | 20 days |  |  | Shannon Slade | 07/01/2026 10:57 |  | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment confirmed with tenant - CL 17/06 - Electrical cert received and uploaded - CL 12/06 - BATHROOM WORKS 3RD JULY. EMAIL SENT TO TT REGARDING D&M 04/06 - Bathroom works are complete. Electrical works booked for 9th June. WORKS WERE BOOKED FOR 3RD, HOWEVER TENANT DIDN'T WANT WORKS COMPLETED. TENANT IS NOW ON HOLIDAY FOR A FEW WEEKS - WORKS BOOKED TO COMMENCE 16TH APRIL FOR TWO DAYS. 20/04 - CALLED TENANT AFTER NO ACCESS AND REBOOKED FOR 2ND AND 3RD OF JUNE. | WIP | 897.66
2025-12-05 08:41:00 | Jeffway - As Per John Oyeniyi: Please reglaze 4nos blown windows and repaint over dirty patch in ceiling in the Kitchen | 2026-02-25 10:15:00 |  | 2026-02-25 12:54:00 | Routine Repairs | 1311235 | 4 Randolph Avenue, Hartcliffe | 37004/1 | Works Completed | Invoiced | 36/936 |  | 15 days |  |  | Lainie Lavin | 29/12/2025 08:41 |  | Fully Complete | 2026-02-27 | Yes |  |  | Complete | 218.42
2025-12-05 08:41:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? JOE COTTRELL ATTENDING 8/12/25. 10 DAY PERIOD ENDS 22/12/25 | 2026-01-23 08:00:00 | 2026-01-23 | 2026-01-26 11:46:00 | Routine Repairs | 1065389 | 11 Redshelf Walk, Brentry | 36978/3 | Works Completed | Invoiced | 36/937 | 2026-01-26 11:46:00 | 15 days |  |  | Lainie Lavin | 29/12/2025 08:41 | No | Fully Complete | 2026-02-03 | Yes |  |  | Complete | 143.59
2025-12-04 15:41:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST, JOE COTTRELL ATTENDING 8/12/25. 10 DAY PERIOD ENDS 22/12/25 |  | 2026-01-26 | 2026-01-26 11:35:00 | Routine Repairs | 1025690 | 10 Marsh Street, Avonmouth | 36929/3 | Works Completed | Invoiced | 36/934 | 2026-01-26 11:35:00 | 15 days |  |  | Lainie Lavin | 24/12/2025 15:41 | No | Fully Complete | 2026-02-03 | Yes |  |  | Complete | 154.45
2025-12-04 14:07:00 | URGENT-JEFFWAY- As per Ian O-FAO CHARLIE : DAMP AND MOULD WASH AND PAINT , EXTRACTOR FANS IN KITCHEN AND BATHROOM | 2026-04-29 13:45:00 |  | 2026-04-29 14:45:00 | Routine Repairs | 1491992 | 100 Risdale Road | 36693/1 | Works Completed |  | 36/929 | 2026-04-29 13:45:00 | 15 days |  |  | Shannon Slade | 24/12/2025 14:07 | No | Post-completion Items To Complete | 2026-06-08 | Yes |  | 16/06 - Email received from IO regarding the SORS, email forwarded to CH to investigate - CL 08/06 - KPI requested - CL 23/04 - Appointment booked to refix plinths after flooring replaced to complete work - CL | Complete | 1675.59
2025-12-04 10:38:00 | Repair kitchen sink unit, reseal behind sink to wall and reinstall the plinth. As per James saunders | 2026-03-31 09:15:00 |  | 2026-03-31 16:33:00 | Disrepair | 1190143 | 85 Whitmore Avenue | 36744/1 | Works Completed | Invoiced | 36/991 |  | 20 days |  |  | Shannon Slade | 06/01/2026 10:38 |  | Fully Complete | 2026-04-15 | Yes |  | BOOKED FOR 31ST MARCH | Complete | 109.32
2025-12-04 10:11:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 10/12/25. 10 DAY PERIOD ENDS 24/12/25 | 2026-01-30 12:00:00 |  | 2026-02-27 08:32:00 | Routine Repairs | 4130465 | 16 Sanders Close, Ashton Vale | 36709/3 | Works Completed | Invoiced | 36/931 | 2026-01-30 12:00:00 | 15 days |  |  | Lainie Lavin | 24/12/2025 10:11 | No | Post-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI requested - CL Variation sent to JC for approval - CL | Complete | 1051.88
2025-12-03 15:30:00 | Wrap round scaffold for 3 sides to enable roof works to be undertaken wrap round scaffold |  |  | 2026-04-13 14:03:00 | Routine Repairs | 1223809 | 119 Kenmare Road | 34946/1 | Works Completed | ACE Agreed | 36/924 |  | 15 days |  |  | Shannon Slade | 23/12/2025 15:30 |  | Post-completion Items To Complete | 2026-04-27 | Yes |  | CONTRACTOR ATTENDING TODAY TO TAKE MEASUREMENTS - 27/3. Awaiting confirmation dates from contractor - 30/3. 31/03 - LMT ON SITE TODAY. 13/04 - WORKS COMPLETED, EMAIL ISSUED TO BCC CONFIRM IF SCAFFOLDING CAN BE OFF-HIRED. | Complete | 5780.85
2025-12-03 14:40:00 | JW - AS PER JOHN O: PLEASE FIX WALL TILES ON WALL ABOVE BATH AND REPAIR SPOT ON BATH | 2026-06-11 08:00:00 | 2026-06-11 |  | Routine Repairs | 1306269 | 31 Maynard Close | 36534/1 | Works Started | ACE Agreed | 36/927 | 2026-04-27 14:00:00 | 15 days |  |  | Shannon Slade | 23/12/2025 14:40 | No | Pre-completion Items To Complete |  |  |  | 12/06 - Job has now gone to a complaint, awaiting instructions from EH (de-sent notice) - CL 03/06 - NA on 01/06 appointment rescheduled - CL 12/05 - No access on the 12/05 JW to rebook 06/05 - Follow on appointments booked for 11/05 and 12/05 to repair bath chip. Appointment need to be reschedule due to operative being ill - CL 29/04 - Appointment booked with tenant for 05/05 and 06/05 to complete repair to bath - CL 23/04 - Appointment | Held BCC | 400.4
2025-12-03 14:27:00 | Jeffway- PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? TOM WALKER ATTENDING 09/12/25. 10 DAY PERIOD ENDS 23/12/25. | 2026-02-19 09:00:00 | 2026-02-19 | 2026-02-19 10:17:00 | Routine Repairs | 1051189 | 29 DRAGONSWELL ROAD | 36435/3 | Works Completed | Invoiced | 36/930 | 2026-01-21 08:00:00 | 15 days |  |  | Shannon Slade | 23/12/2025 14:27 | No | Fully Complete | 2026-02-24 | Yes |  | 07/04 - KPI request added and forwarded to EH - CL | Complete | 143.59
2025-12-03 13:51:00 | Jeffway-PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR A? TOM WALKER ATTENDING 09/12/25. 10 DAY PERIOD ENDS 23/12/25. | 2026-01-20 08:00:00 | 2026-01-20 | 2026-01-20 09:17:00 | Routine Repairs | 1044333 | 25 BURGHILL ROAD | 36457/3 | Works Completed | Invoiced | 36/928 | 2026-01-20 09:17:00 | 15 days |  |  | Shannon Slade | 23/12/2025 13:51 | No | Post-completion Items To Complete | 2026-02-12 | Yes |  |  | Complete | 233.07
2025-12-03 10:27:00 | Complaint works contact Andrew Griffiths, | 2026-03-05 08:00:00 |  |  | Disrepair | 1159382 | 92 TWINNELL HOUSE | 36321/1 | Works Started | ACE Agreed | 36/990 | 2026-03-05 08:00:00 | 20 days |  |  | Shannon Slade | 05/01/2026 10:27 | No | Suspended: On hold |  |  |  | LEAK STILL PRESENT AT PROPERTY - EMAIL ISSUED TO BCC | Held BCC | 290.42
2025-12-02 11:26:00 | Please contact Andrew Griffiths BCC |  |  |  | Disrepair | 1076331 | 16 Westleigh Road | 29022/1 | New Works Instruction | ACE Agreed | 36/988 |  | 20 days |  |  | Shannon Slade | 02/01/2026 11:26 |  | Suspended: Awaiting asbestos info |  |  |  | SPOKE WITH TENANT TODAY, SHE NO LONGER WANTS BATH INSTALLED IN THE PROPERTY. SHE SAID THERE IS ALSO SOMETHING WRONG WITH THE FLOORING. ATTEMPTED TO CONTACT SURVEYOR, BEEN INFORMED NO LONGER WORKS FOR BCC. WAITING FOR SOMEONE TO CONTACT HER FROM BCC. | Held BCC | 5826.45
2025-12-02 10:16:00 | DISREPIAR- TOM LEAR - JEFF WAY TO CARRY OUT WORKS AS PER S1 COMPLAINT | 2026-07-06 08:00:00 | 2026-07-03 |  | Disrepair | 1016473 | 55 HENACRE ROAD | 29849/1 | Works Started | ACE Agreed | 36/989 | 2026-04-22 08:00:00 | 20 days |  |  | Shannon Slade | 02/01/2026 10:16 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Unable to get hold of tenant, voicemail left - CL 15/06 - WIP - SHOWER PANELS BOOKED FOR 3RD JULY. 24/03 - WORKS BOOKED FOR 22ND APRIL, 29TH AND 30TH APRIL AND 1ST OF MAY. | Appointment booked | 858.55
2025-12-01 16:59:00 | JW- As per Rob D -RENEW 2 X SECTIONS OF REAR GARDEN PATH THAT ARE CRACKED/BREAKING UP. ONE AREA RHS OF BACK DOOR APPROX 5M2 AND A 1M2 AREA TO BOTTOM OF STEPS LEADING TO WASHING LINE | 2026-05-11 08:45:00 |  |  | Routine Repairs | 1287305 | 5 Redford Crescent, Withywood | 35667/1 | New Works Instruction | ACE Agreed | 36/916 |  | 15 days |  |  | Lainie Lavin | 19/12/2025 16:59 |  | Pre-completion Items To Complete |  |  |  | 24/06 - PO sent to AG Builders, awaiting date - CL 27/03 - Appointment booked for 08/05 and 11/05 - CL Unable to contact tenant voicemail left and text sent - CL | Awaiting appointment date | 749.94
2025-12-01 16:59:00 | JW - As per Rob D - Fill crack to l/room ceiling, patch repair to landing ceiling, renew plaster/skim to rear wall by backdoor, renew bath tiles to basin and paint wall under basin, renew all kickboards to kitchen base units | 2025-12-23 08:00:00 | 2025-12-23 | 2025-12-23 15:15:00 | Routine Repairs | 1277787 | 20 Felton Grove, Bedminster Down | 35678/1 | Works Completed | Invoiced | 36/917 | 2026-01-22 08:00:00 | 15 days |  |  | Lainie Lavin | 19/12/2025 16:59 | No | Fully Complete | 2026-01-26 | Yes |  |  | Complete | 396.95
2025-12-01 16:59:00 | JW-As per Jeff N-Disconnect/reconnect water&waste supplies to kitchen sink&remove. fix new 900mm&400mm water damage base units. Fix 500mm of damage worktop to match .Fix 2no new draws and refix.fix new plinth to suit | 2026-02-20 08:00:00 |  | 2026-02-20 09:08:00 | Routine Repairs | 35651/1 | 20 Borleyton Walk, Withywood | 35651/1 | Works Completed | ACE Agreed | 36/918 | 2026-02-20 08:00:00 | 15 days |  |  | Lainie Lavin | 19/12/2025 16:59 | No | Pre-completion Items To Complete | 2026-03-13 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 1066.88
2025-12-01 16:59:00 | Jeffway - As per Ian O - FAO DARREN . KITCHEN PLINTHS / EXTERNAL CRACK REPAIR / COPING STONES MEET ON SITE TO DISCUSS WORKS | 2026-04-16 12:00:00 |  | 2026-04-15 15:26:00 | Routine Repairs | 1197860 | 77 Hazelbury Road, Knowle | 35641/1 | Works Completed | Invoiced | 36/919 | 2026-04-16 13:30:00 | 15 days |  |  | Lainie Lavin | 19/12/2025 16:59 | No | Pre-completion Items To Complete | 2026-05-08 | Yes |  | 16/06 - KPI received and uploaded - CL 08/05 - KPI requested - CL 30/04 - Variation request sent - CL Tenant advised me that the plinths and the window overhauls have already been completed. She will send some pictures when she gets home after work - CL | Complete | 869.88
2025-12-01 16:59:00 | Jeffway - As per Jeff N - External works to gully and pipe work to rear elevation - See SOR Breakdown for work notes required | 2026-07-08 12:00:00 | 2026-07-08 |  | Routine Repairs | 1286777 | 27 Pigott Avenue, Withywood | 35649/1 | Works Started | ACE Agreed | 36/920 | 2026-03-31 07:57:00 | 15 days |  |  | Lainie Lavin | 19/12/2025 16:59 | No | Pre-completion Items To Complete |  |  |  | 29/05 - WORKS ISSUED TO CONTRACTOR. WAITING FOR RESPONSE. 05/05 - Update needed from Chloe M - CL Contact details confirmed. Spoke with tenant and booked a site visit for SH on 31/03 - CL Incorrect number given, contact detail request sent to CM - CL | Appointment booked | 478.57
2025-12-01 11:09:00 | complaint works- please see email and report- Thomas Lear | 2026-04-17 08:00:00 |  | 2026-03-06 13:18:00 | Disrepair | 1167540 | 21 BOURNE ROAD | 35564/1 | Works Completed | Invoiced | 36/987 |  | 20 days |  |  | Shannon Slade | 30/12/2025 11:09 |  | Fully Complete | 2026-03-19 | Yes |  |  | Complete | 570.81
2025-12-01 08:59:00 | As per darryl's (07733 831 884) request - Please erect scaffolding to chimney (need access to chimney), please ensure set to surveyor height - PLEASE ADVISE DATE OF ERECTION | 2026-04-22 08:15:00 |  | 2026-03-26 08:32:00 | Routine Repairs | 1058475 | 30 Lanercost Road, Southmead | 35403/1 | Works Completed |  | 36/922 |  | 15 days |  |  | Lainie Lavin | 19/12/2025 08:59 |  | Pre-completion Items To Complete | 2026-05-08 | Yes |  | 23/06 - KPI request chased - CL 16/04 - Site visit booked with tenant for SH and DJ on 22/04 at 10am. Unable to make contact with tenant, voicemail and text message left to make contact - CL Works complete, scaffolding dismantled. BCC have signed off roof works | Complete | 2399.06
2025-11-28 15:57:00 | Scaffolding upto and around the chimney stack. Only on bcc side. At least three tiles down from stack front and back, repair felt at rear of stack, install 3x gc1 gas cowls, renew flaunching, reseal lead and waterseal stack. |  |  | 2026-03-13 11:19:00 | Routine Repairs | 1227743 | 121 Newquay Road, Knowle | 35206/1 | Works Completed | Invoiced | 36/921 |  | 15 days |  |  | Lainie Lavin | 18/12/2025 15:57 |  | Fully Complete | 2026-03-23 | Yes |  |  | Complete | 2700.68
2025-11-27 10:21:00 | Disrepair works - James Bailey (surveyor) Bedroom - strip back damaged plaster, treat brick, replaster, mist coat, anticondensation paint Kitchen - d+m wash pipes Living room - - strip back damaged plaster, treat brick, replas | 2026-02-25 08:00:00 | 2026-06-29 | 2026-06-29 11:44:00 | Disrepair | 1299167 | 5 Englishcombe Road | 3697/2 | Works Completed |  | 36/984 | 2026-05-13 08:00:00 | 20 days |  |  | Shannon Slade | 24/12/2025 10:21 | No | Pre-completion Items To Complete |  | Yes |  | 30/06 - Works complete, variations need to be added - CL 05/06 - PIPES NEED TO BE ADJUSTED AT PROPERTY. WORKS BOOKED TO BE COMPLETED 29TH JUNE. PLASTERER ON SITE TODAY - NEED TO CHECK WITH CHARLIE WHAT WORKS ARE REMAINING THERE TO ARRANGE - PLASTERING COMPLETED - WAITING FOR CHARLIE TO CONFIRM OTHER WORKS 30/03 - PLASTERING TO L/ROOM COMPLETE. BEDROOM PLASTERING BOOKED FOR 10TH APRIL. DECS TO BE | Complete | 4558.1
2025-11-26 12:53:00 | complaint works- Bedroom 2 works- Daughters bedroom | 2026-02-17 08:00:00 | 2026-07-22 |  | Disrepair | 1169897 | 96 Capgrave Crescent | 34475/1 | Works Started | ACE Agreed | 36/960 | 2026-02-16 08:00:00 | 20 days |  |  | Shannon Slade | 23/12/2025 12:53 | No | Pre-completion Items To Complete |  |  |  | 01/06 - REPLASTRING OF BEDROOM BOOKED FOR 23RD JUNE. TENANT DOESNT WANT BOTH BEDROMS DONE AT SAME TIME SO ANOTHER APPOINTMENT TO BE BOOKED. 19/05 - SITE VISIT FOR CHARLIE TO INSPECT PLASTER REPAIRS 22ND MAY | Appointment booked | 7467.67
2025-11-26 12:45:00 | Complaint disrepair works / as per G Squared site survey | 2025-12-22 08:00:00 |  | 2025-12-22 12:00:00 | Disrepair | 1073003 | 53 TORMARTON CRESCENT | 34469/1 | Works Completed | Invoiced | 36/959 | 2025-12-22 08:00:00 | 20 days |  |  | Shannon Slade | 23/12/2025 12:45 | Yes | Fully Complete | 2026-02-06 | Yes |  |  | Complete | 53.58
2025-11-26 11:59:00 | Complaint disrepair works / as per CG | 2026-02-26 08:00:00 |  | 2026-04-24 11:16:00 | Disrepair | 1151639 | 11 Lansdowne Court | 33358/1 | Works Completed | ACE Agreed | 36/911 | 2026-02-18 08:00:00 | 20 days |  |  | Shannon Slade | 23/12/2025 11:59 | No | Post-completion Items To Complete | 2026-05-07 |  |  | PLASTERING COMPLETED, PAINTING COMPLETED. REMAINING WORKS BOOKED FOR 24TH APRIL. 05/05 -WORKS COMPELTED, WAITING FOR POST INSPECTION/HANDOVER FROM COMMERICAIL | Complete | 674.75
2025-11-26 09:50:00 | Complaint works contact Andrew Griffiths | 2026-02-23 08:00:00 |  |  | Disrepair | 1221303 | Home Mead, 26 Creswicke Road | 29144/1 | Works Started | ACE Agreed | 36/898 | 2026-02-23 08:00:00 | 20 days |  |  | Shannon Slade | 23/12/2025 09:50 | No | Suspended: Awaiting Client Action/Response |  |  |  | 19/05 - JWC WORKS COMPLETED, BUT UNABLE TO GET HOLD OF TENANT FOR GLAZING WORKS, EMAIL ISSUED TO BCC TO CONFIRM IF ANY OTHER DETAILS ON FILE. 14/05 - CHASED WSG FOR UPDATE. 08/04 - JWC WORKS COMPLETED, FAN ISSUED TO D&M AND GLAZING WORKS SENT TO SUBCONTRACTOR | Held BCC | 1107.85
2025-11-26 08:50:00 | Disrepair Work. 1. Electric Shower - Overhaul 2. Install new extract fan to bathroom 3. Install new extract fan to kitchen 4. Overhaul all windows and doors to property 5. Treat mould and decorate bedroom 2 6. Decorate bedroom 1 7. Replace defective light switch to kitechen | 2026-06-05 12:00:00 |  | 2026-06-05 14:21:00 | Disrepair | 1018311 | 23 Humberstan Walk | 4719/2 | Works Completed | ACE Agreed | 36/894 |  | 20 days |  |  | Shannon Slade | 23/12/2025 08:50 |  | Pre-completion Items To Complete |  | Yes |  | WORKS BOOKED THROUGH BCC - WORKS BOOKED TO COMMENCE 7TH APRIL OVER 4 DAYS. 15/04 - WORKS WERNT COMPLETED DUE TO EXTRA WORKS ON SITE. WORKS BOOKED FOR 28TH AND 29TH MAY. | Complete | 1897.98
2025-11-25 15:36:00 | RENEW FLOOR TO STAIRCASE AND FIRST FLOOR LANDING AFTER ENVIROCALL HAD REMOVED ASBESTOS TIL FLOORING |  |  | 2026-02-27 12:18:00 | Routine Repairs | 1844015 | 29-35A Derham Road | 29535/1 | Works Completed | Invoiced | 36/1311 |  | 35 days |  |  | Carlene Lynette Lynch | 16/01/2026 15:36 |  | Pre-works Items To Complete | 2026-05-08 | Yes |  | 03/06 - KPI received and uploaded - CL 08/05 - Revised KPI requested - CL 27/04 - KPI request sent - CL | Complete | 2245.28
2025-11-25 10:21:00 | ROF - roof leak into child'sbedroom has caused ceiling to fail. Please investigate and report back works required as per Matt Ford. Asb report to follow | 2026-01-08 08:00:00 | 2026-01-08 | 2026-01-08 09:45:00 | Routine Repairs | 1308549 | 10 MOWCROFT ROAD | 30358/2 | Works Completed | Invoiced | 36/886 | 2026-01-08 08:00:00 | 15 days |  |  | Shannon Slade | 15/12/2025 10:21 | No | Fully Complete | 2026-01-26 | Yes |  |  | Complete | 856.28
2025-11-25 10:09:00 | Complaint works- Please see email and report. | 2026-04-29 08:00:00 |  |  | Disrepair | 1165204 | 45 BARTON HOUSE | 34228/1 | New Works Instruction | ACE Agreed | 36/1120 |  | 20 days |  |  | Shannon Slade | 22/12/2025 10:09 |  | Pre-completion Items To Complete |  |  |  | 1/7 - called no answer, needs re-booking. 30/06 - NA on 29/06 appointment needs rescheduled - CL 16/06 - NO ACCESS ON 9TH, WORKS RE BOOKED FOR 23RD JUNE19/05 - WORKS RE BOOKED FOR THE 9TH JUNE DUE TO OPERATVIVE ISSUES ON PREVIOUS APPOINTMENT. -NO ACCESS ON 9TH - TRIED TO TENANT TO RE BOOK - SEND DATES TO TOM FOR PHONE CALLS 07/04 - ATTEMPTED TO CALL TODAY, NO ANWSER. MESSAGE LEFT. | WIP | 801.79
2025-11-24 15:03:00 | JW - As per Joe Cottrell - Various works throughout property - Email sent to JW (Shannon/Charlie) with full works order description 24/11/2025 | 2026-02-02 09:30:00 |  | 2026-02-09 15:24:00 | Routine Repairs | 1281409 | 23 Hersey Gardens, Withywood | 33766/1 | Works Completed | Invoiced | 36/891 | 2026-01-23 08:00:00 | 15 days |  |  | Shannon Slade | 12/12/2025 15:03 | No | Fully Complete | 2026-03-16 | Yes |  |  | Complete | 1591.18
2025-11-24 14:59:00 | JW - Jeff Neck - Scrap water damage texture paint work off bathroom ceiling & repair,Apply plaster skim finish to complete ceiling. Apply anti condensation paint to complete ceiling. Remove and refix existing light fitting | 2026-03-24 13:15:00 |  | 2026-03-26 14:55:00 | Routine Repairs | 1302563 | 55 HARECLIVE ROAD | 33771/1 | Works Completed | ACE Agreed | 36/890 | 2026-03-18 08:00:00 | 15 days |  |  | Shannon Slade | 12/12/2025 14:59 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  |  | Complete | 172.39
2025-11-24 14:54:00 | JW - AS PER ROB DOIDGE - BLOCKING UP AND THEN PATCH SKIM THE FIREPLACE HOLE TO LIVING ROOM . ALSO REMOVE OLD BIT OF HEARTH TO FLOOR AND MAKE GOOD WITH LATEX AS REQUIRED. | 2026-02-13 09:00:00 |  | 2026-02-13 11:51:00 | Routine Repairs | 1282195 | 4 Horsepool Road, Withywood | 33759/1 | Works Completed | Invoiced | 36/889 | 2026-02-06 08:59:00 | 15 days |  |  | Shannon Slade | 12/12/2025 14:54 | No | Fully Complete | 2026-02-27 | Yes |  |  | Complete | 480.9
2025-11-24 14:45:00 | JW - As per Jeff Neck - Inspect leak around bathroom shower, remove tiles as required and repair/ reseal/retile | 2026-01-16 11:00:00 |  | 2025-12-22 12:48:00 | Routine Repairs | 1278597 | 129 FOUR ACRES | 33810/1 | Works Completed | Invoiced | 36/892 |  | 15 days |  |  | Shannon Slade | 12/12/2025 14:45 |  | Post-completion Items To Complete | 2026-03-19 | Yes |  | 07/04 - KPI added and sent to EH - CL | Complete | 85.88
2025-11-24 12:24:00 | JW - Rob Doidge - Renew base unit to kitchen, Renew drawer to kitchen unit, Flooring - Discuss with Rob for locations | 2026-07-13 10:00:00 | 2026-07-13 |  | Routine Repairs | 1248653 | 34 HIGHBURY ROAD | 33711/1 | New Works Instruction | ACE Agreed | 36/882 |  | 15 days |  |  | Shannon Slade | 12/12/2025 12:24 |  | Pre-completion Items To Complete |  |  |  | 08/05 - Appointment rescheduled due to operative illness - CL | Appointment booked | 300.64
2025-11-24 11:44:00 | AS PER NICHOLAS CORY JW TO SKIM WALLS IN STAIRWELL AND DECTORATE. | 2026-05-12 08:00:00 | 2026-06-01 | 2026-04-15 11:35:00 | Routine Repairs | 1275883 | 17 Dancey Mead | 7166/4 | Works Completed |  | 36/875 | 2026-04-09 08:00:00 | 15 days |  |  | Lainie Lavin | 12/12/2025 11:44 | No | Pre-completion Items To Complete | 2026-06-08 | Yes |  | 08/06 - KPI requested - CL 01/06 - Unable to contact tenant, text sent - CL 11/5 - chased up email for omitting dec works (LL). 29/04 - Email sent to NC regarding omitting the decs. Tenant called to say after a visit from BCC he would like to decs to be put on hold for a few months - CL 27/04 - Appointment needs to be rebooked du | Complete | 718.44
2025-11-24 10:24:00 | Complaint works contact Andrew Griffiths Please contact Andrew Griffiths BCC Roof Inside | 2025-12-16 08:15:00 |  | 2026-01-15 12:00:00 | Routine Repairs | 1275941 | 31 Dancey Mead, Highridge | 33572/1 | Works Completed | Invoiced | 36/874 |  | 15 days |  |  | Lainie Lavin | 12/12/2025 10:24 |  | Post-completion Items To Complete | 2026-01-23 | Yes |  |  | Complete | 1108.05
2025-11-24 10:10:00 | JW - As per Jeff Neck -Various works throughout kitchen - Refer to SOR breakdown for specfic comments | 2026-05-13 08:00:00 | 2026-05-13 | 2026-05-13 12:00:00 | Routine Repairs | 1317595 | 37 Wymbush Crescent | 33722/1 | Works Completed | ACE Agreed | 36/885 | 2026-04-30 08:00:00 | 15 days |  |  | Shannon Slade | 12/12/2025 10:10 | No | Post-completion Items To Complete | 2026-06-08 | Yes |  | 08/06 - KPI request - CL 01/05 - Appointment reschedule due to illness - CL 27/04 - Follow on appointment to booked for 01/05 - CL | Complete | 1132.64
2025-11-24 10:04:00 | JW - Rob Doidge - REFIX WOBLY WC PAN, REFIX BATH AT SHOWER END AND RESEAL AROUND END. REFIX LOOSE FLOORING TO LANDING, PATCH REPAIR TO PLASTERBOARD ON BEDROOM CEILING. STAINBLOCK REPAINT KITCHEN CEILING | 2026-04-24 16:00:00 |  | 2026-04-24 08:00:00 | Routine Repairs | 1278804 | 181 FOUR ACRES | 33713/1 | Works Completed | Invoiced | 36/884 | 2026-03-31 08:00:00 | 15 days |  |  | Shannon Slade | 12/12/2025 10:04 | No | Pre-completion Items To Complete | 2026-05-05 | Yes |  | 05/05 - KPI requested - CL 27/04 - Job complete awaiting completion photos from DW as EasyBop was down - CL | Complete | 302.34
2025-11-24 09:58:00 | JW - Rob D - renew bath panel, renew sealant around bath in full,Renew skirting on wc wall & bath panel,Renew bathroom non slip flooring&renew boxing behind w.c, L-Room - renew self levelling screed to floor in full, 16m2 | 2026-07-24 08:00:00 | 2026-07-24 |  | Routine Repairs | 1309859 | 40 OAK HOUSE | 33695/1 | New Works Instruction | ACE Agreed | 36/883 |  | 15 days |  |  | Shannon Slade | 12/12/2025 09:58 |  | Pre-completion Items To Complete |  |  |  | 03/07 - NA on 02/07, appointment rescheduled - CL 01/07 - Appointment rescheduled due to op being unavailable, voicemail left and text sent - CL 30/06 -Appointment confirmed with tenant - CL 24/06 - Appointment rebooked with tenant as operative was called away on an emergency - CL Appointment reschedule to 31/03 as requested by resident - CL - Need to rebook appointment as op was off sick | Appointment booked | 865.87
2025-11-24 09:54:00 | JW - As per Tom Walker - : No handrail on staircase. To be I stalled mopstick timber handrail | 2026-04-17 13:15:00 |  | 2026-03-25 09:30:00 | Routine Repairs | 1303011 | 561 Hareclive Road, Hartcliffe | 33568/1 | Works Completed | Invoiced | 36/873 | 2026-03-25 08:00:00 | 15 days |  |  | Lainie Lavin | 12/12/2025 09:54 | No | Pre-completion Items To Complete | 2026-04-28 | Yes |  | 28/04 - KPI request sent - CL | Complete | 97.68
2025-11-24 09:44:00 | AS PER NICHOLAS CORY JW TO RENEW DOOR LATCH, NEW FLR BDS & RISER ON STAIRS, POLYSAFE FLOORING IN BATHROOM | 2026-02-26 08:00:00 |  | 2026-03-27 08:54:00 | Routine Repairs | 1275883 | 17 Dancey Mead | 7166/3 | Works Completed | ACE Agreed | 36/872 | 2026-02-26 08:00:00 | 15 days |  |  | Lainie Lavin | 12/12/2025 09:44 | No | Post-completion Items To Complete | 2026-06-08 | Yes |  | 08/06 - KPI requested - CL 01/06 - WAITING FOR CONFIRMATION THAT WORKS ARE COMPLETD BY FF SENT EMAIL TO FF, AWAITING RESPONSE FOR DATE -17/3. Chased up email -27/3. Awaiting response for pics from ff -10/4. | Complete | 341.48
2025-11-21 16:39:00 | Roofers to strip first 3 rows of felt, batten and tiles on all sides, replace all fascia`s, soffits, and rainwater goods with new UPVC, fit eave ventilators and re-bed any hips that are removed and insulate any sloping ceilings whilst | 2026-05-28 12:00:00 |  | 2026-05-28 10:06:00 | Routine Repairs | 1273456 | 31 Brunel Road | 33435/1 | Works Completed | Invoiced | 36/880 |  | 15 days |  |  | Shannon Slade | 11/12/2025 16:39 |  | Fully Complete | 2026-06-02 |  |  | 27/05 - Left a voicemail informing tenant of site visit 28/05 - CL 23/04 - Work dates confirmed with tenant. Scaffolding to be erected 16/05 and work to commence 18/05. Unable to make contact with tenant, voicemail and text message sent - CL 13/04 - Unable to make contact with tenant, voicemail and text message sent - CL | Complete | 10120.97
2025-11-21 16:29:00 | Replace soffits, Facia`s and rainwater goods on all sides, take off 3 rows of tiles on all sides and replace felt batten and eave ventilators and re-bed any hips during the works, insulate any slopping ceiling | 2026-04-15 12:30:00 |  | 2026-04-15 08:30:00 | Routine Repairs | 1241107 | 10 Brixham Road | 33424/1 | Works Completed | Invoiced | 36/871 | 2026-04-15 08:33:00 | 15 days |  |  | Shannon Slade | 11/12/2025 16:29 | No | Fully Complete | 2026-04-27 | Yes |  | 17/04 - Email sent to off hire scaffolding. Email sent to MF. Completion photos uploaded - CL 09/04 - SCAFFOLDING BEING ERECTED 13TH APRIL. WORKS ISSUED TO SHEPPS. | Complete | 7988.53
2025-11-21 16:09:00 | Scaffolding 3 sides of the property for roofers to replace fascia soffit and gutters 3 sides Strip bottom course of felt and battens, install insulation to sloping ceilings, eave trays and breathable felt and close in. Scaffolding to all 3 sides of the property for roofers to replace fascia soffit and gutters all around. Strip bottom course of felt and battens, install insulation to sloping ceilings. Install eave trays and breathable felt and close in. |  |  | 2026-03-04 13:47:00 | Routine Repairs | 1221825 | 43 Ilminster Avenue, Knowle | 33411/1 | Works Completed | Invoiced | 36/870 |  | 15 days |  |  | Lainie Lavin | 11/12/2025 16:09 |  | Fully Complete | 2026-03-05 | Yes |  |  | Complete | 8108.56
2025-11-21 13:33:00 | Complaint works- Please see email and report. | 2026-02-10 08:00:00 |  | 2026-02-23 08:14:00 | Disrepair | 1261092 | 27 Shepton Walk | 33298/1 | Works Completed | Invoiced | 36/909 | 2026-02-10 08:00:00 | 20 days |  |  | Shannon Slade | 18/12/2025 13:33 | No | Fully Complete | 2026-03-25 | Yes |  |  | Complete | 1006.86
2025-11-21 13:02:00 | Hack off, loose rendering on parapet wall, re-render, stack needs pointing, this is on the rear of the property, scaffolding is up. stack needs flaunching, check for leak, water seal, chimney and rendering, Copings. Inspected by BCC Roofers | 2025-12-08 08:00:00 |  | 2026-02-23 11:10:00 | Disrepair | 1115055 | 158 RICHMOND ROAD | 30598/1 | Works Completed | Invoiced | 36/869 |  | 20 days |  |  | Shannon Slade | 18/12/2025 13:02 |  | Post-completion Items To Complete | 2026-02-23 | Yes |  |  | Complete | 464.31
2025-11-21 12:19:00 | JW-AS PER JOHN O: NEW FLOOR IN BATHROOM AND KITCHEN, STAIN BLOCK AND RE-PAINT BATHROOM CEILING, OVERHAUL KITCHEN FAN, RENEW EXTRACTOR FAN IN BATHROOM, CHANGE BATH PANEL, RE-SILICONE BATH | 2026-05-19 12:00:00 | 2026-05-19 | 2026-05-19 16:44:00 | Routine Repairs | 1274142 | 21 Cobhorn Drive, Withywood | 33271/1 | Works Completed | ACE Agreed | 36/868 | 2026-03-17 08:00:00 | 15 days |  |  | Lainie Lavin | 11/12/2025 12:19 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI request sent - CL 30/04 - Unable to make contact with tenant voicemail and text sent - CL 28/04 - Awaiting a new appointment from Compliance - CL Awaiting appointment date from Compliance for fan install and overhaul - CL | Complete | 1180.81
2025-11-21 12:09:00 | JW - AS PER JOHN O: REDECORATION, REGROUTING AND TILING WORK IN BATHROOM. | 2026-03-05 08:00:00 |  | 2026-03-05 14:21:00 | Routine Repairs | 1313140 | 28 Stillingfleet Road, Hartcliffe | 33262/1 | Works Completed | Invoiced | 36/866 | 2026-03-05 08:00:00 | 15 days |  |  | Lainie Lavin | 11/12/2025 12:09 | No | Pre-completion Items To Complete | 2026-04-09 | Yes |  |  | Complete | 193.31
2025-11-21 12:09:00 | JW - AS PER JOHN O: RE-PAINT WALL ABOVE BATH, CHANGE BATH PANEL, RE-SILICON AROUND WINDOW FRAME IN LIVING ROOM AND PATCH REPAIR |  |  | 2026-03-26 15:24:00 | Routine Repairs | 1286722 | 19 Pigott Avenue, Withywood | 33259/1 | Works Completed | Invoiced | 36/867 |  | 15 days |  |  | Lainie Lavin | 11/12/2025 12:09 |  | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 20/04 - KPI received and uploaded - CL 15/04 - KPI request sent - CL | Complete | 257.66
2025-11-21 11:49:00 | Complaint disrepair works / as per CG | 2026-01-26 11:30:00 |  | 2026-03-02 10:21:00 | Disrepair | 1163491 | 20 ASHMEAD HOUSE | 33304/1 | Works Completed | Invoiced | 36/910 | 2026-01-22 12:00:00 | 20 days |  |  | Shannon Slade | 18/12/2025 11:49 | No | Post-completion Items To Complete | 2026-03-19 | Yes |  |  | Complete | 665.01
2025-11-21 09:59:00 | Jeffway - As per John Oyeniyi - REDECORATION WORK IN THE KITCHEN AND BATHROOM | 2026-07-03 12:00:00 | 2026-07-03 |  | Routine Repairs | 1281318 | 11 Hersey Gardens, Withywood | 32892/1 | Works Started | ACE Agreed | 36/864 | 2026-03-26 08:00:00 | 15 days |  |  | Lainie Lavin | 11/12/2025 09:59 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Appointment confirmed with tenant - CL 16/06 - Op unable to complete work as tenant wanted to go out. Follow on appointment booked - CL 02/06 - WORKS ARE NOT COMPLETED, WORKS BOOKED INTO BE COMPLETED 15TH JUNE. 27/05 - No answer from tenant, voicemail and text message sent - CL 06/05 - KPI requested - CL No answer from tenant - 17/4/26. | Appointment booked | 1083.13
2025-11-21 09:09:00 | JW - Rob D - take down and renew rear section of wall from lhs boundary approx 4lin meters to rhs. 6ft High, renew with a timber fence to allow for movement due to large tree roots. Photos emailed to Shannon 21/10/25 |  | 2026-01-22 | 2026-01-22 12:08:00 | Routine Repairs | 1286540 | 6 Pesley Close, Withywood | 32872/1 | Works Completed | Invoiced | 36/861 | 2026-01-22 12:11:00 | 15 days |  |  | Lainie Lavin | 11/12/2025 09:09 | No | Fully Complete | 2026-01-28 | Yes |  |  | Complete | 1123.42
2025-11-21 09:09:00 | JW - Rob D - - renew blown dgu to kitchen, overhaul dripping taps to basin, renew 1 x missing tile to shelf behind WC and trim, 2 x bedroom doors catching on the carpet |  |  | 2026-03-26 14:38:00 | Routine Repairs | 1311940 | 96 Rookery Way, Hartcliffe | 32875/1 | Works Completed | Invoiced | 36/862 |  | 15 days |  |  | Lainie Lavin | 11/12/2025 09:09 |  | Pre-completion Items To Complete | 2026-04-17 | Yes |  | 20/04 - KPI received and uploaded - CL | Complete | 290.46
2025-11-21 09:09:00 | JW - Ian O - WORKS OUTSTANDING FROM PREVIOUS ORDER : RE POINT PATIO THAT WAS POORLY DONE / MISSING PASSIVE VENT , FILLING INSIDE FRONT DOOR , CLOSE OFF DUCTING BEHIND KITCHEN | 2026-07-02 12:00:00 |  |  | Routine Repairs | 1207961 | 44 Wharnecliffe Gardens, Whitchurch | 32869/1 | Works Started | ACE Agreed | 36/863 | 2026-03-23 12:00:00 | 15 days |  |  | Lainie Lavin | 11/12/2025 09:09 | No | Pre-completion Items To Complete |  |  |  | 01/07 - Unable to get hold of tenant, voicemail left and text sent - CL 26/06 - Appointment rebooked due to op being ill - CL 15/06- Appointment on 12/06 cancelled by tenant, new appointment given - CL 29/05 - rebooked 02/06 due to op sickness 27/04 - No access, appointment needs to be rescheduled - CL 21/04 - Front door completed 26/03. Follow on appointment booked for 23/04 - CL Tenant has complaint of previous works, awaiting update from Darren Whitchurch how to proceed -27/3. 31/03 - report | Held BCC | 190.2
2025-11-21 08:49:00 | Scaffolding upto gutter height at rear of property as photo. Roofers to renew first course of felt and batten, installing eves trays, possible insulation too eves? Renew lead slate to stench pipe. insulate eaves when uncovered if possible with 50mm rockwool slabs |  | 2026-04-08 | 2026-04-07 13:04:00 | Routine Repairs | 1189920 | 41 Whitmore Avenue, Broomhill | 32839/1 | Works Completed | ACE Agreed | 36/859 |  | 15 days |  |  | Lainie Lavin | 11/12/2025 08:49 |  | Pre-completion Items To Complete | 2026-03-31 | Yes |  |  | Complete | 8059.74
2025-11-21 07:49:00 | JW - As per Jeff - Various plastering work to kitchen and hallway, Anti condensat paint to kitchen ceiling only, Apply emulsion paint to kitchen &hallway walls. Refix kitchen wall cupboards &radiator. Fix new lever handles on kitchen door. Remove kitchen wall cupboards / wall fan / light fitting and radiator in hallway. Scrap hack off water damage plaster work to complete ceiling and walls in kitchen and hallway . Apply plaster skim to complete ceiling and all kitchen and hallway walls. Apply anti condensation paint to ceiling only. Apply emulsion paint to kitchen and hallway walls. Refix kitchen wall cupboards and radiator. Fix new lever handles on kitchen door. | 2026-05-22 08:00:00 | 2026-05-22 | 2026-05-22 12:22:00 | Routine Repairs | 1278791 | 180 Four Acres, Withywood | 32806/1 | Works Completed | Invoiced | 36/860 | 2026-04-08 08:00:00 | 15 days |  |  | Lainie Lavin | 11/12/2025 07:49 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 30/06 - KPI received and updated - CL 29/05 - KPI requested - CL Called tenant no answer, left voice note awaiting response -10/4. | Complete | 1391.74
2025-11-20 17:19:00 | JW - As per Rob Doidge - REFIX / RESECURE 3 X LOOSE UPVC EXTERNAL WINDOW SILLS TO FRONT ELEVATION | 2026-01-28 12:00:00 |  | 2026-01-28 13:41:00 | Routine Repairs | 1289130 | 70 Sherrin Way, Withywood | 32795/1 | Works Completed | Invoiced | 36/858 |  | 15 days |  |  | Lainie Lavin | 10/12/2025 17:19 |  | Fully Complete | 2026-02-26 | Yes |  |  | Complete | 83.38
2025-11-20 14:39:00 | JW - As per Jeff Neck - Apply latex to seal corridor and part living floor at position of water damage floor tiles which have been lifted by others |  | 2025-12-03 | 2025-12-03 12:34:00 | Routine Repairs | 1303806 | 46 Hayleigh House, Silcox Road, Hartcliffe | 32055/1 | Works Completed | Invoiced | 36/855 |  | 15 days |  |  | Lainie Lavin | 10/12/2025 14:39 |  | Post-completion Items To Complete | 2025-12-17 | Yes |  |  | Complete | 210.69
2025-11-20 14:39:00 | JW - As per Rob Doidge - RENEWAL OF WINDOW MOUNTED FAN IN BATHROOM, USE SLIMLINE VERSION DUE TO BLIND. PAINT CEILING IN FULL WITH HALOPHEN AND CLEAN OFF UPVC WINDOW OF MOULD | 2026-05-12 12:00:00 | 2026-05-14 | 2026-05-14 10:18:00 | Routine Repairs | 1299805 | 31 Faber Grove, Hartcliffe | 32042/1 | Works Completed |  | 36/856 | 2026-02-23 15:00:00 | 15 days |  |  | Lainie Lavin | 10/12/2025 14:39 | No | Pre-completion Items To Complete | 2026-06-11 | Yes |  | 11/06 - KPI requested - CL 02/06 - VO sent to RD - CL 18/05 - Completed awaiting photos 15/05 - chasing compliance for completion photos 20/04 - NA for fan installation. Appointment to be rebooked - CL | Complete | 442.85
2025-11-20 14:39:00 | JW - As per Rob Doidge - REPAIRS TO GUTTERING ONLY AT FRONT OF PROPERTY, DROPPED SECTION TO LHS NEAR NO.23 AND 2 X BRACKETS/ JOINTS ABOVE CANOPY BY DOWNPIPE, GUTTER ONLY AS FASCIA LIKELY TO BE RENEWED ON EXTERNAL WORKS PROG NEXT YEAR | 2026-03-17 08:00:00 |  | 2026-03-17 14:07:00 | Routine Repairs | 1284704 | 25 Millground Road, Withywood | 32044/1 | Works Completed | Invoiced | 36/857 | 2026-03-17 08:00:00 | 15 days |  |  | Lainie Lavin | 10/12/2025 14:39 | No | Fully Complete | 2026-03-19 | Yes |  |  | Complete | 164.02
2025-11-20 13:19:00 | JW - As per Jeff - Various works required throughout property, See SOR comments for specific location details Hack off damage plaster work to the sides and behind ground floor toilet and reskim to match existing levels. Remove rotten timber skirting at this position and refix new plastic . Apply anti condensation to complete ceiling. Fix condensation fan in external wall in ground floor bathroom. Apply emulsion paint to all bathroom walls . Overhaul and repaint front timber door . Overhaul and repaint rear back garden door . | 2026-06-29 13:00:00 | 2026-06-29 |  | Routine Repairs | 1308516 | 3 Mowcroft Road, Hartcliffe | 31982/1 | Works Started | ACE Agreed | 36/854 | 2026-04-02 08:00:00 | 15 days |  |  | Lainie Lavin | 10/12/2025 13:19 | No | Pre-completion Items To Complete |  |  |  | 30/06 - Outstanding work needs to be identified and booked - CL 01/06 - Unable to contact tenant, voicemail left - CL 12/05 - TENANT HAS CONFIRMED SHE'S ON AVAILABLE ON MONDAY, WORKS TO BE RE BOOKED. 21/04 - Follow on appointment booked for 29/05 to complete work - CL 09/04 - Unable to make contact with tenant voicemail and text sent - CL 08/04 - Unable to contact tenant | WIP | 807.84
2025-11-20 08:59:00 | Jeffway - please replace sloping ceiling approx 2sqm in small bedroom with thermal plasterboard and redecorate. Contact is Melissa Edwards 07442675013. | 2026-01-23 08:00:00 | 2026-01-23 | 2026-01-23 14:59:00 | Routine Repairs | 1233712 | 12 Tavistock Road, Knowle | 31740/1 | Works Completed | Invoiced | 36/848 | 2026-01-08 10:04:00 | 15 days |  |  | Lainie Lavin | 10/12/2025 08:59 | No | Post-completion Items To Complete | 2026-02-16 | Yes |  |  | Complete | 318.0
2025-11-19 16:09:00 | AS PER JOHN OYENIYI: RENEW SOME PAVING SLABS IN THE REAR GARDEN TO MAKE SAFE AND FUNCTIONAL, AND APPLY GLOSS PAINT TO KITCHEN EXTERNAL DOOR TO THE SIDE FACING THE GARDEN | 2026-02-05 08:00:00 | 2026-02-09 | 2026-02-05 10:45:00 | Routine Repairs | 1223570 | 59 Kenmare Road, Knowle, Bristol | 31646/1 | Works Completed | Invoiced | 36/851 | 2026-01-30 08:00:00 | 15 days |  |  | Lainie Lavin | 09/12/2025 16:09 | No | Fully Complete | 2026-02-12 | Yes |  |  | Complete | 177.04
2025-11-19 11:09:00 | Complaints works - lounge and hallway - re-raised due to jobs being handed back from WMS | 2026-02-04 08:00:00 | 2026-07-10 |  | Disrepair | 1307751 | Millmead House, 1 Silcox Road | 31414/1 | Works Started | ACE Agreed | 36/907 | 2026-02-04 08:00:00 | 20 days |  |  | Shannon Slade | 16/12/2025 11:09 | No | Pre-completion Items To Complete |  |  |  | 16/06 - WORKS RE BOOKED FOR 10TH JULY AT TENANTS REQUEST. 05/06 - WORKS BEING COMPLETED 8TH JUNE. 24/03 - EMAIL ISSUED TO BCC TO CONFIRM HOW TO PROCEED. | Appointment booked | 983.21
2025-11-19 10:05:00 | Complaint disrepair works / as per G Squared site survey |  |  |  | Disrepair | 1234044 | 10 TAVISTOCK WALK | 31567/1 | New Works Instruction | ACE Agreed | 36/906 |  | 20 days |  |  | Shannon Slade | 16/12/2025 10:05 |  | Pre-completion Items To Complete |  |  |  | 15/04 - NEED UPDATE FROM DARREN. 10/04 - QUOTE ISSUED TO BCC, WAITING FOR APPROVAL.14/04 - QUOTE HAS BEEN APPROVED, WAITING FOR MIKE ROE FRENCH TO UPDATE ORDER. |  | 3211.1
2025-11-18 18:11:00 | JEFF WAY - ROOF REPAIRS AS PER IAN OGBORNE/ CHRIS BRAKE. | 2026-01-15 08:00:00 |  | 2026-02-03 11:56:00 | Routine Repairs | 1210180 | 1 Bantock Close, Inns Court, | 30583/1 | Works Completed | Invoiced | 36/847 | 2026-02-03 15:44:00 | 15 days |  |  | Lainie Lavin | 08/12/2025 18:11 | No | Pre-completion Items To Complete | 2026-03-25 | Yes |  |  | Complete | 1063.04
2025-11-18 16:19:00 | AS PER NICHOLAS CORY JEFFWAY TO REHANG KITCHEN CUPBOARD , CUPBD ON SITE , PLA WK REQUIRED TO FILL HOLES | 2026-05-18 07:00:00 | 2026-05-18 | 2026-05-18 17:41:00 | Routine Repairs | 1216495 | 29a Creswicke Road, Knowle | 30950/4 | Works Completed | ACE Agreed | 36/849 | 2026-05-18 08:00:00 | 15 days |  |  | Lainie Lavin | 08/12/2025 16:19 | No | Pre-completion Items To Complete | 2026-06-12 | Yes |  | 12/06 - KPI requested - CL 27/03 Appointment booked for 18/05. Email and letter sent - CL | Complete | 47.39
2025-11-18 13:49:00 | Complaint disrepair works / as per G Squared site survey | 2026-02-04 08:00:00 | 2026-02-05 | 2026-02-05 13:39:00 | Disrepair | 1063203 | 146 OKEBOURNE ROAD | 30697/1 | Works Completed | Invoiced | 36/905 | 2026-02-04 08:00:00 | 20 days |  |  | Shannon Slade | 15/12/2025 13:49 | No | Fully Complete | 2026-02-16 | Yes |  |  | Complete | 642.88
2025-11-18 13:42:00 | DN786139 - RESPONSE REPAIR OVER FLOW - Complaint disrepair works / as per G Squared site survey | 2026-02-03 12:00:00 | 2026-02-03 | 2026-02-03 13:00:00 | Disrepair | 1069836 | 23 STANDON WAY | 30727/1 | Works Completed | Invoiced | 36/904 | 2026-02-03 12:15:00 | 20 days |  |  | Shannon Slade | 15/12/2025 13:42 | No | Fully Complete | 2026-02-16 | Yes |  |  | Complete | 192.43
2025-11-18 11:49:00 | as per Aaron Watkins - quote from Jeffway for demolish of extension and new external rear door |  | 2026-01-06 | 2026-01-06 10:48:00 | Routine Repairs | 1288988 | 54 Sherrin Way, Withywood | 30593/1 | Works Completed | Invoiced | 36/846 |  | 15 days |  |  | Lainie Lavin | 08/12/2025 11:49 |  | Post-completion Items To Complete | 2026-01-07 | Yes |  |  | Complete | 10985.0
2025-11-18 09:29:00 | Complaint Disrepair work: Jeffway to prep and gloss paint both the rear and front doors. (second sor code is on previous order to be re-attended) | 2026-06-23 08:00:00 |  | 2026-02-19 13:19:00 | Disrepair | 1219303 | 110 EXMOUTH ROAD | 1234784 | Works Completed | ACE Agreed | 36/833 |  | 20 days |  |  | Shannon Slade | 15/12/2025 09:29 |  | Post-completion Items To Complete | 2026-03-19 | Yes |  |  | Complete | 77.42
2025-11-17 13:24:00 | DN786139 - disrepair works as per C. Grigg survey - disrepair works to replace cancelled job |  | 2026-07-14 |  | Disrepair | 1224084 | 24 KERRY ROAD | 5177/2 | New Works Instruction | ACE Agreed | 36/887 |  | 20 days |  |  | Shannon Slade | 12/12/2025 13:24 |  | Pre-completion Items To Complete |  |  |  | 02/07 - Email sent to CG regarding rescheduling appointment to August as requested by tenant - CL 30/06 - Spoke with tenant who informed me that she sent an email confirming her availability and is awaiting a response - CL WORKS BOOKED FOR 2ND JULY, 13-16TH JULY - FLOORING WORKS TO BE BOOKED UPON COMPLETION | Appointment booked | 3764.35
2025-11-17 10:20:00 | DN786139 - Remedial works following disrepair claim | 2026-08-07 08:00:00 | 2026-07-30 |  | Disrepair | 1245143 | 37 DARTMOOR STREET | 4829/2 | New Works Instruction | ACE Agreed | 36/903 |  | 20 days |  |  | Shannon Slade | 12/12/2025 10:20 |  | Pre-completion Items To Complete |  |  |  | 01/07 - Appointments confirmed with tenant - CL EMAIL ISSUED TO JAMES BAILEY REGARDING LEAK IN PROPERTY. 30/03 - CHASED JB FOR RESPONSE. | Appointment booked | 1533.01
2025-11-17 10:11:00 | Complaints work - works throughout property. Re-raised | 2026-06-10 09:30:00 | 2026-06-30 | 2026-06-30 14:16:00 | Disrepair | 1010500 | 192 BROADLANDS DRIVE | 30060/1 | Works Completed | ACE Agreed | 36/902 | 2026-06-10 10:00:00 | 20 days |  |  | Shannon Slade | 12/12/2025 10:11 | No | Pre-completion Items To Complete |  | No |  | 16/06 - ALL WORKS COMPLETED APART FROM DECS, BOOKED FOR 23RD JUNE. 29/05 - NO ACCESS FOR WORKS ON 28TH APRIL. APPOINTMENT RE BOOKED FOR 9TH OF JUNE. DATE ISSUED TO BCC. WORKS BOOKED FOR 18TH MARCH - NO ACCESS, EMAIL ISSUED TO BCC 19/03 - ACCESS LETTER BEING ISSUED, WORKS BOOKED FOR 21/04. 23/04 - TENANT WASNT HOME ON 21ST. SPOKE WITH TENANT VIA PHONE AND REBOOKED FOR 13/05. | Complete | 1012.65
2025-11-17 10:06:00 | DN786139-response repairs overflow - Complaint disrepair works - as G Squared survey. | 2026-03-18 10:00:00 | 2026-07-02 |  | Disrepair | 1024595 | 39 MANCROFT AVENUE | 29993/2 | Works Started | ACE Agreed | 36/901 | 2026-03-17 08:00:00 | 20 days |  |  | Shannon Slade | 12/12/2025 10:06 | No | Pre-completion Items To Complete |  |  |  | 01/07 - Tenant has said all work has been completed and only fan outstanding - CL 25/06 DGU needs to be fitted for fan - CL 24/06 - NA unable to get hold of tenant, voicemail left - CL 15/05 - WORKS REBOOKED FOR 18TH, 24TH AND 25TH JUNE. -NO ACCESS ON 13TH MARCH - REBOOKED VIA EMAIL FOR 20TH APRIL, 21ST APRIL, 5TH AND 6TH MAY | WIP | 1784.41
2025-11-17 10:03:00 | Complaints work as per G Squared survey | 2026-02-23 08:00:00 |  |  | Disrepair | 1156770 | 15 ROPEWALK HOUSE | 30018/1 | New Works Instruction | ACE Agreed | 36/900 |  | 20 days |  |  | Shannon Slade | 12/12/2025 10:03 |  | Suspended: Awaiting Client Action/Response |  |  |  | 14/05 - WALLS ARE STILL TO WET FOR BATH PANELS TO BE INSTALLED. EMAILED TT TO CONFIRM HOW TO PRIOCEED. 10/04 - WORKS WERE UNABLE TO BE TILED DUE TO WALLS BEING WET. TOM TAYLOR HAS CONFIRMED TO INSTALL BATH PANELS INSTEAD. WORKS BOOKED FOR 06/05. | Held BCC | 290.99
2025-11-17 09:59:00 | tower upto gutter height in front of bedroom bay window, allowing room either side of bay window. Roofers/repair leak affecting bedroom ceiling. Scaffolders will require access to gardens of x2 private properties, (13 & 14 parbrook court). | 2026-01-19 08:00:00 | 2026-01-19 | 2026-01-19 16:01:00 | Routine Repairs | 1202615 | 16 PARBROOK COURT | 30038/1 | Works Completed | Invoiced | 36/830 | 2026-01-19 08:30:00 | 15 days |  |  | Shannon Slade | 05/12/2025 09:59 | No | Fully Complete | 2026-02-16 | Yes |  |  | Complete | 1333.78
2025-11-17 09:21:00 | COMPLAINT- Rake out and renew sealant around window in bedroom 2. Measure up and renew blown glazing unit in bedroom 1. Secure loose bath panel with extra fitting | 2026-01-28 16:45:00 |  | 2026-03-06 09:59:00 | Disrepair | 1310652 | 14 PAWLETT ROAD | 30377/1 | Works Completed | ACE Agreed | 36/895 | 2026-01-28 16:45:00 | 20 days |  |  | Shannon Slade | 12/12/2025 09:21 | No | Post-completion Items To Complete | 2026-03-10 | Yes |  |  | Complete | 261.36
2025-11-12 13:45:00 | Disrepair- Charlotte Smart As per Scott Schedule,, quantities not accurate please advise when work is starting to meet on site to finalise quantities charlotte.smart2@bristol.gov.uk | 2026-06-08 12:00:00 |  | 2026-04-13 08:22:00 | Disrepair | 1109451 | 106a Cotham Brow | 29125/1 | Works Completed | ACE Agreed | 36/897 |  | 20 days |  |  | Shannon Slade | 09/12/2025 13:45 |  | Post-completion Items To Complete | 2026-04-30 | Yes |  | 10/04 - EMAIL ISSUED TO LOTTIE REGARDING WORKS 13/04 - DAR COMPLETING SITE VISIT TODAY TO SEE IF WORKS ARE COMPLETED. 15/04 - SITE VISIT COMPLETED. WAITING FOR UPDATE FROM DARREN. | Complete | 50.0
2025-11-12 12:49:00 | AS PER NICHOLAS CORY JW TO RENEW BATH TAP ENDS AGAINST WALL TILE TO CEILING BOTH ENDS , INSULATE PIPE WORK BEHIND BATH AND TO W/C , FLOOR UPSTAND AGAINST BATH PANELS , SHOWER CURTAIN AND NEW SKIRTING UNDER SINK | 2026-02-03 08:00:00 |  | 2026-02-06 09:00:00 | Routine Repairs | 1076546 | 40 Westleigh Road, Southmead | 29006/2 | Works Completed | ACE Agreed | 36/825 | 2025-12-16 08:00:00 | 15 days |  |  | Lainie Lavin | 02/12/2025 12:49 | No | Post-completion Items To Complete | 2026-03-19 | Yes |  | 23/06 - KPI update request sent - CL 07/04 - KPI request added and forwarded to EH - CL | Complete | 2518.98
2025-11-12 11:29:00 | Complaints work - works throughout property. Re-raised | 2026-01-07 11:15:00 |  | 2026-01-07 15:15:00 | Disrepair | 1073274 | 83 TRANMERE AVENUE | 29023/1 | Works Completed | Invoiced | 36/896 | 2026-01-07 08:00:00 | 20 days |  |  | Shannon Slade | 09/12/2025 11:29 | No | Post-completion Items To Complete | 2026-02-05 | Yes |  |  | Complete | 698.34
2025-11-12 09:57:00 | Complaint- Charlotte Smart As per Scott Schedule, charlotte.smart2@bristol.gov.uk |  | 2026-06-10 |  | Disrepair | 1024028 | 638 Long Cross | 29196/1 | New Works Instruction | ACE Agreed | 36/899 |  | 20 days |  |  | Shannon Slade | 09/12/2025 09:57 |  | Suspended: Awaiting Client Action/Response |  |  |  | 01/07/26 Email sent to BCC for an update UNABLE TO GET HOLD OF TENANT. 30/03 - TRIED TO CONTACT TENANT AGAIN TODAY. EMAIL SENT TO CHARLOTTE AND TOM TAYLOR FOR ASSISTANCE. | Held BCC | 2314.36
2025-11-11 14:49:00 | Disrepair works for Tom Lear | 2026-04-22 11:30:00 |  |  | Disrepair | 1077185 | 13 Wilton Close | 28666/1 | Works Started |  | 36/845 | 2026-01-30 09:00:00 | 20 days |  |  | Shannon Slade | 08/12/2025 14:49 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Timberwise due attend today 16/06 - CHASED TW FOR DATE. 05/06 - TIMBERWISE ISSUED REPORT TO US 04/06, SENT TO BCC TODAY. 19/05 - WAITING FOR TIMBERWISE? 23/03 - TIMBERWISE HAS BEEN STRUGGLING TO GET HOLD OF TENANT TO COMPLETE DAMP SURVEY - I HAVE ASKED THEM TO CONFIRM DATE THEY WOULD LIKE TO ATTEND SO I CAN RING THE TENANT TOO. | WIP | 2246.65
2025-11-11 14:19:00 | Bathroom Mould by window. fit extrct fan, rnw bath panel. LIV ROOM - ceiling, hack off, replaster & decorate. BED1 - Mould on ceiling in the corner, APPLY MLD WASH, EXTERNAL - Exposed wires loose on wall & back of door. cut down aerial/ele | 2026-03-05 12:00:00 |  |  | Disrepair | 1024039 | 640 Long Cross | 28604/1 | New Works Instruction | ACE Agreed | 36/843 |  | 20 days |  |  | Shannon Slade | 08/12/2025 14:19 |  | Pre-completion Items To Complete |  |  |  | 16/06 - NO ACCESS ON 11TH JUNE. WAITING FOR ELECTRICIAN TO REBOOK 20/05 BCC post inspecting 21/05 will sign off after visit BATHROOM WORKS COMPLETED. WORKS TO BE COMPLETED 13TH MARCH. 30/03 - EMAIL ISSUED TO LOTTIE ON HOW TO PROCEED WITH WORKS. | WIP | 509.19
2025-11-11 14:19:00 | DISREPIAR- TOM LEAR - JEFF WAY TO CARRY OUT WORKS AS PER S1 COMPLAINT | 2026-01-08 08:00:00 |  | 2026-03-23 13:53:00 | Disrepair | 1282399 | 32 Horsepool Road | 28710/1 | Works Completed | Invoiced | 36/844 | 2026-01-08 13:41:00 | 20 days |  |  | Shannon Slade | 08/12/2025 14:19 | No | Fully Complete | 2026-06-01 |  |  | 22/04 - Tenant cancelled appointment for 27/04 stating she will not be at home - CL | Complete | 1233.1
2025-11-11 11:09:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 29/9/25. 10 DAY PERIOD ENDS 13/10/25 |  |  | 2025-10-02 10:16:00 | Routine Repairs | 1281409 | 23 Hersey Gardens, Withywood | 13366/1 | Works Completed | Invoiced | 36/823 |  | 15 days |  |  | Lainie Lavin | 01/12/2025 11:09 |  | Post-completion Items To Complete | 2025-10-14 | Yes |  |  | Complete | 183.92
2025-11-11 08:48:00 | Jeffway - works agreed with Kellie. Please replace loft insulation. Mike from our roofing dept needs to inspect the loft once the existing insulation is removed to diagnose why there appears to be dust coming down into the prope Jeffway - works agreed with Kellie. Please replace loft insulation. Mike from our roofing dept needs to inspect the loft once the existing insulation is removed to diagnose why there appears to be dust coming down into the property from the loft. please contact mike - michael.roe-french@bristol.gov.uk to advise when works are booked in for. Tenant has breathing difficulties which may be affected by this dust/deposit so please can the works be booked in as soon as possible. | 2025-11-21 12:00:00 |  | 2025-11-24 14:20:00 | Routine Repairs | 3822353 | 15 St Tecla Close, Shirehampton | 16733/1 | Works Completed | Invoiced | 36/819 |  | 15 days |  |  | Lainie Lavin | 01/12/2025 08:48 |  | Post-completion Items To Complete | 2025-11-24 | Yes |  |  | Complete | 1375.88
2025-11-10 17:39:00 | Plaster kitchen ceiling following asbestos removal as per Tom Taylor (07557 930840) | 2026-01-07 12:00:00 |  | 2026-03-20 09:57:00 | Disrepair | 1151731 | 21 Lansdowne Court | 28492/1 | Works Completed | ACE Agreed | 36/842 | 2026-02-06 10:12:00 | 20 days |  |  | Shannon Slade | 05/12/2025 17:39 | No | Post-completion Items To Complete | 2026-03-25 | Yes |  |  | Complete | 1296.68
2025-11-10 17:30:00 | RD - REPAIR PLASTER WC WALL LHS, STAINBLOCK PILLAR AND WALL RHS OF IT IN BED. OVERHAUL WC FLUSH. RENEWAL OF FLOOR STRIPS TO KIT. OVERHAUL F/DOOR, HAS DROPPED LHS. FRONT PATH REPAIR CHUNK ON LHS AND COVER OVER HOLE BY MANHOLE. | 2026-05-27 08:00:00 | 2026-06-03 | 2026-05-27 09:49:00 | Routine Repairs | 1291594 | 8 Withywood Road, Withywood | 24559/1 | Works Completed | ACE Agreed | 36/818 | 2026-03-23 08:00:00 | 15 days |  |  | Lainie Lavin | 28/11/2025 17:30 | No | Pre-completion Items To Complete |  | No |  | 03/06 - Tenant called back and confirm sahe does not want remaining work on order carried out and she will take the matter up with BCC. Unable to contact tenant voicemail left to make contact - CL 28/04 - Operative attended on 27/05 and was refused access due to tenant no being happy with what is on the order. Email sent to RD and CM on how to proceed - CL 20/04 - Follow on appointments booked for 05/05 and 27/05 to complete the work - CL | Complete | 573.99
2025-11-10 15:39:00 | AS PER NICHOLAS CORY JEFFWAY TO HACK OFF ALL OLD PLASTER ON EXTERNAL WALL PAINT WITH BITUMIN RE RENDER WITH SAND/CEMANT AND WATERPROOFER, SKIM FINISH AND PAINT | 2026-07-06 12:00:00 | 2026-07-06 |  | Routine Repairs | 1239823 | 138 Bedminster Road, Bedminster, Bristol, BS3 5NP | 28437/1 | Works Started | ACE Agreed | 36/815 | 2026-04-30 13:00:00 | 15 days |  |  | Lainie Lavin | 28/11/2025 15:39 | No | Pre-completion Items To Complete |  |  |  | 22/04 - Follow on appointment booked for 08/05. Decs to be arrange once plastering completed - CL | WIP | 995.1
2025-11-10 13:59:00 | DISREPIAR- TOM LEAR - JEFF WAY TO CARRY OUT WORKS AS PER S1 COMPLAINT | 2026-04-01 08:00:00 |  | 2026-04-01 12:18:00 | Disrepair | 1236277 | 71 Wallingford Road | 27815/1 | Works Completed | Invoiced | 36/841 | 2026-04-01 08:00:00 | 20 days |  |  | Shannon Slade | 05/12/2025 13:59 | No | Fully Complete | 2026-04-15 | Yes |  |  | Complete | 433.73
2025-11-10 13:36:00 | DISREPAIR WORKS | 2025-12-09 08:00:00 |  | 2026-02-13 12:26:00 | Routine Repairs | 1141680 | 17 Chaplin Road | 1225043 | Works Completed | Invoiced | 36/813 | 2025-12-01 08:00:00 | 15 days |  |  | Shannon Slade | 28/11/2025 13:36 | No | Fully Complete | 2026-02-20 | Yes |  |  | Complete | 3179.54
2025-11-10 12:14:00 | Jeffway-As per Ian Ogborne- PROVIDE AND FIT NEW FLOORING IN BATHROOM | 2026-03-10 14:15:00 |  | 2026-03-10 14:08:00 | Routine Repairs | 1281272 | 7 HERSEY GARDENS | 24258/1 | Works Completed | Invoiced | 36/811 | 2026-03-10 14:08:00 | 15 days |  |  | Lainie Lavin | 28/11/2025 12:14 | No | Pre-completion Items To Complete | 2026-04-29 | Yes |  | 16/06 - KPI received and uploaded - CL 29/04 - KPI requested - CL 16/04 - Email sent to FF for completion photos - CL FF confirmed works completed on 10/03 - CL Email sent to FF for update - CL | Complete | 151.28
2025-11-07 14:59:00 | JEFF WAY FAO JOHN OYENIYI - DECORATIONS :WORK ON DAMP STAINED WALLS AND CEILINGS. THE PROPERTY IS VOID AT THE MOMENT, ACCESS TO KEY SAFE WOULD BE GRANTED AHEAD. | 2026-01-29 10:30:00 |  | 2026-03-17 09:06:00 | Routine Repairs | 1252488 | 139 Littlecross House, Phipps Street, Southville, Bristol, BS3 1SL | 27440/1 | Works Completed | ACE Agreed | 36/803 | 2025-12-11 13:15:00 | 15 days |  | 2026-03-25 10:57:48 | Lainie Lavin | 27/11/2025 14:59 | No | Post-completion Items To Complete | 2026-06-18 | Yes |  | 18/06 - KPI request sent - CL Works to be cancelled as per email from Chloe on 17/03 Tenant has completed works themselves | Complete | 111.71
2025-11-07 10:56:00 | Remove coping stone and replace lead underneath, repair/ rebed pots on chimney, renew render on parapet wall LHS & RHS rear elevation Job added due to age of works/ return for defects Jeff Way - As per Jeff Neck: Hack off plaster/render on internal hallway wall and rerender in sand/cement with waterproofer agent. Reskim to suit exsiting level and repaint complete wall.... | 2025-11-28 08:00:00 |  | 2026-12-04 13:39:00 | Routine Repairs | 1244968 | 223 Coronation Road, Southville | 23840/1 | Works Completed | Invoiced | 36/802 | 2025-11-21 08:00:00 | 15 days |  |  | Darren Whitchurch | 27/11/2025 10:56 | No | Fully Complete | 2026-03-25 | Yes |  |  | Complete | 3068.92
2025-11-05 16:59:00 | JEFF WAY - AS PER ROB DOIDGE - RENEWAL OF KITCHEN PLASTERBOARD CEILING DAMAGED AFTER VARIOUS LEAKS. NA.D TO ARTEX COATING. 2 X COATS OF PAINT TO NEW CEILING AND MIST COAT . APPROX 7M2 | 2026-06-11 16:15:00 | 2026-06-18 | 2026-06-18 12:12:00 | Routine Repairs | 1298631 | 160 Crosscombe Drive, Hartcliffe, Bristol | 27014/1 | Works Completed | ACE Agreed | 36/810 | 2026-05-22 08:00:00 | 15 days |  |  | Lainie Lavin | 25/11/2025 16:59 | No | Pre-completion Items To Complete |  | Yes |  | 08/05 - Appointment rescheduled due to illness - CL 27/03 - Appointments booked for 07/05 and 11/05 - CL Additional contact details receive from EH - CL Still Unable to contact tenant as phone currently unavailable. Additional contact details requested fr | Complete | 397.04
2025-10-30 11:54:00 | JEFF WAY AS PER IAN OGBORNE - FAO DARREN ,CONCRETE PATH REMOVAL AND FORM STEP/PAD | 2026-05-27 08:00:00 | 2026-05-27 |  | Routine Repairs | DN619274 | 139 Ilchester Crescent, Bedminster Down, Bristol, BS13 7HP | 24267/1 | Works Started |  | 36/799 | 2026-02-04 08:00:00 | 15 days |  |  | Lainie Lavin | 19/11/2025 11:54 | No | Pre-completion Items To Complete |  |  |  | 28/05 - Works completed by JP awaiting photos - CL 27/04 - Appointment needs to be rescheduled due to sickness - CL 21/04 - Job marked complete incorrectly an appointment booked for 24/04 to complete work - CL 15/04 - KPI requested - CL | Complete | 531.62
2025-10-30 11:54:00 | JEFF WAY - AS PER ROB DOIDGE - FITTING OF NEW DOWNPIPE TO LHS OF FRONT ELEVATION, LEAVE SHORT AS TENANT WILL RUN INTO A WATER BUTT | 2026-04-11 08:00:00 |  | 2026-04-11 11:41:00 | Routine Repairs | 619274 | 7 Coldpark Road, Withywood | 24275/1 | Works Completed | ACE Agreed | 36/814 |  | 15 days |  |  | Lainie Lavin | 19/11/2025 11:54 |  | Pre-completion Items To Complete |  | Yes |  | 27/04 - Work to be review by DW - CL Appointment rescheduled to 28/04 as operative being unable to carry out work due to weather conditions - CL | Complete | 1030.69
2025-10-24 12:09:00 | RENEW SEALANT TO BATHROOM FLOOR/FIT NEW FANS AND RENEW PULL SWITCH | 2026-01-23 10:00:00 | 2026-01-26 | 2026-01-26 11:30:00 | Routine Repairs | 1272624 | 841 Bishport Avenue | 1166676 | Works Completed | Invoiced | 36/795 | 2026-01-26 08:00:00 | 15 days |  |  | Shannon Slade | 13/11/2025 12:09 | No | Post-completion Items To Complete | 2026-02-06 | Yes |  |  | Complete | 1058.78
2025-10-22 15:21:00 | As per Sean P: ** URGENT ORDER**. Fencing to the left hand side needs installing at the front of the property where neighbour has installed clear metal see through fence. Run along side to block off ourside/next door from looking in. Please install 6ft fencing to run in line with current one. Erect 1.80m high interwoven or overlap panel fencing complete with panels fixed to 75x75mm posts, capping, gravel board, excavation, concrete, backfill, remove spoil, reinstatement.. Meet Sean Phelon onsite at earliest convenience to go over work. | 2025-11-21 15:00:00 |  | 2025-11-21 14:46:00 | Routine Repairs | 358 | 138 Novers Lane, Knowle, Bristol BS4 1QP | 42841/1 | Works Completed | Invoiced | 36/794 | 2025-11-21 08:00:00 | 15 days |  |  | Lainie Lavin | 11/11/2025 15:21 | No | Fully Complete | 2025-12-19 | Yes |  |  | Complete | 558.88
2025-10-21 12:07:00 | complaints works- (Area name) Description of works needed. Living room Mould wash two section of the walls and finish with anti mould paint. Mould wash to pvc window. Overhaul window unit. Bathroom New fan to be installed. Cut out silicone to window unit and renew. Pvc mould wash. Rake out grout to remove any mould. Kitchen Pvc mould wash window unit. Works outside LOC -Bedroom 2 Hack off plaster and renew head to window. Pvc mould wash window. Overhaul window. | 2025-12-04 08:00:00 |  | 2026-03-17 12:28:00 | Disrepair | 1068559 | 52 SILVERHILL ROAD | 1233204 | Works Completed | Invoiced | 36/788 |  | 20 days |  |  | Shannon Slade | 17/11/2025 12:07 |  | Fully Complete | 2026-04-02 | Yes |  |  | Complete | 669.23
2025-10-20 10:56:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 11/11/25. 10 DAY PERIOD ENDS 25/11/25 |  | 2025-10-31 | 2025-10-31 08:44:00 | Routine Repairs | 1036437 | 26 TRYM SIDE | 1240278 | Works Completed | Invoiced | 36/777 |  | 15 days |  |  | Shannon Slade | 07/11/2025 10:56 |  | Post-completion Items To Complete | 2025-10-31 | Yes |  |  | Complete | 214.51
2025-10-20 08:58:00 | As per Rob Doidge: Minor cracks on child's bedroom wall and small area of blown plaster RHS of window sill, Please repair and patch paint as required. | 2025-11-17 08:00:00 | 2025-11-17 | 2025-11-17 09:00:00 | Routine Repairs | 1273025 | 28 Borleyton Walk, Withywood, Bristol BS13 8QJ | 1241070 | Works Completed | Invoiced | 36/781 | 2025-10-30 08:00:00 | 15 days |  |  | Lainie Lavin | 07/11/2025 08:58 | No | Fully Complete | 2025-12-03 | Yes |  |  | Complete | 104.46
2025-10-17 12:04:00 | Renew approx 1m2 beige kitchen floor tile, latex blown below, repaint living room ceiling in full 12m2, install new post, handrails and balustrades to the stair case, approx 1.5m length, overhaul 2x front bedroom windows, and small patch repairs to blown paint on rear elevation by back door 1m2 as per Robert Doidge. | 2025-11-10 08:00:00 | 2025-11-10 | 2025-12-18 11:23:00 | Routine Repairs | 1292962 | 373 Bishport Avenue, Hartcliffe, Bristol BS13 0BN | 1240350 | Works Completed | Invoiced | 36/780 | 2025-10-30 08:00:00 | 15 days |  |  | Lainie Lavin | 06/11/2025 12:04 | No | Post-completion Items To Complete | 2026-01-14 | Yes |  |  | Complete | 1543.15
2025-10-17 11:32:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 11/11/25. 10 DAY PERIOD ENDS 25/11/25 | 2026-01-09 12:15:00 | 2026-01-09 | 2025-12-04 08:15:00 | Routine Repairs | 1019449 | 55 KINGS WESTON AVENUE | 1240321 | Works Completed | Invoiced | 36/778 |  | 15 days |  |  | Shannon Slade | 06/11/2025 11:32 |  | Fully Complete | 2025-12-04 | Yes |  |  | Complete | 143.59
2025-10-17 09:56:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 5/11/25. 10 DAY PERIOD ENDS 19/11/25 |  |  | 2025-10-23 08:04:00 | Routine Repairs | 1278280 | 74 Four Acres | 1240187 | Works Completed | Invoiced | 36/775 |  | 15 days |  |  | Shannon Slade | 06/11/2025 09:56 |  | Fully Complete | 2025-10-29 | Yes |  |  | Complete | 143.59
2025-10-17 09:39:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 5/11/25. 10 DAY PERIOD ENDS 19/11/25 |  | 2025-10-31 | 2025-10-31 08:56:00 | Routine Repairs | 1291992 | 57 Aldwick Avenue | 1240163 | Works Completed | Invoiced | 36/774 |  | 15 days |  |  | Shannon Slade | 06/11/2025 09:39 |  | Fully Complete | 2025-11-03 | Yes |  |  | Complete | 198.34
2025-10-15 16:01:00 | As per Scott Barry - Please hack off and hardwall defective areas from fire on floor 5 outside 31-33 10m2. Please prepare and skim all walls and ceiling and defective area in secondary lobby in-between lobby for flats and lift area 25m2. Please remove fire damaged skirting. Any issues please call 07867370522. |  | 2025-10-21 | 2025-10-21 10:08:00 | Routine Repairs | 1828859 | STANDFAST ROAD | 1239144 | Works Completed | Invoiced | 36/773 |  | 15 days |  |  | Shannon Slade | 04/11/2025 16:01 |  | Fully Complete | 2025-10-22 | Yes |  |  | Complete | 688.67
2025-10-14 18:26:00 | As per Darryl's (07733 831 884) request - Major external and internal cracks. In front bedroom where verticle crack near window, hack 1SM back to brickwork so we can inspect for cracks to inner leaf. PLEASE ADVISE SURVEYOR WHEN APP. SCHEDULED FOR SO THEY CAN ATTEND. Many thanks | 2025-11-10 08:00:00 | 2025-11-10 | 2025-11-10 13:10:00 | Routine Repairs | 1029567 | 9 Portbury Grove, Shirehampton | 1238643 | Works Completed | Invoiced | 36/768 |  | 15 days |  |  | Lainie Lavin | 03/11/2025 18:26 |  | Fully Complete | 2025-12-04 | Yes |  |  | Complete | 68.02
2025-10-14 16:50:00 | Rapleys works order Scaffolding erect for client roofing inspection clear gutters replace 6x vinyl kitchen floor tiles replace seals to living room window , stain block and paint 1m2 rear bedroom skim and paint 2m2 |  | 2025-11-13 | 2025-11-13 09:55:00 | Routine Repairs | 1299849 | 35 FABER GROVE | 1039201 | Works Completed | Invoiced | 36/792 |  | 15 days |  |  | Shannon Slade | 03/11/2025 16:50 |  | Fully Complete | 2025-11-13 | Yes |  |  | Complete | 2899.71
2025-10-14 08:52:00 | Plasterer - CASA test came back NAD, Plasterer to renew 15.5 m2 kitchen/diner ceiling. | 2025-10-30 08:00:00 | 2025-10-30 | 2025-11-05 10:01:00 | Routine Repairs | 1287623 | 61 Redford Crescent, Withywood, Bristol BS13 8SA | 1237898 | Works Completed | Invoiced | 36/766 | 2025-10-31 08:00:00 | 15 days |  |  | Lainie Lavin | 03/11/2025 08:52 | No | Fully Complete | 2025-11-19 | Yes |  |  | Complete | 993.88
2025-10-10 10:09:00 | Complaint works-Living room Cut out silicone and renew around window unit. Bathroom Toilet Paint soil pipe. Hallway Carefully patch repair wall and replaster or box in electrics to cover hole within wall. Install new insulation to the back of the hatch. Bedroom 1 Mould wash and Paint reveals to window to remove all mould growth. Mould wash sections to the ceiling and relay insulation within loft. Scrape out and fill cracks to ceiling. Paint entire ceiling. Patch repair to ceiling needed. Under 1 square meter. Bedroom 2 Cut out silicone to window unit and mould wash window. Mould wash sections to the ceiling. Paint sections of ceiling. Kitchen Ease fire door. | 2025-12-11 09:00:00 |  | 2026-01-28 13:51:00 | Disrepair | 1299667 | 17 FABER GROVE | 1237048 -16558/1 | Works Completed | Invoiced | 36/837 | 2026-01-28 09:00:00 | 20 days |  |  | Shannon Slade | 06/11/2025 10:09 | No | Fully Complete | 2026-02-04 | Yes |  |  | Complete | 942.0
2025-10-09 15:07:00 | Jeff Way - Stain block water damage ground floor bathroom ceiling and apply anti condensation paint to complete ceiling and walls . Fix new fan. Remove water damage bath panel and refix acrylic . Lift existing vinyl sheet flooring clear sub floor and relay new as per Jeff Neck. | 2025-12-16 12:00:00 |  | 2026-03-27 13:12:00 | Routine Repairs | 1289470 | 25 Spartly Drive | 1235459 | Works Completed | ACE Agreed | 36/759 | 2025-12-16 12:00:00 | 15 days |  |  | Lainie Lavin | 29/10/2025 15:07 | No | Post-completion Items To Complete | 2026-04-17 | Yes |  | 16/04 - Variation sent to JN for approval - CL Works completed , awaiting photos to upload for ready to handover -30/3. | Complete | 672.92
2025-10-09 14:51:00 | JEFF WAY - Scrape loose water damage paint work off kitchen ceiling. Apply stain block to damaged areas . Apply emulsion to complete ceiling. FAO JEFF NECK | 2026-02-12 08:00:00 |  | 2026-02-12 10:22:00 | Routine Repairs | 1269790 | 46 Winterstoke House, Duckmoor Road, Ashton, Bristol BS3 2EP | 1236201 | Works Completed | ACE Agreed | 36/756 | 2026-02-12 08:00:00 | 15 days |  |  | Lainie Lavin | 29/10/2025 14:51 | No | Post-completion Items To Complete | 2026-02-26 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 125.05
2025-10-09 11:43:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 5/11/25. 10 DAY PERIOD ENDS 19/11/25. | 2025-10-22 08:00:00 | 2025-10-22 | 2025-10-31 14:19:00 | Routine Repairs | 1069905 | 1 Stanton Road, Southmead, Bristol BS10 5SS | 1235884 | Works Completed | Invoiced | 36/755 |  | 15 days |  |  | Lainie Lavin | 29/10/2025 11:43 |  | Fully Complete | 2025-11-10 | Yes |  |  | Complete | 176.78
2025-10-09 11:27:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 5/11/25. 10 DAY PERIOD ENDS 19/11/25 | 2025-10-17 10:00:00 | 2025-10-17 | 2025-10-24 07:55:00 | Routine Repairs | 0000163 | 16 Richeson Close, Henbury, Bristol, BS10 7FU | 1235861 | Works Completed | Invoiced | 36/754 |  | 15 days |  |  | Lainie Lavin | 29/10/2025 11:27 |  | Fully Complete | 2025-10-28 | Yes |  |  | Complete | 143.59
2025-10-09 10:27:00 | Jeff Way - Repaint ground floor W/C ceiling after leak as per Tom Walker | 2025-11-24 12:00:00 | 2026-01-28 | 2026-01-28 16:02:00 | Routine Repairs | 0000267 | 5 Ashton Rise, Ashton Vale, Bristol, BS3 2DG | 1235070 | Works Completed | Invoiced | 36/751 | 2026-11-26 16:09:00 | 15 days |  |  | Lainie Lavin | 29/10/2025 10:27 | No | Fully Complete | 2026-02-16 | Yes |  |  | Complete | 219.92
2025-10-09 10:23:00 | JEWFF WAY - AS PER ROB DOIDGE - REMOVAL OF WEED / SHRUB FROM CHIMNEY STACK AND REPOINT WHERE ROOT GROWING FROM. UPSTAIRS LANDING, REPAIR WALL PLASTER LHS OF DOOR FRAME WHERE BACK TO BARE BRICK. | 2026-01-19 12:00:00 | 2026-01-16 | 2026-01-16 09:46:00 | Routine Repairs | 1273150 | 9 Bourton Walk, Bedminster Down, Bristol BS13 7AL | 1235763 | Works Completed | Invoiced | 36/753 | 2026-01-07 09:48:00 | 15 days |  |  | Lainie Lavin | 29/10/2025 10:23 | No | Fully Complete | 2026-02-26 | Yes |  |  | Complete | 1254.48
2025-10-09 09:58:00 | JEFF WAY - FILLING OF GAPS AND CRACKS TO SIDE PATH WHERE IT HAS DROPPED AWAY FROM FRONT DOOR. APPROX 6 LINEAR METERS. HAVE USED SQM SOR AS PER ROB DOIDGE. | 2025-10-21 12:00:00 | 2025-10-21 | 2025-11-07 11:23:00 | Routine Repairs | 1288079 | 34 Riverland Drive, Withywood, Bristol BS13 8PL | 1235744 | Works Completed | Invoiced | 36/752 |  | 15 days |  |  | Lainie Lavin | 29/10/2025 09:58 |  | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 254.38
2025-10-08 15:56:00 | Complaint works- Kitchen Kitchen trunking to be reinstalled. (not included in Loc) Livingroom BCC plumber to inspect radiator. Mould wash and paint small section of skirting. Mould wash and paint small section of ceiling. Bathroom Small timber patch to be installed on the wall around pipework, decorate when fitted. Bedroom 1 Strip off paint to external wall and internal wall and mould wash and paint walls with bio check. Bedroom 2 Renew silicone to window unit. Repaint window board. Mould wash and paint window reveals. | 2026-02-13 12:00:00 |  | 2026-02-13 14:54:00 | Disrepair | 1311735 | 51 Redwood House | 1235458 | Works Completed | Invoiced | 36/835 |  | 20 days |  |  | Shannon Slade | 04/11/2025 15:56 |  | Fully Complete |  |  |  |  | Complete | 906.86
2025-10-08 09:46:00 | JEFF WAY - EXTERNAL WALL LHS OF FRONT DOOR, SCRAPE LOOSE FLAKING PAINT, PREPARE WALL AND REPAINT IN FULL, APPROX 10M2 MAGNOILIA MASONRY PAINT. BOTTOM RHS OF FRONT DOOR, PATCH REPAIR MISSING CONCRETE AND PATCH PAINT. LINEAR CRACK ABOVE LIVING ROOM WINDOW, RAKE OUT, FILL WITH FLEXI WEATHERPROOF SEALANT AND PATCH PAINT, APPROX 3 LIN METERS AS PER ROB DOIDGE. | 2025-11-07 12:00:00 | 2025-11-07 | 2025-11-07 13:30:00 | Routine Repairs | 1304467 | 14 Holbrook Crescent, Hartcliffe, Bristol BS13 0EU | 1235016 | Works Completed | Invoiced | 36/749 | 2025-10-10 09:00:00 | 15 days |  |  | Lainie Lavin | 28/10/2025 09:46 | No | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 289.12
2025-10-07 16:55:00 | WORKS. As per Alvaro Ibanez resent to Jeffway -Bathroom. Mould treat/decoration under the basin. Take up existing floorboards and renew with vinyl finish. Renew flooring under bathtub. Renew bathtub with shower mixer. Install shower curtain. Add tiles around the bath area up to the ceiling. Renew skirting board. Paint ceiling and walls. Renew window's handle. Renew door handles. -Kitchen. Tile splash back for new cooker. Corner area of external wall / wall adjoining living room. Hack off dama | 2026-07-02 13:00:00 | 2026-07-02 |  | Disrepair | 1062675 | 18 MONSDALE CLOSE | 1234888 | Works Started | ACE Agreed | 36/834 | 2026-04-07 08:00:00 | 20 days |  |  | Shannon Slade | 03/11/2025 16:55 | No | Pre-completion Items To Complete |  |  |  | 05/06 - WAITING FOR UPDATE FROM STEVE H, FOLLOWING SITE VISIT WORKS BOOKED TO COMMENCE 7TH APRIL, WAITING FOR CONFIRMATION FROM BCC. 24/04 - MAJOIRTY OF WORKS COMPLETED, RETURNING TO TILE ON THE 8TH MAY | WIP | 4599.61
2025-10-07 11:21:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 15/10/25. 10 DAY PERIOD ENDS 29/10/25 | 2025-10-15 08:00:00 | 2025-10-15 | 2025-10-15 11:59:00 | Routine Repairs | 1312307 | 36 Rowan House, Bishport Avenue, Hartcliffe, Bristol BS13 0RT | 1234079 | Works Completed | Invoiced | 36/748 |  | 15 days |  |  | Lainie Lavin | 27/10/2025 11:21 |  | Fully Complete | 2025-10-20 | Yes |  |  | Complete | 143.59
2025-10-07 10:35:00 | Jeffway- as per Tom Walker-Replace sliding door mechanism to non standard bathroom door, Replacement of bathroom door sliding mechanism. | 2025-12-19 08:00:00 | 2025-12-19 | 2025-12-19 10:45:00 | Routine Repairs | 1283790 | 1 Langford Road, Bedminster Down, Bristol BS13 7AP | 1233852 | Works Completed | Invoiced | 36/747 | 2025-12-19 08:00:00 | 15 days |  |  | Lainie Lavin | 27/10/2025 10:35 | No | Post-completion Items To Complete | 2026-01-06 | Yes |  |  | Complete | 144.31
2025-10-06 14:33:00 | PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 8/10/25. 10 DAY PERIOD ENDS 22/10/25 |  | 2025-10-24 | 2025-10-24 07:50:00 | Routine Repairs | 1280713 | 27 Gay Elms | 1232247 | Works Completed | Invoiced | 36/736 |  | 15 days |  |  | Lainie Lavin | 24/10/2025 14:33 |  | Fully Complete | 2025-10-28 | Yes |  |  | Complete | 143.59
2025-10-03 15:03:00 | AS PER ROB DOIDGE - REMOVAL AND REFITTING OF 2 X CORNER BASE UNITS TO KITCHEN TO FILL ANY PEST HOLES. ALSO FILL PEST HOLES IN METER CUPBOARD AND UNDER BATH AS REQUIRED. REMOVE AND REFIX BATH PANEL FOR THIS. EXTERNAL PATH RUNNING AROUND PROPERTY, CEMENT THE GAP AALL WAY AROUND BETWEEN PATH AND GARDEN WHERE IT HAS DROPPED ALLOWING PEST ACCESS. APPROX 12 LINEAR METERS . CCTV DRAIN SURVEY ALSO TO CHECK FOR ANY DEFECTS IN DRAINAGE SYSTEM | 2026-04-30 12:00:00 |  | 2026-04-24 12:29:00 | Routine Repairs | 1286777 | 27 Pigott Avenue, Withywood | 1232826 | Works Completed | ACE Agreed | 36/742 | 2025-12-19 08:00:00 | 15 days |  |  | Lainie Lavin | 23/10/2025 15:03 | No | Post-completion Items To Complete | 2026-05-08 | Yes |  | 08/05 - KPI requested - CL 24/04 - QS to check over what has been carried out, amend sors accordingly for handover - CL Site visit booked for SH to attend and assess work - CL Unable to contact tenant and no facility to leave a voicemail. Text sent - CL | Complete | 668.29
2025-10-03 14:50:00 | Repair crack running through central position of 1st floor front bedroom ceiling, rub back to suit existing levels and apply emulsion paint to compete ceiling. Cut concrete foot path at the bottom of concrete garden steps and fix new plastic ACO drain in discharge into soil flower bed . The new drain to be position to prevent surface water from sloping front garden ponding out side front door. FAO JEFF NECK | 2026-06-10 08:00:00 | 2026-06-10 | 2026-06-10 16:00:00 | Routine Repairs | 1286277 | 22 Newland Walk, Withywood, Bristol BS13 9DZ | 1232815 | Works Completed | Invoiced | 36/741 | 2026-06-10 08:00:00 | 15 days |  |  | Lainie Lavin | 23/10/2025 14:50 | No | Post-completion Items To Complete | 2026-06-29 | Yes |  | 30/06 - KPI received and uploaded - CL 29/06 - KPI requested - CL 07/05 - Tenant called to rescheduled her appointment as she has a hospital appointment on the 15/05 - CL 05/05 - Appointment needs to rescheduled due to sickness - CL 23/03 - Unable to contact tenant due to phone being switched off , text message sent - C | Complete | 239.88
2025-10-03 09:43:00 | Fence to rear and side to the property requires replacing as approved by KPD/SK (20m of feather edge boarding and framing) PLEASE LIAISE WITH STEVE KENNA IF ANY QUESTION REGARDING WORKS/LOCATIONS | 2026-01-28 08:00:00 | 2026-01-28 | 2026-01-29 09:44:00 | Routine Repairs | 1210204 | 5 Bantock Close, Inns Court, Bristol BS4 1XD | 1232501 | Works Completed | Invoiced | 36/740 | 2025-12-17 08:00:00 | 15 days |  |  | Lainie Lavin | 23/10/2025 09:43 | No | Fully Complete | 2026-01-30 | Yes |  |  | Complete | 3411.09
2025-10-03 09:38:00 | SCRAPING OF OLD ARTEX TO KIT CEILING FOLLOWING LEAK, RE SKIM CEILING IN FULL AND THEM MIST COAT AND PAINT X 2 COATS. APPROX 8M2 AREA | 2026-04-08 15:30:00 |  | 2026-04-08 18:08:00 | Routine Repairs | 1279545 | 38 Four Acres Close | 1232497 | Works Completed | Invoiced | 36/739 | 2026-03-24 07:45:00 | 15 days |  |  | Lainie Lavin | 23/10/2025 09:38 | No | Pre-completion Items To Complete | 2026-04-09 | Yes |  |  | Complete | 405.11
2025-10-03 09:06:00 | Remove loose / Broken ceramic wall tiles on splashback in bathroom , clean off wall and cut / refix new tiles to suit. FAO JEFF NECK | 2025-12-22 08:00:00 | 2025-12-22 | 2025-12-22 11:06:00 | Routine Repairs | 1279283 | 12 Four Acres Close, Withywood, Bristol BS13 8QN | 1232460 | Works Completed | Invoiced | 36/738 |  | 15 days |  |  | Lainie Lavin | 23/10/2025 09:06 |  | Post-completion Items To Complete | 2026-01-06 | Yes |  |  | Complete | 107.96
2025-10-03 08:49:00 | JEFF WAY - Replace door frames and doors on kitchen, dining room and living room Repair damaged tiles around bath and reseal FAO TOM WALKER. | 2026-03-27 08:00:00 |  | 2026-03-27 10:19:00 | Routine Repairs | 1272179 | 675 Bishport Avenue | 1232448 | Works Completed | Invoiced | 36/840 | 2026-03-26 08:00:00 | 15 days |  |  | Lainie Lavin | 23/10/2025 08:49 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI requested - CL | Complete | 853.35
2025-10-02 15:47:00 | PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 16/10/25. 10 DAY PERIOD ENDS 30/10/25 |  | 2025-10-24 | 2025-10-24 07:39:00 | Routine Repairs | 1240171 | 72 Birch Road, Southville, Bristol BS3 1PF | 1232336 | Works Completed | Invoiced | 36/737 |  | 15 days |  |  | Lainie Lavin | 22/10/2025 15:47 |  | Fully Complete | 2025-10-28 | Yes |  |  | Complete | 143.59
2025-10-02 12:01:00 | DISREPAIR- WORKS- AS PER THOMAS LEAR- Kitchen plastering/ painting- Plastering: 400 x 2200 total (hack -off small section of wall around kitchen opening and redecorate from leak damage) Patch repair Fill holes around door opening. Bathroom - •Vinyl flooring - 2.237m x 1.5m. renew flooring. •1 bath panel - 1.7m •Renew bath silicone •Patch repair ceiling, over skim ceiling and decorate. 2.2 x 2.2 •Renew fan within Dutch. •renew Boxing / new tiles end of bath. Straight run of ply without shelfs. Tiles to top of boxing. Stud Wall to bathroom loose (remove radiator and install/ socket on wall) •Fix stud / reboard plaster •2.2 x 2.1 stud repair ( remove small section of plasterboard and refix sol plate to stud) Hallway ceiling / wall patch repair •Patch repair / paint from electrical rewire. Bedroom •Patch repair / paint from electrical rewire. Living Room- asbestos ceiling. paint from electrical rewire. •Patch repair wall / paint. B | 2025-11-18 08:00:00 |  | 2025-12-11 14:18:00 | Disrepair | 1301844 | 41 GREENDITCH AVENUE (KS1541) | 1232075 | Works Completed | Invoiced | 36/787 | 2025-11-12 08:00:00 | 20 days |  |  | Shannon Slade | 29/10/2025 12:01 | No | Fully Complete | 2025-12-12 | Yes |  |  | Complete | 1982.35
2025-10-02 12:00:00 | PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING, DBH WITH TOM WALKER 9/10/25. 10 DAY PERIOD ENDS 23/10/25 |  | 2025-10-06 | 2025-10-06 12:19:00 | Routine Repairs | 1232064 | 33 Wymbush Crescent, Hartcliffe, Bristol BS13 0BB | 1232064 | Works Completed | Invoiced | 36/735 |  | 15 days |  |  | Lainie Lavin | 22/10/2025 12:00 |  | Fully Complete | 2025-10-14 | Yes |  |  | Complete | 183.31
2025-10-02 11:48:00 | PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 9/10/25. 10 DAY PERIOD ENDS 23/10/25 |  | 2025-10-06 | 2025-10-06 12:08:00 | Routine Repairs | 1317460 | 14 Wymbush Crescent, BS13 0BB | 1232041 | Works Completed | Invoiced | 36/734 |  | 15 days |  |  | Lainie Lavin | 22/10/2025 11:48 |  | Fully Complete | 2025-10-14 | Yes |  |  | Complete | 143.59
2025-10-02 09:39:00 | Recommended works as per Site visit from Gavin authorised by KPD/AW - Fan works, Roof vent tile, Scaffolding & Dec works | 2026-05-11 10:00:00 |  |  | Urgent Repair | 1281443 | 28 Hersey Gardens, Withywood, Bristol BS13 8RR | 1231839 | Works Started | ACE Agreed | 36/733 | 2026-01-27 08:00:00 | 5 days |  |  | Lainie Lavin | 08/10/2025 09:39 | No | Pre-completion Items To Complete |  |  |  | 116/06 - Vent needed to be ordered and fitted, assistance requested. Tenant at 28 hersey went out st 9:30...she was apparently told I'd be there at 8. Roof vent is fitted in the right location 3 rows up to match the rest of the street. Electrician should have no problem fitting his flexible hose. - CL 2/06 - Vent need to be ordered and fitted - CL 14/04 - CASA to attend 14/04 to carry out survey - CL Awaiting BCC to confirm CASA attendance and send over report | WIP | 2284.53
2025-10-01 12:33:00 | JEFF WAY - AS PER ROB DOIDGE - REPAIR TO SUBFLOOR RHS OF COOKER WHERE HOLE, RENEW 2 X BLUE WALL TILES AND SCRAPE, SEAL AND REPAINT WALL BEHIND AND LHS OF TUMBLE DRYER, APPROX 3M2, SEALANT TO SKIRTING BOARD ON SAME WALL ALSO. | 2026-03-25 09:30:00 |  | 2026-03-03 09:05:00 | Routine Repairs | 1283610 | 57 King Georges Road, Bishopsworth, Bristol, BS13 8LS | 1231454 | Works Completed | Invoiced | 36/731 | 2025-12-04 13:30:00 | 15 days |  |  | Lainie Lavin | 21/10/2025 12:33 | No | Pre-completion Items To Complete | 2026-03-31 | Yes |  | 28/04 - KPI received and uploaded - CL Email sent to RD advising of the D&M issue at the property and the tenant refusing any further work until dealt with. Appointment booked for mould clean to kitchen wall booked for 25/03 - CL | Complete | 50.0
2025-10-01 12:25:00 | race leak to cupboard under stairs from kitchen , replace stop tap and check fittings. Due to the internal leakage hack off damage plaster work to internal cupboard walls and living room wall on the adjacent side. Again on the external living corner wall hack off damage plaster work in corner position. Apply plaster skim finish to match existing levels. Repaint patch plaster areas to suit. Re fix timber skirting at repaired positions. External reseal high level PVC gutter joint between the two properties which is leaking and causing damp / wet on the brickwork as per Jeff Neck. | 2026-07-01 12:00:00 | 2026-07-01 |  | Routine Repairs | 1314154 | 22 Totshill Drive, Hartcliffe, Bristol BS13 0QU | 1231446 | Works Started | ACE Agreed | 36/730 | 2026-05-20 08:00:00 | 15 days |  |  | Lainie Lavin | 21/10/2025 12:25 | No | Pre-completion Items To Complete |  |  |  | 02/07 - Review needed by manager to identify any outstanding work needed - CL 30/06 - Unable to get hold of tenant and no facility to leave a voicemail. Text sent - CL 07/04 - Follow on appointments booked for 21/05,26/05 and 01/06 - CL Unable to contact tenant and no facility to leave a voicemail. Text message sent to make contact - CL. Chased up tenant awaiting contact -30/3. | Manager review needed | 538.22
2025-10-01 10:41:00 | AS PER ROB DOIDGE - BATHROOM - SUBFLOOR REPAIR AROUND SINK / END OF BATH AND INSPECTION OF REST PRIOR TO RENEWING VINYL. PLEASE RIP UP OLD VINYL FIRST. 3M2 APPROX FLOOR AREA | 2026-02-17 08:00:00 |  | 2026-03-10 08:46:00 | Routine Repairs | 1238513 | 16 Alpha Road, Southville, Bristol BS3 1DH | 1231052 | Works Completed | Invoiced | 36/729 | 2026-02-17 08:00:00 | 15 days |  |  | Lainie Lavin | 21/10/2025 10:41 | No | Fully Complete | 2026-03-16 | Yes |  |  | Complete | 182.37
2025-10-01 09:29:00 | DAMP & MOULD AS PER NICHOLAS CORY PLA TO REMOVE BOTTOM 5CM SO PLA NOT TOUCHING CON FLOOR OF BATHROOM NEW SKIRTING ON BATHROOM WALL AND UNDER BASIN AND KITCHEN PARTY WALL MAKE SURE SKIRTING IS OFF THE FLOOR SILICONE GAP IN BATHROOM AND KITCHEN , PAINT WOOD WORK. RE PAINT BATHROOM WALL, PIPE INSUL MAINS WATER PIPE IN BATHROOM | 2026-04-28 11:00:00 |  | 2026-04-28 09:50:00 | Routine Repairs | 1230815 | 21 Ringwood Crescent, Southmead, Bristol BS10 5RJ | 1230815 | Works Completed | ACE Agreed | 36/727 | 2026-04-27 08:00:00 | 15 days |  |  | Lainie Lavin | 21/10/2025 09:29 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL | Complete | 251.83
2025-09-30 14:11:00 | complaints works- Kitchen New extractor fan. Remove and renew silicone to window and door. Pvc mould wash to window and door. Mould wash and anti mould paint to window and door reveals. Window overhaul. Living Room Renew plasterboard to head of bay window. Insulation to head of bay window. Full decorations to new plasterboard, window reveals and patch repair on the wall. Redecoration to window board. Overhaul two windows units' side and bay window. Cut out silicone and renew to windows. Hallway Replace handle to front door. Overhaul door. | 2026-06-09 08:00:00 |  |  | Disrepair | 1208500 | 57 Whittock Road | 1230835 | Awaiting Target Start | ACE Agreed | 36/831 |  | 20 days |  |  | Shannon Slade | 27/10/2025 14:11 |  | Post-completion Items To Complete |  |  |  | 18/05 - WORKS BOOKED FOR 3RD JUNE, 11TH AND 12TH OF JUNE. | Awaiting appointment date | 936.41
2025-09-30 11:55:00 | Complaint disrepair work: - Carry out service of windows of the property - Hallway - patch repair cracked plaster at low level by front door reveal, mist and paint - Kitchen - hack and repair plaster cracks by top of window, and back door reveal. - Living room - Install hit and miss vent cover on passive vent. Hack off and renew, damaged plasterwork on left hand side wall, and mist, stain block and decorate (with stain block). - Bedroom 1 - hack back along horizontal crack at right of window, investigate, report, and renew plaster, mist and decorate patch. - Clean gutters - Wooden windowsill in Bedrooms - strip back and renew damaged paintwork | 2025-11-18 08:00:00 |  | 2025-12-12 11:09:00 | Disrepair | 1271450 | 2 Arthurswood Road | 1230515 - 14213/3 | Works Completed | Invoiced | 36/786 | 2025-12-10 08:00:00 | 20 days |  |  | Shannon Slade | 27/10/2025 11:55 | No | Post-completion Items To Complete | 2025-12-16 | Yes |  |  | Complete | 1111.73
2025-09-30 10:11:00 | Driveway works as agreed with Darren @ Jeffway. Renewal of concrete on driveway, grade garden area to concrete, form new steps rear garden, rebed 2 x man hole covers and 1 gas cover, repair concrete blocks at high level shed area. Fit aco drain front of drive with steel covers into existing driveway drain outlet as per existing. Clear bickwork from loft. Please contact Melissa Edwards 07442675013 to discuss further |  | 2025-12-05 | 2025-12-05 10:30:00 | Routine Repairs | 1204633 | 58 Showering Road, Stockwood, Bristol BS14 8DN | 1229781 | Works Completed | Invoiced | 36/721 |  | 15 days |  |  | Lainie Lavin | 20/10/2025 10:11 |  | Post-completion Items To Complete | 2025-12-08 | Yes |  |  | Complete | 6915.24
2025-09-29 11:18:00 | Jeff Way - Rub down loose paint work in kitchen make repairs and repaint to match existing. Check on hollow plaster work on hallway wall and side of stairs Note tenant to verify position . Caulk gun up the side or timber staircase along cracking . Stick back 2no vertical vinyl treads on kitchen / bathroom steps. Repaint repaired patch plaster work. check and overhaul PVC windows as per Jeff Neck. | 2025-12-22 13:00:00 |  | 2025-12-22 14:46:00 | Routine Repairs | 1246453 | 45 Friezewood Road, Ashton, Bristol BS3 2AD | 1229181 - 6223/1 | Works Completed | Invoiced | 36/720 |  | 15 days |  |  | Lainie Lavin | 17/10/2025 11:18 |  | Fully Complete | 2026-04-29 | Yes |  | 06/05 - KPI received and uploaded - CL 29/04 - KPI requested - CL 22/04 - Paint photos uploaded - CL Works complete, awaiting photos of paint works -30/3. | Complete | 311.41
2025-09-29 09:27:00 | Damp and Mould AS PER NICHOLAS CORY BATHROOM WALL UNDER WINDOW HACK OFF RENEW WITH SAND CEMENT WATERPROOFER SKIM FINISH AND DEC. NEW DOOR FRAME TO LIVING ROOM . REAR DOOR TO FULLGLOSS ON INSIDE | 2026-05-01 11:00:00 | 2026-05-01 |  | Routine Repairs | 1234975 | 22 TORRINGTON AVENUE | 1102465 | Works Started | ACE Agreed | 36/723 | 2026-03-20 12:00:00 | 15 days |  |  | Shannon Slade | 17/10/2025 09:27 | No | Post-completion Items To Complete |  |  |  |  | Complete | 254.68
2025-09-24 18:27:00 | Complaint works as per Tom Taylor (07557 930840) - KITCHEN: Replace plastic catch and reinstate face to the kitchen unit below sink; make good tiled finish. BEDROOM 1: Apply adhesive and refix wallpaper in position; redecorate affected wall with 2 coats of emulsion to nearest break line. EXTERNAL: Clean/clear gutters to front elevation, replace distorted guttering. | 2025-11-13 08:00:00 |  | 2025-11-13 16:15:00 | Disrepair | 1314596 | 35 TYNTE AVENUE | 1227601/13740/1 | Works Completed | Invoiced | 36/744 | 2025-11-13 08:00:00 | 20 days |  |  | Shannon Slade | 21/10/2025 18:27 | No | Fully Complete | 2025-11-18 | Yes |  |  | Complete | 207.65
2025-09-24 16:52:00 | Please replaster approx 2sqm of wall in the first floor front bedroom below and to the RHS of the window following damage - water ingress. Please contact Melissa Edwards 07442675013 if you need to discuss further. | 2025-09-29 08:00:00 | 2025-09-29 | 2025-09-29 11:45:00 | Routine Repairs | 1225725 | 32 LISBURN ROAD | 1227557 | Works Completed | Invoiced | 36/705 | 2025-09-29 08:00:00 | 15 days |  |  | Shannon Slade | 14/10/2025 16:52 | Yes | Post-completion Items To Complete | 2025-10-15 | Yes |  |  | Complete | 108.56
2025-09-24 15:13:00 | Minor decoration works: - make good hole in wall round rad pipe in bathroom - paint Kitchen ceiling (cover up old light fixings) - paint patch of wall next to rad in hallway. | 2025-10-22 08:00:00 |  | 2025-10-22 11:04:00 | Disrepair | 3785259 | 34 TREGARTH ROAD | 1227441 | Works Completed | Invoiced | 36/743 | 2025-10-22 08:00:00 | 20 days |  |  | Shannon Slade | 21/10/2025 15:13 | No | Fully Complete | 2025-10-24 | Yes |  |  | Complete | 187.88
2025-09-24 12:44:00 | Reraising the job - please skim coat the bedroom ceiling and paint. | 2025-11-25 08:00:00 |  | 2026-03-06 14:32:00 | Routine Repairs | 1197666 | 70 Griggfield Walk, Hengrove, Bristol BS14 9UG | 1084698 | Works Completed | Invoiced | 36/712 | 2025-10-27 08:00:00 | 15 days |  | 2026-01-20 14:30:51 | Lainie Lavin | 14/10/2025 12:44 | No | Fully Complete | 2026-03-16 | Yes |  |  | Complete | 236.32
2025-09-24 11:06:00 | JEFF WAY - AS PER ROB DOIDGE - REPAIR AS REQUIRED WATER DAMAGED SUBFLOORING TO PANTRY AND GOING INTO LIVING ROOM. APPROX 4M2 IN PANTRY ( FULL ROOM) AND AROUND 3/4M2 INTO LOUNGE. TENANT TO REMOVE APPLIANCES FROM PANTRY AND TAKE UP OWN FLOOR COVERING PRIOR TO WORKS SO PLEASE LIAISE WITH TENANT IN ADVANCE ON A DATE | 2025-11-20 08:00:00 | 2025-11-20 | 2025-11-24 10:53:00 | Routine Repairs | 1254166 | 17 Malago Road | 1227200 | Works Completed | Invoiced | 36/711 |  | 15 days |  |  | Lainie Lavin | 14/10/2025 11:06 | No | Fully Complete | 2025-11-25 | Yes |  |  | Complete | 210.2
2025-09-24 10:52:00 | Carpenter External Contractor Jeff way to fit standard 4inch bullnose skirting to 3x bedrooms and landing Asbestos report attached, please provide after pictures BCC contact Luke Pomphrey | 2025-11-07 08:00:00 | 2025-11-07 | 2025-11-07 17:00:00 | Routine Repairs | 1236891 | 137 Wedmore Vale, Bedminster, Bristol BS3 5JA | 1226992 | Works Completed | Invoiced | 36/710 | 2025-11-07 08:00:00 | 15 days |  |  | Lainie Lavin | 14/10/2025 10:52 | No | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 1169.17
2025-09-23 16:42:00 | Urgent - Leak into bedroom. CONTRACTOR to erect scaffold to both sides of rear extension to investigate leak, as per Paul Rogoll. | 2026-02-09 08:00:00 | 2026-02-04 | 2026-02-04 09:29:00 | Routine Repairs | 7769360 | 48 Lime Road, Bedminster, Bristol, BS3 1LT | 64602/1 | Works Completed | Invoiced | 36/703 | 2026-02-04 08:00:00 | 15 days |  |  | Lainie Lavin | 13/10/2025 16:42 | No | Fully Complete | 2026-02-16 | Yes |  |  | Complete | 2607.17
2025-09-23 12:58:00 | Scaffolding required to front and back, to renew first course of felt and battens, fit eave protectors, renew rotting fascia and soffit board, with plastic, take off and refit guttering as per Matt Ford. |  | 2025-12-10 | 2025-12-10 09:57:00 | Routine Repairs | 1261058 | 22 Shepton Walk, Bedminster, Bristol BS3 5NU | 1226196 | Works Completed | Invoiced | 36/701 |  | 15 days |  |  | Lainie Lavin | 13/10/2025 12:58 |  | Fully Complete | 2025-12-19 | Yes |  |  | Complete | 4493.1
2025-09-23 12:36:00 | complaint works- Hallway Repainting required around the door surround. Ease front door to ensure it sits tightly against the weather seals. Apply flexible sealant around the internal door frame. Living room Overhaul required for two window units due to gaps in seals and a loose security lever. Mould wash and paint small sections of mould on the external wall. Seal hole to wall within living room. Kitchen Mould wash and repainting needed on cupboard walls. Scrape out ceiling and wall cracks, then fill and repaint. Replace kitchen extractor fan. Overhaul rear door and externally seal. Kitchen units to be removed for mould wash and repainting. Gate bolts within cavity to be sealed. Outdoor furniture to be moved by tenant. Tumble dryer vent to be sealed. install 4m French drain or ACO drain. Cut back paving slab to accommodate drainage installation. Rear guttering leaking; all guttering to be cleaned and overhauled. Toilet room Hack off plaster around the soil | 2025-11-20 08:00:00 |  |  | Disrepair | 1063690 | 35 PEN PARK ROAD | 12969/1 | Works Started |  | 36/789 | 2025-11-19 08:00:00 | 20 days |  |  | Shannon Slade | 20/10/2025 12:36 | No | Post-completion Items To Complete |  |  |  | 12/06 - SCAFFOLD ERECTED. DARREN SPEAKING TO SHEPS 08/06- SCAFFOLDING BEING ALTERED 12TH JUNE. 23/03 - WORKS RE BOOKED FOR 22ND AND 23RD APRIL - TL TO BOOK WITH TENANT AND CONFIRM ACCESS TO FULL HOUSE AND USE OF BREAKER. 27/04 - INTERNAL WORKS COMPLETED. SCAFFOLDING BEING ERECTED 28TH AND SITE VISIT 29TH APRIL | WIP | 6743.18
2025-09-23 11:40:00 | Complaint works- Bedroom 1 Mould wash PVC window unit. Renew silicone to window unit. Scrape off affected paint to window board and re-paint. Overhaul window unit. Check passive vent to bedroom. Bedroom 2 Mould wash PVC window unit. Renew silicone to window unit. Scrape off affected paint to window board and re-paint. Overhaul window unit. Check passive vent to bedroom. Livingroom X2 window units to be replaced. Overhaul both windows. Re-silicone window units. Replace right hand side window board. Paint both window boards. Kitchen Fan to be installed in place of passive vent. Renew window silicone. Pvc mould wash to window. Mould wash and paint small patch of mould on lower wall. Renew plinth board under sink unit. Hallway Pvc mould wash to window unit. Overhaul window unit. Renew silicone to window unit. Ease and adjust front door to make it tighter to weather strips. Bathroom Fan to be fitted in place of passive vent. Mould | 2025-11-18 08:00:00 |  | 2025-12-09 10:46:00 | Disrepair | 1304218 | 13 Herridge Road | 1226461 | Works Completed | Invoiced | 36/784 |  | 20 days |  |  | Shannon Slade | 20/10/2025 11:40 | No | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 1703.23
2025-09-23 08:54:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 29/9/25. 10 DAY PERIOD ENDS 13/10/25 |  | 2025-10-02 | 2025-10-02 12:02:00 | Routine Repairs | 1281409 | 23 Hersey Gardens, Withywood | 1225170 | Works Completed | Invoiced | 36/704 |  | 15 days |  |  | Shannon Slade | 13/10/2025 08:54 |  | Post-completion Items To Complete | 2025-10-14 | Yes |  |  | Complete | 183.92
2025-09-23 08:16:00 | Disrepair. Repair door frame, install extractor in window. plus other things. SOR Additional Description: Bedroom3 door frame splice latch section off frame and make good. replace bath panel and move frame back, so panel tucks under the bath lip. Install fan in casment fix window shut. replace missing black tiles. repair draft bedroom window |  |  | 2025-11-12 10:24:00 | Disrepair | 1024824 | 97 MANCROFT AVENUE | 1218253 | Works Completed | ACE Agreed | 36/714 |  | 20 days |  |  | Shannon Slade | 20/10/2025 08:16 | No | Post-completion Items To Complete | 2026-03-27 | Yes |  |  | Complete | 651.07
2025-09-19 14:38:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 8/10/25. 10 DAY PERIOD ENDS 8/10/25 | 2025-10-08 08:00:00 | 2025-10-08 | 2025-10-22 07:24:00 | Routine Repairs | 1025689 | 9 Marsh Street, Avonmouth, Bristol BS11 9JZ | 1220279 | Works Completed | Invoiced | 36/689 |  | 15 days |  |  | Lainie Lavin | 09/10/2025 14:38 |  | Fully Complete | 2025-10-28 | Yes |  |  | Complete | 223.03
2025-09-19 13:13:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 30/9/25. 10 DAY PERIOD ENDS 14/10/25 | 2025-10-03 08:00:00 | 2025-10-03 | 2025-10-06 11:03:00 | Routine Repairs | 1285003 | 13 MOLESWORTH CLOSE | 1224133 | Works Completed | Invoiced | 36/700 |  | 15 days |  |  | Shannon Slade | 09/10/2025 13:13 |  | Fully Complete | 2025-10-13 | Yes |  |  | Complete | 174.79
2025-09-19 11:58:00 | PRE MUTUAL EXCHANGE INSPECTION, JEFF WAY - Parapet wall on rear garden store is unstable. To be made safe. FAO TOM WALKER |  | 2025-10-22 | 2025-10-22 12:27:00 | Routine Repairs | 1071290 | 12 Stoulton Grove, Brentry, Bristol BS10 7JG | 1218158 | Works Completed | Invoiced | 36/691 | 2025-10-05 12:19:00 | 15 days |  |  | Lainie Lavin | 09/10/2025 11:58 | No | Post-completion Items To Complete | 2026-02-16 | Yes |  |  | Complete | 446.13
2025-09-19 11:45:00 | JEFF WAY - Make repairs to plaster walls in bathroom and apply sealer to staining on walls .Paint ceiling and walls in anti condensation paint. Fix new plastic skirting around perimeter of walls. | 2026-07-24 08:00:00 | 2026-07-24 |  | Routine Repairs | 1309213 | 75 Murford Avenue, Hartcliffe, Bristol BS13 9JY | 1219891 | Works Started | ACE Agreed | 36/690 | 2026-03-25 08:00:00 | 15 days |  |  | Lainie Lavin | 09/10/2025 11:45 | No | Pre-completion Items To Complete |  |  |  | 03/06 - No access on 02/06, appointment rescheduled - CL 24/04 - Appointment rescheduled - CL | WIP | 482.58
2025-09-19 08:46:00 | JEFF WAY - Parapet wall on rear garden store is unstable. To be made safe. FAO TOM WALKER | 2025-10-02 08:00:00 | 2025-10-02 | 2025-10-02 10:47:00 | Routine Repairs | 1223811 | 12 Stoulton Grove, Brentry, Bristol BS10 7JG | 1223811 | Works Completed | Invoiced | 36/683 | 2025-10-30 09:00:00 | 15 days |  |  | Lainie Lavin | 09/10/2025 08:46 | Yes | Fully Complete | 2025-11-19 | Yes |  |  | Complete | 284.22
2025-09-18 15:57:00 | Complaint Disrepair work - Replace the floor covering in the living room and bathroom - Hit and miss vent installed in the chimney breast in living room - Overhaul fans in bathroom and kitchen and check humidity stat level isn't too low. - Heating inspection of radiator in bathroom and property, and flush system. - Service windows ensure proper function - Patch repair enamel in three spots next to drain in bath - Renew one riser to lower stairs - Draft stopper on front door at bottom - Sealant around tiles in bathroom - Repair wired front door glass - Roof inspection to chimney stack, to ensure no leaks - Mould wash in bedroom under window | 2025-11-11 08:00:00 |  |  | Disrepair | 1284986 | 11 Molesworth Close | 1223687 - 8605/2 | New Works Instruction | ACE Agreed | 36/708 |  | 20 days |  |  | Shannon Slade | 15/10/2025 15:57 |  | Post-completion Items To Complete |  |  |  | 20/05 - Jeffway to rebook, any issues return back to BCC for follow on. | Awaiting appointment date | 2315.22
2025-09-18 13:05:00 | Carpenter External contractor Jeffway group to hack out old sealant and reseal around all windows internally, Asbestos report sent. please provide before and after pictures BCC contact Luke Pomphrey | 2025-10-03 08:00:00 | 2025-10-03 | 2025-10-03 09:21:00 | Routine Repairs | 1208088 | 8 Whartons, Callington Road, Brislington, Bristol BS4 5BT | 1223156 | Works Completed | Invoiced | 36/684 | 2025-10-03 08:00:00 | 15 days |  |  | Lainie Lavin | 08/10/2025 13:05 | Yes | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 276.53
2025-09-18 11:21:00 | Works following inspection as per Andy Griffiths (07345 491671) - BATHROOM: Overhaul extractor fan, ensure this is cleaned internally and fully operational; mould treatment and paint bathroom ceiling. KITCHEN: overhaul extractor fan, ensure this is cleaned internally and fully operational | 2026-04-01 08:00:00 |  | 2026-05-06 13:16:00 | Disrepair | 1231545 | 2 Saunton Walk | 1223374 | Works Completed | ACE Agreed | 36/707 |  | 20 days |  |  | Shannon Slade | 15/10/2025 11:21 |  | Post-completion Items To Complete | 2026-05-12 |  |  | TENANT HASNT GOT ANY HOLIDAY UNTIL IT RENEWS IN APRIL. APPOINTMENT ARRANGED FOR 01/04. 05/05 -OP WAS SICK ON THE 24TH APRIL, WORKS HAVE BEEN RESCHEDULED FOR 6TH MAY. FANS HAVE ALREADY BEEN FITTED AT THE PROPERTY BY BCC? 07/05 - WORKS COMPLETED. | Complete | 258.43
2025-09-18 10:55:00 | JEFF WAY - As per Sean P : Skim around pipe in bedroom LHS by door. Redecorate whole celling after leak from flat. | 2026-04-10 08:00:00 |  | 2026-04-10 10:39:00 | Routine Repairs | 1303486 | 14 Hayleigh House, Silcox Road | 1223344 | Works Completed | Invoiced | 36/839 | 2026-04-10 10:41:00 | 15 days |  |  | Lainie Lavin | 08/10/2025 10:55 | No | Pre-completion Items To Complete | 2026-04-20 | Yes |  | 085/05 - KPI received and uploaded - CL 20/04 - KPI request sent - CL TENANT CALLED TO CONFIRM THEY DO NOT WANT ANY PAINTING DONE AT THE FLAT. Confirm with BCC to close down order and cancel works | Complete | 50.0
2025-09-17 13:27:00 | RG - Redecorate kitchen after smoke damage | 2025-10-30 08:00:00 | 2025-10-30 | 2025-09-24 13:30:00 | Routine Repairs | 1303806 | 46 Hayleigh House, Silcox Road, Hartcliffe | 1222521 | Works Completed | Invoiced | 36/685 | 2025-09-24 08:00:00 | 15 days |  |  | Lainie Lavin | 07/10/2025 13:27 | Yes | Fully Complete | 2025-11-19 | Yes |  |  | Complete | 357.28
2025-09-17 10:14:00 | DISREPAIR WORKS (with quoted repairs from Jeffway). As per Alvaro Ibanez. Balcony repairs. | 2025-10-14 08:00:00 |  | 2025-10-15 11:00:00 | Disrepair | 1031272 | 5 ORLEBAR GARDENS | 1222238 | Works Completed | Invoiced | 36/724 | 2025-10-15 08:00:00 | 20 days |  |  | Shannon Slade | 14/10/2025 10:14 | No | Fully Complete | 2025-10-27 | Yes |  |  | Complete | 6721.75
2025-09-17 08:15:00 | Carpentry External contractor joinery items made at joinery for collection if you wise to use joinery sheet attached with sizes Jeffway to Renew kite winders - one to be cut onsite- to stairs and reinforce 2 treads/risers please provide before and after pictures BCC contact Luke Pomphrey | 2026-02-23 08:00:00 |  | 2026-02-23 09:46:00 | Routine Repairs | 1280304 | 17 Gatehouse Close, Withywood | 1222057 | Works Completed | Invoiced | 36/838 | 2026-02-23 08:00:00 | 15 days |  |  | Lainie Lavin | 07/10/2025 08:15 | No | Fully Complete | 2026-03-19 | Yes |  |  | Complete | 179.74
2025-09-16 12:50:00 | complaint works- (Area name) Description of works needed. Livingroom Hack off a replaster around door frame. Small section of paint to scrape back and redecorate. One double socket to replace. Overhaul of window unit. Renew silicone to window unit. Bedroom 1 Mould wash and paint mould present on walls/ceiling in a patch. Unblock vent and install vent that can open and shut. Hack-off required to window head and re plaster. Decorations to window head. PVC mould wash to window unit. Renew silicone around window unit. Bedroom 2 Renew light switch. Gaps identified at both the top and bottom of the door frame; filling and repair. Remove kitchen door and install new door tenants recharge. Overhaul pvc window unit. Renew silicone to window unit. Radiator overhaul as not working. Patch repair small section of wallpaper. Splice repair door frame. Bathroom Entire room requires mould washing and repainting. Renew bathroom fan. New tiles to b | 2026-06-08 08:00:00 |  | 2026-04-27 14:32:00 | Disrepair | 1297718 | 10 CROSSCOMBE DRIVE | 1221432 - 11554/1 | Works Completed | ACE Agreed | 36/790 | 2025-11-24 08:00:00 | 20 days |  |  | Shannon Slade | 13/10/2025 12:50 | No | Post-completion Items To Complete |  | Yes |  | 23/03 - WORKS BOOKED FOR 24TH AND 25TH MARCH 27/03 - Darren Wallis completed part works. need to re-book final works. | Complete | 2982.13
2025-09-15 15:19:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 25/9/25. 10 DAY PERIOD ENDS 9/10/25 | 2025-10-16 08:00:00 | 2025-10-16 | 2025-09-26 14:09:00 | Routine Repairs | 1284646 | 16 Millground Road, Withywood, Bristol BS13 8NF | 1220636 | Works Completed | Invoiced | 36/687 |  | 15 days |  |  | Lainie Lavin | 03/10/2025 15:19 |  | Fully Complete | 2025-09-30 | Yes |  |  | Complete | 143.59
2025-09-15 15:12:00 | CONTRACTOR: Please replace bottom of porch plywood and decorate, take off fascia board and replace with upvc, replace guttering on porch, remove first 1m of felt and battens, fit eave ventilators, new felt and batten, replace any broken tiles with best match, as per Matt Ford - please see images with email sent 15/9. |  |  | 2025-10-16 11:32:00 | Routine Repairs | 1209729 | 16 Andover Road | 1220579/10560/1 | Works Completed | Invoiced | 36/678 |  | 15 days |  |  | Shannon Slade | 03/10/2025 15:12 |  | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 1309.7
2025-09-15 14:52:00 | 35 Beverston Gardens, Lawrence Weston, Bristol BS11 0SB |  | 2025-10-01 | 2025-10-01 12:44:00 | Routine Repairs | 1008997 | 35 Beverston Gardens, Lawrence Weston, Bristol BS11 0SB | 1220398 | Works Completed | Invoiced | 36/688 |  | 15 days |  |  | Lainie Lavin | 03/10/2025 14:52 |  | Fully Complete | 2025-10-03 | Yes |  |  | Complete | 156.81
2025-09-15 13:00:00 | Complaint disrepair work: - Overhaul locking mechanism on front door so door closes easier Bathroom - Repair of chip in bath - Renew silicon around bath - Overhaul/renew x4 window handles in living room and son's bedroom - Overhaul windows in son's room and living room, and renew sealant around window, renew pane. - Patch repair plaster in corner of son's room, mist and paint. | 2025-11-14 08:00:00 | 2026-07-27 |  | Disrepair | 1242520 | 10 CANYNGE HOUSE PREWETT STREET | 1219096 | Works Started | ACE Agreed | 36/791 | 2025-11-14 08:00:00 | 20 days |  |  | Shannon Slade | 10/10/2025 13:00 | No | Pre-completion Items To Complete |  |  |  | 02/07 - NA on 01/07 appointment rescheduled - CL 12/05 - WORKS BBOOKED FOR 21ST MAY | Appointment booked | 494.79
2025-09-15 11:50:00 | JEFF WAY - Make repairs to plaster walls in bathroom and apply sealer to staining on walls .Paint ceiling and walls in anti condensation paint. Fix new plastic skirting around perimeter of walls FAO JEFF NECK | 2026-05-18 08:00:00 | 2026-07-20 |  | Routine Repairs | 1257256 | 53 Northfield House, Catherine Mead Street, Southville, Bristol BS3 1XD | 1219887 | Works Started | ACE Agreed | 36/699 | 2026-04-29 12:00:00 | 15 days |  |  | Lainie Lavin | 03/10/2025 11:50 | No | Post-completion Items To Complete |  |  |  | 05/05 - NA on 29/05 - CL Appointments booked for 28/04 and follow on 29/04 - CL | WIP | 247.32
2025-09-15 10:54:00 | JEFF WAY - AS PER ROB DOIDGE - RENEW 1 X WALL UNIT DOOR TO MATCH EXISTING. FIX LOOSE WALL UNIT DOOR, SECURE LOOSE BASE UNIT BY FRIDGE AND REFIX MISSING KICKBOARDS TO SAME UNIT | 2025-10-21 08:00:00 | 2025-10-21 | 2025-10-21 12:00:00 | Routine Repairs | 1286493 | 40 Paybridge Road, Withywood, Bristol BS13 8PU | 1219776 | Works Completed | Invoiced | 36/697 | 2025-10-21 08:00:00 | 15 days |  |  | Lainie Lavin | 03/10/2025 10:54 | No | Fully Complete | 2025-11-19 | Yes |  |  | Complete | 160.23
2025-09-15 10:23:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 25/9/25. 10 DAY PERIOD ENDS 9/10/25 |  | 2025-09-26 | 2025-09-26 14:13:00 | Routine Repairs | 00267 | 5 Ashton Rise, Ashton Vale, Bristol, BS3 2DG | 1219525 | Works Completed | Invoiced | 36/696 |  | 15 days |  |  | Lainie Lavin | 03/10/2025 10:23 |  | Fully Complete | 2025-09-26 | Yes |  |  | Complete | 143.59
2025-09-12 14:43:00 | DISREPAIR WORKS as per Alvaro Ibanez. BEDROOMS 1 & 2. Strip wall paper. Mould wash. Erect timber stud wall on wall adjoining neighbouring property-1 side only. Insulation in stud walls. Renew skirting board. Paint new plaster. Mould treatment of ceiling adjacent to external front wall. BEDROOM 1 & LIVING ROOM. Overhaul sash window. Re-decorate window both sides. GARAGE. Mould treatment on walls. Renew mastic sealant to sky light. Apply one coat of Flexacryl to skylight reveal. FRONT ELEV |  | 2026-07-06 |  | Disrepair | 1268026 | 12 WELLINGTON TERRACE | 1218862 | New Works Instruction | ACE Agreed | 36/1121 |  | 20 days |  |  | Shannon Slade | 09/10/2025 14:43 |  | Suspended: Awaiting Client Action/Response |  |  |  | 03/07- izak booked 06/07 PM to cold call and get the tenants reason for plastering refusal 13/05 - DARREN HAS CONFIRMED THAT TENANT IS REFUSING WORKS TO BEDROOM2 UNTIL A VISIT IS COMPLETED BY BCC TO RE-CONFIRM WORKS REQUIRED. CAN YOU CONTACT AND LET ME KNOW UPDATE?WORKS BOOKED TO COMMENCE 7TH APRIL. 24/04 - DARREN TO PROVIDE UPDATE TO JAMES REG | Held Tenant | 4465.74
2025-09-12 12:35:00 | Carpenter External contractor Jeffwayy group collect frame and door from wellington road to renew bathroom door ling and internal flush door and decorate complete please provide before and after pictures BCC contact Luke Pomphrey | 2025-10-30 08:00:00 | 2026-03-03 | 2026-03-02 14:15:00 | Routine Repairs | 1285321 | 8 Nailsea Close, Bedminster Down, Bristol BS13 7EH | 1218518 | Works Completed | Invoiced | 36/695 | 2025-10-30 08:00:00 | 15 days |  |  | Lainie Lavin | 02/10/2025 12:35 | No | Fully Complete | 2026-03-16 | Yes |  |  | Complete | 356.04
2025-09-12 12:33:00 | Disrepair works to complete. Bathroom Install cap and cove flooring removing all skirting, main bedroom Scrape wall seal and paint. install two, hit and miss vents on doors one in bedroom same room as painting and one understairs cupboard. Kitchen replace two 500 wall unit doors above kettle. | 2026-04-22 08:00:00 |  | 2026-04-22 11:53:00 | Disrepair | 1259809 | 14 PROCTOR HOUSE | 1218663 - 10608/1 | Works Completed | ACE Agreed | 36/719 | 2026-04-22 08:00:00 | 20 days |  |  | Shannon Slade | 09/10/2025 12:33 | No | Fully Complete | 2026-06-12 |  |  | JWC WORKS COMPLETED, WAITING FOR FANTASY FLOORING TO COMPLETE WORKS 30/03 - FLOORING COULDN'T GO AHEAD DUE TO SOME BOXING IN THAT WAS REQUIRED. EMAILED FANTASY TO CONFIRM THIS IS NOW COMPLETED, WAITING FOR DATE OF RETURN. 09/04 - FF ATTENDING 22/04./ | Complete | 622.59
2025-09-12 12:20:00 | Urgent - Plasterer - F/On 001156505 - 4sm of Bed2 ceiling to renew, over-skim complete ceiling CASA test result NAD | 2025-10-08 12:00:00 | 2025-10-08 | 2025-12-08 11:25:00 | Routine Repairs | 1262551 | 61 Southbow House, Duckmoor Road | 1203316 | Works Completed | Invoiced | 36/674 |  | 15 days |  |  | Lainie Lavin | 02/10/2025 12:20 |  | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 686.41
2025-09-12 12:03:00 | Carpentry Sub Contractor Jeff way Collect materials from Wellington road less spindles alloud to cover cost of materials replace 2 and half newels 3.8 meter, 38x spindles ands replace 1 floor board top of stairs, please prove after pictures BCC contact Luke Pomphrey | 2025-10-16 12:15:00 | 2025-10-16 | 2025-10-16 08:52:00 | Routine Repairs | 1169728 | 76 Capgrave Crescent, Broomhill, Bristol BS4 4TW | 1218409 | Works Completed | Invoiced | 36/692 | 2025-10-16 12:15:00 | 15 days |  |  | Lainie Lavin | 02/10/2025 12:03 | No | Fully Complete | 2025-10-17 | Yes |  |  | Complete | 952.26
2025-09-12 11:57:00 | JEFF WAY - AS PER ROB DOIDGE - RENWAL OF PLASTERBOARD BATHROOM CEILING, RENEWAL OF LIGHT FITTING AND REPAINTING OF ALL WALLS , CLEAN OFF PIPEWORK ALSO | 2025-10-06 08:00:00 | 2025-10-06 | 2025-10-13 09:50:00 | Routine Repairs | 1299587 | 9 Faber Grove, Hartcliffe, Bristol BS13 0LD | 1218620 | Works Completed | Invoiced | 36/694 | 2025-10-06 08:00:00 | 15 days |  |  | Lainie Lavin | 02/10/2025 11:57 | No | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 346.4
2025-09-12 10:57:00 | Carpenter External contractor Jeffway group collect materials from wellington road joinery shop 20 spindles to allow for material cost, 1x newel post 85/85mm 2x handrail/base rail 40x spindles. Please provide before/after pictures BCC contact Luke Pomphrey | 2025-10-15 08:00:00 | 2025-10-15 | 2025-10-15 17:00:00 | Routine Repairs | 1287383 | 16 Redford Crescent, Withywood, Bristol BS13 8SD | 1218448 | Works Completed | Invoiced | 36/693 | 2025-10-15 08:00:00 | 15 days |  |  | Lainie Lavin | 02/10/2025 10:57 | No | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 878.84
2025-09-12 10:33:00 | complaint works- Jeffway works as per email. see Gdrive for email. | 2025-11-13 08:00:00 |  | 2026-04-08 14:58:00 | Disrepair | 1162341 | 7 GREAT GEORGE STREET | 1218470 - 10472/1 | Works Completed | Invoiced | 36/718 | 2025-10-22 07:30:00 | 20 days |  |  | Shannon Slade | 09/10/2025 10:33 | No | Fully Complete | 2026-04-29 | Yes |  | 23/03 - SCRAPING COMPLETED ETC, ALLOWED TO DRY. PAINTING BOOKED FOR 31 MARCH TO COMPLETE PAINTING | Complete | 2278.88
2025-09-11 14:58:00 | External Contractor Jeffway to assist pest control works for Orbis remove and refit kitchen units as required. BCC contact Luke Pomphrey Darren Whitchurch aware of works. |  | 2025-12-19 | 2025-12-19 13:30:00 | Routine Repairs | 1157739 | 10 Somerset House, Trinity Walk, Lawfords Gate | 1215807 | Works Completed | Invoiced | 36/836 |  | 15 days |  |  | Lainie Lavin | 01/10/2025 14:58 | No | Fully Complete | 2026-01-05 | Yes |  |  | Complete | 332.76
2025-09-11 14:38:00 | Disrepair works, extractor fans and other works | 2025-12-09 09:15:00 |  | 2026-01-29 12:11:00 | Disrepair | 1108390 | 52B CITY ROAD | 1218114 | Works Completed | Invoiced | 36/716 | 2026-01-27 14:14:00 | 20 days |  |  | Shannon Slade | 08/10/2025 14:38 | No | Fully Complete | 2026-02-04 | Yes |  |  | Complete | 1039.02
2025-09-11 10:36:00 | Specialist projects - Ground investigations- Yuliya | 2025-09-24 08:00:00 | 2025-09-24 | 2025-09-24 15:30:00 | Routine Repairs | 1216620 | Queens Road Bk 130-140, Queens Road | 1216620 | Works Completed | Invoiced | 36/662 | 2025-09-24 07:30:00 | 15 days |  |  | Lainie Lavin | 01/10/2025 10:36 | Yes | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 201.28
2025-09-10 17:59:00 | Complaint works as per Tom Taylor (07557 930840) - External: Clear guttering to front of property. Bathroom: Strip wallpaper from affected wall, prepare wall and redecorate with anti mould bathroom paint; Mould treatment to ceiling; install extractor fan. Kitchen: Redecorate ceiling with 2 coats emulsion; Stain block and redecorate affected walls with 2 coats of emulsion; sand down skirting below boiler and apply 2 coats of gloss. Provide enclosure for pipework below the boiler. | 2025-10-14 08:00:00 |  | 2026-06-01 10:30:00 | Disrepair | 1010635 | 218 BROADLANDS DRIVE | 1217639 | Works Completed | ACE Agreed | 36/715 |  | 20 days |  |  | Shannon Slade | 07/10/2025 17:59 |  | Pre-completion Items To Complete |  | Yes |  | 19/05 - APPOINTMENT MADE FOR SUPERIVSOR TO ATTEND AND INSPECT IF FAN IS FITTED,. | Complete | 1063.85
2025-09-10 16:17:00 | Works following inspection as per Andy Griffiths (07345 491671) - Bed 1: Stain block and paint over window reveal; refix loose radiator; repair/replace loose light switch. Bed 2: Patch prepare and paint internal wall shared with bedroom one; fit new drop pendant. Living room: Stain block and paint over window reveal. Bathroom: Investigate leak into kitchen below. Kitchen: Replace defective tiles and repair sub floor. External: Resit ridge tiles | 2025-10-13 08:00:00 |  | 2025-10-13 14:45:00 | Disrepair | 1068139 | 5 SILVERHILL ROAD | 1217583 | Works Completed | Invoiced | 36/717 | 2025-10-13 08:00:00 | 20 days |  |  | Shannon Slade | 07/10/2025 16:17 | No | Post-completion Items To Complete | 2025-11-18 | Yes |  |  | Complete | 1563.05
2025-09-10 15:55:00 | Please paint both bathroom and kitchen ceiling plus the kitchen walls | 2025-10-07 08:00:00 | 2025-10-07 | 2025-10-07 09:55:00 | Routine Repairs | 1256855 | 13 Northfield House, Catherine Mead Street | 1217522 | Works Completed | Invoiced | 36/669 |  | 15 days |  |  | Lainie Lavin | 30/09/2025 15:55 |  | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 554.4
2025-09-10 13:39:00 | Works following inspection as per Andy Griffiths (07345 491671) - Replace the gutter on the rear elevation including return; damaged electrical socket requires replacing; fit window restrictor in bedroom 2. Please knock loudly and give tenant time to answer the door. |  |  | 2025-10-27 08:21:00 | Disrepair | 1186863 | 62 SHERWELL ROAD | 1217367 | Works Completed | ACE Agreed | 36/709 |  | 20 days |  |  | Shannon Slade | 07/10/2025 13:39 |  | Post-completion Items To Complete | 2026-01-19 | Yes |  |  | Complete | 1708.24
2025-09-10 11:52:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR - JOE COTTRELL ATTENDING 18/09/25. 10 DAY PERIOD ENDS 02/10/25. |  | 2025-09-17 | 2025-09-17 15:11:00 | Routine Repairs | 1047230 | 126 Clover Ground, Westbury On Trym | 1217269 | Works Completed | Invoiced | 36/668 |  | 15 days |  |  | Lainie Lavin | 30/09/2025 11:52 |  | Fully Complete | 2025-09-22 | Yes |  |  | Complete | 143.59
2025-09-10 10:45:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR - TOM WALKER ATTENDING 24/09/25. 10 DAY PERIOD ENDS 08/10/25. |  | 2025-09-17 | 2025-09-17 10:59:00 | Routine Repairs | 1305982 | 48 Maidenhead Road, Hartcliffe | 1217192 | Works Completed | Invoiced | 36/667 |  | 15 days |  |  | Lainie Lavin | 30/09/2025 10:45 |  | Fully Complete | 2025-09-29 | Yes |  |  | Complete | 158.82
2025-09-10 10:33:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR - TOM WALKER ATTENDING 23/09/25. 10 DAY PERIOD ENDS 07/10/25. |  | 2025-09-17 | 2025-09-17 10:38:00 | Routine Repairs | 1272179 | 675 Bishport Avenue | 1217170 | Works Completed | Invoiced | 36/666 |  | 15 days |  |  | Lainie Lavin | 30/09/2025 10:33 |  | Fully Complete | 2025-09-29 | Yes |  |  | Complete | 348.98
2025-09-10 10:20:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR - TOM WALKER ATTENDING 23/09/25. 10 DAY PERIOD ENDS 07/10/25. | 2026-01-08 08:00:00 |  | 2026-02-09 16:34:00 | Routine Repairs | 1303011 | 561 Hareclive Road, Hartcliffe | 1217155 | Works Completed | Invoiced | 36/665 | 2026-01-08 16:35:00 | 15 days |  |  | Lainie Lavin | 30/09/2025 10:20 | No | Pre-completion Items To Complete | 2025-09-24 | Yes |  |  | Complete | 334.94
2025-09-09 14:15:00 | As per Sean P: Renew light to utility room celling. Kitchen: re stick down/replace 10x vinyl tiles in kitchen ones coming up in various places by washing machine. Front bedroom - Small handle loose replace this one and large window stay, and handle loose please look at and replace if required. Repaint utility celling after light comes down. Renew architraves ( utility side to hallway ) then re gloss after. | 2026-04-02 08:00:00 |  | 2026-04-02 12:13:00 | Routine Repairs | 1244366 | 51 Church Lane | 1216799 | Works Completed | Invoiced | 36/663 |  | 15 days |  |  | Lainie Lavin | 29/09/2025 14:15 |  | Pre-completion Items To Complete | 2026-04-17 | Yes |  | 08/05 - KPI received and uploaded - CL 17/04 - KPI requested - CL Tenant confirmed works not required 02/04 | Complete | 95.42
2025-09-09 11:19:00 | Complaint disrepair work - Service windows of 3 bed house (BCC internal teams will be renewing 2 blown and 1 cracked panes) - Renew silicon around the bath and panelling - Prep and gloss paint back door on both sides - Overhaul bathroom fan - Install windowsill in front small room/3rd bedroom | 2026-04-15 09:30:00 |  | 2026-03-18 10:01:00 | Disrepair | 1227641 | 103 NEWQUAY ROAD | 1216569 | Works Completed | ACE Agreed | 36/728 |  | 20 days |  |  | Shannon Slade | 06/10/2025 11:19 |  | Post-completion Items To Complete | 2026-03-30 | Yes |  | 20/05 -BCC post inspected on 27/05 | Complete | 422.85
2025-09-09 10:49:00 | Scrape and paint bathroom ceiling | 2025-11-19 08:00:00 | 2025-11-19 | 2025-11-19 12:00:00 | Disrepair | 1190143 | 85 Whitmore Avenue | 1212749/23724/2 | Works Completed | Invoiced | 36/646 | 2025-11-19 08:00:00 | 20 days |  |  | Shannon Slade | 06/10/2025 10:49 | No | Post-completion Items To Complete | 2025-11-25 | Yes |  |  | Complete | 180.44
2025-09-09 09:50:00 | DISREPAIR WORK | 2025-10-10 08:00:00 | 2026-04-02 | 2025-11-10 15:12:00 | Disrepair | 1073809 | 32 Trowbridge Road | 1215848 | Works Completed | ACE Agreed | 36/657 | 2025-11-10 08:00:00 | 20 days |  |  | Shannon Slade | 06/10/2025 09:50 | No | Post-completion Items To Complete | 2026-04-29 | Yes |  |  | Complete | 391.14
2025-09-08 17:24:00 | DISREPAIR WORK | 2025-09-22 08:00:00 |  | 2025-12-19 13:25:00 | Disrepair | 1219303 | 110 EXMOUTH ROAD | 1215834 | Works Completed | Invoiced | 36/656 | 2025-09-22 08:00:00 | 20 days |  |  | Shannon Slade | 03/10/2025 17:24 | No | Fully Complete | 2026-01-07 | Yes |  |  | Complete | 331.61
2025-09-08 16:39:00 | remove existing loft insulation and replace to 450mm, stain block and paint landing ceiling | 2025-09-24 08:00:00 |  |  | Disrepair | 1264488 | 160 ST JOHNS LANE | 1215799 | Works Started | ACE Agreed | 36/655 | 2025-09-24 08:00:00 | 20 days |  |  | Shannon Slade | 03/10/2025 16:39 | No | Pre-completion Items To Complete |  |  |  | 20/05 - SEND TWO OPS . WORKS ON HOLD - WAITING FOR UPDATE FROM BCC 05/05 - ADVISED TO ASSIST WITH MOVING CABINET. WORKS BOOKED TO BE COMPLETED 12TH MAY. | WIP | 638.32
2025-09-08 14:25:00 | JEFF WAY - Check bathroom toilet cistern and pipe work for leaks. Overhaul bathroom and rear bedroom windows. Lift and replace 4no vinyl floor tiles in kitchen floor area FAO JEFF NECK | 2025-11-06 08:00:00 | 2025-11-06 | 2025-10-15 11:12:00 | Routine Repairs | 1282582 | 38 HUNTINGHAM ROAD | 1182588 | Works Completed | Invoiced | 36/661 |  | 15 days |  |  | Lainie Lavin | 26/09/2025 14:25 |  | Fully Complete | 2025-10-17 | Yes |  |  | Complete | 153.09
2025-09-08 09:53:00 | DISREPARI WORKS | 2026-05-13 12:00:00 |  | 2026-05-13 14:19:00 | Disrepair | 1215269 | 136 STATION ROAD | 1215269 | Works Completed | Invoiced | 36/654 | 2025-11-03 12:00:00 | 20 days |  |  | Shannon Slade | 03/10/2025 09:53 | No | Fully Complete | 2026-06-12 |  |  | 23/03 - SNAGGING BOOKED FOR 2ND APRIL - WINDOW FANS SENT TO GLAZING COMPANY FOR HOLES TO BE PUT IN WINDOWS AND THEN WILL ARRANGE ELECTRICIAN FOLLOWING THIS. 31/03 - WSG COMPLETED WINDOW WORKS, TASKED TO D&M TO BOOK ELECTRICIAN. | Complete | 2389.03
2025-09-05 09:35:00 | RG - Tenant wants the bathroom floor order reraised | 2026-07-27 16:00:00 | 2026-07-27 |  | Routine Repairs | 1227436 | 76 NEWQUAY ROAD | 1214544 | New Works Instruction | ACE Agreed | 36/618 |  | 15 days |  |  | Lainie Lavin | 25/09/2025 09:35 |  | Pre-completion Items To Complete |  |  |  | 03/06 - FF to attend 18/06 and 19/06 - CL 29/05 Re issued to FF now that floor has been made safe, sent email awaiting date Appointment booked for 22/04. | Appointment booked | 271.84
2025-09-04 09:36:00 | COMPLAINT WORKS - DISREPAIR WORKS | 2026-02-16 12:00:00 | 2026-02-16 |  | Disrepair | 1191726 | 72 WYNDHAM CRESCENT | 1213803 | New Works Instruction | ACE Agreed | 36/651 |  | 20 days |  |  | Shannon Slade | 01/10/2025 09:36 |  | Suspended: Refused by resident |  |  |  |  | Held Tenant | 2338.15
2025-09-03 18:34:00 | Make good plaster to the ceiling and wall in kitchen cupboard and repair/replace draught excluder to balcony door | 2025-09-24 12:00:00 | 2025-09-24 | 2025-09-24 14:20:00 | Disrepair | 1258646 | 51 Patterson House Prewett Street | 1213852 | Works Completed | Invoiced | 36/652 |  | 20 days |  |  | Shannon Slade | 30/09/2025 18:34 |  | Fully Complete | 2025-09-26 | Yes |  |  | Complete | 72.55
2025-09-03 15:41:00 | Install UPVC trims to heads of windows in living room, replace cracked glazed to living room, clear guttering and repair distored guttering to RHS of property. Replace ltter box, stian block and paitn ceiling | 2025-11-10 09:00:00 |  | 2026-01-23 10:30:00 | Disrepair | 1189679 | 12 WHITMORE AVENUE | 1213769 | Works Completed | Invoiced | 36/650 | 2025-10-07 08:00:00 | 20 days |  |  | Shannon Slade | 30/09/2025 15:41 | No | Fully Complete | 2026-06-12 |  |  |  | Complete | 93.43
2025-09-03 12:22:00 | incorrectly wired fans and small area of pointing needed | 2025-09-17 12:00:00 | 2025-09-17 | 2025-09-17 08:26:00 | Disrepair | 1189577 | 222 Whiteway Road | 1213669 | Works Completed | Invoiced | 36/659 | 2025-09-17 12:00:00 | 20 days |  |  | Shannon Slade | 30/09/2025 12:22 | Yes | Fully Complete | 2025-09-17 | Yes |  |  | Complete | 259.44
2025-09-02 17:37:00 | Renew window handle to kitchen window, seal gap between the kitchen countertop and windowsill, minor mould, isoalted patch on bathroom ceiling and to living room window frames | 2025-11-19 12:00:00 | 2025-11-19 | 2025-11-19 17:00:00 | Disrepair | 1315840 | 16 Willow House Bishport Avenue | 1213263 | Works Completed | Invoiced | 36/649 | 2025-11-19 12:00:00 | 20 days |  |  | Shannon Slade | 29/09/2025 17:37 | No | Post-completion Items To Complete | 2025-12-09 | Yes |  |  | Complete | 107.64
2025-09-02 14:56:00 | DISREPAIR WORKS - bed 1: stain block and paint both sections of staining and historic mould growth in bedroom. Repair leak to chimney stack lead flashing. Living room hack of crack to wall near door and replaster. Paint patch of new plastering. Splice door frame and ease door. kitchen renew kitchen fan unit | 2026-01-13 08:00:00 | 2026-01-13 | 2026-02-12 11:11:00 | Disrepair | 1016791 | 101 HENACRE ROAD | 1213129 | Works Completed | Invoiced | 36/648 | 2025-10-14 11:30:00 | 20 days |  |  | Shannon Slade | 29/09/2025 14:56 | No | Fully Complete | 2026-02-24 | Yes |  |  | Complete | 2579.69
2025-09-02 12:55:00 | Snagging repairs from disrepair claim. Kitchen - hack off damp and damaged plastr, re-plaster to match existing. Replace damp affected skirting board and section of architrave. Redec wall and skirting board to suitable breakpoint to match existing. Decorate repaired areas to suitable break point to match existing. bed 1 replace damp affected skirting board and decorate. apply fungical wash to black mould growth. redecorate affected and to match existing. re attach PVC win |  |  |  | Disrepair | 1016188 | 25 HENACRE ROAD | 1213072 | Works Cancelled | Works Cancelled | 36/647 |  | 20 days | 3: Omitted from Contract | 2026-01-09 13:50:51 | Shannon Slade | 29/09/2025 12:55 |  | Works Cancelled | [5 empty] | 931.1
2025-09-02 11:39:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR - JOE COTTRELL ATTENDING 17/09/25. 10 DAY PERIOD ENDS 01/10/25. |  | 2025-10-16 | 2025-10-16 11:53:00 | Routine Repairs | 1307820 | 8 Millmead House Silcox Road | 1212454 | Works Completed | Invoiced | 36/779 |  | 15 days |  |  | Shannon Slade | 22/09/2025 11:39 |  | Fully Complete | 2025-10-20 | Yes |  |  | Complete | 143.59
2025-09-01 14:31:00 | Mex Repairs - Install window wire restrictors to all windows -5no | 2025-10-01 13:00:00 | 2025-10-01 | 2025-10-01 14:30:00 | Routine Repairs | 1257574 | 85 Northfield House, Catherine Mead Street | 1212041 | Works Completed | Invoiced | 36/615 | 2025-10-01 13:00:00 | 15 days |  |  | Lainie Lavin | 19/09/2025 14:31 | No | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 81.9
2025-09-01 12:07:00 | JEFF WAY - Fix new timber doorlining in lounge entrance wall . Make good plastersurround to match existing levels . Fix new timber door complete with all fittings. Apply under coat and gloss finish. - Jeff Neck | 2026-04-08 08:00:00 | 2026-04-08 | 2026-04-08 08:36:00 | Routine Repairs | 1285672 | 61 NEWLAND ROAD | 1211858 | Works Completed | ACE Agreed | 36/614 | 2026-04-08 08:00:00 | 15 days |  |  | Lainie Lavin | 19/09/2025 12:07 | No | Pre-completion Items To Complete | 2026-04-16 | Yes |  | 16/04 - KPI request sent - CL Appointment rescheduled with tenant, letter and text message sent - CL | Complete | 528.81
2025-09-01 11:10:00 | Jeff Way - Fix new fan in 1st floor front bathroom in external wall. Fix new fan in ground floor kitchen window . Overhaul all windows and handles. Repair water damage ceiling in kitchen . Lift existing vinyl flooring in kitchen and make good sub floor and refix. - Jeff Neck | 2026-04-27 08:00:00 | 2026-05-25 | 2026-05-26 12:02:00 | Routine Repairs | 1273569 | 10 CHALCROFT WALK | 1211788 | Works Completed | Invoiced | 36/613 |  | 15 days |  |  | Lainie Lavin | 19/09/2025 11:10 |  | Post-completion Items To Complete | 2026-06-29 | Yes |  | 30/06 - KPI received and uploaded - CL 29/06 - KPI requested - CL 29/05 - Email sent to FF to chase completion - CL 08/05 - FF to attend 25-26/05 - CL 07/05 - Variation approved email sent to FF - CL 280/4 - Email sent to JN for variation for kitchen floor repair - CL 24/04 - Tenant called back and confirmed appointment for SH to attend 8am 27/04 to inspect the floorin | Complete | 809.97
2025-09-01 10:43:00 | Apply mould wash treatment to hallway / kitchen/ toilet and bedroom - Jeff Neck | 2025-09-29 08:00:00 | 2025-09-29 | 2025-09-29 12:15:00 | Routine Repairs | 1293078 | 386 Bishport Avenue, Hartcliffe | 1211751 | Works Completed | Invoiced | 36/611 | 2025-09-29 08:00:00 | 15 days |  |  | Lainie Lavin | 19/09/2025 10:43 | No | Post-completion Items To Complete | 2025-11-19 | Yes |  |  | Complete | 108.05
2025-09-01 09:25:00 | External contractor Jeffway group to over clad porch ceiling with UPVC cladding and fit Upvc soffit to porch canopy/bay window, please send after pictures Photo's/Asbestos report to follow BCC contact Luke Pomphrey | 2026-02-23 08:00:00 | 2026-02-23 | 2026-02-23 09:43:00 | Routine Repairs | 1312954 | 2 Shortwood Walk, Hartcliffe | 1210557 | Works Completed | Invoiced | 36/610 | 2026-02-23 08:00:00 | 15 days |  |  | Lainie Lavin | 19/09/2025 09:25 | No | Fully Complete | 2026-03-19 | Yes |  |  | Complete | 507.0
2025-08-29 14:42:00 | Plasterer - F/On 001139989 - 15 sqm of living room ceiling to overboard and skim , (Tenants daughter is a chronic Asthmatic) textured ceiling painted with polytex, CASA test came back NAD. R.M | 2025-11-19 12:00:00 | 2025-10-16 | 2025-10-16 12:04:00 | Routine Repairs | 1288740 | 13 SELLEY WALK | 21052/1 | Works Completed | Invoiced | 36/769 | 2025-10-16 12:04:00 | 15 days |  |  | Shannon Slade | 18/09/2025 14:42 | No | Post-completion Items To Complete | 2026-01-19 | Yes |  |  | Complete | 485.55
2025-08-29 12:27:00 | Jeffway-AS PER ROB DOIDGE - REPAIR TO SUBFLOOR IN BATHROOM, PLYBOARD SEEMS TO HAVE POPPED / RISEN, LINO OK TO RE USE |  |  | 2025-09-17 07:54:00 | Routine Repairs | 0000284 | Flat 10 Centenary House, 1 Micklewright Close | 1211271 | Works Completed | Invoiced | 36/606 |  | 15 days |  |  | Lainie Lavin | 18/09/2025 12:27 |  | Pre-completion Items To Complete | 2025-09-19 | Yes |  |  | Complete | 286.84
2025-08-29 12:25:00 | Jeffway- as per Rob Doidge-RENEWAL OF ROTTEN BACK DOOR SILL AND STAIN TO MACTCH DOOR. SILICON THE TOP OF WEATHERBOARD TO BACK DOOR ALSO | 2025-09-17 11:30:00 | 2025-09-17 | 2025-09-17 11:35:00 | Routine Repairs | 1317653 | 11 Wymbush Gardens | 1211266 | Works Completed | Invoiced | 36/607 | 2025-09-17 11:30:00 | 15 days |  |  | Lainie Lavin | 18/09/2025 12:25 | Yes | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 133.99
2025-08-29 12:19:00 | Jeffway- as per Tom Walker-Replacement bath panel. Redec kitchen ceiling. | 2025-10-31 08:00:00 | 2025-10-31 | 2025-12-04 15:23:00 | Routine Repairs | 1105073 | 5 Barnabas Street | 1211263 | Works Completed | Invoiced | 36/608 | 2025-10-03 08:00:00 | 15 days |  |  | Lainie Lavin | 18/09/2025 12:19 | No | Post-completion Items To Complete | 2025-12-19 | Yes |  |  | Complete | 313.15
2025-08-29 12:15:00 | Jeffway-as per Tom Walker-Render repair to rear elevation. Lower corner | 2025-10-01 08:00:00 | 2025-10-01 | 2025-10-01 11:57:00 | Routine Repairs | 1245096 | 37 COTSWOLD ROAD | 1211257 | Works Completed |  | 36/609 | 2025-09-30 12:30:00 | 15 days |  |  | Lainie Lavin | 18/09/2025 12:15 | No | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 206.19
2025-08-29 11:48:00 | Jeffway-As per Jeff Neck-Knock down cracked single skin block work on external outbuilding in rear garden down to concrete sub floor and clear all waste. Tenant to allow rear garden fence to be taken down for access from rear lane. |  | 2025-12-11 | 2025-12-11 14:39:00 | Routine Repairs | 1299101 | 13 Dyers Close, Hartcliffe, Bristol BS13 0LW | 1211234 | Works Completed | Invoiced | 36/801 | 2025-12-11 14:43:00 | 15 days |  |  | Lainie Lavin | 18/09/2025 11:48 | No | Post-completion Items To Complete | 2026-01-22 | Yes |  |  | Complete | 629.25
2025-08-29 11:02:00 | AS PER ROB DOIDGE - STRIP TOP 6 INCHES OF WALLPAPER ALL AROUND KITCHEN PRIOR TO FULLY REDECORATING AND CAULKING KITCHEN CEILING. POORLY DONE BY PREVIOUS CONTRACTOR. TNT WILL TAKE OFF REST OF PAPER WHEN READY. RENEW SEALANT INTERNALLY TO LIVING ROOM WINDOW WHERE MISSING | 2025-11-05 17:00:00 | 2025-11-05 | 2025-11-05 10:52:00 | Routine Repairs | 1214988 | 61 Connaught Road, Knowle | 1211195 | Works Completed | Invoiced | 36/602 |  | 15 days |  |  | Lainie Lavin | 18/09/2025 11:02 |  | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 301.9
2025-08-27 16:26:00 | Jeffway-AS PER ROB DOIDGE - FIT NEW EXTRACTOR FANS TO EXISTING OUTLETS IN BATHROOM AND KITCHEN, DRILLING / MAKING GOOD TO WALL ONLY REQUIRED IN BATHROOM send to JWE for the Fan | 2025-09-24 08:00:00 | 2025-09-24 | 2025-09-24 14:26:00 | Routine Repairs | 1282195 | 4 Horsepool Road, Withywood | 1203588 | Works Completed | ACE Agreed | 36/598 |  | 15 days |  |  | Lainie Lavin | 16/09/2025 16:26 |  | Post-completion Items To Complete | 2025-10-16 | Yes |  |  | Complete | 590.77
2025-08-27 12:57:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 1/9/25. 10 DAY PERIOD ENDS 15/9/25 | 2026-01-08 12:00:00 |  | 2026-09-17 12:50:00 | Routine Repairs | 1283790 | 1 Langford Road, Bedminster Down, Bristol BS13 7AP | 1210196 | Works Completed | Invoiced | 36/597 | 2025-09-12 10:52:00 | 15 days |  |  | Lainie Lavin | 16/09/2025 12:57 | No | Fully Complete | 2025-09-17 | Yes |  |  | Complete | 143.59
2025-08-26 17:05:00 | JEFF WAY - Bathroom cut out loose / water damage plasterboard ceiling over bath in corner position and cut / fix new to suit .Apply new skim plaster finish to complete ceiling. Repaint bathroom ceiling / small toilet wall and ceiling and kitchen ceiling complete in anti condensation paint .Fix 2no new fans in bath and kitchen positions. FAO JEFF NECK | 2026-04-07 08:00:00 | 2026-04-07 | 2026-02-26 13:22:00 | Routine Repairs | 1310776 | 32 PAWLETT ROAD | 1209884 | Works Completed | ACE Agreed | 36/591 | 2026-04-07 08:00:00 | 15 days |  |  | Lainie Lavin | 15/09/2025 17:05 | No | Fully Complete | 2026-02-26 | Yes |  |  | Complete | 1069.06
2025-08-26 16:54:00 | JEFF WAY - Apply mould treatment to bathroom ceiling . Fix new fan in external sloping wall with external tiled roof vent. Make repair to plastered window head in bathroom . Overhaul all windows. FAO JEFF NECK | 2026-05-19 08:00:00 | 2026-06-10 | 2026-06-10 10:37:00 | Routine Repairs | 1299087 | 11 DYERS CLOSE | 1209879 | Works Completed |  | 36/593 | 2026-01-06 09:00:00 | 15 days |  |  | Lainie Lavin | 15/09/2025 16:54 | No | Pre-completion Items To Complete | 2026-07-02 |  |  | 23/06 - KPI request sent - CL 11/06 - Works complete, post-inspection to be booked - CL 09/06 - Appointment confirm with tenant - CL 06/05 - Tenant informed me that all work had been completed. Only outstanding is the trim by loft hatch - CL 27/04 - Needs to be rescheduled due sickness - CL Decorating booked for 24/04 - CL | Complete | 1487.82
2025-08-26 10:09:00 | Jeffway - Plasterer to hack off loose plaster on right hand side of bedroom, bond and skim 9 metres where loose plaster has come off bedroom 1 upstairs. | 2025-09-16 08:00:00 | 2026-09-16 | 2026-03-27 08:54:00 | Routine Repairs | 1314789 | 54 Tynte Avenue | 1208657 | Works Completed | Invoiced | 36/588 | 2025-09-15 08:00:00 | 15 days |  |  | Lainie Lavin | 15/09/2025 10:09 | No | Pre-completion Items To Complete | 2026-04-29 | Yes |  | 29/04 - KPI requested - CL | Complete | 528.75
2025-08-26 10:08:00 | JEFF WAY - AS PER ROB DOIDGE - OVERHAUL BATHROOM AND W.C WINDOWS, BOTH CURRENTLY WONT CLOSE. RENEW BANNISTER RAILS IN PLACE OF LOOSE / WEAK EXISTING. RAILS ONLY. FIX DROPPED SECTION OF GUTTERING TO FRONT RHS ELEVATION AND SMALL PATCH OF CEMENT TO BE FILLED OVER GAS PIPE TO FRONT PATH. | 2025-10-03 12:00:00 | 2025-10-03 | 2025-10-03 16:30:00 | Routine Repairs | 1304445 | 11 HOLBROOK CRESCENT | 1208955 | Works Completed | Invoiced | 36/587 | 2025-10-03 12:00:00 | 15 days |  |  | Lainie Lavin | 15/09/2025 10:08 | No | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 299.98
2025-08-22 15:01:00 | JEFF WAY - KITCHEN FLOORING , RE/SECURE REAR BACK DOOR FRAME , WEATHER PROOF REAR DOOR ( JOB IS AWAITING STRUCTURAL SURVEY) AS PER IAN OGBORNE. | 2026-06-05 14:30:00 | 2025-12-18 | 2025-12-18 11:42:00 | Routine Repairs | 1281056 | 2 GOULSTON WALK | 1208582 | Works Completed | ACE Agreed | 36/584 | 2025-09-23 10:00:00 | 15 days |  |  | Lainie Lavin | 12/09/2025 15:01 | No | Post-completion Items To Complete |  | No |  | 10/06 - Contact details are the same as on file. Email sent to IO for additional contact details for tenant - CL 05/05 - Enable to make contact with tenant, voicemail and text sent - CL 07/04 - Unable to contact tenant for DW to carry out a site visit, voicemail left - CL | Complete | 817.78
2025-08-22 11:40:00 | JEFF WAY - AS PER ROB DOIDGE - REFIX LOOSE SINK BACK TO BATHROOM WALL, RENEW TILES SPLASHBACK X 4 TILES, RENEW LOOSE BATH TILES AS REQUIRED INDIVIDUALLY AS REQUIRED AND RENEW CISTERN TO W.C . WC PAN LOOSE ALSO SO TIGHTEN UP AND ENSURE NO LEAKS TO REAR FLEXI CONNECTOR | 2026-02-04 11:30:00 | 2026-02-04 | 2026-02-04 16:15:00 | Routine Repairs | 1310992 | 72 Pawlett Road, Hartcliffe, Bristol | 1208364 | Works Completed | Invoiced | 36/926 | 2026-02-04 11:30:00 | 15 days |  |  | Shannon Slade | 12/09/2025 11:40 | No | Fully Complete | 2026-02-06 | Yes |  |  | Complete | 502.71
2025-08-21 13:22:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR JOE COTTRELL ATTENDING 27/8/25. 10 DAY PERIOD ENDS 10/9/25 |  | 2025-10-03 | 2025-10-03 09:19:00 | Routine Repairs | 1298120 | 74 Crosscombe Drive, Hartcliffe | 1208034 | Works Completed | Invoiced | 36/578 |  | 15 days |  |  | Lainie Lavin | 11/09/2025 13:22 |  | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 143.59
2025-08-21 12:18:00 | Complaint works as per Tom Taylor - THROUGHOUT: Minor mould treatment in patches, Service and clean guttering, install weatherstrip to front door and repair concrete below front door, Check windows throughout. KITCHEN: Refit rubber window gasket. BEDROOM 2: Ease and adjust window unit. LIVING ROOM: Ease and adjust window unit. |  |  | 2025-09-23 09:16:00 | Disrepair | 1298528 | 138 Crosscombe Drive | 1207983 | Works Completed | Invoiced | 36/644 | 2025-09-23 09:17:00 | 20 days |  |  | Shannon Slade | 18/09/2025 12:18 | No | Post-completion Items To Complete | 2025-10-21 | Yes |  |  | Complete | 430.11
2025-08-21 12:10:00 | JEFF WAY - Cut out access panel on hallway wall at position of damp patch to trace the leakage from the existing shower pipework . Repair as required and re board to suit. Apply skim plaster finish to hallway wall at position of repair and internal wet room side and end walls FAO JEFF NECK | 2025-09-25 08:00:00 |  | 2026-09-25 16:00:00 | Routine Repairs | 1292655 | 326 Bishport Avenue, Hartcliffe | 1207980 | Works Completed | ACE Agreed | 36/580 |  | 15 days |  |  | Lainie Lavin | 11/09/2025 12:10 |  | Pre-completion Items To Complete | 2026-03-25 | Yes |  |  | Complete | 199.96
2025-08-21 11:57:00 | JEFF WAY - Per paint timber moulding and fix to existing timber skirting at perimeter around kitchen flooring at positions where the concrete floor has dropped to close off gapping FAO JEFF NECK | 2025-10-31 12:00:00 | 2025-10-31 | 2025-10-31 16:15:00 | Routine Repairs | 1252864 | 142 Luckwell Road | 1207973 | Works Completed | Invoiced | 36/582 | 2025-10-31 12:00:00 | 15 days |  |  | Lainie Lavin | 11/09/2025 11:57 | No | Post-completion Items To Complete | 2025-11-19 | Yes |  |  | Complete | 81.06
2025-08-20 17:30:00 | REPAIRS FOLLOWING EXPERT SURVEY REPORT | 2025-09-30 08:00:00 | 2025-09-30 | 2025-09-30 16:15:00 | Disrepair | 1276637 | 36 DERHAM ROAD | 1207753 | Works Completed | Invoiced | 36/645 | 2025-09-30 08:00:00 | 20 days |  |  | Shannon Slade | 17/09/2025 17:30 | No | Fully Complete | 2025-10-07 | Yes |  |  | Complete | 1027.01
2025-08-20 12:16:00 | Complaint works following letter of claim- silicone sealant to be replace on the external of the front door frame. hack off 1 square meter to head of front door and decorate. Stick back wallpaper to hallway. Overhaul both windows Cut out silicone to window unit and replace. Mould wash and paint bathroom ceiling full. New fan to be fitted. Small patch repair to ceiling around pull switch. PVC mould wash. Overhaul window unit. Remove tape to trickle vent. PVC mould wash. Remove the internal plastic trim and apply caulking within the exposed gap to reduce cold transfer across the reveals. Sand and Varnish rear door. Renew trickle vent. Overhaul windows x2. Install new fan. Move draught excluder forward. Overhaul window unit. Mould wash corner of bedroom and paint with Biocheck. Mould wash PVC window unit. Overhaul window unit. PVC mould wash unit. Overhaul window unit. Renew PVC trim to window unit. PVC mould wash window unit. | 2026-06-10 12:00:00 | 2026-06-10 |  | Disrepair | 1291414 | 16 WHITING ROAD | 1207534 | Works Started | ACE Agreed | 36/658 | 2025-09-10 08:00:00 | 20 days |  |  | Shannon Slade | 17/09/2025 12:16 | No | Suspended: Awaiting Client Action/Response |  |  |  | 01/07 query sent to BCC as order and Value on Easybop dont match 18/05 - GLAZING WORKS TO BE OMITTED DUE TO PRCING. SITE VISIT REQUIRED TO SEE IF WORKS ARE COMPLETED. 07/04 - GLAZING QUOTE RECEVIED - SENT TO COMMERCIAL TEAM AND WILL SEND TO YOU SHORTLY. 07/04 - EMAIL ISSUED TO BCC REGARIDNG WINDOW QUOTE. WAITING FOR RESPONSE. 13/04 - WINDOW QUOTE DECLINED BY BCC. TO BE OMITTED. FAN WORKS ISSUED TO JWE. | WIP | 1392.66
2025-08-18 12:33:00 | Post Mex Repairs - Check / Overhaul Shower trap - Tenant stated broken ? - Check all windows open and unlock from the handles and check all air vents open - install internal door to kitchen - Overhaul kitchen tap - change tap cartridge if needed | 2025-10-16 08:00:00 | 2025-10-16 | 2025-10-16 12:00:00 | Routine Repairs | 1205996 | 118 Whittock Road, Stockwood, | 1205996 | Works Completed | Invoiced | 36/581 | 2025-10-16 10:32:00 | 15 days |  |  | Lainie Lavin | 08/09/2025 12:33 | No | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 229.81
2025-08-14 16:06:00 | Jeffway-AS PER ROB DOIDGE - REBED STEP TO END OF FRONT PATH WHERE LOOSE AMD ENSURE NO WOBBLE OR TRIP HAZARD. CRACK TO TOP OF PATH TO BE BROKEN OUT AND RELEVELLED AMD THE GAP TO GRASS SIDE OF PATH TO BE FILLED AS REQUIRED WITH CEMENT | 2025-10-09 11:15:00 | 2025-10-09 | 2025-11-07 10:47:00 | Routine Repairs | 1297467 | 9 Collinson Road, Hartcliffe | 1205161 | Works Completed | Invoiced | 36/575 |  | 21 days |  |  | Lainie Lavin | 12/09/2025 16:06 |  | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 121.84
2025-08-13 11:34:00 | Jeff Way - Plaster in patch to kitchen ceiling, new base unit kitchen, adjust kitchen draw as per Rosanna Gardiner | 2026-05-11 14:30:00 | 2026-05-11 | 2026-05-11 10:57:00 | Routine Repairs | 1293932 | 42 Blackthorn Road, Hartcliffe | 1204399 | Works Completed |  | 36/573 | 2026-03-11 08:00:00 | 21 days |  |  | Lainie Lavin | 11/09/2025 11:34 | No | Pre-completion Items To Complete | 2026-06-11 | Yes |  | 11/06 - KPI requested - CL Follow on appointment booked for 27/03. | Complete | 365.25
2025-08-12 15:56:00 | Sanctuary Scheme follow on works Subcontractor Jeffway group to replace wooden side gate 1030mm wide 1900mm high ledge a braces type lockable from inside. please provide before and after pictures BCC contact Luke Pomphrey. | 2025-11-13 08:00:00 | 2025-11-13 | 2025-11-13 15:00:00 | Routine Repairs | 1214648 | 15 Colchester Crescent, Knowle, | 1204100 | Works Completed | Invoiced | 36/572 | 2025-11-13 08:00:00 | 21 days |  |  | Lainie Lavin | 10/09/2025 15:56 | No | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 316.97
2025-08-11 14:20:00 | There is ongoing evidence of various leaks into the property. Please arrange joint inspection of the roof. Contact Melissa Edwards 07442675013 to discuss further. | 2025-12-12 08:00:00 | 2025-12-12 | 2025-12-18 14:41:00 | Routine Repairs | 1058588 | 82 Lanercost Road, Southmead | 1191907 | Works Completed | Invoiced | 36/672 | 2025-12-11 08:00:00 | 15 days |  |  | Shannon Slade | 01/09/2025 14:20 | No | Fully Complete | 2025-12-19 | Yes |  |  | Complete | 3172.18
2025-08-08 13:13:00 | DISREPAIR WORKS | 2025-10-01 08:00:00 | 2025-10-01 | 2025-08-29 07:28:00 | Disrepair | 1306747 | 13 MELLENT AVENUE | 1202564 | Works Completed | Invoiced | 36/643 |  | 20 days |  |  | Shannon Slade | 05/09/2025 13:13 |  | Fully Complete | 2025-10-21 | Yes |  |  | Complete | 791.85
2025-08-07 12:09:00 | JEFF WAY - PRE MUTUAL EXCHANGE ELECTRIC TEST. SURVEYOR TOM WALKER ATTENDING 11/8/25. 10 DAY PERIOD ENDS 25/8/25 | 2026-01-12 08:00:00 |  | 2026-01-13 12:22:00 | Routine Repairs | 1028133 | 31 OLD QUARRY ROAD | 1197908 | Works Completed | Invoiced | 36/571 |  | 21 days |  |  | Lainie Lavin | 05/09/2025 12:09 |  | Pre-completion Items To Complete | 2025-09-24 | Yes |  |  | Complete | 329.99
2025-08-07 09:06:00 | Relay insulation as its not sat on the plasterboard | 2025-12-15 08:00:00 | 2026-06-24 |  | Routine Repairs | 1097161 | 22 Romney Avenue | 1067416 | New Works Instruction | ACE Agreed | 36/510 |  | 21 days |  |  | Shannon Slade | 05/09/2025 09:06 |  | Pre-completion Items To Complete |  |  |  | 29/05 - MESSAGE LEFT TO TENANT. WORKS BOOKED FOR 24TH JUNE. 08/05 - Unable to reach tenant, voicemail left - CL 27/04 - Site visit to be booked with SH - CL 22/04 - Unable to make contact with tenant, voicemail and text message sent - CL | Appointment booked | 540.0
2025-08-05 09:18:00 | JEFF WAY - Apply 2 coats of sealant compound to concrete canopy roof and scrap/repair painted render wall to side of house and apply masonry paint FAO JEFF NECK | 2025-09-19 09:00:00 | 2025-09-19 | 2025-09-19 10:00:00 | Routine Repairs | 1293589 | 524 BISHPORT AVENUE | 1200240 | Works Completed | Invoiced | 36/256 | 2025-09-18 13:15:00 | 21 days |  |  | Lainie Lavin | 03/09/2025 09:18 | No | Post-completion Items To Complete | 2025-09-24 | Yes |  |  | Complete | 144.94
2025-08-05 08:40:00 | JEFF WAY - AS PER ROB DOIDGE - REMOVAL OF CORNER KIT BASE UNIT TO THEN FILL LARGE HOLE USED BY RATS AROUND DUCTING / BOXING. FILL AS REQUIRED. BATHROOM FLOOR BEHIND SINK, PLEASE FIT SMALL SECTION OF PLYWOOD OVER EXISTING GAPPY FLOORBOARDS ALSO.USED BY RATS AND FULLY SEAL UP , SMALL SECTION LESS THAN O.5M2 | 2025-09-22 12:30:00 | 2025-09-22 | 2025-09-22 16:30:00 | Routine Repairs | 1271245 | 18 Acresbush Close | 1200197 | Works Completed | Invoiced | 36/252 | 2025-09-22 12:30:00 | 21 days |  |  | Lainie Lavin | 03/09/2025 08:40 | No | Fully Complete | 2025-11-19 | Yes |  |  | Complete | 157.37
2025-08-04 17:57:00 | Cavity wall camera survey - check cavity and weep holes to ensure free from defect and make good | 2026-02-05 08:00:00 |  |  | Disrepair | 1124409 | 158 GILL AVENUE | 1200161 | Works Cancelled | Works Cancelled | 36/642 | 2026-02-05 08:00:00 | 20 days | 4: Other | 2026-02-17 11:21:34 | Shannon Slade | 01/09/2025 17:57 | No | Works Cancelled |  |  |  |  | Cancelled | 501.91
2025-08-04 15:55:00 | Leak from above flat, renew ducting /boarding behind bah, approx 2m2 total. paint afterwards, prep and repaint ceiling in full and bath wall in white. fit upvc cover strip to bath windowssill and seal all edges. have allowed extra m2 of ducting off diiculty arises with tiles areas. | 2026-01-06 08:00:00 | 2026-01-23 | 2026-01-06 11:07:00 | Routine Repairs | 1310607 | 8 Pawlett Road | 1166676 | Works Completed | Invoiced | 36/251 | 2025-09-16 09:00:00 | 21 days |  |  | Shannon Slade | 02/09/2025 15:55 | No | Post-completion Items To Complete | 2026-01-07 | Yes |  |  | Complete | 338.79
2025-08-04 15:55:00 | Leak from above flat, renew ducting /boarding behind bah, approx 2m2 total. paint afterwards, prep and repaint ceiling in full and bath wall in white. fit upvc cover strip to bath windowssill and seal all edges. have allowed extra m2 of ducting off d |  |  |  | Routine Repairs | 1310607 | 8 Pawlett Road | 1200120 | Works Cancelled | Works Cancelled | 36/499 |  | 21 days | 4: Other | 2026-06-17 12:48:16 | Shannon Slade | 02/09/2025 15:55 |  | Works Cancelled |  |  |  |  | Awaiting appointment date | 338.79
2025-08-04 15:41:00 | disrepair - JB bedroom 2 BC to carry out drone survey to front elevation. On the back of drone survey, bcc to carried recommended external works. Once ecxternal completed bcc to strip plaster back to brick internally to external widnow wall only. Bcc to treat brik, bcc to replaster affected wall. bcc to apply mist coat. bed 3 bcc carry out drone survey to front elevation. on the back of drone survey. bcc to carried recommendatio external works. bcc to strip plaster back to brick internally to external window wall. bcc to treat brick replaster affected wall apply mist coat. roof carryout drone survey | 2025-11-03 08:00:00 |  | 2026-05-22 11:21:00 | Disrepair | 1158425 | 17 THOMSON ROAD | 1200097 | Works Completed | ACE Agreed | 36/641 |  | 20 days |  |  | Shannon Slade | 01/09/2025 15:41 |  | Pre-completion Items To Complete |  | No |  | 02/07 - Unable to contact tenant voicemail left and email sent - CL - 05/06 - WORKS COMPLETED, WAITING FOR PICTURES. LMT RETURNED TO COMPLETE WORKS AS PER INSTRUCTION FROM DARREN. SCAFFOLD NOW OFF-HIRED. REMAINING WORKS TO BE SCHEDULED. 23/04- INTERNAL WORKS BOOKED FOR 14TH MAY, DECS BOOKED FOR 18TH MAY | Complete | 3343.17
2025-07-31 14:40:00 | Reissued job, as per prvious one aged please fit new base on two wall units which are bowed and replace kitchen plinth. can you update me once complete so i can let accessible homes know. | 2025-11-04 08:00:00 | 2025-11-04 | 2025-11-04 12:00:00 | Routine Repairs | 1296011 | 2 Chaundey Grove | 1198829 | Works Completed | Invoiced | 36/250 | 2025-11-04 08:00:00 | 21 days |  |  | Shannon Slade | 29/08/2025 14:40 | No | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 80.78
2025-07-30 17:09:00 | DISREPAIR SNAGGING |  |  | 2025-09-26 07:32:00 | Disrepair | 1110083 | 4 DERMOT STREET | 1184974 - 5776/1 | Works Completed | Invoiced | 36/637 |  | 20 days |  |  | Shannon Slade | 27/08/2025 17:09 |  | Post-completion Items To Complete | 2025-10-21 | Yes |  |  | Complete | 354.88
2025-07-30 07:00:00 | DAMP & MOULD Insulation as per BB tidy existing loft insulation ensuring there are no voids and overlay with 200mm of mineral wool insulation ensuring placement right up to the eaves | 2026-02-02 08:00:00 |  | 2026-01-22 13:06:00 | Routine Repairs | 1297401 | 93 COLESHILL DRIVE | 1194951 | Works Completed | ACE Agreed | 36/389 |  | 21 days |  |  | Shannon Slade | 28/08/2025 07:00 |  | Post-completion Items To Complete |  | No |  | 29/05 - SENT DARREN WALLIS TO GET PHOTOS FOR JOB. -Awaiting images from subcxontractor of loft works -2/4. Chased up again -8/4. | Complete | 980.5
2025-07-28 16:10:00 | Repair bathroom tiles, bedroom walls and ceiling, hall cupboard ceiling | 2025-11-03 08:00:00 | 2025-11-03 | 2025-10-31 12:09:00 | Routine Repairs | 1275394 | 40 CUTLER ROAD | 1196290 | Works Completed | Invoiced | 36/241 | 2025-10-29 08:00:00 | 21 days |  |  | Shannon Slade | 26/08/2025 16:10 | No | Fully Complete | 2025-12-22 | Yes |  |  | Complete | 862.31
2025-07-28 15:50:00 | Fit timber fillet under cladding; renew broken window handle | 2025-10-17 17:00:00 |  | 2025-09-19 13:33:00 | Routine Repairs | 1284646 | 16 Millground Road, Withywood, Bristol BS13 8NF | 1196471 | Works Completed | Invoiced | 36/242 | 2025-09-19 10:15:00 | 21 days |  |  | Shannon Slade | 26/08/2025 15:50 | No | Fully Complete | 2026-03-19 | Yes |  |  | Complete | 50.0
2025-07-28 14:29:00 | Ceiling repairs, anti-condensation paint, fan install, mortar and render repairs | 2025-11-18 08:00:00 | 2025-11-18 | 2025-11-04 15:07:00 | Routine Repairs | 1245529 | 49a Foxcote Road | 1196403 | Works Completed | ACE In Progress | 36/243 |  | 21 days |  |  | Shannon Slade | 26/08/2025 14:29 |  | Pre-completion Items To Complete | 2026-04-16 | Yes |  | 16/04 - KPI request sent - CL Unable to contact tenant as phone number is not working. Email sent to CM for additional contact details - CL | Complete | 828.13
2025-07-24 12:43:00 | Take down double-boarded kitchen ceiling; skim and paint | 2025-12-22 11:45:00 | 2025-12-22 | 2024-12-22 12:00:00 | Routine Repairs | 1314563 | 31 Tynte Avenue | 1194856 - 1798/1 | Works Completed | Invoiced | 36/246 | 2025-09-17 08:00:00 | 21 days |  |  | Shannon Slade | 21/08/2025 12:43 | Yes | Post-completion Items To Complete | 2026-01-07 | Yes |  |  | Complete | 1014.87
2025-07-24 09:49:00 | Fill holes around waste pipe under bath; fit new bath panel and boxing | 2025-09-15 08:00:00 | 2025-09-15 | 2025-10-29 13:45:00 | Routine Repairs | 1252875 | 144 LUCKWELL ROAD | 1194957 | Works Completed | Invoiced | 36/247 | 2025-09-15 09:45:00 | 21 days |  |  | Shannon Slade | 21/08/2025 09:49 | No | Post-completion Items To Complete | 2025-11-19 | Yes |  |  | Complete | 127.84
2025-07-21 11:46:00 | COMPLAINT WORKS AS PER TOM TAYLOR - mould treatment to various rooms and inspection of slabs in rear garden |  |  |  | Disrepair | 3785259 | 34 TREGARTH ROAD | 1192515 | New Works Instruction | Awaiting Cost Estimate | 36/640 |  | 20 days |  |  | Shannon Slade | 15/08/2025 11:46 |  | Suspended: Awaiting asbestos info |  |  |  |  | Cancelled | 0.0
2025-07-18 10:18:00 | Damp and Mould repairs - As per BB clean out guttering to property, remove and replace defective tiles to bathroom, remove and dispose of shower seat , reseal boxing in bathroom, overhaul window, all works as per Jeff Way schedule of works and survey recommendations. | 2025-10-30 08:00:00 |  | 2025-10-30 17:00:00 | Routine Repairs | 1225441 | 150 LEINSTER AVENUE | 1191762 | Works Completed | Invoiced | 36/732 | 2025-10-30 08:00:00 | 15 days |  |  | Shannon Slade | 07/08/2025 10:18 | No | Fully Complete | 2025-12-03 | Yes |  |  | Complete | 575.88
2025-07-17 14:54:00 | Damp and Mould as per BB tidy existing loft insulation and overlay with 250mm of mineral insulation ensuring placement up to the eaves. | 2026-06-23 08:00:00 |  |  | Routine Repairs | 1278984 | 201 FOUR ACRES | 1191303 | New Works Instruction | ACE Agreed | 36/877 |  | 15 days |  |  | Shannon Slade | 06/08/2025 14:54 |  | Pre-completion Items To Complete |  |  |  | 25/06 - Phone currently unavailable. Email sent to tenant to make contact - CL Awaiting confirmation of works from contractor - 27/3. Chased up -2/4. | Awaiting appointment date | 882.45
2025-07-17 14:46:00 | DAMP &amp; MOULD as per BB tidy existing loft insulation and Overlay existing with 100mm of mineral wool insulation ensure placement to the eaves. | 2025-11-28 12:00:00 |  | 2025-11-28 10:07:00 | Routine Repairs | 1275509 | 68 CUTLER ROAD | 1191252 | Works Completed | Invoiced | 36/876 |  | 15 days |  |  | Shannon Slade | 06/08/2025 14:46 |  | Fully Complete | 2025-12-04 | Yes |  |  | Complete | 515.0
2025-07-16 13:24:00 | Pre-inspection: front door does not shut properly | 2025-09-15 13:30:00 | 2025-09-15 | 2025-09-15 18:00:00 | Routine Repairs | 1284419 | 8 LULSGATE ROAD | 1190562 | Works Completed | Invoiced | 36/227 | 2025-09-15 13:30:00 | 21 days |  |  | Shannon Slade | 13/08/2025 13:24 | No | Fully Complete | 2025-11-21 | Yes |  |  | Complete | 123.06
2025-07-15 15:47:00 | Jeffway to renew bottom 3x kite winder and risers to stairs as soon as possible. please provide before and after picture bcc contact Luke Pomphrey luke.pomphrey@bristol.gov.uk | 2025-09-15 12:00:00 | 2025-09-15 | 2025-10-15 12:31:00 | Routine Repairs | 1273503 | 4 CHALCROFT WALK | 1190524 | Works Completed | Invoiced | 36/528 | 2025-09-15 13:45:00 | 21 days |  |  | Lainie Lavin | 12/08/2025 15:47 | No | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 174.39
2025-07-15 15:12:00 | DAMP &amp; MOULD As per BB tidy and relay existing loft insulation and overlay existing with 1oomm of mineral wool insulation, Clean and repair gutters and gutter defects as per Jeff way survey. |  |  | 2026-01-05 11:31:00 | Routine Repairs | 1277118 | 70 ELMTREE DRIVE | 1190082 | Works Completed | Invoiced | 36/879 |  | 15 days |  |  | Shannon Slade | 04/08/2025 15:12 |  | Fully Complete | 2026-01-07 | Yes |  |  | Complete | 456.17
2025-07-15 15:02:00 | Damp and Mould Insulation remove tenent belongings form loft and re-lay existing loft insulation ensuring placement to the eaves. |  |  | 2025-11-26 09:22:00 | Routine Repairs | 1283472 | 56 KEBLE AVENUE | 1189984 | Works Completed | Invoiced | 36/878 | 2025-11-26 09:21:00 | 15 days |  |  | Shannon Slade | 04/08/2025 15:02 | No | Fully Complete | 2025-11-28 | Yes |  |  | Complete | 314.56
2025-07-15 14:05:00 | Replace floorboards in rear bedroom and cupboard; overboard landing | 2025-10-27 08:00:00 | 2025-10-27 | 2025-10-27 16:15:00 | Routine Repairs | 1302109 | 12 Grinfield Avenue | 1189191 | Works Completed | Invoiced | 36/230 | 2025-10-27 08:00:00 | 21 days |  |  | Shannon Slade | 12/08/2025 14:05 | No | Fully Complete | 2025-11-24 | Yes |  |  | Complete | 640.21
2025-07-15 14:03:00 | Supply and fit internal bathroom door | 2025-09-25 08:00:00 | 2025-09-25 | 2025-09-25 11:30:00 | Routine Repairs | 1268413 | 2 Whitemead House | 1189121 | Works Completed | Invoiced | 36/231 | 2025-09-25 09:15:00 | 21 days |  |  | Shannon Slade | 12/08/2025 14:03 | No | Post-completion Items To Complete | 2025-09-25 | Yes |  |  | Complete | 212.75
2025-07-14 13:55:00 | Snagging repairs. As per Alvaro Ibanez. Living room. Patch on the wall (behind sofa) adjoining the bedroom needs decoration. Wall tested dry. - Left side trickle vent renewal.- Ceiling crack repairs.- Right side window gasket renovation.- Repairs 2 hole on wall.- Mould treatment on various areas. Kitchen. Paint over grout smudge on wall above newly tiled section of splashback. Porch. Mould treatment around front window/door frame. |  |  |  | Disrepair | 1313979 | 9 The Brambles Grinfield Avenue | 1188994 | New Works Instruction | ACE Agreed | 36/725 |  | 20 days |  |  | Shannon Slade | 08/08/2025 13:55 |  | Suspended: On hold |  |  |  | 15/05 - UPDATE FROM PREVIOUS TRACKER, ALL WORKS COMPLETED OTHER THAN MOULD TO THE L/ROOM. EMAIL ISSUED TO BCC. | Held BCC | 262.06
2025-07-10 12:34:00 | Renew kitchen ceiling following leak | 2025-09-22 08:00:00 | 2025-09-22 | 2025-09-04 11:41:00 | Routine Repairs | 1285638 | 56 Newland Road | 1187466 - 4439/1 | Works Completed | Invoiced | 36/233 |  | 21 days |  |  | Shannon Slade | 07/08/2025 12:34 |  | Post-completion Items To Complete | 2026-01-07 | Yes |  |  | Held Tenant | 595.56
2025-07-10 09:57:00 | Kitchen ceiling collapsed due to leak | 2025-09-19 09:00:00 | 2025-09-19 |  | Routine Repairs | 1300078 | 30 FULFORD ROAD | 1187344 | Works Started | ACE In Progress | 36/234 | 2025-09-19 08:30:00 | 21 days |  |  | Shannon Slade | 07/08/2025 09:57 | No | Pre-completion Items To Complete |  |  |  |  | Complete | 414.55
2025-07-09 14:19:00 | KITCHEN - Inspect main col-water pipe for leaks, due to excessive dampness on the wall. Renew skirting board damage by damaged by damp cols-water pipe. Renew mortice on back door. BEDROOM 1 - Mould wash on ceiling area, above front external wall. Mouls wash treatment on window.BEDROOM 2 - Mould wash on ceiling area, above rear external wall. Apply m | 2025-11-21 08:00:00 | 2025-11-21 | 2025-12-01 17:00:00 | Disrepair | 1213985 | 3 CHEPSTOW ROAD | 1042300 | Works Completed | Invoiced | 36/624 | 2025-11-21 08:00:00 | 20 days |  |  | Shannon Slade | 05/08/2025 14:19 | No | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 1983.82
2025-07-09 08:26:00 | JEFF WAY - Rising damp on party wall and chimney breast in living room on the right hand side of stack. FAO ROSANNA GARDINER |  |  | 2026-01-29 10:11:00 | Routine Repairs | 1255636 | 25 Martock Road, Bedminster, Bristol BS3 5QN | 1106058 | Works Completed | Invoiced | 36/195 | 2025-12-18 09:14:00 | 21 days |  |  | Shannon Slade | 06/08/2025 08:26 | No | Fully Complete | 2026-03-13 | Yes |  |  | Complete | 1466.74
2025-07-08 12:38:00 | Renew kitchen flooring, patch repair to living room ceiling | 2026-03-18 15:00:00 | 2001-01-01 | 2026-03-18 13:54:00 | Routine Repairs | 1310196 | 11 OXLEAZE | 1186460 | Works Completed | ACE In Progress | 36/235 | 2025-09-18 08:00:00 | 21 days |  |  | Shannon Slade | 05/08/2025 12:38 | No | Pre-completion Items To Complete |  | No |  | 11/06 - Unable to contact tenant, voicemail left - CL 29/05 - Works complete, struggling to gain access for photos, have been several times | Complete | 358.01
2025-07-07 13:36:00 | DISREPAIR |  |  | 2025-09-19 09:57:00 | Disrepair | 1214999 | 63 CONNAUGHT ROAD | 1185510 | Works Completed | Invoiced | 36/638 | 2025-09-19 09:58:00 | 20 days |  |  | Shannon Slade | 01/08/2025 13:36 | No | Fully Complete | 2025-09-19 | Yes |  |  | Complete | 672.57
2025-07-04 12:53:00 | Damp &amp; Mould-Fabric- relay loft insulation to eaves | 2025-10-23 08:00:00 |  | 2025-12-28 09:31:00 | Routine Repairs | 3079467 | 208 Ashton Drive, Ashton Vale, Bristol BS3 2QA | 1184774 | Works Completed | Invoiced | 36/761 | 2025-10-23 08:00:00 | 15 days |  |  | Lainie Lavin | 24/07/2025 12:53 | No | Fully Complete | 2025-12-04 | Yes |  |  | Complete | 393.2
2025-07-04 12:16:00 | : Inspect - please inspect the bathroom and pipes as tnt reports ongoing issue with leak from bathroom into room below. | 2025-09-19 08:00:00 | 2025-09-19 | 2025-10-31 09:18:00 | Routine Repairs | 1228951 | 15 Padstow Road, Knowle, | 1184738 | Works Completed | Invoiced | 36/550 |  | 21 days |  |  | Lainie Lavin | 01/08/2025 12:16 |  | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 342.29
2025-07-04 11:32:00 | (wc) PRE-INSPECT: The ceiling in my front room is cracked and breaking, where I think the plaster has blown | 2025-10-15 08:00:00 |  | 2025-10-17 12:39:00 | Routine Repairs | 1309315 | 93 Murford Avenue, Hartcliffe | 1184703 - 2067/1 | Works Completed | Invoiced | 36/518 |  | 21 days |  |  | Lainie Lavin | 01/08/2025 11:32 |  | Post-completion Items To Complete | 2026-01-07 | Yes |  |  | Complete | 589.76
2025-07-02 11:10:00 | Replace tiles around bath; tile shelf at back of bath | 2025-09-15 08:00:00 | 2026-09-15 | 2025-09-15 13:30:00 | Routine Repairs | 1195159 | 2 Curland Grove, Whitchurch | 1181732/4075/1 | Works Completed | Invoiced | 36/212 | 2025-09-15 08:00:00 | 21 days |  |  | Shannon Slade | 30/07/2025 11:10 | No | Fully Complete | 2025-12-15 | Yes |  |  | Complete | 327.76
2025-07-02 08:21:00 | JEFF WAY - 5 new 300 x 300 new floor tiles in the kitchen and a dope threshold internally. Varnish back door ro prevent penetrating damp FAO ASHLEY SMITH | 2025-12-10 09:00:00 |  | 2025-12-10 10:57:00 | Routine Repairs | 1224324 | 28 Kildare Road, Knowle, | 1166788 | Works Completed | Invoiced | 36/540 | 2025-12-10 09:00:00 | 21 days |  |  | Lainie Lavin | 30/07/2025 08:21 | No | Fully Complete | 2026-02-27 | Yes |  |  | Complete | 146.35
2025-07-02 08:09:00 | Jeffway-As per Ian Ogborne-KITCHEN REPAIRS , BATHROOM FLOORING AND PANEL , OUT BUILDING ROOF AND REPAIRS | 2026-06-05 08:15:00 |  |  | Routine Repairs | 1282651 | 139 Ilchester Crescent | 5599/1 | New Works Instruction |  | 36/1484 |  | 35 days |  |  | Carlene Lynette Lynch | 19/08/2025 08:09 |  | Pre-completion Items To Complete |  |  |  | 05/06 - SCAFFOLD BEING ERECTED 11TH JUNE | Next Appointment Needed | 2280.83
2025-07-01 13:00:00 | Repair damaged window cill | 2025-10-13 12:00:00 | 2025-10-13 | 2025-10-13 14:41:00 | Routine Repairs | 1074153 | 70 TROWBRIDGE ROAD | 1167961 | Works Completed | Invoiced | 36/112 | 2025-10-13 12:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 78.35
2025-07-01 13:00:00 | Remove trunking from hole in wall, rebrick the hole, bond and plaster, replace damaged tiles | 2025-12-18 08:00:00 | 2025-12-18 | 2026-03-05 09:47:00 | Routine Repairs | 1173699 | 5 DERWENT ROAD | 1168151 | Works Completed | ACE Agreed | 36/113 | 2025-12-18 08:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL | Complete | 261.4
2025-07-01 13:00:00 | erect scaffold, renew gutters to front elevation complete. Renew waste to kitchen sink | 2026-07-13 08:00:00 | 2026-07-13 |  | Routine Repairs | 2199044 | BK 15-16 BOUVERIE STREET | 1177553 | New Works Instruction | ACE Agreed | 36/116 |  | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 |  | Pre-completion Items To Complete |  |  |  | 20/04 - Contact details received from NS. Email sent to confirm which address needed pipe renewal - CL Asbestos report received from EM - CL Asbestos report request sent - CL asbestos survey only received on 27/03, so action from then., | Appointment booked | 2216.9
2025-07-01 13:00:00 | Top up loft insulation 50m2 | 2025-10-14 08:00:00 | 2025-10-14 | 2025-10-14 16:30:00 | Routine Repairs | 1101253 | 22 The Gaskins, Downman Road, Lockleaze, Bristol, BS7 9TS | 1174266 | Works Completed | Invoiced | 36/118 | 2025-10-14 08:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 515.0
2025-07-01 13:00:00 | Relay Loft insulation 40m2, insulate loft hatch | 2026-04-10 08:00:00 | 2026-04-10 | 2026-04-10 08:19:00 | Routine Repairs | 1175968 | 22 Gingells Green | 1174904 | Works Completed | ACE Agreed | 36/119 |  | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 |  | Pre-completion Items To Complete | 2026-04-16 | Yes |  | 16/04 - KPI request sent - CL Appointment booked with tenant for loft insulation to be carried out on 10/04- CL | Complete | 478.13
2025-07-01 13:00:00 | Clean out gutters, infill small hole in render, paint bathroom ceiling in anti condensation paint | 2026-01-07 08:00:00 | 2026-05-07 | 2026-05-07 19:13:00 | Routine Repairs | 1229749 | 16 PEVENSEY WALK | 1185736 | Works Completed | ACE Agreed | 36/121 | 2026-01-07 08:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 29/06 - KPI requested - CL 06/05 - Appointment rescheduled to 07/05 - CL WORKS BOOKED FOR 05/05. | Complete | 241.91
2025-07-01 13:00:00 | Fill hole in brickwork | 2026-03-27 17:00:00 |  | 2026-03-27 10:02:00 | Routine Repairs | 1192774 | 6 Brocks, Callington Road, Brislington, Bristol BS4 5BX | 1186014 | Works Completed | Invoiced | 36/123 | 2026-03-27 17:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Pre-completion Items To Complete | 2026-04-29 |  |  | 28/05 - KPI received - CL 29/04 - KPI requested - CL Tenant said there is no hole internally or externally in property/flat - 27/3. | Complete | 50.0
2025-07-01 13:00:00 | Top up loft insulation and replaster window wall to bed 1. | 2025-10-29 08:00:00 | 2025-10-29 | 2025-10-29 11:15:00 | Routine Repairs | 1226104 | 28 LURGAN WALK | 1183341 | Works Completed | Invoiced | 36/124 | 2025-10-29 08:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Fully Complete | 2026-01-07 | Yes |  |  | Complete | 640.68
2025-07-01 13:00:00 | Top up loft insulation | 2025-12-02 08:00:00 | 2025-12-02 | 2026-01-28 13:53:00 | Routine Repairs | 1303055 | 2 HARTGILL CLOSE | 1183301 | Works Completed | ACE Agreed | 36/125 | 2025-09-09 08:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Pre-completion Items To Complete | 2026-03-13 | Yes |  | 16/04 - KPI request chased - CL 07/04 - KPI request added and sent to EH - CL | Complete | 412.0
2025-07-01 13:00:00 | Tile bathroom 4sqm. Tile kitchen splashback - approx 3.5m2 | 2026-04-24 14:00:00 | 2026-04-24 | 2026-04-24 09:21:00 | Routine Repairs | 1206242 | 14 The Coots | 1185430 | Works Completed | ACE Agreed | 36/127 | 2026-04-24 08:31:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Pre-completion Items To Complete | 2026-05-08 | Yes |  | 08/05 - KPI requested - CL 22/04 - Appointment arrange with tenants mother for DW to attend in morning to check over the WC. Awaiting a call back from tenants mother regarding getting the flooring laid on 23/04 and 24/04. Appointment confirmed with tenant | Complete | 2070.33
2025-07-01 13:00:00 | Top up insulation, clean gutters and repair brickwork by rear window cill | 2026-07-10 12:00:00 | 2026-07-10 |  | Routine Repairs | 1236540 | 11 Wardour Road | 1188116 | New Works Instruction | ACE Agreed | 36/128 |  | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 |  | Pre-completion Items To Complete |  |  |  | 30/06 - Appointment rescheduled at residents request - CL 16/06 - Appointment rescheduled at tenant request - CL 27/04 - Appointment booked for 27/05, Awaiting a date for gutter clean - CL21/04 - Email received from tenant with contact number - CL 20/04 - Email details received from BB. Email sent to tenant to make contact. Email sent to AG and BB as numbers supplie | Appointment booked | 439.88
2025-07-01 13:00:00 | Clear gutters and top up loft insulation | 2026-04-23 13:00:00 | 2026-04-23 | 2026-03-23 08:26:00 | Routine Repairs | 1201974 | 23 Morden Walk | 1188072 | Works Completed | ACE Agreed | 36/129 | 2026-03-24 08:23:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 15/04 - KPI request sent - CL | Complete | 103.8
2025-07-01 13:00:00 | Ventilator and wall hack replaster and insulation | 2026-06-16 10:00:00 |  |  | Routine Repairs | 1237736 | 62 Willinton Road | 1176914 | New Works Instruction | ACE Agreed | 36/130 |  | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 |  | Pre-completion Items To Complete |  |  |  | 02/07 - Review needed to assess on what is required - CL 18/06 - Awaiting JIS from DW - CL 12/06 - Site inspection booked with tenant - CL 11/5 - no answer, attempt to contact again (LL).13/04 - Unable to make contact with tenant voicemail and text message sent - CL Asbestos reported requested - CL asbestos report received on the 27/03, works now to be booked | Manager review needed | 448.05
2025-07-01 13:00:00 | Carry out window repairs |  |  |  | Routine Repairs | 1083449 | 5 MORRIS ROAD | 1177431 | Works Cancelled | Works Cancelled | 36/131 |  | 21 days | 4: Other | 2026-06-02 13:37:12 | Charlie Higginson | 29/07/2025 13:00 |  | Works Cancelled |  |  |  |  | Cancelled | 911.23
2025-07-01 13:00:00 | VARIOUS WORKS |  |  |  | Routine Repairs | 1016804 | 103 Henacre Road | 1183952 | Works Cancelled | Works Cancelled | 36/132 |  | 21 days | 4: Other | 2026-06-02 13:22:41 | Charlie Higginson | 29/07/2025 13:00 |  | Works Cancelled |  |  |  | 02/06 - Unable to make contact with tenant, voicemail left - CL 11/5 - added asbestos report, sent from chloe.11/5 - chased up asbestos survey appointment awaiting response from surveyor (LL). 23/04 - Envirocall have been unable to arrange a date with tenant. Contact details received. Awaiting appointment date from En | Cancelled | 1566.57
2025-07-01 13:00:00 | replace fans in kitchen and bathroom. Replace trickle vents on all windows throughout property. Install thermovent 100 to replace existing passive vents in all 3 bedrooms. Remove RH bedroom door and cut to allow from 10mm undercut and rehand. Clean and serviceall windows throughout | 2026-05-11 12:00:00 | 2026-05-11 | 2026-04-23 18:44:00 | Routine Repairs | 1064228 | 13 PEVERELL CLOSE | 1188623 | Works Completed | ACE Agreed | 36/135 | 2025-12-08 11:15:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Pre-completion Items To Complete | 2026-06-12 | Yes |  | 12/06 - KPI requested - CL 18/5 - on held as awaiting for vo approval from BCC. 27/04 - Appointment booked with tenant for work to be complete - CL Follow on appointment for fan replacements on 31/03 - CL, No Access on 31/03 will get compliance to try again. 08/04 - CHASER EMAIL ISSUED TO D&M TO BOOK WORKS IN. 09/04 - ELECTRICAL WORK | Complete | 923.47
2025-07-01 13:00:00 | tidy existing loft insulation and overlay with additional 100mm of mineral insulation paying attention to ensure insulation is placed to eaves | 2025-10-24 11:45:00 | 2025-10-24 | 2025-09-05 10:00:00 | Routine Repairs | 1093749 | 25 MONTREAL AVENUE | 1189176 | Works Completed | Invoiced | 36/136 |  | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 |  | Fully Complete | 2026-01-07 | Yes |  |  | Complete | 453.2
2025-07-01 13:00:00 | building fabric hack off/re render under bed 1 ba window | 2025-11-07 08:00:00 | 2025-11-07 | 2025-11-04 16:00:00 | Routine Repairs | 1180263 | 13 LAVINGTON ROAD | 1189446 - 4394/3 | Works Completed | Invoiced | 36/137 | 2025-11-04 08:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Post-completion Items To Complete | 2025-12-03 | Yes |  |  | Complete | 169.14
2025-07-01 13:00:00 | Remove water damaged ceiling in kitchen cupboard, fix new plasterboard ceiling, skim, paint | 2025-11-14 08:00:00 | 2025-11-14 | 2025-12-17 12:23:00 | Routine Repairs | 1118930 | 24 Brockworth Crescent | 1125985 | Works Completed | Invoiced | 36/138 | 2025-12-17 08:00:00 | 21 days |  |  | Charlie Higginson | 29/07/2025 13:00 | No | Fully Complete | 2026-01-07 | Yes |  |  | Complete | 77.29
2025-06-26 09:53:00 | External door/window frame sealant, weatherboard, draught strip, handrail extension | 2025-09-30 08:00:00 | 2025-09-30 | 2025-09-17 13:30:00 | Routine Repairs | 1315680 | 5 Whitmead Gardens | 1180740 | Works Completed | Invoiced | 36/214 | 2025-09-17 11:30:00 | 21 days |  |  | Shannon Slade | 24/07/2025 09:53 | No | Fully Complete | 2025-12-15 | Yes |  | 09/04 - KPI received and uploaded - CL | Complete | 240.77
2025-06-24 11:27:00 | Disrepair woirks |  | 2025-09-10 | 2025-09-10 09:05:00 | Disrepair | 1255056 | 143 MARKSBURY ROAD | 1179251 | Works Completed | Invoiced | 36/636 |  | 20 days |  |  | Shannon Slade | 21/07/2025 11:27 |  | Fully Complete | 2025-10-21 | Yes |  |  | Complete | 1200.71
2025-06-23 12:05:00 | Plastering and painting repairs around front door and bedroom | 2026-01-20 08:00:00 | 2026-01-20 | 2026-01-20 09:30:00 | Routine Repairs | 1277050 | 57 Elmtree Drive, Withywood, Bristol | 1178696 | Works Completed | Invoiced | 36/216 | 2025-09-16 08:00:00 | 21 days |  |  | Shannon Slade | 21/07/2025 12:05 | No | Fully Complete | 2026-01-30 | Yes |  |  | Complete | 78.64
2025-06-20 15:36:00 | Fit 4.2m mop stick handrail to stairs | 2025-10-13 08:00:00 | 2025-10-13 | 2025-10-13 12:00:00 | Routine Repairs | 1227594 | 93 NEWQUAY ROAD | 1177829 | Works Completed | Invoiced | 36/218 | 2025-10-13 08:00:00 | 21 days |  |  | Shannon Slade | 18/07/2025 15:36 | No | Fully Complete | 2025-10-14 | Yes |  |  | Complete | 113.96
2025-06-19 12:57:00 | Hack off loose plaster ceiling and re-skim | 2026-06-18 15:15:00 | 2026-06-18 | 2026-06-18 12:11:00 | Routine Repairs | 1313106 | 20 Stillingfleet Road | 1177729 | Works Completed | ACE In Progress | 36/219 | 2026-04-16 08:00:00 | 21 days |  |  | Shannon Slade | 17/07/2025 12:57 | No | Pre-completion Items To Complete |  | Yes |  | 10/06 - Appointment confirmed with tenant - CL 28/05 - WORKS NEED TO BE REARRANGED DUE TO OPERATIVE SICKNESS. Tenant called to reschedule appointment from 14/04 to the 16/04 CL Unable to contact tenant, voicemail left and text message sent to make contact. | Complete | 604.62
2025-06-19 10:01:00 | Taps, shower pump, sealant, patch render, patio lock | 2025-09-18 08:00:00 | 2025-09-18 | 2025-09-18 13:15:00 | Routine Repairs | 1269121 | 4 Wimborne Road | 1177531 | Works Completed | Invoiced | 36/220 | 2025-09-18 08:00:00 | 21 days |  |  | Shannon Slade | 17/07/2025 10:01 | No | Post-completion Items To Complete | 2025-09-25 | Yes |  |  | Complete | 542.66
2025-06-16 19:18:00 | D&amp;M Repairs Jeff Way Insulation | 2025-10-16 12:00:00 | 2025-10-16 | 2025-11-19 14:38:00 | Routine Repairs | 1194190 | 20 Cowling Drive, Stockwood, Bristol BS14 8DS | 1176130 | Works Completed | Invoiced | 36/764 |  | 15 days |  |  | Lainie Lavin | 04/07/2025 19:18 | No | Fully Complete | 2025-12-03 | Yes |  |  | Complete | 360.5
2025-06-16 11:40:00 | Fill, repair and redecorate landing ceiling | 2025-09-17 11:30:00 | 2025-09-17 | 2025-09-17 16:30:00 | Routine Repairs | 1292882 | 363 Bishport Avenue, Hartcliffe | 1175766 | Works Completed | Invoiced | 36/221 | 2025-09-17 11:30:00 | 21 days |  |  | Shannon Slade | 14/07/2025 11:40 | No | Post-completion Items To Complete | 2025-11-21 | Yes |  |  | Complete | 89.92
2025-06-12 11:17:00 | JEFF WAY - BATH PANEL , TILES IN BATHROOM , PLASTER AND PAINTING FAO IAN OGBORNE | 2025-11-18 12:15:00 | 2025-11-18 | 2025-10-24 09:05:00 | Routine Repairs | 1312476 | 54 Rowan House, Bishport Avenue, Hartcliffe, Bristol BS13 0RT | 1174546 | Works Completed | Invoiced | 36/679 | 2025-09-18 12:00:00 | 15 days |  |  | Lainie Lavin | 02/07/2025 11:17 | No | Post-completion Items To Complete | 2025-12-19 | Yes |  |  | Complete | 231.11
2025-06-12 09:06:00 | Rapleys works order window mounted extractor to bathroom paint bedroom 2 4m2 gutter clean with vacuum paint bathroom 4m2 |  |  | 2025-09-24 12:29:00 | Routine Repairs | 1286904 | 61 Queens Road | 1070244 | Works Completed | Invoiced | 36/170 |  | 21 days |  |  | Shannon Slade | 10/07/2025 09:06 |  | Post-completion Items To Complete | 2025-09-24 | Yes |  |  | Complete | 259.5
2025-06-12 08:00:00 | Loft insulation | 2025-10-28 11:45:00 | 2025-10-28 | 2025-10-13 16:15:00 | Routine Repairs | 1040966 | 12 Ashburton Road | 1174893 | Works Completed | Invoiced | 36/87 | 2025-10-13 10:30:00 | 21 days |  |  | Shannon Slade | 10/07/2025 08:00 | No | Fully Complete | 2025-12-03 | Yes |  |  | Complete | 463.5
2025-06-12 08:00:00 | Loft insulation | 2025-11-24 08:00:00 | 2025-11-25 |  | Routine Repairs | 1066553 | 109 RINGWOOD CRESCENT | 1174896 | New Works Instruction | ACE Agreed | 36/88 |  | 21 days |  |  | Shannon Slade | 10/07/2025 08:00 |  | Suspended: Awaiting Client Action/Response |  |  |  | 11/5 - emailed BB for an update (LL). 14/04 - Email sent to contractor on confirming if work has been completed - CL emailed contractor if works have been done, awaiting update - 2/4. | Held BCC | 360.5
2025-06-12 08:00:00 | Loft insulation and sealant to bath | 2025-10-22 12:15:00 | 2025-10-22 | 2026-03-26 15:41:00 | Routine Repairs | 1189522 | 155 Whiteway Road | 1174902 | Works Completed | ACE Agreed | 36/89 | 2025-10-22 11:15:00 | 21 days |  |  | Shannon Slade | 10/07/2025 08:00 | No | Post-completion Items To Complete | 2026-04-16 | Yes |  | 16/04 - KPI request sent - CL | Complete | 422.94
2025-06-12 08:00:00 | Jeffway to repair wall | 2025-10-21 08:00:00 | 2025-10-21 | 2025-10-21 11:21:00 | Routine Repairs | 1297456 | 8 COLLINSON ROAD | 1176125 | Works Completed | ACE Agreed | 36/90 | 2025-10-21 08:00:00 | 21 days |  |  | Shannon Slade | 10/07/2025 08:00 | No | Pre-completion Items To Complete | 2026-04-29 | Yes |  | 29/04 - KPI requested - CL | Complete | 90.36
2025-06-11 09:56:00 | D&amp;M Repairs Loft Insulation &amp; Gutter Repairs | 2025-10-03 08:00:00 |  | 2025-11-21 14:33:00 | Routine Repairs | 1092064 | 31 Lockleaze Road, Horfield | 1173911/1570/1 | Works Completed | Invoiced | 36/671 | 2025-10-03 08:00:00 | 15 days |  |  | Lainie Lavin | 01/07/2025 09:56 | No | Fully Complete | 2025-12-09 | Yes |  |  | Complete | 926.78
2025-06-10 11:53:00 | Rapleys Works Order - Damp & Mould 12 sqm Mould wash - bathroom | 2026-03-13 12:00:00 | 2026-03-13 | 2026-03-13 15:49:00 | Urgent Repair | 1306678 | 3 MELLENT AVENUE | 1173233 | Works Completed | ACE Agreed | 36/200 |  | 7 days |  |  | Shannon Slade | 18/06/2025 11:53 |  | Pre-completion Items To Complete | 2026-04-16 | Yes |  | 16/04 - KPI request sent - CL works already completed | Complete | 50.0
2025-06-10 09:57:00 | Rapleys Works Order - Damp & Mould Replace window gaskets -4lm 7 Bathroom - remove existing ceiling, install thermal board, skim coat, redec Insulate pipework 3lm -WC Gutter & Downpipe clean throughout | 2025-09-16 08:00:00 | 2026-07-24 |  | Routine Repairs | 1306678 | 3 MELLENT AVENUE | 001173225 | New Works Instruction | ACE In Progress | 36/201 |  | 21 days |  |  | Shannon Slade | 08/07/2025 09:57 |  | Pre-completion Items To Complete |  |  |  | 25/06- BCC CALLED TO REARRANGE TENANTS APPOINTMENT. REBOOKED FOR 24TH AND 28TH JULY 29/05 - WORKS BOOKED FOR 29TH JUNE AND 3RD JULY. WAITING FOR ABESTOS REPORT FROM CHLOE. Awaiting Job info sheet | Appointment booked | 1871.52
2025-06-10 08:26:00 | JEFF WAY - AS PER ROB DOIDGE - FIT NEW EXTRACTOR FAN TO BATHROOM IN PLACE OF PASSIVE VENT. TREAT AND PAINT ALL MOULD TO BATHROOM CEILING / SLOPES IN FULL AND TO DOWNSTAIRS WC WALLS WHERE REQUIRED. APPROX 6M2 TOTAL PLUS 3 UPLIFT. REFIX LOOSE HANDRAIL TO TOP OF STAIRS AND RENEW APPROX 1 LIN M SECTION TO REAR TIMBER FASCIA / SOFFIT, RHS OF REAR ELEVATION. TOWER SCAFF REQUIRED . UNBLOCK GULLY TO SIDE OF PROPERTY JUST PAST FRONT DOOR. | 2025-10-24 08:00:00 | 2025-10-24 | 2025-10-24 09:12:00 | Routine Repairs | 1290773 | 34 TYNTESFIELD ROAD | 1172808 | Works Completed | Invoiced | 36/202 |  | 21 days |  |  | Shannon Slade | 08/07/2025 08:26 |  | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 1341.24
2025-06-09 16:01:00 | JEFF WAY - 2 X EXTRATOR FANS , SINK BACKSPLASH TILES , STAIRCASE OVERHAUL , DECS , SILICONE WINDOW FAO IAN OGBORNE |  |  | 2025-08-21 07:28:00 | Routine Repairs | 1255625 | 24 Martock Road, Bedminster | 1172395 | Works Completed | Invoiced | 36/203 |  | 21 days |  |  | Shannon Slade | 07/07/2025 16:01 |  | Fully Complete | 2025-10-24 | Yes |  |  | Complete | 1063.57
2025-06-09 15:00:00 | JEFF WAY - Bathroom extractor fan, mould wash, external doors to be painted, refix floor tiles. | 2025-10-01 08:00:00 | 2025-10-01 | 2025-10-01 12:00:00 | Routine Repairs | 1292462 | 279 Bishport Avenue, Hartcliffe | 1172307 | Works Completed | Invoiced | DN568207/78 | 2025-10-01 08:00:00 | 21 days |  |  | Shannon Slade | 07/07/2025 15:00 | No | Fully Complete | 2025-12-03 | Yes |  |  | Complete | 645.12
2025-06-09 12:53:00 | Wall in back garden is cracked along cement beds in several places making it wobble and unsafe tenant has two young kids |  | 2025-06-26 | 2025-06-26 07:35:00 | Urgent Repair | 1291992 | 57 Aldwick Avenue | 1172152 | Works Completed | Invoiced | DN568207/74 |  | 7 days |  |  | Shannon Slade | 17/06/2025 12:53 |  | Fully Complete | 2025-10-24 | Yes |  |  | Complete | 50.0
2025-06-09 12:11:00 | Rewire 3 bed property |  |  |  | Routine Repairs | 1853027 | 93 King Georges Road | 1172060 | New Works Instruction | ACE Agreed | DN568207/73 |  | 21 days |  |  | Shannon Slade | 07/07/2025 12:11 |  | Suspended: On hold |  |  |  | 02/06 - Still on hold with CO - CL 01/06 - Email sent MF for update - CL 11/5 - chased up update from CO (LL). Chased up an update from ciaran.o'bern@bristol.gov.uk -7/5 FOLLOWING SHANNONS PREVIOUS EMAIL -7/5 LL. Confirmed with surveyor to keep on held -8/5. | Held BCC | 3274.57
2025-06-09 11:57:00 | 1st Floor hall window bottom left patch repair to render hack off renew and paint left side of front door rack out crack and refill and dec both repairs | 2025-11-10 12:00:00 | 2025-11-10 | 2025-12-18 15:13:00 | Routine Repairs | 1269314 | 31 Windsor Terrace | 1172047 | Works Completed | Invoiced | DN568207/72 |  | 21 days |  |  | Shannon Slade | 07/07/2025 11:57 |  | Post-completion Items To Complete | 2025-12-19 | Yes |  |  | Complete | 554.51
2025-06-06 10:58:00 | Mist Coat and 2 x coats of white emulsion to kitchen ceiling on new plaster. Approx 10m2 | 2025-09-22 12:15:00 | 2025-09-22 | 2025-11-07 08:25:00 | Routine Repairs | 1299598 | 10 Faber Grove (KS1753) | 1171059 | Works Completed | Invoiced | DN568207/69 | 2025-09-17 08:00:00 | 21 days |  |  | Shannon Slade | 04/07/2025 10:58 | No | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 151.6
2025-06-04 11:41:00 | Firstly check under bath to ensure no leaks prior to renewing damaged section of kit ceiling, approx 4m2 and then full repaint to ceiling approx 10m2 | 2025-09-16 10:00:00 | 2025-09-16 | 2025-09-22 11:00:00 | Routine Repairs | 1265936 | 4 Sydney Row | 1169952 | Works Completed | Invoiced | DN568207/65 | 2025-09-15 09:00:00 | 21 days |  |  | Shannon Slade | 02/07/2025 11:41 | No | Fully Complete | 2025-12-03 | Yes |  |  | Complete | 337.06
2025-05-30 14:45:00 | PREINSPECT -- tnt reporting issues with ramp going up to front door cracks showing and is raised causing trip hazard, please assess. | 2025-09-16 12:00:00 |  | 2025-09-16 14:00:00 | Routine Repairs | 1317506 | 20 Wymbush Crescent, Hartcliffe | 1167490 - 92561/1 | Works Completed | Invoiced | 36/673 | 2025-09-16 13:15:00 | 15 days |  |  | Lainie Lavin | 19/06/2025 14:45 | No | Fully Complete | 2026-04-14 |  |  |  | Complete | 57.32
2025-05-30 14:40:00 | Pre-inspection-inspect the path, the concreate is breaking up in places and has large cracks. | 2025-09-17 08:00:00 | 2026-02-12 | 2026-02-12 10:48:00 | Routine Repairs | 1277061 | 59 Elmtree Drive, Withywood | 1167479 | Works Completed | Invoiced | 36/520 |  | 21 days |  |  | Lainie Lavin | 27/06/2025 14:40 |  | Fully Complete | 2026-02-12 | Yes |  |  | Complete | 312.48
2025-05-29 11:04:00 | JEFF WAY - Refix loose timber door frame on landing front bedroom. Repair plasterwork to side of door frame to match artex finish. Hack off hollow plasterwork to mid wall rear bedroom, rebond to match existing levels and reskim to suit. Mist coat to cover new plaster FAO JEFF NECK | 2025-09-25 08:00:00 | 2025-09-25 | 2025-09-23 09:45:00 | Routine Repairs | 1314983 | 32 Upjohn Crescent | 1166767 | Works Completed | Invoiced | 36/533 | 2025-09-23 08:00:00 | 21 days |  |  | Lainie Lavin | 26/06/2025 11:04 | No | Post-completion Items To Complete | 2026-01-30 | Yes |  |  | Complete | 163.44
2025-05-28 15:31:00 | Install 2 x Axia Rivi7 with 2 core drills (bathroom and kitchen) | 2026-04-15 10:15:00 | 2026-04-15 |  | Urgent Repair | 1295267 | 43 Bourchier Gardens, Hartcliffe, | 1166442 | New Works Instruction | ACE Agreed | 36/526 |  | 7 days |  |  | Lainie Lavin | 05/06/2025 15:31 |  | Suspended: Awaiting Client Action/Response |  |  |  | 11/5 - chased up on how to proceed (LL).20/04 - Email sent to BCC on how to proceed - CL. Chased up email to surveyor following carlenes email - 7/5. | Held BCC | 999.22
2025-05-28 15:22:00 | ROF - several tiles not sitting right around chimney allowing water ingress | 2026-03-23 14:00:00 | 2025-10-01 | 2025-10-27 13:59:00 | Urgent Repair | 1295267 | 43 Bourchier Gardens, Hartcliffe, | 1166427 | Works Completed |  | 36/525 | 2025-09-17 10:15:00 | 7 days |  |  | Lainie Lavin | 05/06/2025 15:22 | No | Post-completion Items To Complete | 2026-05-14 |  |  |  | Complete | 50.0
2025-05-25 15:33:00 | REPAIR JEFFWAY Damp & Mould AS PER NICHOLAS CORY REMOVE X3 BRICK ON SIDE ELV CORRESPONDING WITH DAMP PATCH GOING UP STAIRS, RENEW X6 BRICKS , FILL HOLES AND RE POINT , INSIDE RENEW BOTTOM ROW OF TILES IN BATHROOM AND 2M2 AVOVE BATH AND NEXT TO WINDOW , HACK OFF PLASTER FROM UNDER WINDOW IN STAIRS TO FRONT ELEV | 2025-11-06 12:00:00 | 2025-11-06 | 2025-11-06 21:00:00 | Routine Repairs | 1239823 | 138 Bedminster Road, Bedminster, Bristol, BS3 5NP | 1164310 | Works Completed | Invoiced | 36/554 | 2025-11-06 17:15:00 | 21 days |  |  | Lainie Lavin | 24/06/2025 15:33 | No | Post-completion Items To Complete | 2025-12-18 | Yes |  |  | Complete | 837.2
2025-05-23 13:45:00 | Mould treatment to kitchen and bathroom ceilings, hall ceiling and walls at high level, replace secttion of worktop to kitchen and seal, overhaul bathroom extractor fan, no power and wipe down mould from bathroom window and reveals | 2026-02-13 10:45:00 |  | 2026-02-13 13:22:00 | Disrepair | 1008715 | 39 BARWICK HOUSE THE RIDGE | 1161378 | Works Completed | Invoiced | 36/634 | 2026-02-11 09:00:00 | 20 days |  |  | Shannon Slade | 20/06/2025 13:45 | No | Fully Complete | 2026-03-02 | Yes |  |  | Complete | 1644.68
2025-05-21 16:35:00 | Complaint works as per tom taylor - bed 1 overhaul window. Bed 2 - overhaul window, stain block area of staining to the front corner of the wall in W.C, remove flaking paint and redec affected area |  | 2026-07-27 |  | Disrepair | 1025189 | 154 Mancroft Avenue | 1163169 | New Works Instruction | ACE Agreed | 36/635 |  | 20 days |  |  | Shannon Slade | 18/06/2025 16:35 |  | Pre-completion Items To Complete |  |  |  | 17/06 - NO ACCESS ON LAST APPOINTMENT, REARRANGED FOR 27TH JULY. ISSUED TO BCC TO SEND ACCESS LETTER. 19/03 - NO ACCESS ON 5TH MAY. WORKS BOOKED FOR 29TH MAY. -WORKS BOOKED FOR 13TH AND 14TH APRIL - TL IS GOING TO GET ASSISTANCE FROM HOUSING OFFICE ALSO. 15/04 - LOFT WORKS COMPLETED.REMAINING WORKS TO BOOKED FOR 5TTH MAY. | WIP | 2245.2
2025-05-21 16:28:00 | JEFF WAY - FRONT DOOR / PORCH, PLEASE REMOVE DOORMAT AND FILL THE GAP IN FLOOR UP TO REST OF FLOOR LEVEL, TNT KEEPS TRIPPING, FILL WITH APPROPRIATE MATERIAL AS PER ROB DOIDGE | 2025-09-17 08:00:00 | 2025-09-17 | 2025-09-17 11:20:00 | Routine Repairs | 1195308 | 39 Davids Road, Knowle | 1163171 | Works Completed | Invoiced | 36/530 | 2025-09-17 08:00:00 | 21 days |  |  | Lainie Lavin | 19/06/2025 16:28 | No | Fully Complete | 2025-10-17 | Yes |  |  | Complete | 75.0
2025-05-14 08:00:00 | Replace extractor fan to bathroom |  |  |  | Disrepair | 1192683 | 3 CALLINGTON ROAD | 1159019 | New Works Instruction | Awaiting Cost Estimate | 36/633 |  | 20 days |  |  | Shannon Slade | 11/06/2025 08:00 |  | Suspended: Awaiting asbestos info |  |  |  |  | Complete | 0.0
2025-05-13 10:50:00 | DAMP & MOULD REPAIR AS PER BARRIE BARKER JEFF WAY TO REPOINT BRICKWORK 1 LM AROUND PROPERTY, REPAIR CRACKED AND DAMAGED BRICKS TO THE RIGHT OF REAR DOOR, REMOVE 3 BRICKS ALL ELEVATIONS TO INSPECT CONDITION OF CAVITY WALL INSULATION AND REPLACE. PLEASE CONTACT ME WHEN ATTENDING SITE SO I CAN INSPECT. |  |  |  | Routine Repairs | 1237098 | 16 Wellgarth Walk, Knowle, | 1157530 | New Works Instruction | ACE Agreed | 36/547 |  | 21 days |  |  | Lainie Lavin | 11/06/2025 10:50 |  | Suspended: Awaiting Client Action/Response |  |  |  | 11/5 - Req update from BB (LL).14/04 - BB will make some enquiries and get back to me - CL Email sent to BB on how to proceed - CL. Emailed BB for update on carlenes email -7/5. | Held BCC | 155.18
2025-05-13 10:20:00 | JEFF WAY - WINDOW OVERHAUL AS PER IAN OGBORNE. |  | 2025-09-01 | 2025-09-01 15:13:00 | Routine Repairs | 1300432 | 99 Fulford Road, Hartcliffe, Bristol BS13 0AD | 1157979 | Works Completed | Invoiced | 36/677 |  | 15 days |  |  | Lainie Lavin | 03/06/2025 10:20 |  | Post-completion Items To Complete | 2025-09-17 | Yes |  |  | Complete | 109.02
2025-04-30 16:20:00 | Gutter clearance front and rear and replacement of at least 1 bracket above front door canopy causing gutter to overflow, possibly also one to rear. |  |  |  | Routine Repairs | 1297058 | 11 Coleshill Drive, Hartcliffe | 1151708 | New Works Instruction | ACE Agreed | DN568207/49 |  | 21 days |  |  | Carlene Lynette Lynch | 30/05/2025 16:20 |  | Pre-completion Items To Complete |  |  |  | 30/06 - Chases Elite for appointment date - CL 26/06 - Email sent to Elite with new contact dates - CL 25/06 - Tenant called and confirmed her new number. Tenant number is out of service email sent to RD for additional contact details. Email sent to tenant to make contact - CL 16/06 - Email sent to Elite for an update - CL 01/06 - PO sent to Elite - CL | Appointment booked | 141.57
2025-04-30 13:54:00 | Renewal of lino to downstairs w.c following asbestos floor tile removal by envirocall, please liaise with them for dates etc. Possible variation required for subfloor repair once all tiles have been removed and extent of issue known. |  | 2025-10-27 | 2025-10-27 11:28:00 | Routine Repairs | 1308914 | 9 MURFORD AVENUE | 1151535 | Works Completed | Invoiced | DN568207/48 |  | 21 days |  |  | Carlene Lynette Lynch | 30/05/2025 13:54 |  | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 159.28
2025-04-30 08:30:00 | JEFF WAY - AS PER ROB DOIDGE - LOUNGE / DINING ROOM - DECS WORKS FOLLOWING BOILER LEAK FROM ABOVE. APPROX 6M2 OF STAINBLOCKING TO WALLS AND CEILINGS PRIOR TO PATCH DECORATING IN WHITE. TREATMENT AND PAINTING TO MOULD AROUND PATIO DOOR REVEALS AND TO BATH WALLS / CEILING AS REQUIRED. SERVICE EXT FAN IN BATHROOM ALSO AND ALSO REPAIR AS REQUIRED KITCHEN SINK HOT TAP. N.A.D TO ARETX TO DINING ROOM CEILING | 2025-11-06 08:00:00 | 2025-11-06 | 2025-11-06 14:15:00 | Routine Repairs | 1302154 | 30 Grinfield Avenue, Hartcliffe | 1151074 | Works Completed | Invoiced | 36/539 | 2025-09-19 08:00:00 | 21 days |  |  | Lainie Lavin | 30/05/2025 08:30 | No | Fully Complete | 2025-11-14 | Yes |  |  | Complete | 401.71
2025-04-28 09:52:00 | JEFF WAY - FLOORING IN KITCHEN, DECORATIONS , SOIL PIPE LEAK , AND 1 BRICK TO BE REPLACED AS PER IAN OGBORNE. | 2025-09-22 08:00:00 | 2025-09-22 | 2025-11-06 15:11:00 | Routine Repairs | 1209854 | 53 Andover Road | 1149030 | Works Completed | Invoiced | 36/521 | 2025-11-06 08:00:00 | 21 days |  |  | Lainie Lavin | 28/05/2025 09:52 | No | Post-completion Items To Complete | 2025-11-13 | Yes |  |  | Complete | 914.65
2025-04-25 09:33:00 | Scaffolding will be required up to chimney stack, to renew perished bricks and relay loose ones, also fit new cowls on top of chimney reflaunch, and repoint rest of stack as necessary. |  |  | 2025-05-15 12:25:00 | Routine Repairs | 1187742 | 27 ST DAVIDS CRESCENT | 1147761 | Works Completed | Invoiced | 36/296 | 2025-05-15 12:26:00 | 21 days |  |  | Carlene Lynette Lynch | 27/05/2025 09:33 | Yes | Pre-works Items To Complete | 2026-04-10 | Yes |  |  | Complete | 1466.67
2025-04-23 11:51:00 | Stain block kitchen ceiling stain block lounge ceiling paint over stain block in lounge Paint ceiling in kitchen 10sqm Prep and paint any flaky paint in bathroom ceiling Silicone the perimeter of the bathroom floor including above basin Bathroom and kitchen taps Replace extractor fan in kitchen Renew extractor fan in glazing like for like Rake out and regrout tiles in bathroom | 2026-05-20 08:00:00 |  |  | Routine Repairs | 1300692 | 7 FULFORD WALK | 1146735 | Works Cancelled | Works Cancelled | DN568207/40 |  | 21 days | 1: Refusal | 2026-06-09 14:13:57 | Carlene Lynette Lynch | 22/05/2025 11:51 |  | Works Cancelled |  |  |  | 09/06 - BCC confirmed cancellation of works order. Tenant refused works to be carried out, email sent to IO and EH - CL Follow on appointment to complete work booked for 24/04. | Cancelled | 976.97
2025-04-23 11:42:00 | Renew worktop and cut out of sink. Fit handles on kitchen door. Please inspect sub floor in kitchen near sink and report back for any work to be ordered. | 2025-12-05 13:15:00 |  | 2026-01-13 10:20:00 | Routine Repairs | 1491992 | 100 Risdale Road | 1491992 | Works Completed |  | DN568207/39 | 2025-10-21 08:00:00 | 21 days |  |  | Carlene Lynette Lynch | 22/05/2025 11:42 | No | Post-completion Items To Complete | 2026-06-03 |  |  | 03/06 - SPOKE WITH TENANT, ELECTRICAL WORKS HAVE BEEN COMPLETED. Works are complete except for fitting of new extractor fan. Works issued to JW D&M team to book work to fit fans - 27/03. 08/04 - EMAIL ISSUED TO LIN TO BOOK IN FAN WORKS THAT ARE REMAINING. 09/04 - ELECTRICAL WORKS BOOKED FOR 21/04. | Complete | 802.17
2025-04-23 11:20:00 | Bathroom, renew boxing LHS of bath under sink etc with UPVC and fully seal up. Run extra piece of skirting along bath panel and full seal top and bottom also to stop any water going into DS flat. Also check possible leaking connection between wc and cistern. |  |  |  | Routine Repairs | 1298755 | 31 CROSSCOMBE WALK | 1146663 | New Works Instruction | ACE Agreed | DN568207/36 |  | 21 days |  |  | Carlene Lynette Lynch | 22/05/2025 11:20 |  | Pre-works Items To Complete |  |  |  |  | Complete | 174.4
2025-04-23 10:19:00 | DISREPAIR Due to ongoing damp issues from flat 100 |  |  |  | Disrepair | 1159382 | 92 TWINNELL HOUSE | 1146413 | New Works Instruction | ACE Agreed | 36/632 |  | 20 days |  |  | Shannon Slade | 21/05/2025 10:19 |  | Suspended: On hold |  |  |  |  | Held BCC | 203.06
2025-04-22 19:24:00 | DISREPAIR/MOULD WORKS | 2026-06-03 08:00:00 | 2026-07-09 |  | Disrepair | 1196583 | 167 DUTTON ROAD | 1146242 | New Works Instruction | ACE Agreed | 36/631 |  | 20 days |  |  | Shannon Slade | 20/05/2025 19:24 |  | Pre-completion Items To Complete |  |  |  | WAITING FOR UPDATE THAT BCC HAVE ATTENDED AND COMPLETED THEIR WORKS. 07/04 - WORKS CAN NOW GO AHEAD AND BE BOOKED, BCC HAS COMPLETED IN HOUSE WORKS 23/04 - WORKS BOOKED FOR 3RD OF JUNE | Appointment booked | 169.89
2025-04-07 11:08:00 | AS PER ROB DOIDGE - CLADDING, FRONT RHS TO FRONT DOOR - FIT NEW TIMBER BOTTOM CAPPING AS NONE THERE CURRENTLY AND RATS ACCESSING CLADDING. EXTEND TO NEXT DOORS FRONT DOOR IF REQUIRED. DO THE SAME TO CLADDING LHS OF BCK DOOR WHERE CURRENTLY NO BOTTOM TO CLADDING. APPROX 1.5LIN M TOTAL BUT HAVE USED CLOSEST CLADDING SOR I COULD FIND. KITCHEN - PLEASE RENEW BOXING / DUCTING TO PIPEWORK UNDER WORKTOP BY BACK DOOR, DAMAGED FROM PREVIOUS LEAK. SEAL ALL GAPS / EGDES AS HAS BEEN PREVIOUS RAT PROBLEM. BATHROOM - NON TILED WALLS AND BOXING FOR PIPES. PREP AND PAINT IN FULL AND RESEAL CORNERS OF BOXING. APPROX 6 M2 | 2025-10-20 12:00:00 | 2025-10-20 | 2025-10-20 17:00:00 | Routine Repairs | 1279158 | 221 Four Acres, Withywood | 1137558 | Works Completed | Invoiced | 36/542 | 2025-10-20 12:00:00 | 21 days |  |  | Lainie Lavin | 08/05/2025 11:08 | No | Fully Complete | 2025-12-09 | Yes |  | 09/04 - KPI received and uploaded - CL 08/04 - Email sent to RD and JD with photos which were requested - CL | Complete | 360.72
2025-04-03 12:20:00 | JEFF WAY - AS PER ROB DOIDGE - PATCH REPAIR HOLE TO BATHROOM WALL ABOVE TAP END TILES. RESECURE WC TO FLOOR, POSSIBLY RENEW SCREWS. FIT NEW EXTRACTOR FAN TO WALL. RENEW UPVC CILL ABOVE W.C . OVERHAUL / SERVICE WINDOW MOUNTED KITCHEN FAN ALSO. | 2025-11-11 08:00:00 |  | 2026-03-26 15:42:00 | Routine Repairs | 1303248 | 40 Hartgill Close, Hartcliffe | 1136353 | Works Completed | ACE Agreed | 36/527 |  | 21 days |  |  | Lainie Lavin | 06/05/2025 12:20 |  | Pre-completion Items To Complete | 2026-05-13 | Yes |  |  | Complete | 528.84
2025-03-27 | Jeffway-AS PER ROB DOIDGE - RENWAL OF SMALL PATCH OF FLOOR TILES UNDER, TNT WILL MOVE. FILLING OF EXTERNAL CRACKS ABOVE BATHROOM TO SIDE AND LIVING ROOM TO FRONT ALLOWING WATER INGRESS. APPROX 6 LIN METERS. PATCH DECORATING TO LIVING ROOM WINDOW REVEALS WHERE WATER DAMAGED | 2026-05-21 08:00:00 | 2026-05-21 | 2026-05-22 14:40:00 | Routine Repairs | 1275963 | 37 DANCEY MEAD | 1138851 | Works Completed | Invoiced | 36/1221 | 2026-05-21 08:00:00 | 25 days |  |  | Charlie Higginson | 02/05/2025 00:00 | No | Pre-completion Items To Complete | 2026-06-29 | Yes |  | 30/06 - KPI received and uploaded - CL 29/06 - KPI requested - CL 29/05 - FF completed PO sent to FF to replace floor tiles - CL Appointment booked with tenant for decs to be completed on 08/04 - CL POW of Created and sent to Admin to book - 05/04 CH. Plaster in l/room booked ollie and dan - 5/9/25. 13/11 - External patch works complete, Fl | Complete | 257.53
2025-03-20 15:31:00 | Rapleys Works - Damp & Mould Replace window handle - lounge Replace sealant to bath Renew window seals - bathroom | 2026-04-27 08:00:00 |  |  | Routine Repairs | 1282399 | 32 Horsepool Road | 1128734 | Works Cancelled | Works Cancelled | 36/536 |  | 21 days | 4: Other | 2026-06-02 12:27:43 | Lainie Lavin | 17/04/2025 15:31 |  | Works Cancelled |  |  |  | 02/06 - EMAIL ISSUED TO BCC ASKING TO CANCEL WORKS ORDER A WORKS HAVE BEEN COMPELTED UNDER DISREPAIR. 29/04 - Commerical to review as job has now become a disrepair - CL Appointment booked with tenant for 27/04, letter and text sent. | Cancelled | 154.32
2025-03-20 14:21:00 | JEFF WAY- guttering blocked restricting flow from number 34 |  | 2025-10-17 | 2025-10-17 14:32:00 | Routine Repairs | 1312750 | 32 Sampsons Road, Hartcliffe | 1128658 | Works Completed | Invoiced | 36/535 |  | 21 days |  |  | Lainie Lavin | 17/04/2025 14:21 |  | Post-completion Items To Complete | 2025-10-20 | Yes |  |  | Complete | 92.28
2025-03-20 10:02:00 | Roof inspection, glazing sealed unit. | 2025-10-13 08:00:00 | 2025-10-13 | 2026-03-12 08:39:00 | Routine Repairs | 1297172 | 41 Coleshill Drive | 1128378 | Works Completed |  | DN568207/5 | 2025-10-13 08:00:00 | 21 days |  |  | Carlene Lynette Lynch | 17/04/2025 10:02 | No | Post-completion Items To Complete |  | Yes |  | 22/06 - VO sent to IG and EH - CL 17/06 - PO sent to WSG - CL 05/06 - As per phone call with EH, job has been reopened due to glazing unit being missed. EH and Ian to inspect today and get back to me with findings - CL 07/04 - KPI request added to notes - CL | Awaiting appointment date | 1726.62
2025-03-20 08:21:00 | JEFF WAY - TOILET OVERHAUL , SECURE SAIRCASE , WINDOW HANDLES AND OVERHAUL AS PER IAN OGBORNE. | 2025-09-23 08:00:00 | 2025-09-23 | 2025-09-22 16:15:00 | Routine Repairs | 1271869 | 13 Billand Close, Withywood | 1128287 | Works Completed | Invoiced | 36/556 | 2025-09-22 08:00:00 | 21 days |  |  | Lainie Lavin | 17/04/2025 08:21 | No | Fully Complete | 2025-11-21 | Yes |  |  | Complete | 293.92
2025-03-11 15:58:00 | 2 x Glazing, bathroom flooring, and new toilet cistern |  | 2026-02-06 | 2026-02-06 12:02:00 | Routine Repairs | 1314632 | 39 Tynte Avenue (KS 1986) | 1123292 - 1212/1 | Works Completed | Invoiced | 36/529 |  | 21 days |  |  | Lainie Lavin | 08/04/2025 15:58 | No | Fully Complete | 2026-02-17 | Yes |  |  | Complete | 968.78
2025-03-11 14:18:00 | DISREPAIR - Various jobs around property | 2026-04-23 12:00:00 | 2026-06-11 |  | Routine Repairs | 1191146 | 146 WOOTTON ROAD | 001123136 | Works Started | ACE In Progress | 36/194 | 2025-12-05 08:00:00 | 21 days |  |  | Shannon Slade | 08/04/2025 14:18 | No | Pre-completion Items To Complete |  |  |  | 16/06 - Awaiting update from CM - CL 01/06- WORKS BOOKED FOR CHRIS TO COMPLETE 11/06. 05/05 - Disrepair SS to advise - CL 27/04 - Remaining works need to be booked - CL Works due -23/4/26. 15/04 - ELECTRICAL WORKS BOOKED FOR 15/04 | WIP | 819.9
2025-03-10 11:43:00 | PRE INSPECT - Kitchen floor tiles are lifting. This is causing issues as tenant has mobility issues. She says she was told about a year ago that kitchen, and flooring would be replaced due to damp issues. | 2025-10-23 12:00:00 |  | 2025-10-23 11:37:00 | Routine Repairs | 1186056 | 19 Ripon Road, St Annes | 1121849 | Works Completed | Invoiced | 36/545 | 2025-10-23 11:00:00 | 21 days |  |  | Lainie Lavin | 07/04/2025 11:43 | No | Fully Complete | 2026-01-14 | Yes |  |  | Complete | 650.2
2025-03-03 11:11:00 | PLM - Blocked guttering back of house - water is cascading between window and back door making back door swell - water is running under the door when it rains |  | 2025-10-17 | 2025-10-17 14:44:00 | Routine Repairs | 1204531 | 19 Showering Road, BS14 8DL | 1117913 | Works Completed | Invoiced | 36/544 |  | 21 days |  |  | Lainie Lavin | 31/03/2025 11:11 |  | Fully Complete | 2025-10-20 | Yes |  |  | Complete | 92.28
2025-02-28 13:42:00 | PLM - Leaves blocking up guttering above door to sub bk, causing overflow of rain water; concerns about overflow causing ice outside door | 2026-03-17 11:00:00 |  | 2026-03-17 14:10:00 | Routine Repairs | 7098499 | KINGSLEY HOUSE | 1117410 | Works Completed | Invoiced | 36/513 | 2026-03-17 11:00:00 | 21 days |  |  | Lainie Lavin | 28/03/2025 13:42 | No | Fully Complete | 2026-03-19 | Yes |  | 07/04 - KPI request added and sent to EH - CL | Complete | 3583.01
2025-02-24 15:34:00 | Decoration to one bedroom flat - please liase with housing officer for access details |  |  |  | Disrepair | 1197199 | 22 GORLANGTON CLOSE | 1112596 | New Works Instruction | ACE Agreed | 36/630 |  | 20 days |  |  | Shannon Slade | 21/03/2025 15:34 |  | Suspended: On hold |  |  |  |  | Held BCC | 489.31
2025-02-18 18:54:00 | Rapleys Works Order D&M Remove damaged ceiling 3sqm and reboard. & redec 3sqm - kitchen redec 1 sqm - bathroom replace 4 floor tiles - hallway | 2025-10-08 12:00:00 | 2025-10-08 | 2025-10-08 10:56:00 | Routine Repairs | 1241298 | 4 BROOK ROAD | 1111627 | Works Completed | Invoiced | 36/183 | 2025-10-08 12:00:00 | 21 days |  |  | Shannon Slade | 18/03/2025 18:54 | No | Fully Complete | 2025-11-21 | Yes |  |  | Complete | 261.35
2025-02-17 12:20:00 | D&M FANS AS PER NICHOLAS CORY JEFFWAY TO RENEW BATHROOM FAN WITH AXIA RIVIVI7 AND TO INSTALL NE FAN RIVI7 IN KITCHEN | 2026-07-07 08:00:00 | 2026-07-07 |  | Routine Repairs | 1313468 | 92 STILLINGFLEET ROAD | 1110122 | New Works Instruction | ACE Agreed | 36/432 |  | 21 days |  |  | Shannon Slade | 17/03/2025 12:20 |  | Pre-completion Items To Complete |  |  |  | Awaiting appointment date - CL | Appointment booked | 699.73
2025-02-17 12:06:00 | D&M -MOULD WASH AS PER NICHOLAS CORY JEFFWAY TO MOULD WASH LIVING ROOM BEHIND SOFA, FRONT BEDROOM CEILING AND CORNER OF WALL, REAR BEDROOM AROUND WINDOW AREA AND REAR CORNER BEHIND BUNK BED | 2026-06-25 10:00:00 | 2026-05-08 | 2026-03-02 15:44:00 | Urgent Repair | 1313468 | 92 STILLINGFLEET ROAD | 1110103 | Works Completed | ACE Agreed | 36/185 |  | 7 days |  |  | Shannon Slade | 25/02/2025 12:06 |  | Pre-completion Items To Complete | 2026-03-31 | Yes |  | 16/04 - Email sent to NC to chase KPI - CL | Complete | 172.88
2025-02-14 15:36:00 | Out house has been opened up into main dwelling, plus raised path bridging DPC. Please inject outhouse base of all walls. Externally you will need to enter further connected outbuilding to access rear wall. |  |  | 2026-02-03 08:36:00 | Routine Repairs | 1244366 | 51 Church Lane | 1109561 | Works Completed | Invoiced | 36/186 | 2026-02-03 08:35:00 | 21 days |  |  | Shannon Slade | 14/03/2025 15:36 | No | Fully Complete | 2026-03-13 | Yes |  |  | Complete | 2617.3
2025-02-06 09:55:00 | CONTRACTOR- 12m long bay window canopy/roof for this flat and neighbour 24 (also BCC owned). Please re- felt roof on both properties and send any further SOR requirements, as per Matt Ford | 2025-09-23 08:00:00 | 2025-09-23 | 2025-09-23 16:45:00 | Routine Repairs | 1308629 | 26 MOWCROFT ROAD | 1104506 | Works Completed | Invoiced | 36/190 | 2025-09-23 08:00:00 | 21 days |  |  | Shannon Slade | 06/03/2025 09:55 | No | Fully Complete | 2025-10-16 | Yes |  |  | Complete | 1245.12
2025-02-05 16:07:00 | Rapleys Works Order Bathroom - Overhaul toilet pan, new cistern , overhaul sink as leaking, replace bath waste pipe, install extractor through wall. | 2025-10-20 08:00:00 | 2025-10-20 | 2025-10-28 12:02:00 | Routine Repairs | 1255807 | 59 MARTOCK ROAD | 1104318 | Works Completed | Invoiced | 36/439 |  | 21 days |  |  | Shannon Slade | 05/03/2025 16:07 |  | Fully Complete | 2025-11-13 | Yes |  |  | Complete | 328.94
2025-02-05 08:21:00 | JEFF WAY - Lobby area directly next to front door still has areas of rising damp. FAO ROSANNA GARDINER | 2025-10-02 09:30:00 | 2025-10-02 | 2025-10-02 11:30:00 | Routine Repairs | 1253889 | 175 Lynton Road | 1103832 | Works Completed | Invoiced | 36/192 | 2025-10-02 10:30:00 | 21 days |  |  | Shannon Slade | 05/03/2025 08:21 | No | Fully Complete | 2026-01-14 | Yes |  | Works completed by Timberwise or can be signed off | Complete | 3836.2
2025-01-24 13:11:00 | JEFF WAY - AS PER ROB DOIDGE - PATCH REPAIR TO LIVING ROOM CEILING AND MATCHING IN OF ARTEX FINISH. PREVIOUSLY REPAURED BUT THIS APPEARS TO HAVE DROPPED / CRACKING. HAVE ALLOWED FOR 3M2 OF REPAIR . N.A.D TO ARTEX COATING | 2025-11-24 08:00:00 | 2025-11-24 | 2025-12-18 11:28:00 | Routine Repairs | 1292962 | 373 Bishport Avenue, Hartcliffe, Bristol BS13 0BN | 1096691 | Works Completed | Invoiced | 36/622 | 2025-11-10 14:00:00 | 15 days |  |  | Shannon Slade | 13/02/2025 13:11 | No | Post-completion Items To Complete | 2026-01-14 | Yes |  |  | Complete | 188.67
2025-01-17 10:05:00 | Rapleys Works Order Fill crack 1sqm kitchen Renew plaster, seal & redecorate - 2sqm utility, 6sqm WC, 2sqm lounge Renew glazing panel in door |  |  | 2025-02-21 15:12:00 | Routine Repairs | 1258691 | 67 PEARL STREET | 1073533 | Works Completed | Invoiced | 36/172 |  | 21 days |  |  | Shannon Slade | 14/02/2025 10:05 |  | Fully Complete | 2026-02-27 | Yes |  |  | Complete | 318.0
2025-01-15 16:38:00 | AS PER ROB DOIDGE - BATRHOOM, PREP AND REPAINT WINDOW AND BATH WALLS FOLLOWING LEAK. ALSO PATCH REPAIR ATREX FINISH TO BATH CEILING , STAINBLOCK WHERE REQUIRED AND REPAINT IN FULL, FEW BATH TILES TO RENEW THAT HAVE FALLEN OFF, ALL AFTER A HISTORIC LEAK. | 2025-09-16 10:15:00 | 2025-09-16 | 2026-02-13 09:35:00 | Routine Repairs | 1316616 | 16 WOODMEAD GARDENS | 1091154 | Works Completed | Invoiced | 36/173 | 2026-12-01 11:19:00 | 21 days |  |  | Shannon Slade | 12/02/2025 16:38 | No | Fully Complete | 2026-03-02 | Yes |  |  | Complete | 156.67
2025-01-15 16:19:00 | Ashley Smith - Reboard and plaster living room walls, Once Complete redecorate and paint ceiling also | 2025-09-26 08:00:00 | 2025-09-26 | 2025-09-26 14:45:00 | Routine Repairs | 1194747 | 81 Craydon Grove | 1091129 | Works Completed | Invoiced | 36/676 | 2025-09-26 08:00:00 | 15 days |  |  | Shannon Slade | 04/02/2025 16:19 | No | Fully Complete | 2025-11-20 | Yes |  |  | Complete | 1588.69
2025-01-15 15:03:00 | JEFF WAY - New flooring required in the living room and hallway. Most of the old floor has been lifted. Concrete base. Asbestos report identified pevious tiling as ACM. Have ordered envirocall to remove any remaining tiles FAO ROSANNA GARDINER |  |  | 2025-12-03 12:31:00 | Routine Repairs | 1312614 | 10 Sampsons Road (KS1789) | 1091010 - 24083/1 | Works Completed | Invoiced | 36/175 |  | 21 days |  |  | Shannon Slade | 12/02/2025 15:03 |  | Post-completion Items To Complete | 2025-12-17 | Yes |  |  | Complete | 1570.8
2025-01-15 09:16:00 | DAMP & MOULD -AS PER NICHOLAS CORY JEFFWAY AFTER LEAK ON CISTERN HAS BEEN FIXED AND FLOOR CHECKED IN BATHROOM , HACK OFF DAMAGED PLASTER AROUND BACK ROOM RENRENDER USING WATERPROOFER AND S/C AND SKIM FINISH , PAINT TO MATCH | 2025-10-27 08:00:00 | 2025-10-27 | 2026-02-20 16:40:00 | Routine Repairs | 1052171 | 23 Ellsworth Road | 1090132 | Works Completed | Invoiced | 36/176 | 2026-10-13 16:42:00 | 21 days |  |  | Shannon Slade | 12/02/2025 09:16 | No | Fully Complete | 2026-03-06 | Yes |  |  | Complete | 279.03
2025-01-09 10:12:00 | Jeffway - Scaffolding required to front up to chimney stack, to fit GC1 gas cowl, and flaunch top of chimney. Also stack needs painting with Duganite waterproof paint to stop water ingress. |  | 2025-10-13 | 2025-10-13 11:00:00 | Routine Repairs | 1288955 | 50 SHERRIN WAY | 1085911 | Works Completed | Invoiced | 36/178 |  | 21 days |  |  | Shannon Slade | 06/02/2025 10:12 |  | Fully Complete | 2025-10-14 | Yes |  |  | Complete | 1784.92
2025-01-06 13:42:00 | DAMP AND MOULD DISREPAIR WORKS | 2025-10-21 12:00:00 | 2025-10-21 | 2025-10-21 10:46:00 | Disrepair | 1189873 | 36 Whitmore Avenue | 1083570 | Works Completed | Invoiced | 36/628 | 2025-10-21 12:00:00 | 20 days |  |  | Shannon Slade | 31/01/2025 13:42 | No | Post-completion Items To Complete | 2026-01-23 | Yes |  |  | Complete | 162.37
2025-01-06 10:19:00 | DISREPAIR WORKS | 2025-10-22 08:00:00 | 2025-10-22 |  | Disrepair | 1189873 | 36 Whitmore Avenue | 1083270 | New Works Instruction | ACE Agreed | 36/629 |  | 20 days |  |  | Shannon Slade | 31/01/2025 10:19 |  | Suspended: Awaiting Client Action/Response |  |  |  |  | Held BCC | 738.52
2025-01-02 09:24:00 | Remedial works to prevent rats entering property. Please check if there are any holes behind the bath panel when replacing, if there are this may require asbestos removal, see report provided, repair small hole in kitchen ceiling and replace boarded ceiling in bedroom with plasterboard and skim. Tnt is very worried about the kitchen sink unit being removed any holes not being filled straight away to prevent rats entering. If possible, can the kitchen unit removal etc be combined with filling any holes in the wall behind. I have allowed replacement of most of the concrete path running along the side of the property and a small area on the corner, rear garden because there are holes in front of the doors where rats may be entering the walls/property, see photos. If possible, please keep some of the existing path. Contact Melissa Edwards on 07442675013 with any issues |  |  | 2026-02-06 14:49:00 | Routine Repairs | 1285514 | 29 NEWLAND ROAD | 1082012 | Works Completed | Invoiced | 36/180 |  | 21 days |  |  | Shannon Slade | 30/01/2025 09:24 |  | Fully Complete | 2026-03-16 | Yes |  | 16/04 - KPI request chased - CL 07/04 - KPI request added and sent to EH - CL | Complete | 79.94
2024-12-14 22:58:00 | DISREPAIR - Living room - once TT has removed her tv from the wall, strip plaster back install dehum to dry, then replaster and apply mist coat. Damp and mould wash as necessary around the living room. Bathroom - damp and mould wash as necessary around the living room, overhaul bathroom extractor. bedroom 1 - damp and mould wash as necesaary around the living room. bedroom 2 - damp and mould wash as necesaary around the living room | 2026-06-10 08:00:00 |  |  | Disrepair | 1279498 | 33 FOUR ACRES CLOSE | 1072724 | Works Started | ACE Agreed | 36/627 | 2026-03-30 12:00:00 | 20 days |  |  | Shannon Slade | 16/01/2025 22:58 | No | Pre-completion Items To Complete |  |  |  | 16/06 - TENANT HAS REFUSED PLASTERING TO L/ROOM UNTIL KITCHEN PLASTERIGN IS CONFIRMED. EMAIL ISSUED TO BCC. MONDAY/TUESDAY ARE BETTER | Held Tenant | 1375.01
2024-12-12 16:22:00 | Jeff Way - roof is still leaking following repairs to chimney stack. Issue is still not resolved - please update us as soon as possible - previously attended under ref 1028214, as per Matt Ford |  | 2025-01-17 | 2025-01-17 07:57:00 | Routine Repairs | 1281409 | 23 Hersey Gardens, Withywood | 1075181 | Works Completed | Invoiced | 36/161 |  | 21 days |  |  | Shannon Slade | 15/01/2025 16:22 |  | Fully Complete | 2025-03-25 | Yes |  |  | Complete | 59.0
2024-12-09 13:34:00 | AS PER NICHOLAS CORY JEFFWAY TO USE SEMPATAP PRODUCT ON WALL IN LIVING ROOM AGAINST NEXT DOOR STAIR CASE( BRICK WALL PAPER) | 2026-07-15 08:00:00 | 2026-07-08 |  | Urgent Repair | 1310356 | 19 Pavey Close | 1069440 | New Works Instruction | ACE In Progress | 36/165 |  | 7 days |  |  | Shannon Slade | 17/12/2024 13:34 |  | Pre-completion Items To Complete |  |  |  | 09/06 - Appointment confirmed with tenant - CL Struggling to obtain materials for price, job on hold till we receive delivery | Appointment booked | 649.9
2024-12-09 11:49:00 | Rapleys works order Front bedroom door way to renew hinge side door frame door on site lag the pipework in bathroom 4lm paint living room 15m2 kitchen 3m2 bathroom walls and ceiling 6m2 each hallway 3m2 gutter clean with vacuum wall mounted extractor fans revive 7 to kitchen and bathroom - please send across the paperwork | 2025-09-03 08:00:00 |  | 2025-09-03 12:13:00 | Routine Repairs | 1272884 | 14 BORLEYTON WALK | 001069088 | Works Completed | ACE In Progress | 36/166 | 2025-09-03 09:00:00 | 21 days |  |  | Shannon Slade | 10/01/2025 11:49 | No | Post-completion Items To Complete | 2026-06-23 |  |  | 23/06 - KPI requested - CL 11/5 - Awaiting CH to omitt works , chased up (LL). | Complete | 184.56
2024-11-28 17:49:00 | Window overhaul, throughout. Damp and mould wash - throughout. Extractors - supply and fit new extractor in bathroom and kitchen. Replace blownDGU - living room. Fill hole and skim - kitchen (behind boiler) 2 x smoke alarks - hallway and living room | 2026-06-10 12:00:00 |  |  | Disrepair | 1286006 | 139 NEWLAND ROAD | 1064042 | New Works Instruction | ACE Agreed | 36/626 |  | 20 days |  |  | Shannon Slade | 27/12/2024 17:49 |  | Pre-completion Items To Complete |  |  |  | 26/06 - ELECTRICIAN GAINED ACCESS, HOWEVER, FAN NEEDS TO BE FITTED INTO WINDOW, EMAIL SENT TO BCC. 19/03 - BCC HAS ISSUED ACCESS LETTER FOR ELECTRICAL WORKS. WORKS BOOKED FOR 17TH JUNE. | WIP | 2058.1
2024-11-12 11:07:00 | Contractor - Scaffolding required up to gutter height on low level porch roof. Roofers to renew first course of felt and batten. Carpenters to use same scaffolding to renew rotten fascia board approx 3m long. Guttering needs to be renewed as well 3m long. Please clear all guttering around the property. Ref Paul Rogoll. | 2026-03-27 14:15:00 |  | 2026-03-27 10:00:00 | Routine Repairs | 1286824 | 39 Pigott Avenue | 1053364 | Works Completed | ACE Agreed | 36/746 | 2026-01-08 08:00:00 | 15 days |  |  | Shannon Slade | 02/12/2024 11:07 | No | Pre-completion Items To Complete | 2026-04-15 | Yes |  | 23/06 - KPI chased - CL 15/04 - KPI request sent - CL Awaiting pictures from operative before hand over -27/3. | Complete | 1600.33
2024-11-11 16:03:00 | Roofers to check roof leaking, felt possibly ripped. Make safe/repair/report further work needed. | 2025-09-10 09:00:00 | 2020-01-01 | 2026-03-11 10:34:00 | Urgent Repair | 1249452 | 10 Hollidge Gardens | 1030138 | Works Completed | Invoiced | 36/152 | 2025-09-10 09:00:00 | 7 days |  |  | Shannon Slade | 19/11/2024 16:03 | No | Pre-completion Items To Complete | 2026-03-11 | Yes |  | 13/04 - KPI received and uploaded. 07/04 - KPI request sent PR and EH as original can not be located - CL | Complete | 1645.73
2024-11-05 13:28:00 | Bedroom 1 (front room) remove sloped sections of plaster board in room and inside cupboards, replace with thermal board, skim and make good. Bathroom - Supply and fit fan damp and mould wash, strip plaster to brick allow to dry and then re-render and skim, once dry tile behind toilet. Exterior tap outside bathroom removed and capped. Windows - Damp and muld wash to window in bedroom 2 and window overhaul throughout property. Rear Garden - Demolish and remove decking, demolish and remove concrete base on 2nd tier, level whole of second tier. Build rail fence between concrete floor and raised section to prevent falls. Electrics - Full electrical check to property. |  |  | 2026-05-26 16:21:00 | Disrepair | 1225543 | 169 Leinster Avenue | 1050242 | Works Completed | ACE Agreed | 36/625 |  | 20 days |  |  | Shannon Slade | 02/12/2024 13:28 |  | Pre-completion Items To Complete |  | No |  | 27/05 - KPI for Completed works, external works are going to Voids WAITING FOR CONFIRMATION OF PRO-TIDY ATTENDING - CHASE FOR DATE!!! 30/03 - CHASED COMMERICAL AND CHARLIE FOR DATE OF WORKS. | Awaiting appointment date | 9483.56
2024-11-03 12:13:00 | Rapleys works order - skim and paint 3m2 front bedroom cupboard -replace radiator brackets and paint front bedroom 1m2 - overhaul vent in hallway -repair crack and paint wall under stairs cupboard 2m2 -repair crack and paint kitchen ceiling 2m2 -rear porch paint 7m2 -inject dpc 3lm to rear porch | 2025-10-31 08:00:00 | 2025-10-31 | 2025-10-31 09:57:00 | Routine Repairs | 1192989 | 32 Burnbush Close | 1048794 | Works Completed | Invoiced | 36/793 |  | 15 days |  |  | Shannon Slade | 22/11/2024 12:13 |  | Fully Complete | 2025-11-13 | Yes |  |  | Complete | 534.39
2024-10-18 14:13:00 | Renew internal door. Renew plasterboard around front entrance door. Renew internal door. Renew socket next to radiator. | 2025-09-29 08:00:00 | 2025-09-29 |  | Disrepair | 1197199 | 22 GORLANGTON CLOSE | 1041829 | Works Started | ACE Agreed | 36/623 | 2025-09-29 09:00:00 | 20 days |  |  | Shannon Slade | 14/11/2024 14:13 | No | Suspended: Awaiting Client Action/Response |  |  |  | 20/05 - Jeff Way to close down order and KPI for whats been competed. | Held BCC | 514.16
2024-08-15 17:19:00 | Damp/mould in rooms, bricks in alley crumbling, no kitchen extractor, minor spalling & other works |  |  | 2026-11-20 10:26:00 | Routine Repairs | 1210066 | 25 Axbridge Road | 1007526 | Works Completed | Invoiced | 36/156 |  | 21 days |  |  | Shannon Slade | 13/09/2024 17:19 |  | Fully Complete |  |  |  |  | Complete | 2406.23
| Jeff Way - water damage to internal airing cupboard from leak from above flat. Cut out damage plasterboard ceiling reboard and skim to suit . Stain block back and side internal walls. Cut and fix timber architrave around rear access panel. Apply emulsion paint to internal cupboard walls as per Jeff Neck. | 2026-03-06 12:00:00 |  | 2026-03-09 13:42:00 | Routine Repairs | 1269450 | 11 Winterstoke House, Duckmoor Road, Ashton | 1226363 | Works Completed | ACE Agreed | 36/702 | 2026-03-06 12:00:00 | 15 days |  |  | Lainie Lavin | 20/01/2012 14:29 | No | Pre-completion Items To Complete | 2026-03-13 | Yes |  | 07/04 - KPI request added and forwarded to EH - CL | Complete | 69.56
| JEFF WAY - CRACK REPAIR , ROOF INSPECTION , PLASTERING AS PER IAN OGBORNE. | 2026-03-25 11:00:00 | 2026-04-16 |  | Routine Repairs | 1271870 | 14 Billand Close, Withywood | 1128284 | Works Started | ACE Agreed | 36/660 | 2026-03-25 08:43:00 | 15 days |  |  | Lainie Lavin | 20/01/2012 12:26 | No | Pre-completion Items To Complete |  |  |  |  | Complete | 527.41
| JEFF WAY - Front elevation guttering dropped above front door. FAO TOM WALKER. | 2025-09-18 13:30:00 | 2025-09-18 | 2025-09-22 12:30:00 | Routine Repairs | 1074982 | 57 Twenty Acres Road, Southmead | 1208568 | Works Completed | Invoiced | 36/585 | 2025-09-18 12:30:00 | 15 days |  |  | Lainie Lavin | 20/01/2012 14:46 | No | Post-completion Items To Complete | 2025-11-21 | Yes |  |  | Complete | 117.96
| Jeff Way - Overhaul all PVC windows and handles as per Jeff Neck. | 2025-09-29 12:15:00 |  | 2026-03-13 11:02:00 | Routine Repairs | 1282797 | 234 Ilchester Crescent, Bedminster Down | 1197051 | Works Completed | ACE Agreed | 36/670 | 2025-09-29 12:15:00 | 15 days |  |  | Lainie Lavin | 20/01/2012 12:02 | No | Post-completion Items To Complete | 2026-04-14 | Yes |  |  | Complete | 95.17